Document of the Inter-American Development Bank

Belize

Sustainable Tourism Program II

BL-L1020

ECONOMIC ANALYSIS ANNEX

This document was produced by: Onil Banerjee (INE/RND), Martin Cicowiez (Universidad Nacional de la Plata) and Jamie Cotta (INE/RND)

- Table of Contents

Abstract	2

I. Introduction	3

II. Methodology: A National Dynamic Computable General Equilibrium Model for Belize	4

2.1. The Model	4

2.2. The Social Accounting Matrix for Belize	9

2.3. A Snapshot of Belize in the Base Year of 2011	13

2.4. Model Calibration	15

III. Benefits: Forecasting Foreign Tourism Demand	15

3.1. Foreign Overnight Tourist Arrivals and Expenditure Without Program	15

3.2. Foreign Overnight Tourist Arrivals and Expenditure With Program	20

IV. Costs and Break-Even Demand	28

4.1. Investment Structure and Sequencing	28

4.2. Break-even Demand	29

4.3. Preliminary Cost-benefit Analysis	30

V. Estimating Economic Returns	30

5.0. CGE Scenario Design	30

5.1. Model Results	32

5.1.1. Aggregate Results	32

5.1.2. Sectoral Results	35

5.3. Cost-Benefit Analysis	36

VI. Sensitivity Analysis	38

VII. Concluding Remarks	40

APPENDIX A: MATHEMATICAL STATEMENT OF THE DCGE MODEL	45

APPENDIX B: OVERVIEW OF A SOCIAL ACCOUNTING MATRIX	59

# Abstract

This paper evaluates ex-ante the economic impact of the Sustainable Tourism Program II (BL-L1020), a proposed $30 million Belizean Dollar loan from the Inter-American Development Bank (IDB) to the Government of Belize for tourism development in emerging destinations. A dynamic computable general equilibrium (DCGE) model is developed for Belize to estimate the net returns from the investment. The approach developed here builds on the quantitative framework for evaluating public investments in tourism developed in Banerjee et al. (2015) in two critical ways: (i) Belize is data poor while DCGE models are data intense. This paper introduces a generalizable approach to building DCGE models in data poor environments; (ii) results of simulations are highly sensitive to expectations of tourism demand with and without the proposed investment. In this paper, this is addressed in two ways. First, data-driven, auto-regressive integrated moving average methods are used to forecast without program tourism arrivals and expenditure. Second, a quasi-contingent valuation approach is used to assess with program tourism demand. These projections and information on investment structuring and costs are used to calibrate the DCGE model shocks. Results of this analysis show that the proposed investment will have positive impacts on Belize’s economy by hastening economic growth. Gross domestic product increases 3% over the without program baseline by 2040, and unemployment falls from 12% to 10%. Cross validating with a break-even scenario shows that the actual increase in tourism demand resulting from the investment could be considerably less than forecast, with the Government of Belize still recovering all investment costs.

# I. Introduction

This paper evaluates ex-ante the economic impact of the Sustainable Tourism Program II (BL-L1020), a proposed $30 million Belizean Dollar loan from the Inter-American Development Bank (IDB) to the Government of Belize for tourism development in emerging destinations. A dynamic computable general equilibrium (DCGE) model is developed for Belize to estimate the net returns from the investment. The approach developed here builds on the quantitative framework for evaluating public investments in tourism developed in Banerjee et al. (2015) in two critical ways: (i) Belize is data poor while DCGE models are data intense. This paper introduces a generalizable approach to building DCGE models in data poor environments; (ii) results of simulations are highly sensitive to expectations of tourism demand with and without the proposed investment. In this paper, this is addressed in two ways. First, data-driven, auto-regressive integrated moving average methods are used to forecast without program tourism arrivals and expenditure. Second, a quasi-contingent valuation approach is used to assess with program tourism demand.

The goal of the Sustainable Tourism Program II (STP II) is to increase the tourism sector’s contribution to socioeconomic development while maintaining and enhancing natural and cultural capital with special consideration for Belize’s vulnerability to natural disasters and climate change (Lemay et al., 2015). The predecessor to STP II is the Sustainable Tourism Program I, an IDB loan for US$13.2 million executed between 2008 and 2013. The emphasis of STP I was on consolidating the overnight foreign leisure visitor market through investment in Ambergris Caye, Placencia, Cayo and Belize City.

A key strategic divergence from STP I is that STP II focuses on emerging destinations. Consistent with the priorities set forth in Belize’s National Sustainable Tourism Masterplan, the destinations selected for investment are Corozal District, Toledo District, the Mountain Pine Ridge, Chiquibul, Caracol Complex in Cayo District, and Caye Caulker. While Caye Caulker is not so much an emerging destination, its current level of development and vulnerability to natural disasters and climate change warranted investments in terms of urban planning and disaster risk management. The specific objectives of STP II are to: (i) increase tourism employment and tourism sector based income and revenues through enhancement of the tourism product; (ii) promote environmental sustainability and disaster and climate resilience, and; (iii) improve tourism sector governance and create an enabling environment for private investment through institutional strengthening and capacity building (Lemay et al., 2015).

As a component of the Proposal for Operational Development for the IDB loan, an ex-ante economic analysis is required to assess the economic viability of the loan. This paper presents the methodology developed to conduct this analysis in a data poor environment, as well as results and analysis. Following this introduction, the core components of the DCGE model are presented. In this section, the approach to constructing the social accounting matrix (SAM) is discussed, and a snapshot of Belize’s economy, as understood through the SAM is provided. Next, the approach to estimating tourism demand with auto-regressive integrated moving average (ARIMA) methods is described. The estimation of with program tourism demand through a quasi-contingent valuation experiment is then discussed. Section 4 presents the investment structuring and sequencing used as a model input as well as in the estimation of break-even demand. A preliminary cost-benefit analysis is presented considering only direct benefits and costs of the investment, in the absence of factor and other supply constraints. Section 5 describes the calibration of the model shocks, results and analysis. Section 6 tests the robustness of the DCGE with a systematic sensitivity analysis and the final section offers concluding remarks and provides an indication of the methodological frontier of tourism investment analysis.

# II. Methodology: A National Dynamic Computable General Equilibrium Model for Belize

## 2.1. The Model

This study employs the single small open recursive dynamic Computable General Equilibrium (CGE) modelling framework developed in Banerjee, Cicowiez and Gachot (2015b) to evaluate the economic impact of the IDB’s Sustainable Tourism Program II (Banerjee, Cicowiez, & Gachot, 2015b). The mathematical statement of the model is presented in Appendix A while a more detailed description of the model and a manual for its operation may be found in the IDB Working Paper (Banerjee, Cicowiez, & Gachot, 2015a). The model integrates a relatively standard recursive DCGE model with additional equations and variables that single out: (a) the domestic and foreign tourism demand, and; (b) the impact of public capital investment in infrastructure on sectoral productivity (Banerjee et al., 2015a). This DCGE model offers a combination of policy-relevant features for the study of tourism investment and tourism policy counterfactual scenarios in a national economy. Provided disaggregated supply and use data, the model may be regionalized to evaluate district-level investment and policies. Appendix A presents the variables and equations of the model.

Figure 1 depicts the circular flow of income within the economy and between the economy and the rest of the world. Activities are industries that both demand (as intermediate inputs) and supply goods and services. Goods and services are consumed by households and governments, and supplied to export markets and foreign tourists. Activities also demand factors of production (labor, capital, land, natural resources) for their productive processes and make payments to these factors. These payments are transferred to households in the form of wages and rents. Households may also receive income from transfers from the government and transfers from the rest of the country or world (migrant labor, remittances, government subsidies, gifts, etc.). Households pay taxes, consume and save (invest in the capital account).

Figure 1. Circular income flow in the DCGE.

Source: Authors’ own elaboration.

The DCGE model mathematically describes the optimizing behavior of agents in their economic environment; it is a system of equations describing the utility maximizing behavior of consumers, profit maximizing behavior of producers, and the equilibrium conditions and constraints imposed by the macroeconomic environment. Agent behavior is represented by linear and non-linear first order optimality conditions and the economic environment is described as a series of equilibrium constraints for factors, commodities, savings and investment, the government, and rest of the world accounts (Lofgren, Harris, Robinson, Thomas, & El-Said, 2002). The model may be broken into a series of blocks, namely: production, factor markets, institutions, commodity markets, and macroeconomic balances. These model blocks are discussed in turn.

Production

The model’s structure enables a given activity to produce more than one commodity, while any one commodity may be produced by more than one activity. Firms are price takers and minimize costs subject to nested technological constraints. Sectoral output is determined by combining value added with intermediate consumption through a fixed share, Leontief production function. Composite labor is a constant elasticity of substitution (CES) function of various types of labor indicating imperfect substitution between types of labor. Composite capital and land are also formed in this way. Value added is created by a CES function of factors (labor, capital. land and other natural resources) where firms employ factors until the value of the factor’s marginal product is equal to the factor price.

Income and savings

Households receive income from labor, capital, land and transfers from other agents including remittances from abroad. Factor income is apportioned to households in fixed shares while income from transfers is the sum of all transfers for each household category. Households pay direct taxes and make transfers to the government, which constitute contributions to social assistance programs (e.g. employment insurance). The government is a consolidated institutional sector; in practical terms, and due to the lack of data, there is only one government which is the sum of central and local governments. Depending on the selected closure rule, government expenditures are exogenous. Disposable household income is equal to household income net of transfers, taxes and savings. Household savings are a linear function of disposable income.

Income taxes for households are a linear function of their total income. The rest of the world receives income from the sale of imports, returns to capital and transfers while foreign spending consists of export purchases and transfers to agents in the domestic economy. Transfers to households are treated as proportional to their disposable income while household transfers to other institutions are treated as a linear function of total income.

Demand

Goods and services are demanded by households, domestic and foreign tourists, the government, investment and as transport and trade margins. Households have a Stone-Geary utility function, with a linear expenditure system (LES) describing household consumption. In a LES, households use their income to first consume a minimum level of subsistence goods and services. With the supernumerary income remaining, households purchase goods and services according to a linear relationship between income and consumption. LES differ from CES functions in that LES functions have non-unitary income elasticities between all pairs of goods enabling flexibility with regards to substitution possibilities in response to changes in relative prices.

Investment demand is composed of gross fixed capital formation (GFCF) and changes in inventories. GFCF is endogenous with total investment expenditure balanced by the savings and investment constraint where savings is endogenous. Inventory changes are exogenous in the model and fixed in volume. Investment in goods and services occurs in fixed shares. Government expenditures for a given budget also follow this logic.

Tourism demand by commodity can be exogenous or endogenous. In the current application, it is assumed that foreign tourism demand follows an exogenous path, which allows assessment of the impact of increased foreign tourism demand. Section III discusses the development of the with and without tourism demand forecasts used to calibrate the model shocks.

Supply and trade

Belize is too small to affect prices in international and interregional markets and, as a consequence, the Rest of the World (RoW) prices are taken to be exogenous. In the tradable goods sectors, the composite commodity price is a weighted average of local prices and import prices, whereas in most tourism sectors, prices are determined by local average costs. Thus, tourism services produced in the local economy are assumed to be non-tradable.

A constant elasticity of transformation (CET) function describes how industry output responds to changes in prices. This functional form implies that an industry may reorganize production in response to changes in prices, though they cannot perfectly or completely switch from the production of one commodity to another. Industries allocate output to domestic and foreign markets based on the assumption that the goods destined to one market are different from those destined to another market. This assumption is operationalized through a CET function.

World export prices are fixed (i.e. the world export demand curve is horizontal). Domestic and imported commodities are aggregated with a CES function. To reflect heterogeneity in goods and services with regards to their origin, goods and services consumed domestically are aggregate goods composed of domestically produced and imported goods.

Model dynamics

In the DCGE, growth over time is largely endogenous. The economy grows due to accumulation of capital determined by investment and depreciation, labor (determined by exogenously imposed projections), as well as because of improvements in total factor productivity (TFP) which have both endogenous and exogenous components. Apart from an exogenous component, TFP of any production activity potentially depends usually, positively on the levels of government capital stocks and economic openness.

On the supply side of the labor markets, unemployment is endogenous: for each labor type, the model includes a wage curve that imposes a negative relationship between the real wage and the unemployment rate (Blanchflower & Oswald, 2004). For non-labor factors, the supply curves are vertical in any single year.

## 2.2. The Social Accounting Matrix for Belize

The basic accounting structure and much of the underlying data required to implement the CGE model is derived from a Social Accounting Matrix (SAM) for Belize. A SAM is a comprehensive, economy-wide statistical representation of a regional economy at a specific point in time. It is a square matrix with identical row and column accounts where each cell in the matrix shows a payment from its column account to its row account. It is used for descriptive purposes and is the key data input for a CGE. Major accounts in a standard SAM are: activities that carry out production; commodities (goods and services) which are produced and/or imported and sold domestically and/or exported; factors used in production which include labor, capital, land and other natural resources; institutions such as households, government, and the rest of the country and the rest of the world. Generally speaking, most features of the SAM are familiar from social accounting matrices used in other models. However, the SAM developed here has some unconventional features related to the explicit treatment of foreign tourism-related spending. A stylized SAM is provided in Appendix B.

In this study, the DCGE model was calibrated with a SAM for 2011 extracted and customized from the GTAP Version 9 global database developed at Purdue University (Narayanan, Aguiar, & McDougall, 2015b). GTAP 9 is a fully documented, publically available database used world-wide by thousands of quantitative policy modelers. The reference year for GTAP 9 is 2011 and it represents 140 regions and 57 economic activities.

In most cases, countries that have supplied the required input-output (I-O) and related economic data to GTAP are represented individually. The GTAP Data Base includes input-output tables for 109 of the 140 regions represented. Those countries for which I-O tables are not available are considered as composite regions usually composed of more than one country. All Central American countries are represented in GTAP individually, with the exception of Belize, which owing to the absence of I-O tables for Belize, is considered the composite region of ‘the rest of Central America’.

In the development of GTAP, to construct a statistical representation of the economies of composite regions, a combination of individual countries is used. In this process, it is assumed that the production technology or input output structure of a composite region may be approximated by the input output structure of a country with a similar level of development in the region. The estimation procedure for constructing composite regions follows the generalized approach developed by Horridge (2006) and described in Narayanan et al. (2015) is as follows (Horridge, 2006; Narayanan et al., 2015b):

1. To construct an I-O table for a composite region, a primary region is associated with the composite region. This matching is conducted on the basis of similarity in Gross Domestic Product (GDP) per capita. GDP per capita is recognized as a core indicator of level of economic development, economic performance and average living standards (OECD, 2010).

2. The target total GDP is generated for each composite region (this is equivalent to Belize’s GDP in the reference year).

3. Primary countries that match the composite region (Belize) in similarity in GDP per capita are used and GDP weights in terms of country GDP to the total target GDP, are assigned do the primary regions.

4. The I-O coefficients table for the composite region (Belize) is constructed by combining I-O data from the primary region I-O tables, and is summed according to the GDP share weights.

5. Once the I-O table is constructed for the composite region, it is then adjusted so that it matches regional data on macroeconomic aggregates including income, investment, tariffs and trade, and taxation (Narayanan, Aguiar, & McDougall, 2015a).

On the basis of GDP per capita, Belize was associated with the input output structure of Ecuador. In 2011, the base year of the DCGE model, Ecuador had a GDP per capita of US$4,870 compared to that of Belize which was US$4,310. These two countries were indeed two of the most similar countries in terms of GDP per capita in the base year of 2011 (World Bank, 2015).

While the countries of Ecuador and Belize may seem very different in terms of the size of their respective economies and populations, the assumption that is being made here is that Ecuador and Belize use similar technologies in the production of goods and services. As an example, this means that to produce a unit of output of sugarcane for example, both Belize and Ecuador use similar proportions of inputs, which are factor inputs: capital, labor and land, and; intermediate inputs such as pesticides, fertilizers and other intermediate inputs. This logic applies to all sectors of the economy. While an I-O table represents the magnitudes of factors and intermediate inputs that are used to produce a given size of output, what is of concern here are the I-O coefficients which tell us the proportions of inputs that are used in productive processes. Magnitudes are not so important; only the proportions are.

The SAM extracted from the GTAP database has 57 sectors. Following extraction of the Belize SAM from GTAP, the SAM was restructured to fit the model accounting structure of the DCGE model developed in Banerjee et al. (2015). Once SAM and model accounts were aligned, the SAM was customized based on data available for Belize on public versus private investment, taxation and foreign tourism demand. Economic sectors were further aggregated where possible to approximate the structure of those reported by the Statistical Institute of Belize (SIB, 2015). Finally, the SAM was re-balanced using cross-entropy methods (Robinson, Cattaneo, & El-Said, 2001; Robinson & El-Said, 2000).

Table 1 shows the accounts in the SAM, which represent the level of disaggregation of the model. The SAM includes 9 sectors (activities and commodities). The factors of production include skilled and unskilled, private capital stock, land, and a natural resource which is mined. The SAM identifies current accounts for institutions (household, government, and tourists from the rest of world), private and public investment, and various tax accounts.

Table 1. Accounts in the Belize social accounting matrix.

Source: Authors’ own elaboration; Belize SAM.

## 2.3. A Snapshot of Belize in the Base Year of 2011

According to estimates from the SAM, Belize’s Gross Domestic Product (GDP) reached 2,978,502 thousand BZD in fiscal year (FY) 2011 (Table 2). Belize exported only slightly more than it imported while foreign tourism demand was equivalent to almost 10% of GDP.

Table 2. Belize total supply and demand.

Source: Authors’ own elaboration; Belize SAM.

The production and trade structure of Belize is reflected in Table 3. Travel, transport and retail is the most important value-added sector and responsible for 24.4% of economic output and 38.2% of employment. The export share of this sector was 20.0%. Manufacturing was responsible for 20.9% of total economic output and contributed 28.2% of exports; manufactured goods represented the greatest share of imports (68.7%). Agriculture, forestry and fishing was the third most important sector in terms of production with a production share of 18.6%, an employment share of 10.8%, an export share of 21.6% and an import share of 2.3%. Not surprisingly, processed foods accounted for the second highest share of imports at 14.3%. Business and government services were also strong sectors accounting for 12.5% and 15.5% of value added, respectively. These two sectors are also significant employers in Belize responsible for 11.3% and 21.7% of employment respectively.

Table 3. Sectoral production and trade structure in FY 2011 (percent share of total).

Source: Authors’ own elaboration; Belize SAM.

## 2.4. Model Calibration

The model is a dynamic model where dynamic calibration is performed under the assumption that in the baseline, the economy is on a path of balanced growth. In this case, a growth rate is specified and is applied to all model quantities. Relative prices however remain unchanged. In the simulations, the GDP growth rate is always endogenous. Projections of economic growth were derived from the IMF’s World Economic Outlook (IMF, 2015). Population projections were drawn from the United Nations Projections, 2012 Revision (UN, 2015), using the medium variant.

Beyond the SAM, depreciation rates for private and public capital and various elasticities are also used to calibrate the model. These required exogenous elasticities include those in production, trade, consumption, and in the wage/rental rate curve. Estimates of these parameters were obtained from the best available estimates in the relevant literature. To test the robustness of the model and its results with regard to variation in these parameters, a systematic sensitivity analysis was conducted and described in section VI.

# III. Benefits: Forecasting Foreign Tourism Demand

## 3.1. Foreign Overnight Tourist Arrivals and Expenditure Without Program

Tourist arrivals and expenditure projections with and without the STP II program investment are required to calibrate the model shocks implemented in the DCGE. The first step in developing these projections is to develop a forecasting model for without program expenditure and arrivals. The without program projections were based on time series data (1998 to 2014) of foreign tourist overnight arrivals and expenditure at the national level on a monthly basis. These data exclude cruise ship arrivals (Belize Tourism Board, 2015; Central Bank of Belize, 2015).

The time series model developed is an Autoregressive Integrated Moving Average (ARIMA) model which is one of the more widely used approaches to time series forecasting.

An ARIMA model is an auto regression model where the variable of interest is forecast using a linear combination of past values of that variable; in other words, the regression is of the variable against itself. This contrasts with multiple regression models where a variable of interest is forecast as a linear combination of predictive or independent variables. A moving average model uses past forecast errors in a regression. The dependent variable is a weighted moving average of a past predetermined number of forecast errors.

To develop an ARIMA model, time series data must be exhibit stationarity. Data are stationary when its properties do not depend on the time at which the series was observed. Data exhibiting seasonality, such as tourist arrivals, or other time trends, are considered non-stationary. Three tests may be performed to check for stationarity. A simple test for stationarity is a line plot of the data. The data are stationary if the data series is approximately horizontal with constant variance (Becketti, 2013).  Second, autocorrelation function (ACF) plots may be used (Nau, 2015). When the data is stationary, the ACF drops to zero relatively quickly and the Ljung-Box Q statistic has a small p-value, suggesting that the next period change in the variable of interest is uncorrelated with previous periods. Third, and in addition to graphical methods, a unit root test may be performed, the most common of which is the Augmented Dicky-Fuller test (Hyndman & Athanasopoulos, 2013).

In order to transform non-stationary data into stationary data, differencing is performed which is the computation of the difference between consecutive observations in order to eliminate trend and seasonality effects. Seasonal differencing is the difference between an observation and the corresponding observation from the previous year, quarter, month or other time period. Nest, a logarithmic transformation may be undertaken to stabilize time series data exhibiting a high variance.

A non-seasonal ARIMA model is specified as:

y't=c+ϕ1yt-1+…+ϕpyt-p+θ1et-1+…+θqet-q+et                                      (eqn’ 1)

The predictors on the right hand side are the lagged values of y at time t, and lagged errors, e. This form is commonly referred to as an ARIMA(p,d,q) model, where:

y't = the differenced series;

p = order of the autoregressive;

d = degree of first differencing, and;

q = order of the moving average.

Following differencing, the model orders of p and q are identified through graphical ACF plots and Partial Correlation Function (PCF) plots. The log likelihood of the data (which is the logarithm of the probability of the observed data being generated from the model), Akaike’s Information Criterion (AIC) and the Bayesian Information Criterion may all be used to choose the best fitting model.  Better models minimize AIC and BIC (Hyndman & Athanasopoulos, 2013). Once identified, the parameters of the model are estimated, most commonly with the maximum likelihood estimation approach.

The Hyndman-Khandakar algorithm for ARIMA modelling is an automated function in the R statistical package, but may also be performed manually in other statistical packages such as Stata. The algorithm suggested by Hyndman and Athanasopoulos (2013) was followed to estimate the best fitting ARIMA model for Belize’s arrival and expenditure data:

1. The number of differences d is determined using repeated Kwiatkowski-Phillips-Schmidt-Shin (KPSS) tests.

2. The values of p and q are chosen by minimizing the AIC after differencing the data d times. In a step-wise approach:

(a) The model with the smallest AIC is selected from one of the following:

ARIMA(2,d,2),

ARIMA(0,d,0),

ARIMA(1,d,0),

ARIMA(0,d,1).

If d=0 then the constant c is included; if d≥1 then the constant c is set to zero. This model is then called the "current model".

(b) Variations on the current model are then considered by varying p and/or q from the current model by ±1, and c is included/excluded from the current model.

The lowest AIC is again used to select the best and new current model.

3. Step 2(b) is repeated until no lower AIC can be estimated.

4. Model residuals are checked by plotting the ACF of the residuals, and undertaking a portmanteau test of the residuals. If the residuals do not resemble white noise, a different model is tested. Once the residuals resemble white noise, the model is considered to be well calibrated to the data and  it may be used for forecasting (Hyndman & Athanasopoulos, 2013).

Figure 2 shows the actual and predicted tourist expenditure for Belize; in this chart, both an ARIMA and a Seasonal ARIMA model were estimated. Since monthly data were used, the seasonal fluctuations characteristic of tourism demand are evident. The closeness of fit between predicted and actual expenditure reflects the fact that the model is well calibrated and reproducing the historical data with a reasonable degree of accuracy.

Figure 2. Actual and predicted tourist expenditure for Belize.

Source: Authors’ own elaboration.

Figure 3 depicts ARIMA and SARIMA predictions of monthly foreign overnight tourist arrivals to Belize.

Figure 3. Actual and predicted foreign overnight tourist for Belize.

Source: Authors’ own elaboration.

## 3.2. Foreign Overnight Tourist Arrivals and Expenditure With Program

The next step in demand forecasting is to estimate tourist arrivals and expenditure with program. To estimate demand with program, tourist exit surveys were undertaken during the months of April and May 2015. During this period 1,011 surveys of international tourists were conducted at Belize’s Western border of Benque Viejo del Carmen (126 surveys), the Northern border of Santa Elena (125 surveys), and the Philip Goldson International Airport (760 surveys), Belize’s main international airport.

The sample of 1,011 tourists was subdivided into 8 subsamples. For each of the four destinations (Caye Caulker, Cayo San Ignacio, Corozal, Toledo/Punta Gorda), both tourists that had and had not visited the destination were interviewed. For respondents that had visited the destination, the survey assessed motivation for visiting the destination; activities undertaken (see Table 4 for some of the distinguishing features of the destinations); quality of services, and; quality of experience. Respondents were also asked to rate the quality of features and if they needed improvement, for example, with regard to access, general maintenance, environmental quality, signage, safety, quality and diversity of tourism opportunities). Finally, in a quasi-contingent valuation question, respondents were asked if the features that they identified were improved and the opportunities they identified were available, if they would be willing to visit the destination in the future, and how much in addition to what they had spent on their current trip, would they be willing to spend. In this stated preference approach, the critical assumption is made that STP II will address the concerns voiced by respondents as well as improve the tourism product on offer along the lines of what the respondents expressed demand for.

For those tourists that had not visited the destination, respondents were asked if visiting various sites (e.g. table 4; archaeological sites and national parks) and taking part in specific activities such as diving and caving for example, would persuade them to visit the destination in a future visit. For those that responded in the affirmative, again the respondents were asked the quasi-contingent valuation question of how much they would be willing to spend in a future visit.

Table 4. Distinguishing features of the STP II emerging destinations.

| Site | Distinguishing features and activities |
| --- | --- |
| Caye Caulker | Forest and marine reserves, wildlife sanctuary, beach activities and water sports, sport fishing, barrier reef, blue hole, islands, caves, mangrove, cultural events |
| Cayo San Ignacio | National Parks and Reserves, waterfalls, archaeological sites, caves, bird watching horseback riding, cultural activities |
| Corozal | Wildlife Sanctuary, nature reserve, archaeological sites, beach activities and water sports, sport fishing, bird watching, cultural activities |
| Toledo/Punta Gorda | Marine and ecological reserves, National Parks, caves, archaeological sites, bird watching, cultural activities |

Source: Authors’ own elaboration.

Considering first those tourists who visited the destination they were queried about, across all four destinations, 90% of respondents said they would return to the destination on a future trip to Belize (Table 5). Based on general improvements and increased tourism opportunities proposed under the investment program, tourists reported they would spend on average, across the four sites, of USD $141 per day and USD $1,217 per trip in addition to what they had already spent on the current trip.

Table 5. For those that have visited the destination: willingness to return and willingness to spend (BZD).

Source: Authors’ own elaboration.

Among respondents who did not visit the destination they were queried about, when asked if they would be interested in visiting on a future visit to Belize provided certain tourist activities were available, 86%, 75%, 64%, 73% affirmed that they would visit Caye Caulker, Cayo San Ignacio, Corozal, and Toledo/Punta Gorda, respectively (Table 6). For this group, they reported they would spend, on average, USD $276 per day and USD $554 per trip. The fact that this group of tourists reported a lower willingness to pay than those that had visited the destination is aligned with expectations as they did not visit the first time, and they have less knowledge of the characteristics of the destinations and of the utility they might derive from visiting them.

Table 6. For those that have not visited the destination: willingness to visit in the future and willingness to spend (BZD).

Source: Authors’ own elaboration.

The next step in estimating the with program expenditure was to scale up the values obtained through the survey data to the population. In the case of those that have visited the destination, the total additional expenditure across all destinations was calculated as in equation 2:

TAEa=n=14(RRn∙PVn∙WRn∙ASn∙AV)                                                                     (eqn’ 2)

Where:

- TAEa is total additional expenditure for those that have visited the destination;

- N is destination 1 through 4 representing Caye Caulker, Cayo San Ignacio, Corozal and Toledo/Punta Gorda, respectively;

- RR is visitor return rate;

- PV is percent of total annual visitors to Belize that visit the destination;

- WR is percent of those surveyed that would return to the destination in the future;

- AS is additional spend on future trip, and;

- AV is the total annual foreign overnight holiday/leisure visitors to Belize in 2013.

In the case of those tourists that have not visited the destination they were queried about, their willingness to spend on a subsequent trip was calculated slightly differently as in equation 3.

TAEb=n=14(VRRd∙(1-PVd)∙WRd∙ASd∙YS∙AV)                                                 (eqn’ 3)

Where:

- TAEb is total additional expenditure for those that have not visited the destination;

- N is destination 1 through 4 representing Caye Caulker, Cayo San Ignacio, Corozal and Toledo/Punta Gorda, respectively;

- VRR is visitor return rate estimated from the BTB’s Visitor Expenditure and Motivation Survey (VEMS);

- PV is percent of total annual visitors to Belize that visit the destination;

- WR is percent of those surveyed that would visit the destination in the future;

- AS is additional spend on future trip;

- YS is a ‘yea-sayer’ factor (a conservative 0.05 in this paper) which takes into account the reality that although many respondents may say they will visit in the future, the actual likelihood that they will is much lower, and;

- AV is the total annual foreign overnight holiday/leisure visitors to Belize in 2013.

Table 7. With program tourism expenditure calculations; all dollars are BZD.

Source: Authors’ own elaboration; calculations based directly on tourist exit survey data.

The sum of TAEa+TAEb is the estimated total additional with program expenditure. Table 7 summarizes the additional with program expenditure calculations. The table shows that the total additional spend for those that have visited the destination is over BZ$55 million while that of those who have not visited the destination is over BZ$9.2 million. The total additional estimated with program expenditure is BZ$64,838,194. This figure is a key input into the DCGE model for estimation of indirect and induced benefits, as well as for the cost-benefit analysis. Since the DCGE model is an annual model, the monthly expenditure data presented in Figure 2 was aggregated on an annual basis.

Given the DCGE model is an annual model, the distribution of the additional expenditure over time must be determined. In the absence of data to inform this distribution, an assumption needs to be made; the additional expenditure may for example be distributed linearly, or according to another functional form. In this paper, benefits were distributed according to a logistical function as shown in figure 4. According to this functional form, benefits begin accruing in 2018 allowing 2 years following STP II’s first disbursement. By the year 2025, almost 27% of the benefits will have materialized, while by 2030, almost 82% of the benefits will be realized. By 2032, 92% of the benefits will be realized; 100% of the benefits will have materialized by 2040.

Figure 4. Logistical function distribution of with program additional expenditure.

Source: Authors’ own elaboration.

Figure 5 presents with and without program forecasted tourist expenditure. In year 2040, the difference between the predicted with and without program tourist expenditure is equal to BZ$64,838,194.

Figure 5. Actual tourist expenditure, and; predicted without and with program tourist expenditure.

Source: Authors’ own elaboration.

In addition to the temporal distribution of the additional expenditure, it is also necessary to know the approximate distribution of this BZ$64.8 million across commodities in the SAM. The composition of tourism expenditure was derived from the tourist exit surveys which was further validated through verification with the only other earlier reliable source on tourist expenditure patterns released by the Central Bank in 1992 (Lindberg & Enriquez, 1994; Morgan & Campbell, 1992). The resulting composition of tourism expenditure at the national level was estimated as 40% accommodations, 26% food and beverage, 25% gifts and other purchases, and 10% transportation. Across SAM accounts, this expenditure is allocated as in figure 6.

Figure 6. Additional with program tourist expenditure across SAM accounts.

Source: Authors’ own elaboration.

# IV. Costs and Break-Even Demand

## 4.1. Investment Structure and Sequencing

The total STP II investment is BZ$30 million, BZ$21 million of which is destined for investment in infrastructure. Disbursements are to begin gradually in 2016 with the last disbursement in 2020. The disbursement schedule is 6.67% in the first year, 16.67% in the second year, 26.67% in the third year, 33.33% in the fourth year and 16.67% in the final year. Operations and maintenance costs are estimated as 5% of the cost of the infrastructure investment on an annual basis for the entire period of analysis.

Details of the specific investment components may be found in the Pluri-annual Execution and Procurement Plan for the program (Lemay et al., 2015). In summary, in terms of infrastructure, the program will invest in the restoration and enhancement of archeological, cultural and natural attractions, basic infrastructure, and key services to create an enabling environment for private investment. In addition to infrastructure, other program components will finance the development of management and other plans such as a disaster and climate resilience plan, protected areas management plans, and various feasibility studies. Finally, the program will invest in institutional strengthening, capacity building and improving tourism-sector data systems.

## 4.2. Break-even Demand

An optimization routine was programmed in MS Excel to estimate the minimum increase in tourism demand required for the STP II to be economically viable. This optimization routine solves for a scaling factor which is multiplied with the without program benefits. The optimization routine identifies the scaling factor for which the net present value (NPV) of the difference between the scaled benefits net of the program investment costs and the net with program benefits is equal to zero using a discount rate of 12%.

Figure 7. Break-even analysis; without program, net with program and break-even net with program benefits.

Source: Authors’ own elaboration.

Based on the optimization routine, it was calculated that the minimum increase in tourism expenditure for the program to be economically viable was significantly lower than the expected increase in tourism demand estimated in section III. To put this into perspective, in year 2040, the difference in without program benefits and break even with program benefits is BZ$6.3 million, whereas the difference in the without program benefits and net with program benefits estimated based on tourism demand projections is equal to BZ$63.8 million. The proximity of the break-even net benefits with program graphed line in figure 7 and the without program benefits line is illustrative of this.

## 4.3. Preliminary Cost-benefit Analysis

Based on the analysis and projections developed thus far, it is possible to conduct a cost-benefit analysis of the program using only the estimates of direct benefits and costs. If time or resources were not available for a DCGE to be developed, this preliminary analysis would provide an indication of the net returns to the investment. Using the IDB’s discount rate of 12%, the NPV of the investment was estimated at BZ$100.156 million with an internal rate of return (IRR) of 31%. Thus, assuming resources are in abundant supply (no labor, capital or other factor constraints), the program is likely to do much better than just break-even.

# V. Estimating Economic Returns

## 5.0. CGE Scenario Design

This section presents the simulations and analyzes the results from the DCGE model. The following five scenarios were conducted: (a) the baseline scenario, which is the without program scenario; (b) a government investment in tourism infrastructure, institutional strengthening, capacity building and baseline studies; (c) an increase in foreign overnight leisure tourism expenditure; (d) scenarios (b) and (c) implemented jointly, and; (e) a break-even scenario which uses the minimum increase in tourism expenditure required for the program to be economically viable at a 12% discount rate. Details of each scenario follow:

Baseline scenario: this first simulation assumes that average past trends will continue from FY 2011 to FY 2040. In the absence of better projections, it is assumed that Belize is on a balanced growth path, which means that real (i.e. volume) variables grow at the same rate while relative prices do not change. The non-base simulations that follow only deviate from the base beginning in FY 2016 to FY 2040; 2016 is the first year of STP II loan disbursements, while benefits begin to accrue beginning in 2018.

Invest scenario: this simulation imposes increased government investment in tourism infrastructure, institutional strengthening, capacity building and baseline studies financed with the IDB loan. Details of the structure and sequencing of the investment were provided in section 4.1 of this paper. Figure 8 shows how this investment is distributed with respect to the baseline.

Demand scenario: in this simulation, foreign leisure tourist overnight arrivals and expenditure increase. This scenario is based on the with program demand projections developed in section 3.2 of this paper. It is assumed that this increase in demand begins in 2018 and is distributed according to a logistical function, reaching 100% of the increase in demand in the final year of the period of analysis (Figure 8).

Combi scenario: this scenario models the invest and demand scenarios combined.

Combi-BE scenario: this scenario is similar to the previous scenario, but uses the estimated minimum increase in foreign overnight leisure tourism demand required for the program to break even at a 12% discount rate (Figure 8).

Figure 8: Definition of scenarios invest and demand (% deviation from base)

Source: Authors’ own elaboration.

At the macro level, a DCGE model requires the specification of the equilibrating mechanism for three macroeconomic balances. For the non-base scenarios: (a) the government fiscal account is balanced via adjustments in transfers to and from the rest of the world; (b) private investment in Belize follows an exogenously imposed path, and; (c) the real exchange rate equilibrates inflows and outflows of foreign exchange by influencing export and import quantities. The non-trade-related payments of the balance of payments (transfers and foreign investment) are non-clearing and follow exogenously imposed paths.

The base year of the model is FY 2011. For the base scenario, which serves as a benchmark for comparisons, an average growth of 2.5 percent is imposed, based on projections from the 2015 IMF World Economic Outlook (IMF, 2015). In addition, due to the assumption of a balanced growth path, the following assumptions are also imposed: (a) macro aggregates are kept fixed as a share of regional GDP at base year values; (b) transfers to and from the government and the rest of the world to households are also kept fixed as a fixed share of GDP; and (c) tax rates are fixed over time.

## 5.1. Model Results

### 5.1.1. Aggregate Results

Figure 9 shows that as a result of the investment shock (INVEST), there is a small spike in private consumption during the 5 year disbursement period. Private consumption then returns to close to baseline levels, though growing slightly more quickly. The DEMAND scenario shows the gradual increase in tourism demand while the COMBI and COMBI-BE both show the initial spike in consumption due to the investment shock and the subsequent demand  response which increases gradually after 2018, and at a faster rate sometime after 2028. This figure also shows a significant difference in private consumption between the COMBI and the breakeven COMBI scenarios. Figure 10 shows similar trends for gross domestic product.

Figure 9. Change in real private consumption 2016-2040.

Figure 10. Change in real gross domestic product 2016-2040.

Source: Authors’ own elaboration.

Table 7 shows how macro indicators respond to the various shocks. Considering the INVEST scenario, following the spike in government investment due to the program investment, investment begins to return to close to baseline levels by 2025 and even closer by 2040. Private investment grows slightly slower by 2025 due to a small crowding out effect resulting from the large government investment, however, it recovers shortly afterwards. To some extent, this response changes when labor and capital are in greater supply. In other words, if wage increases are constrained and extra labor used would otherwise have been unemployed, these types of crowding out effects may be less substantial.

Stimulated by the enabling environment, private investment begins to grow more quickly and reaches 0.13% by 2040. Considering the demand shock, while there is a small contraction in exports by 2025, exports fully recover and grow more quickly (2.42%) by 2040. The large demand shock also has a large impact on all other indicators, especially private investment growing over 10% above the baseline by 2040. Private consumption is also stimulated and the unemployment rate drops from 12% to 10.32% by 2040.

Table 7. Change in real macro indicators (percent deviation from base).

Source: Authors’ own elaboration.

Considering the COMBI shock, all indicators are positive by 2025 except again for exports which is a result of the large increase in domestic demand due to both the investment and tourism demand shock. The increase in foreign tourism demand in this scenario is also slightly greater than when the demand shock is imposed alone. The impact on GDP is the greatest in this scenario as would be expected from the joint impact of the public investment and concomitant increase in foreign tourism demand. By 2040, GDP is 3.26% greater than in the baseline. The employment generating impact of this scenario is also the greatest among scenarios, with unemployment falling to 10.26% by 2040.

Finally, the COMBI-BE shock represents the economic impact that would result from tourism demand expanding just enough to cover the direct and indirect costs of the public investment. Results for this scenario show that even in this somewhat pessimistic scenario, the public investment results in positive indirect and inducted effects as exhibited through the increase in GDP, 0.70% above the baseline in 2040. Exports and (0.65%) private investment (2.16%) also grow faster while unemployment falls to 11.62% by 2040.

### 5.1.2. Sectoral Results

Table 8 shows impacts on value added. Considering the INVEST scenario, impacts in the early years are slightly negative for those sectors not receiving program investment which represents a reallocation of resources to those sectors most closely linked to the investment such as travel, transport and retail, as well as business and recreational services. There is a slight decline in export value-added of the larger exporting sectors due to the increase in domestic demand for goods and services. By 2040, export value added for almost all sectors is positive.

Table 8. Change in sectoral real value added, exports, and imports (percent deviation from base).

Source: Authors’ own elaboration.

In the DEMAND scenario, there is a positive impact on those sectors producing goods and services most highly demanded by tourists. Imports are also stimulated while exports contract early on. All indicators are positive soon after 2025, again with the largest positive impacts experienced by those sectors servicing the tourism and related sectors. With greater foreign exchange earnings, imports of key sectors also rise by 2025 and to a greater extent by 2040.

Considering the COMBI scenario, while there is some reallocation of resources toward tourism-related sectors in the early years, with some levels of non-tourism related activities declining slightly, the activities of these sectors increase shortly after 2025 and by 2040, all sectors are growing more quickly than in the baseline with exports and import value added for key trading sectors also growing more quickly than in the baseline. The COMBI-BE scenario generates results similar to those of COMBI, though percent deviations are generally less pronounced as would be expected. Certainly, the key mechanisms which determine the size of the economic impacts across sectors resulting from increased tourism demand include: factor supply constraints, exchange rate appreciation, and current government economic policy (Banerjee et al., 2015b; Dwyer, Forsyth, Madden, & Spurr, 2000).

## 5.3. Cost-Benefit Analysis

The results of the COMBI scenario represent the direct, indirect and induced economic impacts of government investment in STP II combined with an increase in inbound overnight leisure tourism demand, given the model assumptions. Thus, given that the project cost is part of the simulations, the cost-benefit analysis can be conducted by simply analyzing the DCGE results for the indicator of interest, which in this national model is GDP. In other words, the simulated impacts using the DCGE model provide the benefit and cost estimates for this calculation. Notice, however, that conventional cost-benefit accounting does not capture all of the indirect and induced benefits captured by simulations using DCGE models.

Using model results and nomenclature to calculate NPV, equation 3 is first solved:

INVNETINC(sim, t)=SIMGDPsim,t-BASEGDP(sim,t)-RGFCBAR2SIM("inv", inv,t)-QGBAR2SIM("inv",c,t)                                                                                                      (eqn’ 3)

Equation 3 uses model variables for calculating the net returns from each simulation, where:

- Sim is a set of model simulations which include the investment (INVEST, COMBI, COMBI-BE);

- T is the time period from t = 0 to t = 24;

- INVNETINC is the net return ;

- SIMGDP is simulated GDP estimated by the DCGE model;

- BASEGDP is the base forecast GDP estimated by the DCGE model;

- RGFCBAR2SIM is the government capital investment in STP II, and;

- QGBAR2SIM is the component of the STP II government investment allocated to the purchase of goods and services.

The series of results arising from equation 3 are then used in equation 4 to calculate NPV.

Analytically:

(eqn’ 4)

Where:

= net present value;

is 2016;

is 2040;

= indicator of interest (GDP in this case) in year t;

= indicator of interest in year t in reference scenario, and;

= discount rate (12%).

Table 9 shows that NPV is the highest in the COMBI scenario, reaching BZ$127.88 million; for the DEMAND scenario, the NPV is slightly less at BZ$121.222. The COMBI-BE scenario shows that there is considerable room for tourism demand to respond in a manner below expectations, with the COMBI-BE NPV equal to BZ$23.4 million. The internal rates of return for each of the three scenarios are all reasonably high, from 21% in COMBI-BE to 31% in the COMBI scenario.

Table 9. Net Present Value (NPV) and Internal Rate of Return (IRR), BZD.

Source: Authors’ own elaboration.

While it may seem curious that the breakeven NPV is greater than zero, this is due to the fact that the break-even minimum increase in tourism demand was calculated outside the model. This is a reflection of the strength of the DCGE analytical framework, which enables estimation of second and third round benefit streams in the form of indirect and induced benefits.

# VI. Sensitivity Analysis

Results of the DCGE model are a function of (i) the model structure (e.g., functional forms used to model production and consumption decisions, macroeconomic closure rules, among other elements); (ii) the base year data used for model calibration (i.e., the SAM), and; (iii) the values assigned to the model elasticities.

The elasticities used in this study implicitly carry an estimation error, as in any similar model. Consequently, a systematic sensitivity analysis of the results was performed with respect to the value assigned to the model elasticities. If the conclusions of this analysis are robust to changes in the set of elasticities used for model calibration, there will be greater confidence in the results generated by the model.

In order to perform the systematic sensitivity analysis, it is assumed that each of the model elasticities is uniformly distributed around the central value used to obtain the results presented in the main text. The range of variation allowed for each elasticity is plus or minus 80%; this represents a wide range of variation for each model elasticity. A variation of the method originally proposed by Harrison and Vinod (1992) was implemented for the systematic sensitivity analysis (Harrison & Vinod, 1992). The aim is to solve the model iteratively with different sets of elasticities. A distribution of results is obtained through this process which enables the construction of confidence intervals for each of the model results. The steps in undertaking the sensitivity analysis are as follows:

Step 1. In the first step, the distribution (i.e., lower and upper bound) for each of the model parameter that will be modified as part of the systematic sensitivity analysis was computed. These were: elasticities of substitution between primary factor of production, trade-related elasticities, expenditure elasticities, and unemployment elasticities for the wage curves.

Step 2. In the second step, the model is solved repeatedly, each time employing a different set of elasticities; it is, therefore, a "Monte Carlo" type of simulation. First, the value for each model elasticity was randomly selected. Second, the model was calibrated using the selected elasticities. Third, the same counterfactual scenarios as described in this paper were executed. Then, the preceding steps were repeated several times, 250 in this case, with sampling with replacement for the value assigned to the elasticities.

Table 10. Sensitivity analysis; real private consumption percent deviation from base; year 2040
95% confidence interval under normality assumption.

Source: Authors’ own elaboration.

Table 10 shows the percentage change in private consumption estimated (i) under the central elasticities, and; (ii) as the average of the 250 observations generated by the sensitivity analysis. For the second case, the upper and lower bounds under the normality assumption were also computed; notice that all runs from the Monte Carlo experiment receive the same weight. As can be seen, the results reported in the main text are significant; the estimates presented in Table 7 are within the confidence intervals reported in Table 10. For example, there is virtual certainty that the COMBI scenario, or the government investment in STP II and expected increase in tourism demand, has a positive effect on private consumption in Belize.

Figure 11. Sensitivity analysis, real private consumption deviation from base in 2040; COMBI scenario.

Source: Authors’ own elaboration.

Figure 11 shows non-parametric estimates of the density function for the percentage change in 2040 in private consumption in the COMBI scenario. This figure shows that the positive sign of the results is not changed when model elasticities are allowed to differ by plus or minus 80% of their central value.

# VII. Concluding Remarks

This paper evaluated ex-ante the economic impact of the Sustainable Tourism Program II (BL-L1020). A DCGE model was developed for Belize to estimate the net returns from the investment. The approach developed in this paper innovates on previous approaches by: (i) developing a generalizable approach to building DCGE models in data poor environments; (ii) constructing data-driven ARIMA and SARIMA models to forecast tourist arrivals and expenditure, and; (iii) estimating with program tourism demand through a quasi-contingent valuation approach.

Results of this analysis show that STP II will have positive impacts on Belize’s economy by stimulating GDP to grow 3% greater by 2040 compared to the without investment baseline, and reducing unemployment from 12% to 10%. Cross validating with a break-even scenario shows that even if the actual increase in tourism demand were considerably less than the with program forecast, the Government of Belize would still recover all costs of investment. The systematic sensitivity analysis confirms that the model and results are robust to significant variation in key model parameters.

A critical caveat must be mentioned. The SAM and DCGE model were built based on the GTAP database which is an estimation of the structure of Belize’s economy. Based on this GTAP extract, the database was customized based on external data sources and a restructuring of the SAM required for calibration of the DCGE. There are significant improvements that could be made to the aggregate SAM developed in this study. With more accurate and disaggregated national accounts information, the SAM could be constructed relying less on the GTAP database and more on data reported by the country. If and when input output tables are available for Belize, these can also be used in reconstructing the SAM so that Belize-specific technology is better represented. Finally, government accounts and balance of payments data, at a disaggregated level, would enable a much better representation of Belize’s taxation system as well as its transactions with the rest of the world in the form of trade and investment. The SAM developed here should be considered a starting point, not an end point.

This paper builds on the framework developed in Banerjee et al. (2015). Data issues aside, there are still ways in which the analysis may be improved. As discussed, model results are highly sensitive to with program tourism demand projections. This aspect of the data generation and analysis process may still be improved. If more detailed information were available on the investment program prior to the implementation of tourist exit surveys, a choice modelling study could be developed to assess in a more rigorous way, tourist willingness to pay for specific program attributes and different levels and combinations of those attributes. At a minimum, knowledge of some of the larger investments that would comprise the program could be used to refine the scenario presented to tourists in the choice modelling study. This information would lead to more accurate with program demand projections, and consequently, a more accurate assessment of returns to large public investments in tourism development.

References

Banerjee, O., Cicowiez, M., & Gachot, S. (2015a). A Framework for Ex-Ante Economic Impact Assessment of Tourism Investments- An Application to Haiti. Retrieved from Washington DC:

Banerjee, O., Cicowiez, M., & Gachot, S. (2015b). A Quantitative Framework for Assessing Public Investment in Tourism – An Application to Haiti. Tourism Management, 51, 157-173. doi:http://dx.doi.org/10.1016/j.tourman.2015.05.015

Becketti, S. (2013). Introduction to Time Series Using Stata. College Station: A Stata Press Publication.

Belize Tourism Board. (2015). Travel and Tourism Statistics Digest. Retrieved from Belize City:

Blanchflower, D. G., & Oswald, A. J. (2004). Well-Being Over Time in Britain and the USA. Journal of Public Economics, 88(7-8, Jul), 1359-1386.

Central Bank of Belize. (2015). Key Tourism Indicators. Retrieved from Belize City: https://www.centralbank.org.bz/rates-statistics/economic-indicators

Dwyer, L., Forsyth, P., Madden, J., & Spurr, R. (2000). Economic Impacts of Inbound Tourism under Different Assumptions Regarding the Macroeconomy. Current Issues in Tourism, 3(4), 325-363. doi:10.1080/13683500008667877

Harrison, G. W., & Vinod, H. D. (1992). The Sensitivity Analysis of Applied General Equilibrium Models: Completely Randomized Factorial Sampling Designs. The Review of Economics and Statistics, 74(2), 357-362. doi:10.2307/2109672

Horridge, J. M. (2006). GTAP 6 Data Base Documentation, Chapter 11.M: Albania. Retrieved from West Lafayette: https://www.gtap.agecon.purdue.edu/resources/res_display.asp?RecordID=1800

Hyndman, R. J., & Athanasopoulos, G. (2013). Forecasting Principles and Practice: OTexts.

IMF. (2015). World Economic Outlook Database. Retrieved from Washington D.C.: https://www.imf.org/external/pubs/ft/weo/2015/01/weodata/index.aspx

Lemay, M., Nuenninghoff, S., Rogers, C., Velasco, M., Banerjee, O., Schueler, K., . . . Chavez, E. (2015). Belize- Sustainable Tourism Program II Retrieved from Washington DC:

Lindberg, K., & Enriquez, J. (1994). An Analysis of Ecotourism's Economic Contribution to Conservation and Development in Belize. Retrieved from Belize City:

Lofgren, H., Harris, R. L., Robinson, S., Thomas, M., & El-Said, M. (2002). A Standard Computable General Equilibrium (CGE) Model in GAMS. Washington, D.C.: IFPRI Retrieved from http://www.ifpri.org/pubs/microcom/5/mc5.pdf.

Morgan, M., & Campbell, S. (1992). Belize Tourism Industry. Retrieved from Belize City:

Narayanan, B., Aguiar, A., & McDougall, R. (2015a). Global Trade, Assistance and Production: The GTAP 9 Data Base. Retrieved from West Lafayette: https://www.gtap.agecon.purdue.edu/databases/v9/v9_doco.asp

Narayanan, B., Aguiar, A., & McDougall, R. (Eds.). (2015b). Global Trade, Assistance and Production: The GTAP 9 Database. West Lafayette: Center for Global Trade Analysis, Purdue University.

Nau, R. (2015). Statistical Forecasting: Notes on REgression and Time Series Analysis. Retrieved from Durham: http://people.duke.edu/~rnau/411home.htm

OECD. (2010). National Accounts at a Glance 2009: OECD Publishing.

Robinson, S., Cattaneo, A., & El-Said, M. (2001). Updating and estimating a social accounting matrix using cross entropy methods. Economic Systems Research, 13(1), 47-64.

Robinson, S., & El-Said, M. (2000). GAMS Code for Estimating a Social Accounting Matrix (SAM) Using Cross Entropy (CE) Methods. Retrieved from Washington D.C.:

Round, J. (2003). Constructing SAMs for Development Policy Analysis: Lessons Learned and Challenges Ahead. Economic Systems Research, 15(2), 161-183. doi:10.1080/0953531032000091153

SIB. (2015). GDP by Activity 1992 - 2013. Retrieved from Belize City: http://www.sib.org.bz/statistics/gross-domestic-product

UN. (2015). World Population Prospects: The 2012 Revision. Retrieved from New York: http://esa.un.org/unpd/wpp/unpp/panel_population.htm

World Bank. (2015). World Development Indicators [Press release]. Retrieved from http://data.worldbank.org/data-catalog/world-development-indicators

# APPENDIX A: MATHEMATICAL STATEMENT OF THE DCGE MODEL

A.1. Introduction

The mathematical presentation of the DCGE uses some notational conventions: capital letters for endogenous variables, lowercase letters for exogenous variables, and Greek letters for behavioral parameters. The endogenous variables with an over bar are assumed to be exogenous as part of the “closure rule” of the model. Besides, all variables at time (t-1) are exogenous at time t. The following set names also apply:

a = activities

c = commodities

i = institutions (i.e., households, enterprises, government, rest of the country, and rest of the world)

insdng = domestic non-government institutions

h = households

e = enterprises

gov = government

roc = rest of the country

row = rest of the world

inv = investment

invg = government investment

invng = non-government investment

A.2. Equations and Variables

Endogenous Variables

average remuneration of factor f

tfp in calibration run

household consumption expenditure

consumer price index

index for domestic producer prices (PDS-based)

government expenditure

exchange rate (dom. currency per unit of for. currency)

government demand scaling factor

gross fixed capital formation

non-government investment by destination

government capital stock

marginal propensity to save for dom non-government inst insdng

savings rate scaling factor

output price of activity a

demand price for comm c produced and sold domestically

price for composite QD-QER

price for composite QD-QMR

supply price for comm c produced and sold domestically

export price for c (domestic currency)

RoC export price for c (domestic currency)

price of intermediate aggregate

replacement cost of capital

import price for c (domestic currency)

RoC import price for c (domestic currency)

composite commodity price for c

value-added price for activity a

producer price for commodity c

level of activity a

quantity sold domestically of domestic output c

QD-QER aggregate for comm c

QD-QMR aggregate of comm c

quantity of exports for commodity c

quantity of exports to RoC for commodity c

quantity demanded of factor f from activity a

supply of factor f

quantity of government demand for commodity c

quantity consumed of commodity c by household h

quantity of commodity c as intermediate input to activity a

quantity of aggregate intermediate input

quantity of investment demand for commodity c

quantity of imports of commodity c

quantity of imports from RoC of commodity c

quantity of goods supplied domestically (composite supply)

RoC tourism demand quantity of comm c

RoW tourism demand quantity of comm c

quantity of trade and transport demand for commodity c

quantity of aggregate value added

quantity of domestic output of commodity c

real exchange rate

real GDP at factor cost (at constant base-year prices)

real gross fixed capital formation

real government savings

government savings

savings domestic non-government institution i

RoC savings (foreign currency)

foreign savings (foreign currency)

total factor productivity index

transfers from dom inst insdng to inst ins

unemployment rate for factor f

dummy variable (zero at equilibrium)

average price of factor f

wage distortion factor for factor f in activity a

factor income

government revenue

income of (domestic non-government) institution insdng

income of institution ins from factor f

Parameters and Exogenous Variables

share for inst ins in the income of factor f

marginal propensity to save for dom non-gov inst insdng

quantity of government demand for commodity c

real gross fixed capital formation

rate of tax on producer gross output value

rate of sales tax

rate of direct tax on dom inst ins

rate of direct tax on factor income

rate of factor use tax

export tax rate for commodity c

import tariff rate for commodity c

transfers from insp to ins or factor

share of inst ins in post-tax post-sav income of inst insp

export price for c (foreign currency)

import price for c (foreign currency)

export price for c to RoC (foreign currency)

import price for c from RoC (foreign currency)

changes in inventories

trade and transport input of c per unit of comm cp produced and sold domest

trade and transport input of c per unit of comm cp exported

trade and transport input of c per unit of comm cp imported

trade and transport input of c per unit of comm cp exported to RoC

trade and transport input of c per unit of comm cp imported from RoC

RoC tourism demand quantity of comm c

RoW tourism demand quantity of comm c

share parameter for CES activity production fn

efficiency parameter in the value added production fn for a

elasticity of substitution between factors

exponent in the value added production fn for a

exogenous component of sectoral TFP

yield of output c per unit of activity a

intermediate input c per unit of aggregate intermediate

aggregate value added coefficient for act a

aggregate intermediate input coefficient for act a

marg shr of hhd cons on commodity c

subsist cons of com c for hhd h

Armington function share parameter for imports commodity c

Armington function share parameter for composite QDMR commodity c

Armington function shift parameter for commodity c

elasticity of substitution between dom goods and imports for c

Armington function exponent for commodity c

CET function share parameter for exports commodity c

CET function share parameter for composite QDER commodity c

CET function shift parameter for commodity c

elasticity of transformation between dom sales and exports for c

CET function exponent for commodity c

Armington function share parameter for RoC imports commodity c

Armington function share parameter for domestic commodity c

Armington function shift parameter for commodity c

elasticity of substitution between dom goods and imports for c

Armington function exponent for commodity c

CET function share parameter for RoC exports commodity c

CET function share parameter for domestic commodity c

CET function shift parameter for commodity c

elasticity of transformation between dom sales and exports for c

CET function exponent for commodity c

constant price elasticity of RoC tourism demand (< 0)

constant price elasticity of RoW tourism demand (< 0)

consumer price index weights

domestic sales price weights

elasticidad-desempleo del salario factor f

productivity term for factor f in act a

velocidad movilidad del capital entre actividades

quantity of commodity c per unit of investment inv

depreciation rate for non-government capital

depreciation rate for government capital

Equations

Production Function

Top Level: Value Added Demand

(PF1)

Top Level: Intermediate Inputs Demand

(PF2)

Second Level: Value Added

(PF3)

(PF4)

(PF5)

Second Level: Intermediate Inputs

(PF6)

Production Commodities

(PF7)

Production Prices

(PF8)

(PF9)

(PF10)

Trade with RoC

RoC Prices

(TC1)

(TC2)

QDD + QMR

(TC3)

(TC4)

(TC5)

QDS + QER

(TC6)

(TC7)

(TC8)

International Trade

World Prices

(TW1)

(TW2)

Supply of Products -- Dom + Imp

(TW3)

(TW4)

(TW5)

(TW6)

Demand of Products -- Dom + Exp

(TW7)

(TW8)

(TW9)

Incomes and Savings

Factors

(Y1)

(Y2)

Domestic Non-Government Institutions;

(Y3)

(Y4)

(Y5)

(Y6)

Households

(Y7)

Government

(Y8)

(Y9)

(Y10)

(Y11)

Rest of the World

(Y12)

Rest of the Country

(Y13)

Final Consumption

Households

(FD1)

Investment

(FD2)

Government

(FD3)

Trade and Transport Margins

(FD4)

Tourism Demand (RoC and RoW); exogenous if eta_roct = 0 and eta_rowt = 0

(FD5)

(FD6)

Unemployment

(U1)

Equilibrium Conditions

Factor Markets

(EQ1)

Commodity Markets

(EQ2)

Savings-Investment

(EQ3)

Miscellaneous

Consumer Price Index

Index for Domestic Producer Prices

Real Exchange Rate

Real GDP at Factor Cost

Investment by Destination; Dynamics

(D1)

(D2)

(D3)

(D4)

(D5)

Government RGFCF

(D6)

(D7)

# APPENDIX B: OVERVIEW OF A SOCIAL ACCOUNTING MATRIX

A SAM is a matrix representation of the interrelationships existent in an economy at the level of individual production sectors, factors, and institutions. As stated in Round (2003), “it is a comprehensive, flexible, and disaggregated framework which elaborates and articulates the generation of income by activities of production and the distribution and redistribution of income between social and institutional groups” (Round, 2003).

The SAM is composed of accounts. For each of these, a cell represents a payment column-wise and a receipt row-wise. Hence, columns represent expenditures for each account whereas rows record the matching incomes. Due to the accounting consistency of the SAM, total expenditure of every account must be equal to its total income. In other words, the total of every row must be equal to the corresponding total of the column. The basic structure of a RSAM is presented in Table B.1.

Table B.1: stylized regional social accounting matrix

Source: Authors’ own elaboration.

Definitions: com = commodities, dom-prod = domestic production, gov = government, RoC = rest of the country, RoW = rest of the world, IO = intermediate consumption, VA = value added, T = taxes, M = imports, INC-F = factor income to/from abroad, TR = transfers, C = private consumption, G = government consumption, E = exports, I = investment, SH = households savings, SG = government savings, and; SF = foreign savings.

The logic behind the SAM transactions is the following. Activities buy intermediate inputs; pay for factors of production, thus generating the value added at factor prices; and pay indirect taxes. All these expenditures are financed with the payments that each activity receives for the sale of its output.

Aggregate supply and demand are both recorded in the commodities accounts. For each commodity, the corresponding account records the sales of aggregate supply (domestic output plus imports from the rest of the country and the rest of the world, and related taxes) as follows: to activities as these demand intermediate goods; to households, government and investment as these demand final goods; and to the rest of the country and the rest of the world as these demands the regions’ exports.

Factors earn returns from their involvement in domestic and foreign (including the RoC) production, and they distribute them, net of taxes, to their owners which generally are households and enterprises.

Institutions (households, enterprises, government, rest of the country, and rest of the world) receive incomes from production factors and (net) transfers that can be either spent in purchasing commodities or saved.

Savings from households, the local and central governments (that is, the current account balance), the rest of the country, and the rest of the world (that is, the current account balance with an opposite sign) add to aggregate savings and these, in turn, are equal to the level of investment in the regional economy.

Gross regional product (GRP) at factor cost builds as activities remunerate factors of production, that is, value added. GRP at market prices equals GRP at factor cost plus indirect taxes and tariffs, which should also be equal to total final demand plus exports minus imports, both from the RoC and RoW.

It is important to emphasize that the SAM extracted and customized here is an estimation of the structure of Belize’s economy. There are significant improvements that could be made to this aggregate SAM. With more accurate and disaggregated national accounts information, the SAM could be constructed relying less on the GTAP database and more on the data reported in the national accounts. If and when input output tables become available for Belize, these may be used in reconstructing the SAM so that Belize-specific technology is better represented in the SAM. Finally, government accounts and balance of payments data, at a disaggregated level, would enable a much better representation of Belize’s taxation system as well as its transactions with the rest of the world in the form of trade and investment.

Summary tables of the tourist exit survey results may be found in: Knight, M. (2015). Tourism Market Study and Identification of Investments for the Sustainable Tourism Program II in Belize (BL-L1020). Washington DC: KnightConsult LLC.

Ideally, if time and resources permitted, a choice modelling study would be undertaken to assess tourists’ willingness to pay for key attributes of STP II.

The exogenous part of total factor productivity growth is adjusted to generate such a growth path. In non-base scenarios, GDP growth is endogenous.

The closure rule determines the mechanisms equalizing demand and supply in all markets featuring the model.

The SAM does not separate enterprises from the households. A single account, named hhd, is taken as representative of the domestic private sector.