## PP
Project Name: Public Sector Smart Energy Programme
Loan 2748/OC-BA and ATN/EX-13316-BA
Procurement Plan for the period January 1, 2017 to June 30, 2018
Item No. | WBS No. | Procurement Description | Procure- ment Type | Estimated Contract Cost | Method | Review Type | Financing Source (IDB %) | Financing Source (EU%) | Financing Source (GOB%) | Prequali-fication (Y/N) | Publication of SPN | Est. Contract Signature Date* | Procure-ment Status | Estimated Contract Completion Date | Comments
1 | 1.1.1.2 | 24,500 LED streetlights | Goods | 8397550 | ICB | Ex-Ante | 38.5 | 61.5 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q4, 2018 | Procurement of 25,000 LED streetlights
2 | 1.1.1.4 | Procurement - Light measuring Equipment | Goods | 2583 | PC | Ex-Poste | 38.5 | 61.4 | 0 | No | Q1 2015 | Q3 2015 | Awarded | Completed | Procurement of Light Measuring Equipment
3 | 1.1.1.6 | 3,000 LED Streetlights Fixtures | Goods | 1500000 | ICB | Ex-Ante | 38.5 | 61.5 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q1, 2018 | Procurement of 3,000 LED Streetlights
4 | 1.2.1.1 | Procurement of energy efficient retrofits for 12 public buildings | Goods | 3407692 | ICB | Ex-Ante | 100 | 0 | 0 | No | Q3, 2017 | Q4, 2017 | Pending | Q4, 2018 | Supply and Installation for the retrofit Energy Efficient Technologies
5 | 1.2.1.2 | Procurement of an Energy Performance Contract for 1 public building | Goods | 742308 | ICB | Ex-Ante | 100 | 0 | 0 | No | Q2, 2017 | Q3, 2018 | Pending | Q4, 2018 | Procurement of an Energy Service Company to undertake an Energy Performance Contract for the retrofit of one government owned building
6 | 1.3.1.1 | Procurement of photo voltaic systems for 12 public buildings | Goods | 5484221 | ICB | Ex-Ante | 100 | 0 | 0 | No | Q3, 2016 | Q4, 2016 | In Process | Q2, 2017 | Supply and installation of solar photo voltaic electricity generation systems
7 | 2.1.1.1 | Public electric vehicles | Goods | 300000 | DC | Ex-Ante | 34 | 0 | 66 | No | n.a. | Q1, 2017 | Pending | Q2, 2017 | Procurement of 6 electric vehicles.
8 | 2.1.1.2 | Public electric vehicles | Goods | 113369 | NCB | Ex-Ante | 100 | 0 | 0 | No | n.a. | Q2, 2016 | Complete | Q2, 2016 | Procurement of 2 electric vehicles.
9 | 2.1.2.3 | Electric vehicle charging units | Goods | 7500 | DC | Ex-Ante | 100 | 0 | 0 | No | n.a. | Q1, 2017 | Pending | Q2, 2017 | Procurement of 6 electric vehicle charging units.
10 | 2.1.2.4 | Electric vehicle charging units | Goods | 2500 | DC | Ex-Ante | 100 | 0 | 0 | No | n.a. | Q2, 2016 | Complete | Q3, 2016 | Procurement of 2 electric vehicle charging units.
11 | 3.1.3.2 | Laboratory equipment - primary, secondary and tertiary institutions | Goods | 200000 | ICB | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q1, 2018 | Procurement of solar photo-voltaic kits for school laboratories
12 | 2.2.3.1 | Procurement of Ocean Energy Data Collection software | Goods | 100000 | NCB | Ex-Ante | 0 | 100 | 0 | No | Q1, 2018 | Q2, 2018 | Pending | Q4, 2018 | Procurement of software for ocean energy data collection
13 | 2.1.2.2 | Construction of Solar PV charging station | Works | 75000 | NCB | Ex-Ante | 100 | 0 | 0 | No | Q3, 2017 | Q4, 2017 | Pending | Q1, 2018 | Procurement of a contractor for the construction of the solar photovoltaic electricity charging station
14 | 2.2.2.1 | Ocean Energy Consultant - Ocean Energy Studies | Consulting Services | 784132 | QCBS | Ex-Ante | 0 | 100 | 0 | No | Q2, 2017 | Q4, 2017 | Pending | Q3, 2018 | Procurement of a Consulting Firm to undertake Ocean Energy Studies
15 | 1.1.1.3 | Procurement of Independent Expert | Consulting Services | 77504 | IICQ | Ex-Ante | 38.5 | 61.5 | 0 | No | Q3 2014 | Q2 2015 | Awarded | Q2, 2015 | Procurement of an individual Consultant to prepare specifications for streetlights
16 | 3.1.1.1 | Capacity Building Consultant | Consulting Services | 200000 | QCBS | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q4, 2018 | Procurement of a Consulting Firm to undertake capacity assessment and capacity building for staff and external partners
17 | 2.2.4.1 | Geographical Information Systems Consultant | Consulting Services | 15750 | NICQ | Ex-Post | 0 | 100 | 0 | No | n.a. | Q2 2015 | Awarded | Q4, 2015 | Procurement of an Individual Consultant for Marine Spatial Mapping
18 | 3.1.2.1 | Institutional Strengthening consultant - FTC & TCPDO | Consulting Services | 325000 | QCBS | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q2, 2018 | Procurement of a Consulting Firm to undertake Institutional Strengthening for the Fair Trading Commission and Town Planning Office
19 | 3.1.3.1 | Public education consultant -Primary, secondary and tertiary institutions trained, certification and Licensing | Consulting Services | 465000 | QCBS | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q2, 2018 | Procurement of a Consulting Firm to undertake training and certification in primary, secondary and tertiary institutions
20 | 3.2.1.1 | Monitoring and Evaluation (M& E) Consultant –Mid-term review | Consulting Services | 75000 | NICQ | Ex-Ante | 91 | 9 | 0 | No | Q3, 2016 | Q1, 2017 | In Process | Q2, 2017 | Procurement of an Individual Consultant to undertake the mid-term review of the program
21 | 3.2.3.1 | M& E Consultant - Supervision of 1.2 and 1.3 (EE and RE retrofits) | Consulting Services | 30000 | CQS | Ex-Post | 91 | 9 | 0 | No | Q2, 2017 | Q4, 2017 | Pending | Q4, 2018 | Procurement of a Consulting Firm to verify the energy baseline for the building and confirm the savings
22 | 3.1.4.1 | Public Awareness Consultant – energy labelling, online resources, media resources, public outreach events and educational entities | Consulting Services | 305000 | QCBS | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q3, 2017 | Pending | Q3, 2018 | Procurement of a Consulting Firm to undertake the public awareness activities in the Program
23 | 3.2.4.1 | M& E Consultant – Energy Audits | Consulting Services | 220000 | QBS | Ex-Ante | 91 | 9 | 0 | No | Q4, 2015 | Q4, 2016 | In Process | Q2, 2017 | Procurement of a consulting firm to undertake energy audits for public buildings as well as the ongoing evaluation of the EE and RE retrofits for public buildings
24 | 3.2.5.1 | External Financial Auditor | Consulting Services | 100000 | QCBS | Ex-Ante | 91 | 9 | 0 | No | n.a | Q4, 2016 | In Process | Q4, 2018 | Procurement of an External Auditor for Auditing of the Annual Financial Statements
25 | 3.2.2.1 | Final Evaluation Consultant | Consulting services | 75000 | CQS | Ex-Ante | 91 | 9 | 0 | No | Q4, 2017 | Q1, 2018 | Pending | Q3, 2018 | Procurement of a final evaluation consultant
26 | 3.1.1.7 | Operations Consultant | Consulting Services | 26667 | NICQ | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q1, 2017 | Pending | Q4, 2017 | Procurement of an Operations Consultant
27 | 3.2.6.6 | Financial Support Consultant | Consulting Services | 14657 | NICQ | Ex-Ante | 100 | 0 | 0 | No | Q1, 2017 | Q1, 2017 | Pending | Q3, 2017 | Procurement of a Financial Support Consultant
28 | 3.2.6.7 | Program Advisor | Consulting Services | 11000 | SSS | Ex-Ante | 100 | 0 | 0 | No | n.a | Q1, 2017 | Pending | Q2, 2017 | Procurement of a Program Advisor to assist in the execution f the PSSEP
29 | 1.1.1.1 | Contracting of BL&P | Non-consulting Services | 0 | SSS | Ex-Ante | 38.5 | 61.5 | 0 | No | n.a. | Q3 2016 | In Process | Q4 2018 | Procurement of Barbados Light and Power Co. Ltd to procure and install 25,000 streetlights
30 | 3.1.1.3.6.7.1 | Training - PURC Utility Regulation and Strategy | Non-consulting Services | 33648 | DC | Ex-Ante | 91 | 9 | 0 | No | n.a. | Q2 2017 | Pending | Q3 2017 | Attendance at the PURC/World Bank 42nd International Training in Utility Regulation and Strategy
31 | 3.1.1.3.6.7.2 | Training - PURC Energy Pricing | Non-consulting Services | 24980 | DC | Ex-Ante | 91 | 9 | 0 | No | n.a. | Q3 2017 | Pending | Q3 2017 | Attendance at the PURC Energy Pricing course
* Estimated Contract Signature Date is the date of award of Contract to the successful bidder
Note on P7: kreid: Are we still paying for the samples.
Note on O12: kreid: Review timeline given that the money has to be spent this FY
Note on O13: kreid: same as above
Note on O16: kreid: review this activity and timeline
Note on L24: kreid: I though we were getting the capcity builing cons to do this if so this timeline must change.
Note on L27: kreid: what about the other consultnat for BNSI that was a precursor to this.