RG-T2682 – Detailed Results Framework DRAFT

| ULTIMATE OUTCOME | Improved meteorological measurement expertise available to address emerging technology needs in member countries. |
| --- | --- |
|  |  |
| INTERMEDIATE OUTCOME | Improved delivery of advanced measurement services by National Metrology Institutes. Indicator 1: # of SMEs that use the improved advanced measurement services. Indicator 2: # Number of services developed to meet local industry needs. | Strengthened links with other regions through improved positioning of the hemispheric metrology infrastructure. Indicator: # of joint quality infrastructure activities between SIM and IAAC and COPANT. |
|  |  |   |  |
| IMMEDIATE OUTCOMES | Strengthened capabilities in regional NMIs Indicator 1: # of international recognized measurement capabilities in emerging technologies related measurements in participating NMIs. Indicator 2: # of participation of NMIs in new comparisons and/or pilot studies. | Improved knowledge of industry needs for services. Indicator 1: # of NMIs that incorporate development of services to support emerging technology demands from their industries. Indicator 2: # of local industry needs assessments conducted. | Increased engagement and dialogue with other regions. Indicator 1: # of scientific staff trained in current and emerging technology measurement needs. Indicator 2: # of participants from LAC region in Metrology for Innovation Forum. |
|  |   |     |   |
| OUTPUTS | Joint research undertaken. Indicator: # of the following: i) joint research projects (personal exchange support); ii) collaborative multinational research efforts. | Internships completed in measurement areas that support emerging technologies. Indicator: # of internships completed. | Technical training workshops held in measurement science. Indicator: # of technical training workshops designed and deployed. | Measurement comparison and pilot studies carried out. Indicator: # of new comparisons and/or pilot studies completed. | Workshops held to strengthen dialogue and delivery of services. Indicator 1: # of laboratory management best practices workshops. Indicator 2: # of NMIs that participated in sector specific workshops with industry. Indicator 3: # of Public-Private dialogue events between NMIs and industry stakeholders. | Training delivered to NMI professionals in the conduct of industrial needs assessment surveys. Indicator 1: # of NMI training events established to support industry Indicator 2: # of NMI professionals trained. | Metrology for Innovation Forum organized. Indicator: # of fora successfully held. | Participation of beneficiary institutions in international fora supported. Indicator: # of documents presented at international fora that mention SIM engagement. |
|  |         |
| ACTIVITIES | Research Organization of workshops seminars, and fora Organization of dialogue events Courses and training Consultancy services |

RG-T2682 – Goals and Means of Verification DRAFT

|  | Result | Indicator | Baseline | Goal | Means of Verification |
| --- | --- | --- | --- | --- | --- |
| Intermediate Outcome 1 | Improved delivery of advanced measurement services by National Metrology Institutes. | Indicator 1: SMEs that hire the technical advice from NMIs concerning the improved advanced measurement services in order to increase competitiveness Indicator 2: Number of services developed to meet local industry needs. | 0 0 | 50 5 | SMEs Contracts with NMIs New services in NMIs available to SMEs assessment. Technical reports |
| Intermediate Outcome 2 | Strengthened links with other regions through improved positioning of the hemispheric metrology infrastructure. | Indicator: joint quality infrastructure activities between SIM and IAAC and COPANT. | 0 | 3 | Agenda/ Programs. Final Minute. |
| Immediate Outcome 1 | Strengthened capabilities in regional NMIs. | Indicator 1: new measurement capabilities in emerging technologies in order to be recognized Indicator 2: NMIs participating in new comparisons and/or pilot studies. | 0 0 | 10 15 | Submission of new CMCs (Calibration and Measurement Capabilities) by NMIs Comparison ´s reports extended by the pilot lab. |
| Immediate Outcome 2 | Improved knowledge of industry needs for services. | Indicator 1of NMIs that incorporate services to support emerging technology demands from their industries. Indicator 2of local industry needs assessments conducted. | 0 0 | 5 5 | NMIs annual reports Study assessment report |
| Immediate Outcome 3 | Increased engagement and dialogue with other regions. | Indicator 1: scientific staff trained in current and emerging technology measurement needs. Indicator 2: participants from LAC region in Metrology for Innovation Forum. | 0 0 | 100 70 | Lists of participants in training events Lists of participants in Forum |
| Output 1 | Joint research undertaken. | Indicator: the following: i) joint research projects (personal exchange support); ii) collaborative multinational research efforts. | 0 | 5 | NMIs |
| Output 2 | Internships completed in measurement areas that support emerging technologies. | Indicator: internships completed. | 0 | 20 | NMIs (internship program) |
| Output 3 | Technical training workshops held in measurement science. | Indicator: technical training workshops designed and deployed. | 0 | 10 | Project database |
| Output 4 | Measurement comparison and pilot studies carried out. | Indicator: new comparisons and/or pilot studies completed. | 0 | 3 | Project database Participants’ feedback |
| Output 5 | Workshops held to strengthen dialogue and delivery of services. | Indicator 1: laboratory management best practices workshops. Indicator 2: NMIs that participated in sector specific workshops with industry. Indicator 3: of Public-Private dialogue events between NMIs and industry stakeholders. | 0 0 0 | 3 20 3 | Agenda/ Programs. List of NMIs participating List of NMIs and industrial representatives |
| Output 6 | Training delivered to NMI professionals in the conduct of industrial needs assessment surveys. | Indicator 1: NMI training events established to support industry Indicator 2: NMI professionals trained. | 0 0 | 5 50 | Project database Lists of participants |
| Output 7 | Metrology for Innovation Forum organized. | Indicator: fora successfully held. | 0 | 1 | Project database |
| Output 8 | Participation of beneficiary institutions in international fora supported. | Indicator: documents presented at international fora that mention SIM engagement. | 0 | 5 | Documents in project database |