## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IDB INE/ENE |  |  |  |  | Public or private sector: Public sector
Project number: RG-T3281 |  |  |  |  | Title of Project: Regulation and Governance: Regional Database and Dissemination
Period covered by the plan: 36 MONTHS (2018-2020)
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): |  | 200000 |  | Consulting services(in US$): | 390000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
|  | Non consulting services | [8 empty] | Quality Based Selection
|  | Workshops/classes - comp. IV | 240000 | QCBS |  | 100 |  | sept, 2018 |  |  | Selection Based on the Consultants' Qualifications
[8 empty] | sept, 2018 |  |  | Selection under a Fixed Budget
|  | Consulting services | [8 empty] | Individual Consultant
|  | Update the energy dossiers - comp. I | 190000 | QCBS |  | 100 |  | sept, 2018 |  |  | National System
|  | Update SER database - comp. II | 70000 | SSS |  | 100 |  | sept, 2018
|  | Survey design and data collection - comp. III | 110000 | QCBS |  | 100 |  | sept, 2018
Individual consultants
|  | Design the energy dossier - comp. I | 20000 | SSS |  | 100 |  | sept, 2018
Total |  |  | 630000 | Prepared by: Virginia Snyder |  |  | Date: July 13 2018
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.