## TCM Period 2018
| Operation Number: |  | RG-T3281 | [7 empty] | Inter-American Development Bank - IDB
| TCM Cycle: |  | TCM Period 2018
| Last Update: |  | 2018-07-25 01:19
Results Matrix
Outcomes
No information related to this operation.
Outputs: Annual Physical and Financial Progress
1 I. Update of Energy Dossiers | [7 empty] | Physical Progress | [5 empty] | Financial Progress
Outputs |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
1.1 Policy briefs completed |  | Energy Dossier |  | Briefs (#) | 4 | 2008 | Energy Dossier updated | P | 0 | 4 |  | 0 | 4 | P | 0 | 210000 |  | 0 |  | 210000 |  | Sustainable Energy and Climate Change | INF
[8 empty] | P(a) | 0 | 4 |  | 0 | 4 | P(a) | 0 | 210000 |  | 0 |  | 210000
[8 empty] | A | 0 |  |  |  | 0 | A | 0 |  |  |  |  | 0
2 II. Database treatment (enhancement and improvement): Sustainable Energy Rating | [7 empty] | Physical Progress | [5 empty] | Financial Progress
Outputs |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
2.1 SER Database updated and completed |  |  |  | Database (#) | 1 | 2018 | Database updated | P | 0 | 1 |  | 0 | 1 | P | 30000 | 30000 |  | 10000 |  | 70000 |  | Sustainable Energy and Climate Change | INF
[8 empty] | P(a) | 0 | 1 |  | 0 | 1 | P(a) | 30000 | 30000 |  | 10000 |  | 70000
[8 empty] | A | 0 |  |  |  | 0 | A | 30000 |  |  |  |  | 30000
3 III. Data collection and treatment from experimental studies on consumers’ behavior | [7 empty] | Physical Progress | [5 empty] | Financial Progress
Outputs |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
3.1 New databases created |  | Consumer behavior database |  | Databases (#) | 0 | 2018 | Database created | P | 0 | 3 |  | 2 | 5 | P | 40000 | 50000 |  | 0 |  | 90000 |  | Sustainable Infrastructure | INF
[8 empty] | P(a) | 0 | 3 |  | 2 | 5 | P(a) | 40000 | 50000 |  | 0 |  | 90000
[8 empty] | A | 0 |  |  |  | 0 | A | 40000 |  |  |  |  | 40000
3.2 Annual reports published |  | Report analyzing the databases |  | Reports (#) | 0 | 2018 | Report | P | 0 | 1 |  | 1 | 2 | P | 0 | 10000 |  | 10000 |  | 20000 |  | Sustainable Energy and Climate Change | INF
[8 empty] | P(a) | 0 | 1 |  | 1 | 2 | P(a) | 0 | 10000 |  | 10000 |  | 20000
[8 empty] | A | 0 |  |  |  | 0 | A | 0 |  |  |  |  | 0
4 IV. Capacity building in Energy Regulation, including dissemination of ENE dataset and analysis: co | [7 empty] | Physical Progress | [5 empty] | Financial Progress
llaboration with the Iberoamerican Energy Regulatory Entities Association (ARIAE)
Outputs |  | Output Description |  | Unit of Measure | Baseline | Baseline Year | Means of verification |  | 2018 | 2019 |  | 2020 | EOP |  | 2018 | 2019 |  | 2020 |  | EOP |  | Theme | Fund | Flags
4.1 Networks/communities of practice strengthened |  | support of round tables together with The Iberoamerican Association (discussion based on the IADB evidences) |  | Networks (#) | 0 | 2018 | Number of round tables completed | P | 0 | 1 |  | 1 | 2 | P | 30000 | 30000 |  | 30000 |  | 90000 |  | Sustainable Infrastructure | INF
[8 empty] | P(a) | 0 | 1 |  | 1 | 2 | P(a) | 30000 | 30000 |  | 30000 |  | 90000
[8 empty] | A | 0 |  |  |  | 0 | A | 30000 |  |  |  |  | 30000
4.2 Individuals Trained |  | to facilitate scholarships for regulators and policy makers to participate on the Iberoamerican School of Regulation training courses (capacity building in LAC regulatory staff to use evidence based tools) |  | Individuals (#) | 0 | 2018 | Number of training sessions participants | P | 0 | 10 |  | 10 | 20 | P | 40000 | 40000 |  | 30000 |  | 110000 |  | Sustainable Energy and Climate Change | INF
[8 empty] | P(a) | 0 | 10 |  | 10 | 20 | P(a) | 40000 | 40000 |  | 30000 |  | 110000
[8 empty] | A | 0 |  |  |  | 0 | A | 40000 |  |  |  |  | 40000
4.3 Training products developed |  | Teaching material developed |  | Products (#) | 0 | 2018 | Number of Teaching material published | P | 0 | 1 |  | 1 | 2 | P | 0 | 20000 |  | 20000 |  | 40000 |  | Sustainable Energy and Climate Change | INF
[8 empty] | P(a) | 0 | 1 |  | 1 | 2 | P(a) | 0 | 20000 |  | 20000 |  | 40000
[8 empty] | A | 0 |  |  |  | 0 | A | 0 |  |  |  |  | 0
Other Cost
Total Cost | [14 empty] | 2018 |  | 2019 |  | 2020 |  | Total Cost
[14 empty] | P | 140000 |  | 390000 |  | 100000 |  | 630000
[14 empty] | P(a) | 140000 |  | 390000 |  | 100000 |  | 630000
[14 empty] | A | 140000 | [5 empty] | 140000