Program Operations Manual

Education Quality Improvement Program – EQIP II

(BL-L1030)

Contents

I.	PURPOSE AND DEFINITION	6

II.	PROGRAM OBJECTIVE, COMPONENTS & FINANCING	7

A.	Objectives	7

B.	Components	7

C.	Program Cost and Financing	10

III.	PROGRAM STRATEGY	11

IV.	PROGRAM EXECUTION	12

A.	Execution Scheme	12

B.	Execution, Key Responsibilities	14

C.	Preconditions to 1st disbursement	17

V.	FINANCIAL RESOURCES & ELEGIBILITY OF EXPENSES	19

VI.	GUIDELINES FOR EXECUTION	19

VII.	PROGRAM PLANNING AND FINANCIAL ADMINISTRATION	19

A.	Annual Operations Plan (AOP)	19

B.	Financial Management	20

C.	Procurement	22

D.	Disbursements	28

E.	Payments: Services and Goods	30

F.	Maintenance	32

G.	Internal Control Procedures, Accounting and Auditing	33

VIII.	PROGRAM SUPERVISION, MONITORING AND EVALUATION	35

A.	Reporting Schedule	36

B.	Inspection and Supervision	36

C.	Internal Evaluations, Monitoring, Control and Reporting	37

D.	Independent Evaluations	38

E.	Program Monitoring and Evaluation Framework (M&EF)	38

IX.	MODIFICATIONS OF THE PROGRAM OPERATING MANUAL	38

Annexes

| Annex 1 | Contractual Conditions for BL-L1030 |
| --- | --- |
| Annex 2 | Detailed Procurement Procedure / QCBS |
| Annex 3 | Selected schools |
| Annex 4 | Monitoring and Evaluation Plan |
| Annex 5 | Annual Operations Plan |
| Annex 6 | Program Procurement Plan |
| Annex 7 | Results Matrix |

Tables

| Table 1 | Summary Cost Table |
| --- | --- |
| Table 2 | Members of the Program Steering Committee |
| Table 3 | Output Indicators and Costs – PMR Matrix |
| Table 4 | Summary of Procurement Process |
| Table 5 | Country Procurement Thresholds |
| Table 6 | Disbursement Forms and Supporting Documents |
| Table 7 | Counterpart Matrix (In-kind) |
| Table 8 | Reporting Schedule |

Abbreviations

| ATLIB | Association of Tertiary Level Institutions of Belize |
| --- | --- |
| BBTE | Belize Board of Teacher Education |
| BL | Belize |
| CDB | Caribbean Development Bank |
| CEO | Chief Executive Officer |
| CSEC | Caribbean Secondary Education Certificate |
| CXC | Caribbean Examination Council |
| EA | Executing Agency |
| EMIS | Education Management Information System |
| EQIP II | Education Quality Improvement Program Phase II |
| ESRP | Education Sector Reform Project |
| EU | European Union |
| FS | Financial Specialist |
| FST | Feedback System for TEI |
| GOB | Government of Belize |
| IDB | Inter-American Development Bank |
| IFI | International Finance Institutions |
| BBTE | Belize Board of Teacher Education |
| ME | Monitoring and Evaluation Specialist |
| MC | Marketing Campaign |
| MDRT | MICO Diagnostic Reading Test |
| MEO | Monitoring and Evaluation Officer |
| MoFED | Ministry of Finance and Economic Development |
| MOEYSC | Ministry of Education, Youth, Sports and Culture |
| MPRC | Ministry of Education, Youth, Sports and Culture Public Relations Committee |
| MSVU | Mount Saint Vincent University |
| NGO | Non-Governmental Organization |
| OII | Office of Institutional Integrity, IDB |
| PA | Project Assistant |
| PC | Project Coordinator |
| PDA | Program Designated Account |
| PEU | Program Executing Unit |
| PO | Project Officer |
| POM | Program Operations Manual |
| PPP | Program Procurement Plan |
| PPRE | Policy, Planning, Research & Evaluation Unit, MOEYSC |
| PRM | Program Results Matrix |
| PS | Procurement Specialist |
| PSC | Program Steering Committee |
| PSD | Program Strategy Diagram |
| PSE | Primary School Examination |
| PSR | Program Status Report |
| QADS | Quality Assurance and Development Services, MOEYSC |
| SPR | Semi-annual Progress Report |
| SSFA | SmartStream Financial Application |
| TA | Technical Assistance |
| TED | Teacher Education and Development Services, MOEYSC |
| TEI | Teacher Education Institutes, MOEYSC |
| TPS | Tertiary, Post-secondary Education Services, MOEYSC |
| TSC | Teaching Services Commission |
| V&T | Visible and Tangible Approach |

# PURPOSE AND DEFINITION

  - The Program Operations Manual (POM) is intended to contribute to the efficient and effective implementation of the Education Quality Improvement Program Phase II Phase II (EQIP II II), by providing clear and transparent operational guidelines. The POM is designed for use by all participants involved in the execution of the Program. In the event of any discrepancy between the POM and the loan contract, the latter will prevail. The Partners include:

- Association of Tertiary Level Institutions of Belize (ATLIB);

- Belize Board of Teacher Education (BBTE);

- Ministry of Finance and Economic Development (MoFED);

- Teaching Services Commission (TSC)

- Office of the CEO, Ministry of Education, Youth, Sports and Culture (MOEYSC);

- Policy, Planning, Research & Evaluation Unit (PPRE), MOEYSC;

- Program Executing Unit (PEU), MOEYSC;

- Program Steering Committee (PSC);

- Public Relations Committee, MOEYSC;

- Quality Assurance and Development Services (QADS), MOEYSC;

- Teacher Education and Development Services (TEDS), MOEYSC;

- Teacher Education Institutes (TEI);

- Tertiary, Post-secondary (TPS), MOEYSC; and

- Consultants (firms or individuals) contracted to prepare, design, develop, monitor or review any aspect, product or outcome of the Program.

  - The operation will finance a total of US$10.1 million over a period of five (5) years. The amount includes a loan of US$10 million financed by the Inter-American Development Bank (IDB) and US$100 thousand in counterpart financing provided by the Government of Belize (GOB). Counterpart financing will be provided through an in-kind contribution.

  - The executing agency is the MOEYSC through the PEU. The PEU will be responsible for the overall execution and coordination of the Program including the procurement and financial management and reporting of EQIP II. The PEU was created as recent as 2011 for the execution of the “Education Sector Reform Project” (ESRP) financed by the Caribbean Development Bank (CDB). In order to efficiently and effectively execute the EQIP II the GOB and IDB decided to strengthen the PEU by adding personnel and providing technical support to the unit.

  - The EQIP II program will involve the procurement of a number of contracts which fall within the following categories: Works, Goods, Consulting (firms and individuals) and non-consulting services.

  - The POM may require adjustments as the execution of the program progresses; consequently, the users of this document are encouraged to forward their observations and recommendations arising from the application of these guidelines to the Project Coordinator, PEU. Following the approval of the POM by the CEO and the IDB, the Project Coordinator, with the further approval of the CEO, will be responsible for incorporating suitable changes to it in accordance with the procedures established in Chapter X: Modifications to the POM.

# PROGRAM OBJECTIVE, COMPONENTS & FINANCING

## Objectives

  - To improve the quality of education at the primary and secondary levels, with a special focus on innovation in Science Technology Engineering Arts and Mathematics (STEAM) education. This general objective will be pursued by achieving the following specific objectives:

- Improve the quality of primary school teachers by expanding the inquiry- and problem-based learning approach; and

- Improve the quality of secondary education teachers by improving teaching practices through inquiry- and problem-based learning approach, and by increasing the sense of belonging in STEAM subjects of female students.

  - The above objectives will be achieved through investments in three main components.

## Components

  - Component I: Inquiry- and Problem-based Learning in the Primary School Classroom (US$4.0 million). The aim of this component is to roll out the EQIP to the 50% of primary schools that have not yet benefitted, bringing the coverage to 100% of primary schools nationwide. To change what happens in Belize’s primary school classroom, the EQIP combines teacher professional development with changes in the pedagogical leadership of schools.

- Sub-component 1.1 – Teacher Professional Development (US$3.0 million). The loan will finance: (i) an international certificate program with 60 hours of on-site and distance practical professional development for primary teachers; and (ii) 20 hours of in-class coaching visits per teacher to provide guidance and modeling in the implementation of lesson plans and use of formative assessments to provide students with individualized instruction.

- Sub-component 1.2 – Pedagogical Leadership and Education Management. (US$2.0 million). To ensure that EQIP teachers have the support they need from their school communities to shift their instructional practice to and inquiry- and problem-based pedagogical approach, the operation will finance: (i) school management training to build school supervision and pedagogical leadership skills; and (ii) parental training workshops on how to support their children’s learning.

  - Component II: STEAM Learning in the Secondary School (US$4.7 million). The component aims to create a Belize STEAM Laboratory School to train teachers, model individualized instruction that centers around the student, and foster innovation and digital transformation in STEAM subjects. The component is structured around two sub-components.

- Sub-component 2.1 – STEAM Laboratory School Infraestructure (US$2.5 million). The operation will finance: (i) rehabilitation and expansion of an existing MOEYSCC building to house the STEAM Laboratory School with capacity for a student population of 300 on the Belize ITVET Campus; (ii) furnishing and equipment of the laboratory school, including STEAM and computer laboratories; and (iii) maintenance and security of the building for during of the execution period of the operation. The overall design will be guided by sustainability, green principles and innovation.

- Sub-component 2.2 – STEAM Laboratory School Management and Training Force (US$1.8 million). The operation will finance technical assistance in the establishment of a Laboratory School management team, including: (i) training of local master teachers to provide continuous in-class professional development with modeling of IPP practices; (ii) detailed design and launch of programs to offer an IPP learning approach for STEAM subjects; (iii) development and implementation of a model for providing individualized instruction to ensure that all students, independent of their initial skill level, will develop the skills necessary to be employable in digital transformation and innovation; and attain the STEAM Laboratory School Diploma.

- Subcomponent 2.3 – Professional Development of STEAM Teachers (US$ 0.4 million). The operation will finance two phases of teacher training: (i) professional development for 40 STEAM Laboratory School teachers who will work in the STEAM Laboratory School; and (ii) training of teachers from 50% of Belize’s STEAM-subject secondary schools and ITVET.

- Sub-component 2.4 – Structured STEAM Internships (US$0.1 million). The operation will finance a structured internship program with 3 models of internship opportunities in different industries. The internship program will incorporate quality assurance procedures; as well as requirements for supervision, evaluation and certification criteria.

  - Component III: Evaluation. Evaluation (US$0.3 million). The aim of the component is to critically examine the program by collecting and analyzing information about activities, characteristics and outcomes. The component is structured around three subcomponents.

  - Sub-component 3.1. Assessment of Classroom Practices (US$0.1 million). Loan resources will be used to finance a qualitative video study of classroom practices at the primary and secondary levels. The study will measure four dimensions – emotional support, classroom organization, instructional support and student engagement – including indicators from the Classroom Assessment Scoring System (CLASS) and the Trends in International Mathematics and Science (TIMSS) Video Study Instrument. At the primary level, the evaluation will contrast classroom practices in a random subsample of EQIP II schools in 2017 with classroom practices at the end of the program. At the secondary level, the evaluation will contrast classroom practices of STEAM teachers in 50% of the country’s schools with practices in the other half of the schools. Teachers will be assigned to the two groups at random.

  - Sub-component 3.2. Assessment of Student Learning and Economic Returns (US$0.2 million). Loan resources will finance the randomization of acceptance of student applicants to the school to assess its effect on STEAM learning, including sense of belonging in STEAM; expectations; problem-solving and critical thinking skills. The sample will be stratified to make sure than an equal number of low- and high-income students receive access to the lab school. The operation will finance an ex-post economic analysis of the operation, including cost-benefit calculation and cost-effectiveness analyses, contrasting treatment and control students.

  - The project will also finance the management of the project to facilitate the execution of the program. This component covers expenses related to the PEU, financial audits, and monitoring and evaluation. It will also finance some office equipment and software to facilitate project execution and monitoring.

## Program Cost and Financing

  - The total cost of this operation is US$10,100,000, of which US$10 million will be financed by the IDB and the GOB will provide counterpart funding in the amount of US$100,000 as in-kind contribution (see Financial Management in chapter VII of this manual). Table 1 below shows the Program’s summary cost table.

Table 1 Summary Cost Table

| Cost Table BL-L1030 (US$ , 000) |
| --- |
| Component/Subcomponent | IDB | Local | Total | % |
| Component I: Primary School Teacher Professional Development. | 4,000 | - | 4,000 | 40% |
| 1.1 Subcomponent: Teacher Professional Development . | 3,000 |  | 3,000 | 30% |
| 1.2 Subcomponent: School Management. | 1,000 |  | 1,000 | 10% |
| Component II: Belize STEAM Laboratory School | 4,773 | - | 4,773 | 47% |
| 2.1 Subcomponent: STEAM Laboratory School infraestructure and equipment. | 2,500 |  | 2,500 | 24% |
| 2.2 Subcomponent: Establishment STEAM Laboratory School | 1,780 |  | 1,780 | 18% |
| 2.3 Subcomponent: Professional Development of STEAM Teachers | 400 |  | 400 | 4% |
| 2.4 Subcomponent: Structured STEAM Internships | 92 |  | 92 | 1% |
| Component III: Evaluation | 335 | - | 335 | 3% |
| 3.1 Subcomponent: Assessment of Classroom Practices. | 110 |  | 110 | 1% |
| 3.2 Subcomponent: Assessment of Student Learning and Economic Returns. | 225 |  | 225 | 2% |
| Project Management & Evaluation | 568 | 100 | 668 | 7% |
| Executing Unit/Project Execution Support | 493 | 100 | 593 | 6% |
| Audit | 75 |  | 75 | 1% |
| Contingency | 325 |  | 325 | 3% |
| Total | 10,000 | 100 | 10,100 | 100% |

# PROGRAM EXECUTION

## Execution Scheme

Execution Responsibility

  - According to the GOB/IDB Loan Contract No. XXXX/OC-BL, and the design of the Program, the Executing Agency (EA) is the Ministry of Education, Youth, Sports and Culture (MOEYSC) through the Program Executing Unit (PEU), responsible for the execution of the loan. The PEU will be the sole unit responsible for the execution of the program, including: the coordination of components, consultancies and key stakeholders; the monitoring of progress and results; procurement and contracting of goods and services; processing of eligible payments; financial management; IDB supervision-related activities; and reporting to the IDB and other Government entities. To enhance accountability throughout the loan implementation the Project Coordinator (PC) at the PEU will update the CEO, technical units and the IDB program Team Leader every month. In such updates the participants will discuss the progress of the Program and challenges in its execution. Throughout the execution of the program the execution team will hold meetings/conference calls as needed.

  - In 2012 the MOEYSC created the PEU to execute the “Education Sector Reform Project” –a Caribbean Development Bank (CDB) Loan. The CDB operation focuses on three key policy objectives: i) strengthened governance of the sector; ii) improved quality and relevance of education; and iii) increased equitable access. The program started implementation in January of 2013 and is expected to execute US$2 million throughout its life.

  - To execute operation BL-L1030 more efficiently and effectively, the MOEYSC and the IDB agreed that the PEU, currently staffed with five individuals (Project Coordinator, Financial Specialist, Engineer, Education Specialist and Administrative Assistant), would require an increase in their manpower capacity by hiring added personnel using additional loan funds, including, a Project Officer, a Monitoring and Evaluation Specialist (ME), a Procurement Specialist (already selected)  and a Monitoring Specialist. The PEU is accountable to the CEO (see organizational structure in paragraph 4.6). For the execution of EQIP II the PEU will comprise:

- 1 Project Coordinator (PC)

- 1 Project Officer (PO)

- 1 Financial Specialist (FS)

- 1 Monitoring and Evaluation Specialist (ME)

- 1 Procurement Specialist (PS)

- 1 Engineer

- 1 Education Specialist

- 1 Project Assistant (PA)

  - The Project Coordinator, the Financial Specialist, the Engineer and the Administrative Assistant will be accountable to both the EQIP II and the CDB program; on the other hand the Project Officer, the Procurement Specialist and the Education Specialist will work exclusively for the EQIP II program. The ME specialist would tentatively work for several IDB financed lending operations.

Program Steering Committee (PSC)

  - A Program Steering Committee (PSC) comprising representatives from 12 different and relevant organizations (See table 2 below), was formed to support the execution of the CDB program. This committee has been chosen also to provide policy direction and support to the EQIP II program. The PSC will meet every three months to receive information about the overall progress of the Program, discuss policy issues and make recommendations to address any bottlenecks. The prime responsibilities of PSC are to:

- Ensure an integrated, effective and efficient program execution through timely guidance and strategic policy level decision making;

- Provide oversight regarding the consistency of the loan contract and program implementation with MOEYSC policies and programs; and

- Promote strong communication links and the dissemination of information regarding program activities to key stakeholders and general public.

  - The PSC is chaired by the CEO. The Project Coordinator/EQIP II will serve as the technical and administrative secretariat. It is important to note that the PSC will not be expected to deal with the day-to-day operation and management of EQIP II. This will be handled by the Project Coordinator, PEU, in collaboration with MOEYSC Technical Units and the Ministry of Finance and Economic Development to ensure conformity with IDB requirements. In addition, to reach quorum in the PSC meetings the participation should be of at least 6 members –at least 2 of which should not be part of the Government of Belize.

Table 2: Members of the Program Steering Committee

| ORGANIZATION | REPRESENTATIVE |
| --- | --- |
| Ministry of Education, Youth & Sports | Chief Executive Officer |
|  | Chief Education Officer |
|  | Deputy Chief Education Officers |
| Ministry of Finance and Economic Development | Senior Advisor |
| Ministry of Economic Development | Chief Executive Officer |
| Ministry of Labor, Local Government, National Emergency Management and Immigration and Nationality | Labor Commissioner |
| Ministry of Human Development | Chief Executive Officer |
| Statistical Institute of Belize | Representative |
| Belize Association of Principals of Secondary Schools | Representative |
| Association of General Managers of Primary Schools | Member (General Manager, Catholic Management) |
| Belize National Teachers’ Union | President |
| Association of Tertiary Level Institutions in Belize (ATLIB) and the Teacher Education Institutes –represented by ATLIB | President of ATLIB |
| Belize Chamber of Commerce and Industry | Representative |
| Program Executing Unit | Project Coordinator |

Ministry of Finance and Economic Development (MoFED)

  - The MoFED participated in the loan negotiations and will play an advisory and monitoring role with respect to the utilization of Loan Funds.  MoFED will make recommendations regarding annual budgetary allocations for the Program giving consideration to physical goals and commitments, and will participate in all IDB administrative missions.

## Execution, Key Responsibilities

Key Responsibilities

  - The PEU key responsibilities are:

- Preparing and updating the Annual Operations Plan for submission and non-objection by the IDB in coordination with relevant MOEYSC technical units.

- Fostering an effective, empowered program execution team comprising the heads of MOEYSC technical units, consultants supporting the implementation and other actors involved in the process.

- Ensuring the achievement of outputs and outcomes through the monitoring of indicators.

- Monitoring and evaluating the operational performance and outputs to include collection and analysis of data, and site visits to ensure quality and consistency with program objectives (e.g. that the intended number of teachers are attending training sessions).

- Monitor the fulfillment of contractual clauses by firms and individual consultants hired by the program, including outputs and delivery dates.

- Organize monthly updates and annual meetings with the program execution team (PEU, MOEYSC technical units, support consultants, etc.) and the IDB Team Leader to report and gather information on all aspects of program management and technical implementation, and prepare minutes of meetings including decisions taken.

- Prepare quarterly, semi-annual and annual reports for the MOEYSC and IDB relative to program finances; and progress regarding AOP and result framework indicators, among others; in accordance with agreed procedures.

- Procurement planning and execution, preparation of tender documents, notices, and contracts for the procurement of goods and services; obtaining no-objections from IDB; and contract management, including development of a database of service providers, the negotiation of technical services and goods, and timely liaison with firms and consultants;

- Submitting disbursement requests to the IDB.

- Conducting supervision-related activities and reporting to the IDB and other GOB’s entities.

- Maintaining an adequate documentation filing system, ensuring all accounting records are maintained in a manner in keeping with best practices; among other tasks.

- Assisting and coordinating with MOEYSC technical units, and other stakeholders the:

- Development and finalization of terms of reference.

- Scheduling and management of consultancies.

- Procurement of goods and services.

- Documentation management.

- Preparation of the Annual Operations Plan, and Procurement Plans.

- Financial management: Preparation of an annual budget to include consolidated program component budgets; expenditure statements for management information, payments, disbursements and financial audits and all other documentation necessary for the fulfillment of contractual obligations; and ensuring compliance with generally accepted accounting and financial record keeping standards and principles, and the application of the administrative and financial procedures established in the Manual of Financial and Administrative Procedures.

- Keep a management and tracking information system to monitor the fulfillment of contractual clauses (see Contractual Conditions for BL-L1030 in Annex 1).

  - Is important to note that the PEU, through the CEO, will be the central entity for all communications between the IDB and the GOB concerning all aspects of the implementation of the Program.

  - The PEU Project Coordinator will:

- Manage the PEU and ensure that all responsibilities and deliverables are met in a timely manner (see paragraph 4.10).

- Work closely and coordinate with the technical units in the MOEYSC and all other stakeholders and co-executors to implement the Program.

- Hold monthly updates and annual meetings with PEU members, the heads of the MOEYSC technical units leading the implementation of components and subcomponents, support consultants and the IDB Team Leader, to report and gather information on all aspects of program management and technical implementation, and prepare minutes of meetings including decisions taken.

- Supervise the consultancies supporting the program execution.

- Conduct on the spot and unannounced inspection visits during training exercises to ensure trainers and participants are present.

- Monitor the implementation of the program and identify and address any problems facing the execution.

- Report regularly to the MOEYSC, IDB, MoFED and the PSC on all aspects of program implementation.

- Produce the following reports:

#### Minutes on meetings/conference calls held with the program executing team to discuss the program progress and challenges in its execution.

#### Quarterly Progress Report.

#### Semi-Annual Progress Report.

#### Annual Progress Report.

- Ensure that all accounting and financial administration requirements are met.

- Supervise all the technical and administrative staff of the PEU.

- With respect to procurement, the Project Coordinator, through the Procurement Specialist, will have the responsibility of: (1) advertising for Expressions of Interest and/or proposals for consultancies (using the methods of ICB or NBC according to the procurement thresholds and to the Request for Proposals); (2) receive the Technical and Financial proposals submitted by the prospective consultants; (3) request the formation of the evaluation committee; (4) open proposals in a public setting making sure that bidding documents are brought at the same time to the opening ceremony; (5) advise the MOEYSC and the evaluation committee on the requirements of evaluation and evaluation criteria; and (6) advise successful bidders of the evaluation results (such letter of advice will be copied to the Office of the CEO) –for more detailed information on the process see procurement section in chapter VII and Annex 2 –Procurement Procedure.

  - The MOEYSC Technical Units key responsibilities are:

- Accept ownership of program activities to ensure participation and commitment of staff members in the implementation of program activities;

- In conjunction with the PEU, implement the activities under his/her portfolio, based on the work plans and implementation schedule for its respective sub-component;

- Contribute to the updating and adjustments to the POM with respect to its sub-components;

- Identify issues and conditions which have an impact on program implementation and propose measures to the PEU and to the PSC in order to address them in a timely manner;

- Ensure adequate communication regarding program implementation amongst its staff as well as with other collaborating  units/divisions;

- Report on a timely basis, the implementation of program sub-components under its direction in accordance with the agreed formats and processes, and during the meetings with the PEU;

- Coordinate and facilitate the consultancies which support program implementation within its units.

## Preconditions to 1st disbursement

  - In accordance with the GOB/IDB Loan Contract No.XXX- Education Quality Improvement Program Phase II, the following conditions should be met prior to the first disbursement of loan resources:

General Conditions:

- The IDB shall have received one or more well-founded legal opinions which establish, with citations of the pertinent constitutional, legal, and regulatory provisions, that the obligations undertaken by the Borrower in the Loan Contract, and those of the Guarantor, if any, in the Guarantee Contract, are valid and enforceable.  Such opinions shall also refer to any other legal question that the IDB may reasonably deem relevant.

- The Borrower, directly or through the Executing Agency, if any, shall have designated one or more officials to represent it in all acts relating to the implementation of this Contract and shall have furnished the IDB with authentic copies of the signatures of said representatives.  Should two or more officials be designated, the designation shall indicate whether such officials may act separately or must act jointly.

- The Borrower, either directly or through the Executing Agency, if any, shall have demonstrated to the IDB that sufficient resources have been allocated to cover, at least during the first calendar year, the execution of the Program in accordance with the investment schedule referred to in the following paragraph.

- The Borrower, either directly or through the Executing Agency, as the case may be, shall have presented to the IDB an initial report prepared in the form indicated by the IDB which, in addition to such other information as the IDB may reasonably request pursuant to the provisions of this Contract, shall set forth: (1) a plan for implementation of the Program including the plans and specifications deemed necessary by the IDB, except with respect to a program for the granting of credits; (2) a calendar or schedule of work or granting of credits, as the case may be; (3) a table of the source and use of funds setting forth a detailed schedule of investments in accordance with the categories of investment established in this Contract and an indication of the annual contributions needed from the various sources of funds from which the Program will be financed; and (4) the content that the progress reports referred to in Article 7.03 of these General Conditions shall have.

- The Borrower or Executing Agency shall have demonstrated to the IDB that it has an adequate financial information system –including the setting up of SmartStream and a parallel accounting system responding to IDB reporting information needs-and internal control structure for the purposes indicated in this Contract.

Special Conditions:

- Prior to first disbursement: the approval by the MOEYSC CEO of: (a) the Program’s Operations Manual (POM); and (b) list of possible names to establish procurement evaluation committee(s). Both the POM and the list of all possible names to establish evaluation committee(s) for procuring goods and services should be submitted for no objection to the IDB.

# FINANCIAL RESOURCES & ELEGIBILITY OF EXPENSES

5.1	The use of resources will be guided by the Loan Contract along with the related Program documents, including the POM and the Program Procurement Plan (PPP).   The resources of the Loan should be utilized in an efficient, effective and transparent manner (refer to Table 1 for costs related to the program).

# PROGRAM PLANNING AND FINANCIAL ADMINISTRATION

  - Key administrative functions to be undertaken by the PEU relate to program planning, procurement, disbursement, and financial management.

## Annual Operations Plan (AOP)

  - The PEU will be responsible for developing a detailed Annual Operations Plan (AOP) prior to the beginning of each calendar year (See AOP in Annex 5). The AOP will be supported by the PPP for the acquisition of goods and services; and a financial plan based on estimated procurement costs and other program activities to be undertaken. The MOEYSC through the PEU will update the Financial Plan on a monthly basis, to include the estimated cash outflows (payments) for the program.  Disbursements projections, which indicate disbursements to be requested from the IDB, broken down according to categories of investments and activities, should be updated quarterly. The AOP is a tool for planning and coordinating the execution of the operation and should be developed in conjunction with the Program Team and other key stakeholders. The AOP is also a tool that assists the PEU in the monitoring of program activities. Every AOP developed shall be submitted for the IDB’s no objection.

  - The AOPs should be structured to monitor the program progress and should consider the following:

- Progress made to date at the activity, output, and outcome levels;

- Expected results and deliverables within the next 18 months at the output and outcome levels;

- All necessary activities to achieve results;

- Unit responsible for executing each activity.

## Financial Management

  - Programming and budget. The Borrower has committed to allocate, for each fiscal year of program execution, adequate financial resources to guarantee the effective execution of the program.

  - Accounting and information systems. Program accounting will be performed using the Government’s financial management system – SmartStream Financial Application (SSFA), in accordance with International Financial and Reporting Standards and International Public Sector Accounting Standards. The SSFA will be supplemented with the use of another appropriate accounting system –such as Quick Books- to facilitate reporting under the program. Such parallel system will be in place for the first year of program execution in order to test and validate SSFA functionality and capacity to respond to program reporting demands.  It will be the responsibility of the IDB Financial Specialist to assess the performance of SSFA and determine whether to discontinue or not the use of the parallel accounting system. It is expected that SSFA will: i) facilitate the recording and classification of all financial transactions according to source of funding, categories of investment and output indicators; and ii) provide information related to, planned versus actual financial execution of the program, commitments made under the program, the financial plan for a 6 months period, financial statements, performance reports and any other reports that may be required from time to time by the MOEYSC and/or the IDB.

  - External control and reports. For each fiscal year during program execution, the MOEYSC through the PEU will be responsible for producing quarterly progress reports, semi-annual unaudited financial reports for the program, annual audited financial statements and one final audited financial statement at the end of the program. The Financial Statements will be audited by a firm of independent public accountants acceptable to the IDB. The firm will be selected according to IDB’s procurement procedures for audit firms (Document AF-200). All reports should include the classification of all disbursements according to the programs output indicators, following the matrix below (see Table 3: Output Indicators and Costs – PMR Matrix).  The purpose of Table 3 is to establish a relation between the output indicators for the EQIP II and its cost, in doing so the PEU will put together a more detailed matrix where every single disbursement made –counterpart and IDB- will be classified in one of the referenced budget lines in table 3 (see column three). If the structure of the operation changes and the need for additional budget lines as described in the table below arises, the PEU will include such new lines as part of one of the output indicators and inform the IDB project team leader of such change.

  - Designated Account. The Program will have a designated Account in the Central Bank of Belize.  For day-to-day operations the PEU will make payments from the Ministry’s account (consolidated account) and on submission of a memo to the Ministry of Finance and Economic Development (MoFED), the funds are then reimbursed from the Central Bank Account to the Consolidated Account.

## Procurement

  - Procurements for the program will be carried out in accordance with the Policies for the Procurement of Works and Goods Financed by the Inter-American Development Bank (GN-2349-9), of March 2011; and the Policies for the Selection and Contracting of Consultants Financed by the Inter-American Development Bank (GN-2350-9), of March 2011 (http://www.iadb.org/en/project-procurement/procurement-polices,8182.html) and with the provisions established in the EQIP II Program Loan Contract and the PPP.  The detailed steps for procurement, regarding the Quality and Cost Based Selection, are presented in annex 2. In addition, prior to any procurement being initiated for this program, the MOEYSC is required to prepare and submit to the IDB a draft General Procurement Notice.

  - The draft Program Procurement Plan is to be approved by the IDB prior to negotiations setting out:

- The particular contracts for the goods, works, and services required to carry out the program during the initial period of 18 months;

- The proposed methods for procurement; and

- The related IDB review procedures.

Table 4: Summary of Procurement Process

| Key Actions | Consulting Services | Goods |
| --- | --- | --- |
| Procurement Planning (Approval of Procurement Plan requires the No objection of the IDB) | Identification of needs Terms of Reference Schedule for delivery | Nature of goods required Specifications for each Schedule for delivery |
| Advertising and Prequalification | No objection required for the TOR and the draft Request for Expressions of Interest Request Expressions of Interest Shortlist firms to be invited to bid | No objection required for Specific Procurement Notice (Goods). Publish notice |
| Bidding | No objection required for the draft RFP and the short list of firms or individuals. Provide/issue approved Request for Proposals to consultants Provide clarification as required Proposal submission Proposals opening | No objection required for the draft bidding documents. Provide/issue approved bidding documents to bidders Provide clarification, as required Bid submission Public bid opening |
| Evaluation | Evaluation of proposal No objection required to the technical evaluation report and to proceed to open the financial proposals. Prepare combined technical and financial report. No objection required to combined technical and financial report and to enter into negotiations. Negotiation. No objection to the initial contract. | Evaluation of Bids. Prepare evaluation report No objection required to the evaluation report Prepare draft contract (if applicable). No objection required to draft contract |
| Issuance of Contract | Contractor General Approval Signing Publication of award (QCBS, QBS, FBS, LCS, CQS and SSS) | Contractor General Approval Signing Publication of award (ICB, LIB, NCB, Shopping, direct contracting and Single source ) |
| Execution | Contract Administration No objection from the IDB required if the contract scope or value is modified. | Contract administration |
| Contract Closure | Finalization of payments Acceptance of services | Finalization of payments Acceptance of goods and/or works |

  - The PEU Procurement Officer will be responsible for finalizing the procurement packages and determining the appropriate procurement procedures after each AOP review, subject to the approval of the PC.

  - The types of procurement methods and selections which will be used in the execution of the program are the following:

- International Competitive Bidding (ICB)

- National Competitive Bidding (NCB)

- Quality and Cost Based Selection (QCBS)

- Quality Based Selection (QBS)

- Shopping

- Direct contracting/sole source

  - For further information regarding the IDB policies on the procurement of goods and services consult the following link http://www.iadb.org/en/project-procurement/procurement-polices,8182.html

  - Procurement methods and thresholds for this program are summarized in Table 5.

Table 5: Country Procurement Thresholds (US$)

| Type of Procurement | ICB | NCB | Shopping/Price Comparison | International Short List |
| --- | --- | --- | --- | --- |
| Goods and non-consulting services. | ≥ 100,000 | 25,000 – 100,000 | <25,000 |  |
|  | Ex-Ante Review | Ex-Ante Review | Ex-Ante Review |  |
| Consulting Services |  |  |  | ≥200,000 |
|  |  |  |  | Ex-Ante Review |

  - Procurement Supervision As shown on Table 5, all procurements will be reviewed ex-ante on every instance, as per the procurement plan, unless otherwise agreed with the Procurement Officer at the IDB Country Office.

  - The PEU’s Procurement Specialist (PS) should be fully knowledgeable of the IDB’s procurement policies. The Procurement Specialist at the IDB will offer targeted training periodically to the relevant officers of the PEU; including:

- Project Coordinator

- Project Officer

- Financial Specialist

- Procurement Specialist

- Administrative Assistant

Evaluation Committee.

  - The procurement process will require the conformation of an Evaluation Committee (EC) to assess the technical and financial proposals submitted by interested parties capable of supplying the program with the goods and services it requires to successfully execute. Below are the rules governing the selection of members for such committee:

- The members of the EC should always include a minimum of 3 or a maximum of 5 members (always an odd number).

- The participating members of the EC should be the following:

(a) a representative of the CEO/MOEYSC office;

(b) an official representing MOEYSC technical unit participating in the execution of EQIP II and associated with the specific TOR; and

(c) an official from the Ministry of Finance and Economic Development.

- All members should be selected from the list of EC members approved by the CEO/MOEYSC and the IDB (see Special Conditions in paragraph 4.14). Should there be individuals that are not in the preapproved list, the no objection from the IDB will have to be requested.

- During the designation of the members for the EC the PEU will determine a reasonable period of time for the EC to issue its recommendation, which will be set in each case in accordance with the complexity of the procurement in question. In any case such period shall not exceed 20 days.

- The EC may request technical support to MOEYSC technical units and/or the PEU to resolve issues which, by their nature, could escape the scope of the EC knowledge, always safeguarding the confidentiality of the information.

  - The PEU shall explore the possibility of using virtual EC meetings to increase the efficiency of the selection and contracting process. For such modality to be used, the PD at the PEU will elaborate, in conjunction with the Procurement Specialist at the IDB, the corresponding policies and procedures Furthermore, both parties shall agree on the criteria to be used to decide which consultancies should be selected using this method.

  - Program Procurement Plan (PPP) The PPP for the Program covering the first 18 months of program execution is summarized in Annex 6. It indicates the procedures to be used for the procurement of goods, the contracting of services, and the method for selecting consultants for each contract or group of contracts. It also indicates cases requiring prequalification; the estimated cost of each contract or group of contracts and the requirement for prior review by the IDB. The PPP will be updated annually or as required by the IDB.

  - Domestic preference: Determining whether it is appropriate and necessary to use domestic preference in the evaluation of bids should be guided by Appendix 2 of document GN-2349-9 paragraphs 1-6.

  - Procurement of goods and services: The review of technical specifications in all procurement cases, during the process of selection is the responsibility of the IDB sector specialist of the Program. The MOEYSC through the PEU will be responsible for the implementation of the program, and the preparation of TORs, short lists, selection of suppliers and service providers, and for awarding and managing these contracts.

  - Single Source Selection. The Single Source Selection method will be used for the procurement of three vital actions:

- Implementation of an interactive Visible and Tangible teaching model for Science, English and Math. The contracting of Mount Saint Vincent University (MSVU) for the implementation of the activities of Component I is justified for it is considered an agency with exceptional worth for the assignment in accordance with 3.10(d) of the IDB’s policies for selection and contracting of consultants GN-2350-9. The contract is estimated to be US $2.3 million, (see EQIP II Loan Contract No.XXX OC-BL).  Following a competitive bidding process (BL-T1049), the MSVU successfully developed and implemented an interactive Visible and Tangible math teaching model in the Belize District. As a result of positive effects identified through a rigorous external evaluation of the program, the MOEYSC requested the present lending operation to bring the Visible and Tangible Math teaching model to scale, and develop and implement corresponding Visible and Tangible teaching models for Science and English.

- The development, piloting and implementation of a teacher profession entry exam. Contracting of the Caribbean Examination Council (CXC) for the development, piloting and implementation of a teacher profession entry exam, including the training of MOEYSC officials. The contract is estimated to be US$327 thousand, (see EQIP II Loan Contract No.XXX OC-BL). The CXC is qualified and is considered and agency with exceptional worth for the assignment in accordance with 3.10(d) of the IDB’s policies for selection and contracting of consultants GN-2350-9. The CXC was established in 1973 by the Caribbean Community (CARICOM) to provide the region with syllabuses of the highest quality; valid and reliable examinations; and certification of international repute, abilities, and interests; as well as services to educational institutions in the development of syllabuses, examinations, and examination administration in the most cost-effective way. The experience and reputation of the CXC will bring assurance to all stakeholders that the exam will be fair and accurately capture test takers’ content and pedagogical knowledge. The tools developed and the experience that the CXC would gain in Belize, have the potential of befitting other CARICOM countries with interest in adopting an entry into profession exam for primary school teachers.

- Implementation of the Education Management Information System (EMIS) prototype. Contracting of the Community Systems Foundation for the implementation of the EMIS prototype with an estimated budget of US $1.1 million, (see EQIP II Loan Contract No.XXX OC-BL). In accordance with paragraph 3.6(c) of the IDB’s policies for the procurement of goods and works (GN-2349-9), the sole sourcing is warranted in view of the fact that these services are available from only one source. Based on review of different education management systems (EMIS), the MOEYSC has selected the OpenEMIS software of UNESCO as a suitable tool for collecting, storing, analyzing and reporting on education information for planning and management purposes. The OpenEMIS software was designed by UNESCO to constitute a basic, customizable and affordable EMIS tool for countries with weak statistical database to be able to adapt it to the needs of specific national contexts. UNESCO makes the software available free of charge to member countries. Since it is open source software, the MOEYSC has the freedom to adapt the instrument to its specific needs. The non-profit Community Systems Foundation has been a partner of UNESCO in the development of the OpenEMIS software and is the only organization tasked by UNESCO to implement the software in UNESCO member countries.

  - Selection of Individual Consultants: Individual consultants are employed on assignments for which: (a) teams of personnel are not required; (b) no additional outside (home office) professional support is required; and (c) the experience and qualifications of the individual are the paramount requirement. When coordination, administration, or collective responsibility may become difficult because of the number of individuals, it would be advisable to employ a firm.

  - Individual consultants are selected on the basis of their qualifications for the assignment. Advertisement is not required and consultants do not need to submit proposals. Consultants shall be selected through comparison of qualifications of at least three candidates among those who have expressed interest in the assignment or have been approached directly by the Borrower. Individuals considered for comparison of qualifications shall meet the minimum relevant qualifications and those selected to be employed by the Borrower shall be the best qualified and shall be fully capable of carrying out the assignment. Capability is judged on the basis of academic background, experience and, as appropriate, knowledge of the local conditions, such as local language, culture, administrative system, and government organization.

  - From time to time, permanent staff or associates of a consulting firm may be available as individual consultants. In such cases, the conflict of interest provisions described in these Policies shall apply to the parent firm and its affiliates.

  - Individual consultants may be selected on a sole-source basis with due justification in exceptional cases, such as: (a) tasks that are a continuation of previous work that the consultant has carried out and for which the consultant was selected competitively; (b) assignments with total expected duration of less than six months; (c) emergency situations resulting from natural disasters; and (d) when the individual is the only consultant qualified for the assignment.

  - Training: As per GN-2350-9 (Policies for the Selection and Contracting of Consultants Financed by the IADB), if the assignment includes an important component for training or transfer of knowledge to Borrower staff or national consultants, the TOR shall indicate the objectives, nature, scope, and goals of the training program, including details on trainers and trainees, skills to be transferred, time frame and monitoring and evaluation arrangements. The cost of the training program shall be included in the consultant’s contract and in the budget for the assignment.

  - Advance contracting/retroactive financing. For the execution of the EQIP II program there was no advance contracting and/or retroactive financing planned.

  - Use of national procurement systems: No national procurement systems will be used in the execution of the program.

Prohibited Practices

  - The IDB requires that all borrowers (including grant beneficiaries), Executing Agencies, and Contracting Agencies as well as all firms, entities and individuals bidding for or participating in an IDB-financed activity including among others, applicants, bidders, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and agents irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank all suspected acts of Prohibited Practices of which they have knowledge or become aware both, during the bidding process and throughout negotiation or execution of a contract. Prohibited Practices are outlined in IDB Code of Ethics and Profession Conduct; and in IDB procurement policies.

## Disbursements

  - All disbursements made under the present operation will be governed by the guidelines set forth by the IDB in the document “IDB Disbursement Guide”. According to IDB guidelines the program may use one or more disbursement methods, with the purpose of ensuring that the executing agency has timely access to the resources needed for proper program execution. The disbursement of funds for the present program are governed by the following guidelines:

- In accordance with Article 4.05 of the General Conditions of the EQIP II Loan Contract,  the IDB may make disbursements against the loan by:

#### transferring to the Borrower the sums to which it is entitled under this Contract, under the modality of reimbursement of expenses and/or Advance of Funds;

#### making payments on behalf of and in agreement with the Borrower to third parties (direct payments), in agreement with the MoFED;

#### by utilizing such other modality as the parties may agree upon in writing.

- Any banking expenses that may be charged by a third party in connection with disbursements shall be borne by the Borrower. Unless the parties agree otherwise, disbursements shall be made only in amounts of not less than the equivalent of one hundred thousand Dollars (US$100,000) each.

- According to ARTICLE 4.03.  of the General Conditions of the EQIP II Loan Contract the IDB may make any disbursements, where:

- the Borrower or the Executing Agency, as the case may be, have submitted in writing, or by electronic means in such form and conditions as may be specified by the IDB, a disbursement request and, in support thereof, shall have supplied to the IDB such pertinent documents and other background materials as the IDB may have required;

- the Borrower or the Executing Agency, as the case may be, have opened and maintains one or more bank accounts in a financial institution to which the IDB shall make the disbursements.

- Unless the IDB otherwise agrees, disbursement requests must be presented no later than thirty (30) days  in advance of the date of expiration of the Original Disbursement Period or any extension thereof.

  - The IDB, under the Advance of Funds methodology, shall disburse the Program resources according to the true liquidity needs of the Program, as evidenced by the PEU’s current and anticipated future commitments and obligations. The PEU’s requests for advance of fund should be made in accordance with the Program`s financial plan, its annual budget and the corresponding AOP, including the PPP.  Before the PEU can be issued with a new advance of funds, at least 80% of the existing advance of funds needs to be justified to the IDB.

  - The PEU will be responsible for the submission of all disbursement requests to the IDB. The funds will be deposited into a Special Account, denominated in US Dollars, established exclusively for the Program at the Central Bank of Belize; the Executing Agency and PEU commit to maintain strict control over the utilization of the funds disbursed so as to ensure the easy verification and reconciliation of balances between the PEU records and the records of the IDB (LMS1 Executive Financial Summary Report).

  - In order to request disbursements from the IDB, the Executing Agency, specifically the PEU will present the following forms and supporting documents (see Table 6):

Table 6: Disbursement Forms and Supporting Documents-

| Disbursement Type | Required documentation | Optional Documentation | Frequency of Disbursements Requests |
| --- | --- | --- | --- |
| Advance of Funds | The Disbursement Request form Financial Plan | List of commitments. Estimated physical-financial progress reports for the program, such as the PEP, POA-PP. Progress Monitoring Report, or others that help demonstrate that the amount requested is reasonable. | Determined based on the programming of the program’s financial execution (consistent with the PEP, AOP-PP, or other applicable planning instruments). Should cover estimated expenses up to no more than six (6) months. |
| Justification of Advances | The Disbursement Request form. Statement of Expenses or Payments Form Program Execution Status (Can be generated from financial system) Reconciliation of Bank Resources | Reports regarding the fulfillment/completion of indicators or milestones or other reports that help demonstrate the program’s progress. Summary of contracts/ Commitments Other agreed upon items. | Submitted when at least 80% of the advanced amount has been used. These statements must be received and accepted by the IDB before the borrower or Executing Agency can receive another advance of funds. |
| Reimbursement of Payments Made | The Disbursement Request form. Statement of Expenses or Payments Form. Program Execution Status. (Can be generated from financial system) | Reports regarding the fulfillment/completion of indicators or milestones or other reports that help demonstrate the program’s progress. Summary of contracts/ Commitments Other agreed upon items. | At least twice a year and no more than four or five times a year, depending on the level of program risk and/or the level of fiduciary capacity of the EA |
| Direct Payment to Supplier | The Disbursement Request form. Statement of Expenses or Payments form. Supporting documentation acceptable to the IDB, e.g.: invoice or payment document evidence of receipt, of the good , or service Correspondence from supplier with banking information |  |  |

  - Generally, supporting documentation for Justification of Advances and Reimbursement of payments made will be kept at the office of the PEU. Support documentation for direct payments will be sent to the IDB for processing. Disbursements’ supporting documents may be reviewed by the IDB on an ex-post basis. These reviews do not entail a blanket approval, based on the samples reviewed, of the whole universe of expenditures.

  - In accordance with Articles 4.03 and 4.08 of the General Conditions to the EQIP II Loan Contract respectively, the Borrower or the Executing Agency, as the case may be (unless the IDB otherwise agrees), must:

- present disbursement requests to the IDB no later than thirty (30) days in advance of the date of expiration of the Original Disbursement Period or any extension thereof;

- present to IDB’s satisfaction, within the Closing Period, the supporting documentation relating to expenditures made for the execution of the Program, and any other information that the IDB may have requested; and

- return to the IDB, at the latest on the day of expiration of the Closing Period, the balance of disbursed resources that has not been duly justified.

## Payments: Services and Goods

  - For this program there will be no investment on works. All payments will be made through the PEU and all requests must be certified by the PEU Project Coordinator. The CEO, MOEYSC or his/her designee is the only official authorized to approve the release of Program funds through the PEU, according to the procedures established in the EQIP II Loan Contract.

  - The PEU will be responsible for ensuring compliance with the financial management, fiduciary obligations and the environmental safeguards during the implementation and management of the Program. A summarized payment procedure for Services and Goods is provided below:

  - Payments to consulting firms and individuals, and suppliers of goods will follow the steps below:

For amounts less or equal to BZ$10,000 (less than approximately US$5,000.00)

- Consultant/service provider submits report and invoice to the PEU;

- Project Assistant (PA) at PEU receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the payment requested matches that in contract records and records on the SmartStream Financial Application (SSFA);

- PA initiates payment process by entering invoice data in the SSFA and submits documentation to the Financial Specialist (FS) at the PEU;

- FS receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the services have been performed accordingly, that the payment requested matches that in contract records and records on the SSFA and all documentation requirements have been satisfied. The FS notifies by email to the Project Coordinator (PC) and provides all supporting documentation upon request;

- PC reviews and gives 1st electronic approval in the SSFA, issues email to the Treasury Department, MOFED, to indicate date of payment, if necessary, and informs via email of payment request to the Financial Officer at the MOEYSC;

- Treasury Department, at the MOFED, receives notification of payment request via the SSFA and email, reviews, gives 2nd approval and issues payment. Transaction is registered in SSFA.

For amounts above BZ$10,000 (more than approximately US$5,000.00)

- Consultant/service provider submits report and invoice to the PEU;

- Project Assistant (PA) receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the payment requested matches that in contract records and records on the SmartStream Financial Application (SSFA);

- PA initiates payment process by entering invoice data in the SSFA and submits documentation to the Financial Specialist (FS) at the PEU;

- FS receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the services have been performed accordingly, that the payment requested matches that in contract records and records on the SSFA and all documentation requirements have been satisfied. The FS notifies by email to the Project Coordinator (PC) and provides all supporting documentation upon request;

- PC reviews and gives 1st electronic approval in the SSFA, issues email to the Treasury Department, MOFED, to indicate date of payment, if necessary, and informs via email of payment request to the Financial Officer at the MOEYSC;

- Financial Accountant, at Treasury Department, at the Ministry of Finance and Economic Development, receives notification and reviews, gives 2nd approval and sends to second Financial Accountant for a 3rd and final approval. Treasury Departments issues payment. Transaction is registered in SSFA.

For payments to overseas accounts, regardless of the amount, the following steps will be observed:

- Consultant/service provider submits report and invoice to the PEU;

- Project Assistant (PA) receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the payment requested matches that in contract records and records on the SmartStream Financial Application (SSFA);

- PA initiates payment process by entering invoice data in the SSFA and submits documentation to the Financial Specialist (FS) at the PEU;

- FS receives and reviews the Consultant`s/provider’s report and verifies invoice to ensure that the services have been performed accordingly, that the payment requested matches that in contract records and records on the SSFA and all documentation requirements have been satisfied. The FS issues memorandum to the Treasury Department requesting the payment and including the following information: amount, banking and wire transfer information, and accounting distribution among others. The memorandum should have a copy of the invoice attached. The FS delivers memorandum to the PC for signature.

- PC reviews documentation and gives 1st approval by signing the memorandum, sends documentation to Accountant General at the Treasury Department and informs via email of payment request to the Financial Officer at the MOEYSC;

- Accountant General receives and reviews documentation, and gives 2nd approval and requests wire transfer to the Central Bank. Transaction is registered in SSFA.

## Maintenance

  - The Government of Belize through the MOEYSC will assume the preservation all the equipment included in the Program in operating conditions in which they were upon their acquisition, at a level compatible with their intended use and particularly to ensure that the equipment included in the program shall be adequately maintained according to generally accepted technical standards; and present to the IDB, within ninety (90) days of the beginning of each year, an annual report on the status of said equipment and an annual maintenance plan for that year, starting from the purchasing of the firsts equipments and during the five (5) years following  completion of the execution of the program.  In addition the PEU will include in the Semi-Annual Progress Report a section indicating what actions have been taken to guarantee the operating conditions of said equipment. The maintenance plan should include: i) detail of the organization responsible for maintenance; and ii) information pertaining to the resources to be allocated for maintenance during the current year. If from the inspections conducted by the Bank or from the reports it receives, it is determined that maintenance does not meet the levels agreed upon, the PEU shall undertake the necessary measures to correct these shortcomings.

## Internal Control Procedures, Accounting and Auditing

  - All financial management of the Program has to comply with IDB’s Financial Reporting and Audit Guide. For this purpose, fiduciary training will be provided to the PEU by IDB’s Financial Specialist at program initiation and during program execution. The PEU will ensure that the relevant members of the team and any other units or divisions in the MOEYSC and other pertinent actors that will be involved in Program financial management will participate in the training.  The following paragraphs are intended to facilitate the execution; in case of any discrepancies between the statements below and the IDB’s policies, the latter will invariably prevail.

  - A Program Code of Accounts will be established prior to the Program commencement, within the SSFA and the parallel accounting system used to facilitate financial reporting (see paragraph 7.5). It is a requirement that the financial reporting of the Program is able to provide reports disaggregated by Component, Activity and Program, as well as by source of financing. The accounting must be done on an accrual-based system. The Financial Specialist will work together with the Financial Officer at the IDB and the SmartStream Unit at the MoFED to make sure that the IDB reporting requirements are satisfied with the use of SSFA.

  - At program initiation the PEU will contract an audit firm acceptable to the IDB to audit their financial statements. The IDB Country Office will also provide the standard accounting and auditing documents to the PEU and the selected Auditors. The PEU must (i) process requests for disbursement and respective justifications of expenses, in accordance with IDB procedures for disbursements; and (ii) submit within 120 days, following the closing of each fiscal year of the EA, and at the closing of the program, audited financial statements –audited by the selected firm of auditors and financed by the Program.

  - The Borrower, or the EA, or the Contracting Agency, as the case may be, shall maintain: i) a financial information system acceptable to the IDB that enables accounting, budgetary and financial record keeping, as well as the issuance of financial statements and other reports related to the resources of the Financing and other financial resources, as the case may be (se paragraph 7.5); and ii) an internal control structure that enables effective Program management; provides reliability regarding the financial information and the physical, magnetic and electronic records and files; and enables the fulfillment of the provisions of the Loan Contract. Auditing records must reflect each and all sources of financing related to the Program, including the counterpart (see paragraph 7.5 for recording format). Detailed accounts are to be kept by the PEU, which is responsible for the timely accounting of the inflows and outflows and the preparation of corresponding financial statements. A filing system must be established that permits indexing of support documents by Component, Sub- component and Activity, by assigning a unique identifier number to activities and which facilitates auditing by program and by contract. This will need to be incorporated into the SSFA as an additional field.

  - The MOEYSC shall preserve the original records of the Program for a minimum period of three (3) years after the date agreed upon for the final disbursement of the Financing, in such a way as to:

- Make possible the identification of sums received from different sources.

- Show, in accordance with the financial information system approved by the IDB, the investments in the Program, financed both with the resources of the Loan and with the other funds to be provided for its complete execution.

- Include sufficient detail to show the goods procured and services contracted, as well as the utilization of such goods and services.

- Provide evidence as to conformity in acceptance, authorization and payments for the purchased or contracted goods and services.

- Maintain documentation relating to the bidding process and the execution of contracts financed by the IDB and other financial sources, including but not limited to, bid packages, summaries, bid evaluations, contracts, correspondence, work product and drafts, invoices, certificates and acceptance reports, and receipts, including documents relating to the payment of commissions, and payments to agents, consultants and contractors.

- Show the cost of investments in each category and the physical and financial progress of the goods and services.

  - The Financial Specialist, PEU, is responsible for consolidating the accounts of the Program, and for obtaining the necessary fiscal information and reports. He/she is also responsible for establishing and strengthening financial accounting controls for the Program, including the development and updating, when necessary, of the Program accounts manuals with the supervision of the Project Coordinator. The accounting system will be organized to provide the necessary documents, enable the verification of transactions, and facilitate the timely preparation of financial statements and reports.  The Program files must be organized in such a way that (i) sums received are identified by source; (ii) Program expenses are reported in accordance with a breakdown of accounts approved by the IDB, making a distinction between sources; and (iii) the necessary details are included to identify the goods acquired and the services contracted, as well as the use of those goods and services.

In-Kind Contribution

  - For the program the GOB has agreed to provide counterpart funding in the amount of US$100,000 as in-kind contribution. Such contribution will be accounted for by considering the man hours of two (2) of the PEU positions that are currently being financed by MOEYSC budget, the Project Coordinator and the Project Assistant. It is estimated that the time required for the EQIP II program from both individuals could amount to an estimated 60% of their total work time. The man hours dedicated to the EQIP II program based on such estimate is more than enough to cover the commitment of US100,000 in the approved five year period of the program. The PEU, through the Project Coordinator and the Project Assistant, shall keep appropriate and updated records of their time spent on the EQIP II program. To support this effort bellow there is a matrix (see Table 7) the PEU should use to record any counterpart contribution, including in-kind, to the program. The Counterpart Matrix should be updated every two weeks.

Table 7: Counterpart Matrix

| Component/ Subcomponent Activities | Time period (Quarter) in year 20XX | Allocated IDB Resources | Counterpart | Comments |
| --- | --- | --- | --- | --- |
|  |  |  | Total Allocated Counterpart (US$) | In-Kind (US$) | Financial (US$) | Details of counterpart contribution |  |
| Component 1 |  |  |  |  |  |  |  |
| Subcomponent |  |  |  |  |  |  |  |
| Activity 1 |  |  |  |  |  |  |  |
| Activity 2 |  |  |  |  |  |  |  |
| Activity 3 |  |  |  |  |  |  |  |
| Etc… |  |  |  |  |  |  |  |

# PROGRAM SUPERVISION, MONITORING AND EVALUATION

## Reporting Schedule

Table 8: Reporting Schedule

| Schedule | Type of Report | Content of Report | Responsible individual / Agent | Submitted to |
| --- | --- | --- | --- | --- |
| After executing team meetings/ conference calls | Minute | Record of meetings (minute) with execution team assessing project management and implementation matters. | PA / PEU | PC/PEU CEO, MOEYSC |
| Quarterly | Quarterly Progress Report | Progress report to PSC on disbursements, achievements and challenges. | PC/PEU | PSC/EQIP II |
| Semi-Annual | Semi-Annual Progress Report | physical progress; financial progress in terms of commitments, payments and disbursements under the loan; updated financial plan; outputs and outcomes measured against program indicators; and work plan and related budgets for the next 6 months Unaudited financial statements Description of actions taken to guarantee the operating conditions of equipment purchased by the loan Output Indicators and Costs – PMR Matrix | PC/PEU FS/PEU | CEO/MOEYSC IDB |
|  |  | Updated Procurement Plan. | PS/PEU |  |
| Annual | Annual Progress Report | AOP for the following calendar year; a forecast of disbursements; an updated Procurement Plan detail achievements in relation to planned activities, outputs and outcomes; and budget analysis, disbursement and financial plan; among others. Output Indicators and Costs – PMR Matrix | PC/PEU | PC/PEU CEO/MOEYSC PSC/EQIP II IDB |
|  |  | Annual audited Program Financial Statements –audited by a firm of independent auditors acceptable to the Bank | Auditors |  |
| PA: Administrative Assistant; CEO: Chief Executive Officer; FS: Financial Specialist; IDB: Inter-American Development Bank; PEU: Program Executing Unit; PC: Project Coordinator; PS: Procurement Specialist; PSC: Program Steering Committee. |

## Inspection and Supervision

  - The Program’s execution will be supervised by the PC at the PEU, who may be assisted in these duties by IDB staff or consultants. The Executing Agency will be informed of the relevant contact person(s), including their respective responsibilities. As part of the overall supervision of the program the IDB will conduct periodic visits to Belize and maintain a Project Monitoring Report (PMR), the IDB’s main system tool for day-to-day monitoring of projects and for tracking the program’s progress toward achieving the milestones specified in the Results Matrix (see Annex 7). Supervision activities carried out by IDB Staff are financed by the Bank.

## Internal Evaluations, Monitoring, Control and Reporting

  - Monitoring and evaluation at the program level, including the day-to-day monitoring of program activities, will be the responsibility of the PO and PC, with support from the Procurement Specialist and Administrative Assistant. The PO will produce the following reports to facilitate monitoring of general program progress and the fulfillment of the indicators identified in the Results Matrix (see Annex 7):

- a minute after every executing team meeting/conference call, assessing project management and implementation matters;

- a quarterly progress report to the PSC on the progress of the loan;

- a semi-annual Progress Report within 60 days after the end of each six-month period during program execution. The semi-annual report will focus on the fulfillment of output indicators and progress towards achieving the outcomes proposed in the Results Framework; they will also analyze the problems encountered and propose corrective measures. The report shall include: (a) physical progress; (b) financial progress in terms of commitments, payments and disbursements under the loan; (c) updated financial plan; (d) outputs and outcomes measured against program indicators; (e) work plan and related budgets for the next 6 months; (f) unaudited  financial statements; (g) a description of actions taken to guarantee the operating conditions of equipment purchased by the loan; and (h) the Output Indicators and Costs Matrix required for the IDB Project Monitoring Report (see Table 3).

- an annual progress report within 120 days, following the closing of each fiscal year of the EA, containing: (a) the AOP for the following calendar year; (b) a forecast of disbursements; (c) an updated Procurement Plan (d) detail achievements in relation to planned activities, outputs and outcomes; (e)  budget analysis, disbursement and financial plan; (f) audited Financial Statements; and (g) the Output Indicators and Costs Matrix required for the IDB Project Monitoring Report, among others.

  - Adjustments to the Program arising from the discussion of these reports will be agreed upon with the IDB in the semi-annual meetings with the PEU.

  - Within the first 6 months of the Program first day of execution, the Project Officer will also be responsible for consolidating all baseline information required for the indicators identified in the Results Framework and for maintaining up-to-date statistics on the indicators.

## Independent Evaluations

  - As part of program evaluation, the PEU will conduct and submit to the IDB a preliminary review 24 months after the Loan Contract becomes effective; a midterm review within 90 days after the date on which 50% of the loan proceeds have been committed; and a final review report 90 days after the date on which 90% has been disbursed. These reports will include, among other:

- An analysis of the Program’s financial execution, by component and financing source.

- A progress in achieving the outputs, outcomes and impacts in the Results Framework, and the results of a comparative analysis against the Program baseline.

- The degree of fulfillment of contractual commitments.

- A summary of the audit reports on the Program’s financial statements, procurement processes, disbursement requests, and internal control systems.

  - The final review report will also include the results of the Program, based on the system of indicators developed by the IDB, in accordance with the agreed Monitoring and Evaluation Plan (see Annex 4) and the IDB Project Completion Report.

  - These reviews will be performed independently by specialists who will be contracted by the PEU and financed by the loan. The reports, including supporting documentation and statistical data, will be kept available for use should the Government of Belize or the IDB decide to conduct an ex-post evaluation after the end of the Program.

## Program Monitoring and Evaluation Framework (M&EF)

  - Please refer to the Program’s Monitoring and Evaluation Operational Guidelines, developed as a separate document.

# MODIFICATIONS OF THE PROGRAM OPERATING MANUAL

9.1	The MOEYSC, in consultation with program partners may suggest changes to the POM in order to adapt it to new conditions or circumstances that may arise during the Program’s execution. Any changes to the POM should be communicated to the IDB and will take effect upon the IDB’s formal approval.

Annexes

Annex 1

Contractual Conditions for BL-L1030

Annex 2

QCBS Procurement Procedure

Annex 3

Selected schools

Annex 4

Monitoring and Evaluation Plan

Annex 5

Annual Operations Plan

Annex 6

Program Procurement Plan

Annex 7

Results Matrix

Results Matrix

| Project Objective: | The main objective of EQIP II is to improve the quality and equity of education at the primary and secondary levels, with a special focus on innovation in Science Technology Engineering Arts and Mathematics (STEAM) education. This general objective will be pursued by achieving the following specific objectives (i) Improve the quality of primary school teachers by expanding the inquiry- and problem-based learning approach; (ii) Improve the quality of secondary education teachers by improving teaching practices with a focus on student-centered science and mathematics learning; and (iii) promote gender-sensitive STEAM teaching. |
| --- | --- |

Expected Impact

| Indicators | Unit of measure | Baseline | Baseline Year | Year 1 | Year 2 | Year 3 | Year 4 | End of Project | Means of verification | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact: Improve the quality of education at the primary and secondary levels |
| Indicator #1. Test of female STEAM skills relative to that without the program (counterfactual) – 2nd form | Standard deviation | 0 | 2024 | 0 | 0 | 0 | 0.10 | 0.10 | RCT Evaluation. The PEU is responsible for contracting. | Applicants to the STEAM Laboratory School will be randomized. |
| Indicator #2. Test of male STEAM skills relative to that without the program (counterfactual) – 2nd form | Standard deviation | 0 | 2024 | 0 | 0 | 0 | 0.10 | 0.10 | RCT Evaluation. The PEU is responsible for contracting. | Applicants to the STEAM Laboratory School will be randomized. |
| Indicator #3. Sense of belonging measure relative to that without the program (counterfactual) – 2nd form | Standard deviation | 0 | 2024 | 0 | 0 | 0 | 0.10 | 0.10 | RCT Evaluation. The PEU is responsible for contracting. | Applicants to the STEAM Laboratory School will be randomized. A modified version of the Psychological Sense of School Membership (PSSM) will be used. |

Expected Outcomes

| Indicators | Unit of measure | Baseline Value | Baseline Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | End of Project | Means of verification | Observations2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Outcome # 1: Improve the quality of primary school teachers by expanding the inquiry- and problem-based learning approach |
| Indicator #1. Pedagogical practice index at the primary level – Standard 5. | % | 39 | 2017 | 0 | 0 | 0 | 0 | 49 | 49 | CLASS and TSVI contracted by the PEU. | The index is composed of 10 indicators from CLASS and the TVSI in 4 dimensions: emotional support, classroom organization, instructional support and student engagement (See PME). |
| Indicator #2. Girls benefiting from trained teachers at the primary level. | # Female students | 0 | 2019 | 0 | 1,000 | 2,000 | 5,000 | 5,800 | 13,800 | Project Progress Report, prepared by the PEU. | CRF Indicator. Benefits are associated with changes in teachers’ pedagogical practices. |
| Indicator #3. Boys benefitting from trained teachers at the primary level. | # Male students | 0 | 2019 | 0 | 1,000 | 2,000 | 5,000 | 5,800 | 13,800 | Project Progress Report, prepared by the PEU. | CRF Indicator. Benefits are associated to changes in teachers’ pedagogical practices. |
|  | Outcome # 2: Improve the quality of secondary education teachers by improving teaching practices with a focus on student-centered science and mathematics learning. |
| Indicator #4. Pedagogical practice index at the secondary level | % | TBD | 2024 | 0 | 0 | 0 | 0 | 5 | 5 | CLASS and TVSI, contracted by the PEU. | The index is composed of 10 indicators from CLASS and the TVSI in 4 dimensions: emotional support, classroom organization, instructional support and student engagement. |
| Indicator #5. Female Students beneficiaries enrolled in the STEAM Laboratory School | # Female Students | 0 | 2019 | 0 | 0 | 0 | 40 | 40 | 80 | EMIS data extracted by the PEU. | CRF Indicator. Benefits are associated to changes in teachers’ pedagogical practices. |
| Indicator #6. Male Students beneficiaries enrolled in the STEAM Laboratory School | # Male Students | 0 | 2019 | 0 | 0 | 0 | 40 | 40 | 80 | EMIS, data extracted by the PEU. | CRF Indicator. Benefits are associated to changes in teachers’ pedagogical practices. |
| Indicator #7. Female Students benefitted by teachers trained in IPP STEAM education | # Female Students | 0 | 2019 | 0 | 0 | 0 | 0 | 6,160 | 6,160 | Progress project report prepared by the PEU | CRF Indicator. Benefits are associated to changes in teachers’ pedagogical practices. |
| Indicator #8. Male Students benefitted by teachers trained in IPP STEAM education | # Male Students | 0 | 2,019 | 0 | 0 | 0 | 0 | 5,800 | 5,800 | Progress project report prepared by the PEU | CRF Indicator. Benefits are associated to changes in teachers’ pedagogical practices. |
|  | Outcome # 3: Promote gender-sensitive STEAM teaching. |
| Indicator #9. Gender Sensitive Pedagogical practice index at the secondary level relative to that without the program (counterfactual) | % | 0 | 2024 | 0 | 0 | 0 | 0 | 5 | 5 | INERSECT sex equity classroom index | Pro-gender flag indicator. The index is composed of 4 indicators from INERSECT: Praise, acceptance, remediation and criticism. |

Outputs

| Outputs | Unit of measure | Baseline Value | Baseline Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | End of project | Means of verification | Observations2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component # 1 Primary School Teacher Professional Development |
| Output #1. Primary school Principals, General and Local Managers, and Education Officers trained in school administration and educational management. | # Persons | 0 | 2019 | 0 | 100 | 100 | 120 | 0 | 320 | Project progress report, prepared by the PEU. | The objective is to provide school administrators and education managers with the knowledge, skills and attitude to become pedagogical leaders. Upon successful completion of 40 hours of professional development, candidates are awarded a Certificate in School Leadership granted by Junior Colleges. |
| Output #2. Parents trained to increase their participation in school management. | # Parents | 0 | 2019 | 0 | 500 | 500 | 500 | 0 | 1,500 | Project Progress Report, prepared by the PEU. | The objective of the 9-hour training is to familiarize parents with IPP in Math, Science and English language; engage them in activities to decrease the climate footprint of their school; and increase their engagement in their children’s education. |
| Output #3. Teachers trained in Inquiry- and Problem-based learning | # Teachers | 0 | 2019 | 0 | 500 | 500 | 500 | 0 | 1,500 | Project Progress Report, prepared by the PEU. | The objective is to train teachers in IPP in Math, Science and English language. Upon successful completion of 80 hours of professional development, candidates are awarded a Professional development certificate from Mount Saint Vincent University in Canada. |
| Component # 2 Belize STEAM Laboratory School |
| Output #1. Set of Construction Documents (Technical Drawings and Specifications) depicting the STEAM School Design approved | Document | 0 | 2019 | 1 | 0 | 0 | 0 | 0 | 1 | MoEYSC approval attained by the PEU. | The objective is to obtain all the documents needed to tender the construction, ensuring design compliance with MoEYSC requirements. |
| Output #2. STEAM Lab School Constructed | School | 0 | 2019 | 0 | 0 | 0 | 0 | 1 | 1 | Works Completion Certificate signed by the MoEYSC, attained by the PEU. | The objective is to provide formal evidence that the building works have been approved by MoEYSC (see architectural link). |
| Output #3. STEAM Laboratory School Furnished | School | 0 | 2019 | 0 | 0 | 0 | 0 | 1 | 1 | Project Progress report, prepared by the PEU. | The list of furniture will be those specified in the final conceptual design document (see architectural link). |
| Output#4. Teachers trained through STEAM Laboratory School | Teachers | 0 | 2019 | 0 | 0 | 0 | 50 | 50 | 100 | Project Progress report, prepared by the PEU. | Pro-gender flag indicator. The objective is to provide teachers with 80 hours of professional development in gender-sensitive classroom practices and inquiry-and problem-based learning at the technical and secondary levels of education. |
| Component # 3 Evaluation |
| Output #1. Primary education endline completed | Document | 0 | 2019 | 0 | 0 | 0 | 1 | 0 | 1 | External consultancy report, contracted by the PEU. | The objective of the document is to inform MoEYSC of the changes produced at the primary level of education. |
| Output #2. Video study secondary education completed | Document | 0 | 2019 | 0 | 0 | 0 | 0 | 1 | 1 | External consultancy report, contracted by the PEU. | The objective of the document is to inform MoEYSC of the changes in teaching practices produced at the secondary level of education. |
| Output #3. RCT Baseline report completed | Document | 0 | 2019 | 0 | 0 | 0 | 1 | 0 | 1 | External consultancy report, contracted by the PEU. | The objective of the document is to inform MoEYSC on the baseline of the STEAM Lab school. |
| Output#4. Evaluation Endline report completed | Document | 0 | 2019 | 0 | 0 | 0 | 0 | 1 | 1 | External consultancy report, contracted by the PEU. | The objective of the document is to inform MoEYSC on the impacts of the STEAM Lab on the achievement of its objectives. |
| Component IV: Project Management |
| Output #1 PEU operated |  | 0 | 2019 | 1 | 1 | 1 | 1 | 1 | 1 | Project Progress Report, prepared by the PEU | The objective is to have a fully operational PEU, defined at a minimum as a unit with a Project coordinator, Procurement Officer, and Finance Officer. |

# Footnotes

The approvals of the relevant   procurement Agency for the Government of Belize and the non-objection of the IDB will be required at various stages throughout the procurement process.

If the operation does not have intermediate impact or outcome targets for any of the indicators, the corresponding years (columns) should be deleted.

If the indicator (impact, outcome and/or output) satisfies the Pro-Gender criteria, please write “Pro-Gender” in this column. If the indicator satisfies the Gender Tracking criteria, please write “Gender Tracking” in this column. If the indicator satisfies the Ethnicity Tracking criteria, please write “Ethnicity Tracking” in this column. These definitions are available in the DEM Toolkit.

At the elementary school level, the RCT of EQIP I informs on the attribution of achievement of the objective.

The original PSSM scale (Goodenow, 1993) has been validated in several studies and has been found to have good psychometric properties.