## Sheet1
Inter-American Development Bank
[9 empty] | VPC/FMP | Annex II - RG-T2649/RG-T2706
Page 1 of 1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Regional |  |  |  |  | Executing agency: IDB |  |  |  |  | Public or private sector: Public
Project number: RG-T2649 and RG-T2706 |  |  |  |  | Title of Project: Increasing Maritime Trade and Transport Efficiency and Connectivity in the Caribbean: Short Sea Shipping Networks
Period covered by the plan: Sep-15 to Dec-17
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): 80,000 |  |  |  | Consulting services(in US$):__520,000__________
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
|  | Components 1, 2 &3 | [8 empty] | International Competitive Bidding
National Competitive Bidding
1 |  | Consulting services | [8 empty] | Shopping
|  | Consulting Firm to perform an analysis of current maritime trade, infrastructure condition and service quality and resulting recommendations of institutional, financial, and legal measures to better govern inter-island maritime trade in the Caribbean, with the intent to propose new short sea shipping route possibilities. | 450000 | FBS | Ex post | 100 | 0 | 2015-11-01 |  |  | Least-Cost Selection
Components 1, 2 &3
2 |  | Consulting services | [8 empty] | Quality and Cost Based Selection
|  | Individual Consultant to support the preparation of ToRs and supervision of studies | 30000 | IICQ | Ex post | 100 | 0 | 2016-01-31
National System
Component 4
3 |  | Consulting services
|  | Individual Consultant to perform an assessment of the feasibility of implementing the Maritime TIM in the Caribbean | 40000 | IICQ | Ex post | 100 | 0 | 2016-02-01
4 |  | Component 1-4 | [8 empty] | Ex Ante
|  | Logistics and material reproduction for two workshops | 40000 | PC | Ex post | 100 | 0 | 2016-03-01 |  |  | Ex Post
Other
|  | logistics | 40000 | PC | Ex post | 100 | 0 | 2016-03-01 |  |  | National System
Total |  |  | 600000 | Prepared by: Sergio Deambrosi |  |  | Date: January, 2016
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.