RPG Procurement Plan Status – September 30, 2008

| Ref. No. | Description of the contract and estimated cost of procurement | Procurement method/ Selection Method | Review (prior or post) | Source of financing and percentage | Expression of Interest (Yes/No) | Status (pending, in process, awarded, cancelled) | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | IDB % | Local/other % |  |  |  |
| 1 | Establishment of a Baseline for Monitoring and Evaluation System for the “Regional DRM for Sustainable Tourism in the Caribbean” project. Estimated Cost US$24,250 M&E Framework Consultant to provide training for the five project National Focal Points (Barbados, The Bahamas, Dominican Republic, Jamaica and Turks & Caicos Isls.), and the Project Advisory Committee on November 9, 2007 US$4355.50 | Individual Consultant. Selection on basis of qualification and submission of technical proposal. Contract Extension | Prior | 100 |  | Yes | Awarded | Original contract completed in October 2008 A follow up contract also completed |
| 2 | Mid-Term Evaluation of the “Regional DRM for Sustainable Tourism in the Caribbean” project. Estimated Cost US$ 16,250 | Individual Consultant. Selection on basis of qualification and submission of technical proposal. | Prior | 100 |  | Yes | Pending | Bank contracts. Midterm review mission pending disbursement level at 50% of Fund allocation. |
| 3 | Final Evaluation of the “Regional DRM for Sustainable Tourism in the Caribbean” project. Estimated Cost US$21,250 | Individual Consultant. Selection on basis of qualification and submission of technical proposal. | Prior | 100 |  | Yes | Pending | Bank contracts. Too soon – evaluation expected after June 2009. |
| 4 | Development of Proposed Standards for Risk Mapping and Vulnerability Assessment for the Tourism Sector in the Caribbean. Estimated Cost US$98,200 | (i) Individual Consultants. Selection on basis of qualification and submission of technical proposal (ii) Or Firm with QCBS | Prior | 100 |  | Yes | Awarded | Contract awarded to DRM of Switzerland – contract signature March 17, 2008. |
| 5 | Development of a Tourism Mitigation Strategy and Plan of Action for the Caribbean. Estimated Cost US$ 112,500 | Firm. Quality- and cost-based selection | Prior | 100 |  | Yes | Awarded | Contract awarded to CEP (Barbados) and contract signature February 11, 2008 |
| 6 | Rapporteurs (2) for regional workshops Estimated Total Cost (US$6000) (US$ 3,000 per rapporteur). | Individual Consultants. Selection on basis of qualification. | Prior | 100 |  | No | Pending | The Regional workshop has been postponed indefinitely pending deliberations on current consultancy contract. |
| 7 | Institutional Strengthening of National Tourism Organizations in the Caribbean. Estimated Cost US$20,000 | Individual. Selection on basis of qualification and presentation of technical proposals. | Prior | 78 | 22 | Yes | Pending | An on-line course is planned which incorporates Disaster Risk Management for the Tourism Sector – with UWI and CTO collaboration. |
| 8 | Project Coordinator for the Project Implementation Unit of the “Regional DRM for Sustainable Tourism in the Caribbean” project. Estimated Cost US$ 140,010 for 3 years. | Individual Consultant. Selection on basis of qualification. | Prior | 100 |  | Yes | Awarded | Contract awarded and assignment began on April 2, 2007. |
| 9 | Technical Officer “Regional DRM for the Project Implementation Unit of for Sustainable Tourism in the Caribbean” project. Estimated Cost US$69,925 for 2.5 years. | Individual Consultant. Selection on basis of qualification. | Prior | 100 |  | Yes | Awarded | Contract awarded, and assignment began on March 1, 2007 |