## Sheet1
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: Paraguay |  |  |  |  | Executing agency: IDB |  |  |  |  | Public or private sector: public
Project number: PR-T1196 |  |  |  |  | Title of Project: Support for the Creation of a Ciudad Mujer (Women’s City) Program in Paraguay
Period covered by the plan: January 2016 - July 2018
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  | 55000 |  | Consulting services(in US$): 558,700
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1. Design of a Ciudad Mujer Model for Paraguay | [8 empty] | International Competitive Bidding
National Competitive Bidding
|  | Goods | [8 empty] | Shopping
|  | Good 1 (brief description) | [8 empty] | Least-Cost Selection
Quality and Cost Based Selection
|  | Non consulting services | [8 empty] | Quality Based Selection
|  | Service 1 (brief description) | [8 empty] | Selection Based on the Consultants' Qualifications
|  | Consulting firms | [8 empty] | Individual Consultant
| 1.1 | Consulting 1. Architectural Design Duration: 50 days | 100000 | CQS |  | 100 | 0 | 2016-03-01 |  |  | National System
| 1.2 | Consulting 9. Design Module: Central Functions (reception, registration, orientation, follow-up and case management) Duration: 100 days | 20000 | CQS |  | 100 | 0 | 2016-03-01
Individual consultants
| 1.3 | Consulting 2. Women's Needs Assessment and Analysis of Service Supply Duration: 25 days | 5000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.4 | Consulting 3. Design Module: Sexual and Reproductive Health Duration: 100 days | 20000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.5 | Consulting 4. Design Module: Economic Autonomy Duration: 115 days | 23000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.6 | Consulting 5. Design Module: Services to Address Violence against Women Duration: 115 days | 23000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.7 | Consulting 6. Design Module: Community education Duration: 75 days | 15000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.8 | Consulting 7. Design Module: Child Care Duration: 75 days | 15000 | NICQ |  | 100 | 0 | 2016-01-01
| 1.9 | Consulting 8. Design Module: Adolescents Program Duration: 100 days | 20000 | NICQ |  | 100 | 0 | 2016-01-01
|  | Subtotal Component 1 | 241000
2 |  | Component 2. Institutional Strengthening for Program Implementation
. |  | Individual consultants
| 2.1 | Consulting 10. Communication Strategy (design, development and implementation) Duration: 315 days | 63000 | NICQ |  | 100 | 0 | 2016-06-01 |  |  | National System
| 2.2 | Consulting 11. Engineer/Construction Specialist - Construction of Procurement Processes and Monitoring Duration: 75 days | 20800 | NICQ |  | 100 | 0 | 2017-01-01
| 2.3 | Consulting 12. Design of Inter-institutional Management and Financial Sustainability of the CCM Duration: 125 days | 25000 | NICQ |  | 100 | 0 | 2016-06-01
| 2.4 | Consulting 13. Design of the Information and Registration Systems Duration: 60 days | 53000 | NICQ |  | 100 | 0 | 2016-06-01
| 2.5 | Consulting 14. Design of Monitoring and Evaluation System Duration: 75 days | 15000 | NICQ |  | 100 | 0 | 2016-06-01
| 2.6 | Consulting 15. Institutional Analysis Duration: 50 days | 10000 | NICQ |  | 100 | 0 | 2017-06-01
| 2.7 | Consulting 16. Cost-benefit Analysis Duration: 50 days | 10000 | NICQ |  | 100 | 0 | 2017-06-01
| 2.8 | Consulting 17. Design and Implementation of the Staff Training Program Duration: 98 days | 19500 | NICQ |  | 100 | 0 | 2016-07-01
| 2.9 | Consulting 18. Strengthening of Institutional Capacity for the Coordination of the Ciudad Mujer Project Duration: 520 days | 101400 | NICQ |  | 100 | 0 | 2016-01-01
Goods and Services
| 3.1 | Airfare and per diem | 50000 | PC |  | 100 | 0 | 2016-01-01 |  | This is for approximately 20 different airfares and per diem to participate in internships in Ciudad Mujer El Salvador in year 1 and 2
| 3.2 | Printing of training materials | 5000 | PC |  | 100 | 0 | 2017-06-01
|  | Subtotal Component 2 | 372700
|  | Contingencies | 32300
|  | TOTAL | 646000
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.
2015-11-11