## Summary
INFORMATION FOR PROCUREMENT PLAN INITIAL
1. Procurement Plan Coverage
Data | From | Until
Procurement Plan Coverage: | January 2019 | Jun 2020
2. Procurement Plan Details
Version ( 1-xxxx (Year) ) : | June 2018
3. Amounts by Investment Category
Investment Category | Amount Financed by the Bank | Total Amount (Including counterpart)
Works | USD $15,884,725.99 | USD 0.00
Goods | USD $269,600.00 | USD 0.00
Non-Consulting Services | USD 0.00 | USD 0.00
Training | USD 76,000.00 | USD 0.00
Operative Costs | USD 0.00 | USD 0.00
Consulting Services (Firms + Individuals) | USD $2,797,947.41 ($1,590,000.41+$1,207,947.00) | USD 0.00
Transfers | USD 0.00 | USD 0.00
Community Participation | USD 0.00 | USD 0.00
Unassigned | USD 0.00 | USD 0.00
Total | USD $19,028,273.40 | USD 0.00
4. Components
Project Components | Amount Financed by the Bank | Total Amount (Including counterpart)
Component 1 - IRRIGATION AND DRAINAGE | USD 17,774,173.40 | USD 0.00
Component 2 - AGRICULTURAL STATISTICS AND INFORMATION | USD 174,100 | USD 0.00
PROJECT AND OPERATIONS MANAGEMENT | USD 1,080,000
Total | USD $19,028,273.40 | USD 0.00

## Procurement Plan
INTER-AMERICAN DEVELOPMENT BANK
SURINAME: SUSTAINABLE AGRICULTURAL PRODUCTIVITY PROGRAM
(SU-L1052)
PROCUREMENT PLAN (PP)
(in US$)
Executing Agency: | Activity: | Additional Information | Procurement Method | Lots Quantity | Process Number | Estimated Amount |  |  | Associated Component | Review Method | Dates |  | Comments - for UCS include selection method
|  |  | (Select one of the options): |  |  | Estimated Amount, in US$: | Estimated Amount IDB %: | Estimated Amount Counterpart %: |  |  | Specific Procurement notice | Contract Signature
Consulting firms
| Consultants to prepare designs, prepare contracting documents and perform supervision of repair works |  | National Competitive Bidding |  |  | $675.101.00 | 100% |  | Component 1 | Ex-Ante | April 2019 | 2019-09-01
| Conduct of studies, environmental designs and supervision for the new hydraulic structures. |  | National Competitive Bidding |  |  | 950000.41 | 100% |  | Component 1 | Ex-Ante | April 2019 | 2019-09-01
| Hydrology Consultancies (National Consultant & HydroBid) |  | Quality and Cost Based Selection |  |  | 150000 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-12-01
| Pesticide Survey and Water Sediment Quality Study |  | Quality and Cost Based Selection |  |  | 200000 | 100% |  | Component 1 | Ex-Ante | 2019-04-01 | 2019-09-01
| Design and Implementation Water quality monitoring system |  | Quality and Cost Based Selection |  |  | 100000 | 100% |  | Component 1 | Ex-Ante | 2019-04-01 | 2019-09-01
| Ecological assessment of the Nanni Swamp |  | Selection Based on the Consultants' Qualifications |  |  | 40000 | 100% |  | Component 1 | Ex-Ante | 2019-06-01 | 2019-09-01
| Design and Conduct of Gender awareness program for first two years |  | Selection Based on the Consultants' Qualifications |  |  | 40000 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-12-01
| Design and implementation of Integrated Water Resources Management Plan |  | Quality and Cost Based Selection |  |  | 90000 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-10-01
| Questionnaire design and pilot survey |  | Selection Based on the Consultants' Qualifications |  |  | 20000 | 100% |  | Component 2 | Ex-Ante | 2019-07-01 | 2019-10-01
| Conduct of survey for baseline |  | Quality and Cost Based Selection |  |  | $75.000.00 | 100% |  | Component 2 | Ex-Ante | 2020-01-01 | 2020-06-01
Individual Consultants
| Conduct Strengthening, Coordination in I&D management activities in Nickerie District |  | Comparison of Qualifications - National Individual Consultant |  |  | 4800 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-10-01
| Strengthening District Water Board Commission in introduction improved O&M at WB level |  | Comparison of Qualifications - National Individual Consultant |  |  | 9000 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-10-01
| Assignment National Consultant in Hydrometry |  | Comparison of Qualifications - National Individual Consultant |  |  | 38667 | 100% |  | Component 1 | Ex-Ante | 2020-01-01 | 2020-04-01
| General and Technical Coordination |  | Comparison of Qualifications - National Individual Consultant |  |  | 540000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-01-01 | 2019-05-01
| Planning Monitoring and Evaluation Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | 108000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-01-01 | 2019-05-01
| Financial Management Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | 144000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-01-01 | 2019-05-01
| Procurement Management Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | 144000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-01-01 | 2019-05-01
| Social and Environmental Monitoring Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | $108,00.00 | 100% |  | Project and Operations Management | Ex-Ante | 2019-03-01 | 2019-06-01
| Communications Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | 108000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-03-01 | 2019-06-01
| Administrative Support Officer |  | Comparison of Qualifications - National Individual Consultant |  |  | 36000 | 100% |  | Project and Operations Management | Ex-Ante | 2019-01-01 | 2019-05-01
| National consultant for training and support in ID management in Nickerie Disitrct. Inclusive of workshop logistics and training material |  | Quality Based Selection |  |  | 9000 | 100% |  | Component 1 | Ex-Ante | 2019-07-01 | 2019-10-01
| Water master and assistants |  | Shopping |  |  | 66480 | 100% |  | Component 1 | Ex-Ante | April 2019 | June 2019
Training services
| Undertake training for WM and WBC. Inclusive of workshop logistics and training material |  | Quality and Cost Based Selection |  |  | 43000 | 100% |  | Component 1 | Ex-Ante | April 2019 | June 2019
| Training in statistics, computing, etc. |  | Selection Based on the Consultants' Qualifications |  |  | 33000 | 100% |  | Component 2 | Ex-Ante | 2020-01-01 | 2020-05-01
Goods
| Procurement of Water Level recorders |  | Shopping |  |  | 14000 | 100% |  | Component 1 | Ex-Ante | 2019-12-01 | 2020-02-01
| Procurement of New Telemetric Water Level recorders/ discharge measurements |  | International Competitive Bidding |  |  | 120000 | 100% |  | Component 1 | Ex-Ante | 2019-12-01 | 2020-04-01
| Procurement of Weather Stations |  | Shopping |  |  | 10000 | 100% |  | Component 1 | Ex-Ante | 2020-01-01 | 2020-04-01
| Vehicles to reinforce ressort offices |  | National Competitive Bidding |  |  | 79600 | 100% |  | Component 2 | Ex-Ante | 2020-04-01 | 2020-07-01
| Computers and similar to reinforce ressort offices |  | National Competitive Bidding |  |  | 35500 | 100% |  | Component 2 | Ex-Ante | 2020-01-01 | 2020-03-01
| Additional improvement of reporting system |  | Shopping |  |  | 6000 | 100% |  | Component 2 | Ex-Ante | 2019-07-01 | 2019-09-01
| Procurement of motorbikes |  | Shopping |  |  | 4500 | 100% |  | Component 1 | Ex-Ante | April 2019 | July 2019
Works
| Undertake the execution of repair works by contractors |  | Two-envelope International Competitive Bidding |  |  | 5850871 | 100% |  | Component 1 | Ex-Ante | 2019-09-01 | 2020-01-01
| Undertake execution works by Contractor 1 for WB1&WB2 |  | Two-envelope International Competitive Bidding |  |  | 3383333.33 | 100% |  | Component 1 | Ex-Ante | 2020-01-01 | 2020-05-01
| Undertake execution works by Contractor 2 for WB1&WB2 |  | Two-envelope International Competitive Bidding |  |  | 3383333.33 | 100% |  | Component 1 | Ex-Ante | 2020-01-01 | 2020-06-01
| Undertake execution works by Contractor 3 for WB1&WB2 |  | Two-envelope International Competitive Bidding |  |  | 3267188.33 | 100% |  | Component 1 | Ex-Ante | 2020-01-01 | 2020-06-01