## Procurement Plan Jul-Dec 2018
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: JAMAICA |  |  |  |  | Executing agency: Jamaica Promotions Corporation (JAMPRO) |  |  |  |  | Public or private sector: Public
Project number: JA-T1151 |  |  |  |  | Title of Project: Implementation Support for Skills Development for Global Services
Period covered by the plan: July 2018 - December 2018
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):____________
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
|  | Component 1 | 160000 | [7 empty] | International Competitive Bidding
Quality Based Selection
|  | Good and works | 40000
1.1 |  | PEU Office Outfitting | 40000 | PC | Country System | 100 | 0 | 2018-09-01 | n.a. | Entails different processes to outfitt PEU given that it is being established: furniture, computers, connectivity, office space among other.
|  | Non consulting services | 20000
1.2 |  | Workshops, stakeholder meetings for Ops Manual consultation and approval, and kick-off workshop | 20000 | PC | Country System | 100 | 0 | Q3 2018 | n.a. | Support for preparation of an operating manual of the JA-L1079 programme’s goals and activities (Workshops, Stakeholder meetings, socialization for Ops Manual Approval). | Selection Based on the Consultants' Qualifications
|  | Individual consultants | 100000
1.3 |  | PEU Programme Director | 41000 | IICQ | Ex ante | 100 | 0 | Q3 2018 | n.a.
1.4 |  | Procurement Specialist | 21000 | IICQ | Ex ante | 100 | 0 | Q3 2018 | n.a.
1.5 |  | Financial Management Specialist | 18000 | IICQ | Ex ante | 100 | 0 | Q3 2018 | n.a.
1.6 |  | Tech Support Consultant | 10000 | IICQ | Ex ante | 100 | 0 | Q3 2018 | n.a. | Individual Consultant to support drafting of tech TORs.
1.7 |  | Project Assistant | 10000 | IICQ | Ex ante | 100 | 0 | Q3 2018 | n.a.
|  | Component 2 | 40000
Non consulting services
2.1 |  | Industry Validation workshop for updated job-readiness: soft, cognitive and foundational digital skills module | 10000 | PC | Country System | 100 | 0 | Q3 2018 | n.a.
Consulting services
2.2 |  | Update of job-readiness curricula: soft, cognitive and foundational digital skills module in the TVET training system | 30000 | IICQ | Ex Ante | 100 | 0 | Q3 2018 | critical |  | Ex Ante
|  | Component 3 | 100000 | [7 empty] | Ex Post
3.1 |  | Analytical work to support the GSS industry (different studies) | 100000 | QCBS | Ex Ante | 100 | 0 | Q3 2018 | n.a. | Entails different studies to be defined as JA-L1079 starts execution. | National System
|  | Data collection of firms operating in the GSS | 50000
Audit
Total |  |  | 300000 | Prepared by: Programme Director GSS Project |  |  | Date: October 2018
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection nder a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical"or "complex"that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.

## Procurement Plan Jan-Mar Rev
Inter-American Development Bank
VPC/FMP
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: JAMAICA | [8 empty] | Executing agency: Jamaica Promotions Corporation (JAMPRO) |  |  |  |  | Public or private sector: Public
Project number: JA-T1151 | [8 empty] | Title of Project: Implementation Support for Skills Development for Global Services
Period covered by the plan: January to March 2019
Threshold for ex-post review of procurements: | [7 empty] | Goods and services (in US$):____________ |  |  |  | Consulting services(in US$):____________
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | TC budget reassigned | Commitments against budgeted components to Dec 31, 2018 | Projected TC budget available as at Dec 31, 2018 | Projected spend Jan - Mar 2019 | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[10 empty] | IDB/MIF % | Local/other % |  |  |  | Direct Contracting
1 |  | Component 1 | 160000 | 160000 | [10 empty] | International Competitive Bidding
Quality Based Selection
|  | Good and works | 40000 | 40000 | 34828 | 5172 | 5172
1.1 |  | PEU Office Outfitting | 40000 | 40000 | 26028 |  |  | PC | Country System | 100 | 0 | 2018-01-01 | n.a. | Entails different processes to outfit PEU given that it is being established: furniture, computers, connectivity, office space among other.
Plus: ACCPAC software
Plus: ACCPAC installation, configuration and training
Plus: ACCPAC renewals in years 2- 5
PEU SPACE
|  | Leases |  |  | 8800
Other costs: Project Mgmt Software
|  | Non consulting services | 20000 | 20000 | 5168 | 14832 | 14832 |  |  |  |  | 2018-01-01
1.2 |  | Workshops, stakeholder meetings for Ops Manual consultation and approval, and kick-off workshop | 20000 | 20000 | 5168 | 14832 |  | PC | Country System | 100 | 0 | Q1 2019 | n.a. | Support to any additional workshops that PEU needs to have to support its operations, sensitize beneficiary agencies on procedures, hosts meeting re GS-EB and/or PSC. | Selection Based on the Consultants' Qualifications
|  | Individual consultants | 100000 | 100000 | 70747 | 29253 | 29253 |  |  |  |  | 2018-01-01
1.3 |  | PEU Programme Director | 41000 | 51000 | 40888 | 10112 |  | IICQ | Ex ante | 100 | 0 | Q1 2019 | n.a.
1.4 |  | Procurement Specialist | 21000 | 21000 | 9692 | 11308 |  | IICQ | Ex ante | 100 | 0 | Q1 2019 | n.a.
1.5 |  | Financial Management Specialist | 18000 | 18000 | 17625 | 375 |  | IICQ | Ex ante | 100 | 0 | Q1 2019 | n.a.
1.6 |  | Tech Support Consultant | 10000 | 0 |  |  |  | IICQ | Ex ante | 100 | 0 | Q1 2019 | n.a.
1.7 |  | Project Assistant | 10000 | 10000 | 2542 | 7458 |  | IICQ | Ex ante | 100 | 0 | Q1 2019 | n.a.
|  | Monitoring & Eval. Specialist | 0 | 0 | 0
2 |  | Component 2 | 40000 | 40000 |  | 40000 | 40000
Non consulting services
2.1 |  | Industry Validation workshop for updated job-readiness: soft, cognitive and foundational digital skills module | 10000 | 10000 | 0 | 10000 |  | PC | Country System | 100 | 0 | Q1 2019 | n.a.
Consulting services
2.2 |  | Update of job-readiness curricula: soft, cognitive and foundational digital skills module in the TVET training system | 30000 | 30000 | 0 | 30000 |  | CQS | Ex Ante | 100 | 0 | Q1 2019 | critical |  | Ex Ante
3 |  | Component 3 | 100000 | 90000 |  | 90000 | 90000 | [7 empty] | Ex Post
3.1 |  | Analytical work to support the GSS industry (different studies) | 100000 | 90000 | 0 |  |  | CQS | Ex Ante | 100 | 0 | Q1 2019 | n.a. | Entails different studies to be defined as JA-L1079 starts execution. | National System
|  | Data collection of firms operating in the GSS | 50000
|  | Data collection of firms operating in the Global Services Sector for the execution of the skills development for Global Services(JA-L1079) |  | 50000 | 0 | 50000 | [5 empty] | Q1 2019
|  | Survey to gauge cultural perception towards the Global Services Sector |  | 40000 | 0 | 40000 | [5 empty] | Q1 2019
4 |  | Component 4 |  | 10000 |  | 10000
4.1 |  | Audit |  | 10000 |  | 10000 | [5 empty] | 2020-03-01
Total |  |  | 300000 |  |  |  |  | Prepared by: Programme Director GSS Project |  |  | Date: December 2018
|  |  |  | 300000 |  | 189257 | 179257
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.
Note on E10: Marjorie Straw: As per signed TC agreement
Note on H25: Marjorie Straw: Remaining funds from TC will only cover one month's compensation for consultants. Note: after January 2019, all compensation will be paid from loan proceeds - retroactive or current.
Note on H32: Marjorie Straw: Procurement processes related to this activity have begun.
Note on G43: Marjorie Straw: Spend related to this activity will occur in 2020.