STANDARD BIDDING DOCUMENTS

**Output and Performance-Based Road Contracts**

**(With or Without Prequalification)**

**TRAIL VERSION**

**Inter-American Development Bank**

**June 2022**

This document was prepared by the Inter-American Development Bank based on the World Bank's Standard Procurement Document for Output and Performance-Based Road Contracts (OPBRC) October 2017.

The IDB thanks the International Bank for Reconstruction and Development (IBRD) for allowing the use and the adaptation of this document for use in its loan operations.

**Revisions**

|  |  |  |
| --- | --- | --- |
| **Version** | **Modification** | **Reason** |
| April 2019 | First publication | First trial edition by IDB |
| January 2020 |  | The review is a consequence of the approval by the Board of Executive Directors of Bank of the Procurement Policies GN-2349-15 on 2nd of July 2019 effective as 1st of January 2020, which includes *interalia*, Best Final Offer (BAFO), Most Advantageous Bid, Negotiations, Notification of Intention of Award, Standstill Period, Disclosure of Beneficial Ownership and Complaints.  In accordance with the Policies, the term "Request for Bid" (RFB) is introduced to distinguish the document from the "Request for Proposals" (RFP) that may be available in the future.  Prohibited Practices are udpated.  The instructions and conditions of contract referring to fax are removed. |
| November 2021 |  | Integration of language and requirements consistent with the Bank's new Environmental and Social Policy Framework (ESPF). |

**Foreword and Notes to the Users of this SBD**

1. This Foreword summarizes the concept of Output - and Performance-based Road Contracts (OPBRC).

2. The Conditions of Contract have been written in order to take into account the specific nature of the services to be provided by the Contractor, which go much beyond the mere execution of pre-defined physical works and to include the “output” basis in the contract. The Contract covers an array of activities needed to achieve and maintain a certain Service Level for road users, starting from design, construction, operation and maintenance including several activities related to the Management (including periodic evaluation) of the road network under contract. It includes carrying out Rehabilitation Works to bring the Road up to pre-defined standards, Improvement Works specified by the Employer aiming at adding new characteristics to the Roads in response to new traffic, safety or other conditions and Emergency Works needed to reinstate the Roads after damage has occurred as a result of natural phenomena with imponderable consequences (such as strong storms, flooding and earthquakes) under the conditions defined in the contract. A separate document has also been prepared and is presented as an Annex, providing “Sample Specifications for OPBRC,” these are mostly geared towards the Management and Maintenance of a variety of road types and will facilitate the preparation of actual and specific Specifications that must be part of the final bidding document.

3. Output-and Performance-based contracting for Roads is designed to increase the efficiency and effectiveness of road asset management and maintenance. It should ensure that the physical condition of the roads under contract is adequate for the need of road users, over the entire period of the contract, which is normally several years. This type of contract significantly expands the role of the private sector, from the simple execution of works to the management and conservation of road assets.

4. In traditional road construction and maintenance contracts, the Contractor is responsible for the execution of works which are normally defined by the Employer, and the Contractor is paid on the basis of unit prices for different work items, i.e. a contract based on “inputs” to the works. The results of traditional road contracts are in many cases less-than-optimal. The problem is that the Contractor has the wrong incentive, which is to carry out the maximum amount of works, in order to maximize its turnover and profits. Even if the work is carried out according to plan and much money is spent, the overall service quality for the road user depends on the quality of the design given to the Contractor who is not accountable for it. In many cases the roads do not last as long as they should because of deficiencies in the original design, aggravated by inadequate maintenance.

5. The OPBRC addresses the issue of inadequate incentives. During the Bidding process, contractors compete among each other by essentially proposing fixed lump-sum prices for bringing the road to a certain service level and then maintaining it at that level for a relatively long period. It is important to understand that contractors are not paid directly for “inputs” or physical works (which they will undoubtedly have to carry out), but for achieving specified Service Levels, i.e., the Rehabilitation of the road to pre-defined standards (if so required by the bidding document), the maintenance service of ensuring certain Service Levels on the roads under contract, and specific improvements (if so required by the bidding document), all representing outputs or outcomes. A monthly lump-sum remuneration paid to the Contractor will cover all physical and non-physical maintenance services provided by the Contractor, except for unforeseen emergency works, which are remunerated separately. The Rehabilitation and Improvement Works, which have been explicitly specified by the Employer in the contract, are quoted on the basis of measurable output quantities and paid as performed. In order to be entitled to the monthly payment for maintenance services, the Contractor must ensure that the roads under contract comply with the Service Levels, which have been specified in the bidding document. It is possible that during some months he will have to carry out a rather large amount of physical works in order to comply with the required Service Levels and very little work during other months. However, his monthly payment remains the same as long as the required Service Levels are complied with.

6. A fundamental feature of the OPBRC is that the “Contractor” must not necessarily and in all cases be a traditional works contractor, but can (if allowed in the bidding document) be any type of firm or business venture having the necessary legal, technical, managerial and financial capacity to fulfill the contract. In any case, the contractor is responsible for designing and carrying out the works, services and actions he believes are necessary in order to achieve and maintain the Service Levels stated in the contract. The Service Levels are defined from a road user’s perspective and may include factors such as average travel speeds, riding comfort, safety features, etc. If the Service Level is not achieved in any given month, the payment for that month may be reduced or even suspended.

7. Under the OPBRC, the Contractor has a strong financial incentive to be both efficient and effective whenever he undertakes work. In order to maximize profits, he must reduce his activities to the smallest possible volume of intelligently designed interventions, which nevertheless ensure that pre-defined indicators of Service Level are achieved and maintained over time. This type of contract makes it necessary for the Contractor to have a good management capacity. Here, “management” means the capability to define, optimize and carry out on a timely basis the physical interventions, which are needed in the short, medium and long term, in order to guarantee that the roads remain above the agreed Service Levels. In other words, within the contract limitations and those required to comply with local legislation, technical and performance specifications and environmental and social regulations, the Contractor is entitled to independently define: (i) what to do, (ii) where to do it, (iii) how to do it, and (iv) when to do it. The role of the Road Administration and of the Employer is to enforce the contract by verifying compliance with the agreed Service Levels and with all applicable legislation and regulations.

8. Maintaining a road network includes both routine and periodic tasks. Routine maintenance consists of many different tasks frequently necessary to maintain the function of the road (such as pothole repairs, cleaning of drainage, sealing of cracks, cutting of vegetation, etc.). Periodic maintenance consists of predictable and more costly measures of a less frequent nature designed to avoid road degradation (such as grading, drainage work, resurfacing, asphaltic concrete overlays, etc.). Intelligent management, the timeliness of interventions and the adequacy of technical solutions are critical. It is expected that the use of private specialized firms under output- and performance-based contracts will unleash significant efficiency gains, and stimulate innovation in comparison with traditional road administration practices.

9. Minimum road conditions and Service Levels are defined through output and performance measures, and these are used under the OPBRC to define and measure the desired performance of the Contractor. In the OPBRC, the defined performance measures are thus the accepted minimum thresholds for the quality levels of the roads for which the Contractor is responsible.

10. The performance criteria should ideally cover all aspects of the contract and take account of the fact that different sub-areas within the contract area might require different Service Levels. Criteria can be defined at three levels (although simpler contracts will not use all of the criteria identified below):

1. Road User Service and Comfort measures, which can be expressed in terms such as:
   * Road Roughness
   * Road and lane width
   * Rutting
   * Skid resistance
   * Vegetation control
   * Visibility of road signs and markings
   * Availability of each lane-km for use by traffic
   * Response times to rectify defects that compromise the safety of road users
   * Attendance at road accidents
   * Drainage off the pavement (standing water is dangerous for road users)
2. Road Durability measures, which can be expressed in terms such as:

* Longitudinal profile
* Pavement strength
* The extent of repairs permissible before a more extensive periodic maintenance treatment is required
* Degree of sedimentation in drainage facilities

1. Management Performance Measures, which define the information the Employer requires both to govern the asset during the term of the contract, and to facilitate the next tender round. Requirements should include:

* Delivery of regular progress reports to the Road Controlling Authority
* Inventory updates and other data sharing requirements
* Maintenance history (so subsequent tenderers can price the work).

To avoid ambiguity, all performance measures must be clearly defined and objectively measurable.

11. Together the performance measures define the minimum acceptable Service Level for the particular road. In setting the measures various criteria (both technical and practical) need to be carefully considered, such as (i) traffic volume and composition, (ii) urban vs. rural roads (iii) flat, hilly or mountainous terrain, (iv) subgrade quality and type, (v) quality of available construction materials, (vi) capacity of available contractors, (vii) any environmental constraints, such as protected areas, parks, forest reserves, etc. However, probably the most important criterion is the question of what Service Level can be afforded and economically justified for the road in question. [Guidance on Service Levels for Unpaved Roads can be found in the World Bank’s “Draft Infrastructure Note: Economically Justified Level of Service of Unpaved Roads”, Rodrigo Archondo-Callao, January 2004]

12. Under the terms of the contract, the Contractor will also be responsible for the continuous monitoring and control of road conditions and Service Levels for all roads or road sections included in the contract. This will not only be necessary to fulfill the contract requirements, but it is an activity which will provide him with the information needed to be able (i) to know the degree of his own compliance with Service Level requirements, and (ii) to define and plan, in a timely fashion, all physical interventions required to ensure that service quality indicators never fall below the indicated thresholds. Under the OPBRC modality, the Contractor will not receive instructions from the Employer concerning the type and volume of road maintenance works to be carried out. Instead, all initiative rests with the Contractor who must do whatever is necessary and efficient to achieve the quality levels required. This concept is expected to lead not only to significant efficiency gains, as mentioned earlier, but also to technological innovation.

13. The beneficiaries of the new concept are expected to be the road users, the Road Administration, and the contractors or other private sector enterprises. In a wider sense, future generations will be able to benefit from a better preservation of past investments in roads. Road users will be able to know the Service Level they can expect in return for the payments they make for the use of the infrastructure (tolls, tariffs, user fees, taxes, etc.). The Road Administrations should benefit by obtaining better overall road conditions at the same levels of expenditure. For contractors and other private sector enterprises, the new type of contracts should open up new business opportunities, in which longer contract periods provide a more stable business environment, and for the establishment of true Public-Private Partnership relations. However, it may be the future generations who will perhaps benefit most, since they will not have to pay for the reconstruction of roads destroyed because of a lack of maintenance today.

14. Although the design of the works and services to be carried out is under the responsibility of the Contractor, this type of procurement requires good preparatory engineering work. It is necessary to prepare comprehensive information on the actual condition of the roads covered by the contract. If rehabilitation works are required, the Employer should define the level of quality (or standard) to be achieved by the Contractor for delivery and completion during the contract. If improvement works are sought, a well-designed bill of quantities defining specific outputs for Bidders to price and, later on, allow measurement and payment of the Contractor, is of paramount importance. Emergency works, although impossible to quantify in advance, will certainly be necessary. To allow Bidders to offer prices for Emergency Works, a unit price bill of quantities (similar for civil works under unit prices) with quantity estimates should be prepared for Bidders to price for Bid evaluation purposes. Later on, these unit prices and real measured volumes of Emergency Works executed will be used for payments. Another important area requiring sound engineering advice is to define if the Rehabilitation Works should be included in the contract or be carried out in advance under a separate “standard” civil works contract. This decision depends in each case on the risks that the Borrower (and his advisor) understands as possible to be administered cost-effectively by the Contractor. In general, if those initial works represent more than 40-50% of the contract value, the risks may be too high and an initial separate contract may be warranted. However, if the Employer wants to have Rehabilitation Works based on a pre-defined design and use this document to connect it to future maintenance by the same Contractor, the documents need to be adapted. In this case, the bill of quantities for Rehabilitation Works should be modified to become similar to those for emergency works and the measurement and payment clauses should be modified for an “input” type contract.

15. When Rehabilitation Works and Improvement Works are not specifically required in the bidding document, it is expected that in order to comply with the contract, the Contractor will most likely have to carry out different types of works, including some small initial rehabilitation and improvements, routine maintenance activities and periodic maintenance works. The definition of the exact nature of the works, their timing, their costing and their implementation is left to the judgment of the Contractor. This means that his capacity must be above the usual capacity of a traditional civil works contractor. In fact, an essential attribute is the capacity to manage roads, while the actual physical execution may either be carried out by the Contractor himself, or by different specialized firms participating in a Joint Venture with the main contractor, or under subcontracts. Joint Ventures may include Engineering firms and medium, small and even micro-enterprises. Consequently, a well-designed prequalification process is highly recommended in order to ensure that only qualified Bidders participate in the Bidding process, even though, the present bidding document can also be used when post-qualification is envisaged. In the design of the prequalification requirements the Employer should consider if the experience of specialized sub-contractors (like an engineering consultant) should be allowed to be added to those of the applicants. The activities which may be delegated by the main contractor to subcontractors not participating in the prequalification process should be listed in the Particular Conditions and Bidders should be alerted about this point in the Bid Data Sheet.

16. Output- and Performance-based Road Contracts transfer a significant burden of risk onto the contractor. It is important that this burden is both equitable and within the capacity of the industry. The contract defines the risk profile carried by the contractor arising from storm events, legislation changes, changes in traffic volumes, and roadside development.

17. Some emergency works should always be foreseen. Those are meant to remedy unexpected damage which occurs as a result of extraordinary natural phenomena, and which affect the normal use of the road network, or the safety and security of the users. For emergency works, the contract limits the responsibility of the Contractor, establishing that the Employer will approve execution of services and separate remuneration based on specific amounts proposed by the Contractor for each case, on the basis of volume of works estimated at each time and on unit prices included in the Bid and in the Contract. A provisional sum is normally set aside for emergency works.

18. The Contractor should be entitled to implement an axle load control system, based on the legislation and in cooperation with local police authorities.

19. Bidders will present their financial offer for:

* the Maintenance Services in the form of the amount of the monthly lump-sum payment demanded by the Bidder according to the conditions of contract (this will be a monthly amount applicable throughout the duration of the contract);
* the Rehabilitation Works (if so required in the Bid Data Sheet), in the form of a lump-sum amount, while indicating the quantities of measurable outputs to be executed in order that the road achieves the performance standards specified in the bidding document. Payments will be made in accordance with the progress in the execution of those measured outputs;
* the Improvement Works (if so required and for the improvements indicated in the bidding document) in the form of unit prices for outputs of each type of improvement works; payments for improvements will be made in accordance with quoted unit prices for those outputs; and
* unit prices for Emergency Works in the form of a traditional bill of quantities. Payments will be made for each emergency on a case-by-case basis, in the amount of a lump-sum value estimated by the Contractor and approved by the Employer, on the basis of the estimated quantities and on the quoted unit process.

There should also be a price adjustment clause applicable to all prices and activities in order to compensate for increases in cost indices.

20. The agreed monthly payment for maintenance works and services will be made to the Contractor if he has complied, during the month for which the payment is to be made, with the agreed Service Levels on the road network under contract. Together with his monthly invoice, the Contractor will report the result of his own evaluation of compliance with the required Service Levels, based on his own monitoring system which is mandatory. His statement will then be verified by the Employer or his representative (supervision consultant) through inspections. If the Service Levels are not met, payments are reduced, based on a schedule given in the contract. Payments may even be suspended, and the contract cancelled, if the contractor fails during an extended period to achieve certain minimum thresholds values of Service Levels. The contract describes the formulas used to calculate payment reduction and potential contract suspensions.

**Preface**

This Standard Bidding Document (SBD) for Output and Performance Based Road Contracts (OPBRC) has been prepared for the use in contracts financed by the Inter-American Development Bank for Request for Bids (RFB)[[1]](#footnote-2) and it is based on the similar Standard Procurement Document (SPD) of The World Bank.

This SBD has been prepared under the Procurement Policy GN-2349-15, approved by the Board of Executive Directors of the Bank on 2nd of July 2019, effective 1st of January 2020. Procurement carried out under the framework of a loan contract applying the previous Procurement Policies (and where the Borrower has not subscribed the new Policies) should use the version of this DEL dated April 2019 available on the Bank's website. Policy GN-2349-15 allows the use of the methods of Best Final Offer (BAFO) in the evaluation of bids or Negotiations (in the presence of an Independent Probity Assurance Authority agreed wth the Bank) in the final award, if so agreed with the Bank and if it is established in the DDL. This document allows using the Best Final Offer method in the evaluation of Bids or the Negotiations with the Most Advantageous Bid in the final award.

This Standard Bidding Document for Procurement of Works and Services under **OPBRC** has been issued by the IDB to provide its clients with an alternative to the traditional methods of procuring road reconstruction, rehabilitation and maintenance. The SBD fits the specific nature of Performance-based Management and Maintenance of Roads (PMMR), but they are also suitable for the procurement of works and services under longer-term “Design-Build-Operate-Maintain (DBOM)” contracts for roads.

The contract herein included differs substantially from traditional contracts for civil works. The basic difference is that under the Output- and Performance-based Road Contract, most of the payments to be made to the Contractor are not based on quantities of works measured by unit prices for works inputs, but on measured “outputs” reflecting the target conditions of the roads under contract (in other words: “what the roads are supposed to look like”), expressed through **“Service Levels.”** These Service Levels are defined in the contract. Another major difference is that the Contractor is fully responsible for the design of the works, which are necessary to reach the required Service Levels, and the durability and performance of the roads over a longer period.

The present document is designed to allow for much flexibility in their use, according to the specific needs of the road network under contract (called “the Road” or “Roads” in the documents). An important focus of the contract is on **Management and Maintenance Services**, including physical works on the Roads under contract, which are needed to maintain the agreed Service Levels over time, but also all activities related to the management and evaluation of the road network under contract. The Contract also allows for the execution of (i) **Rehabilitation Works** to be carried out in order to bring the Roads up to pre-defined standards; (ii) **Improvement Works** aiming at adding new characteristics to the Roads in response to new traffic, safety or other considerations; and (iii) **Emergency Works** comprising of activities needed to reinstate the Roads after damage resulting from unforeseen natural phenomena with imponderable consequences.

It should be noted that the OPBRC is not designed for the Contractor to simply build a road and then move on to other things. It is meant to establish a form of a **longer-term Public-Private Partnership (PPP)** between the contractor and the Government, in which both parties have long-term commitments. The contractor’s focus will not simply be on road construction, but on the **Integral Management of the Road Asset** over a period, which should reflect the expected lifetime of the asset. In this sense, the “contractor” must be a firm or a business venture, which has the legal, technical, managerial and financial capacity to fulfill the contract in all its aspects. Further explanations on the nature and character of Output and Performance-Based Road Contracts are provided in the Foreword and the accompanying User’s Guide of the SBD.

The document offers two alternatives for Section III. “Evaluation Criteria and Qualification”. If the process is preceded by a prequalification, the version marked "after prequalification is used while the version marked "without prequalification " is excluded from the document.

This version of the SBD includes provisions regarding the Bank’s new Environmental and Social Policy Framework[[2]](#footnote-3). This SBD includes the successful Bidder’s Beneficial Ownership Disclosure Form. It also includes recommendations by OII and LEG.

To obtain further information on procurement under IDB-assisted projects or for question regarding the use of this SBD, contact:

Operations Financial Management and Procurement Services Office

Inter-American Development Bank

1300 New York Ave., N.W., Washington D.C. 20577 U.S.A.

procurement@iadb.org

**Standard Procurement Document**

**Table of Contents**

PART 1 – Bidding Procedures 2

Section I - Instructions to Bidders 3

Section II - Bid Data Sheet (BDS) 35

Section III - Evaluation and Qualification Criteria (Following Prequalification) 45

Section III - Evaluation and Qualification Criteria(Without Prequalification) 49

Section IV - Bidding Forms 65

Section V - Eligible Countries 121

PART 2 – Works and Services’ Requirements 125

Section VI - Specifications for Works and Services 127

PART 3 – Conditions of Contract and Contract Forms 135

Section VII - General Conditions 137

Section VIII - Particular Conditions of Contract 219

Section IX - Contract Forms 229

Annex Sample Specifications 245

PART 1 – Bidding Procedures

|  |
| --- |
| Section I - Instructions to Bidders |

Contents

A. General 5

1. Scope of Bid 5

2. Source of Funds 6

3. Prohibited Practices 6

4. Excluded Activities ………………………………………………………… 12

5. Eligible Bidders 12

6. Eligible Materials, Equipment, and Services 15

B. Contents of Bidding Document 15

7. Sections of Bidding Document 15

8. Clarification of Bidding Document, Site Visit, Pre-Bid Meeting 16

9. Amendment of Bidding Document 18

C. Preparation of Bids 18

10. Cost of Bidding 18

11. Language of Bid 18

12. Documents Comprising the Bid 18

13. Letter of Bid, and Schedules 19

14. Alternative Bids 19

15. Bid Prices and Discounts 20

16. Currencies of Bid and Payment 21

17. Documents Comprising the Technical Proposal 21

18. Documents Establishing the Qualifications of the Bidder 21

19. Period of Validity of Bids 21

20. Bid Security 22

21. Format and Signing of Bid 24

D. Submission and Opening of Bids 25

22. Sealing and Marking of Bids 25

23. Deadline for Submission of Bids 25

24. Late Bids 25

25. Withdrawal, Substitution, and Modification of Bids 26

26. Bid Opening 26

E. Evaluation and Comparison of Bids 27

27. Confidentiality 28

28. Clarification of Bids 28

29. Deviations, Reservations, and Omissions 28

30. Determination of Responsiveness 28

31. Nonmaterial Nonconformities 29

32. Correction of Arithmetical Errors 30

33. Conversion to Single Currency 30

34. Margin of Preference 30

35. Evaluation of Bids 30

36. Comparison of Bids 32

37. Abnormally Low Bids 32

38. Best Final Offer or Negotiations 33

39. Qualification of the Bidder 33

40. Employer’s Right to Accept Any Bid, and to Reject Any or All Bids 34

41. Standstill Period 34

42. Notification of Intention to Award 34

F. Award of Contract 35

43. Award Criteria 35

44. Notification of Award 36

45. Debriefing by the Employer 37

46. Signing of Contract 38

47. Performance Security 38

487. Procurement Related Complaint 39

|  |  |  |  |
| --- | --- | --- | --- |
| **Section I. - Instructions to Bidders** | | | |
| **A. General** | | | |
| Scope of Bid | | 1.1 In connection with the Request for Bids indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this bidding document for the procurement of Works and Services as listed below for the award of an **Output- and Performance-based Road Contract (OPBRC).**The name, identification, and number of lots (contracts) of this Bidding are specified in the BDS.The Works and Services under the OPBRC will coverthe Roads indicated **in the BDS** and will consist of:  (a) Maintenance Services or “Services” consisting of all interventions on the Roads which are to be carried out by the contractor in order to achieve and keep the Road performance standards defined by the Service Level included in Section VI, “Specifications for Works and Services” of this bidding document, and all activities related to the management and evaluation of the road network under contract;  (b) Rehabilitation Works, when requested **in the BDS** for the sections of the Road(s) indicated **in the BDS,** consisting of specific types of civil works described in the Specifications;  (c) Improvement Works, when requested **in the BDS,** consisting of a set of specific interventions indicated in the Specifications to add new characteristics to the Roads in response to existing or new traffic and safety or other considerations; and  (d) Works consisting of activities needed to reinstate the Roads and reconstruct their structure or their right of way which has been damaged as a result of natural phenomena with imponderable consequences, such as strong storms, flooding, and earthquakes. | |
|  | | 1.2 Throughout this bidding document:  the term “in writing” means communicated in written form (e.g. by mail, e-mail, and if specified in ITB 1.3, including distributed or received through electronic-procurement system used by the Employer, if applicable) with proof of receipt;  if the context so requires, “singular” means “plural’ and vice versa;  “Day” means calendar day, unless otherwise specified as a “Business Day.” A Business Day is any day that is a working day of the Borrower. It excludes the Borrower’s official public holidays; and  “ESHS” **“ESHS”** means environmental, social, health and safety (including labor, occupational and community health and safety, disaster and climate change, indigenous peoples, vulnerable groups, gender, sexual and gender-based violence (SGBV), stakeholder engagement).  **“SGBV”** refers to any act that is perpetrated against a person’s will and is based on gender norms and unequal power relationships. It encompasses threats of violence, coercion, and harassment. It can be physical, emotional, psychological, or sexual in nature, and can take the form of a denial of resources or access to them. It includes sexual exploitation, abuse and harassment. It can affect persons at any age across the lifespan, and disproportionately affects women, girls, and people of diverse sexual orientations and gender identities.  1.3 If specified **in the BDS**, the Employer intents to use the electronic-procurement system indicated **in the BDS** to manage the aspects of this procurement process specified **in the BDS[[3]](#footnote-4)**. | |
| Source of Funds | | 1. The Borrower (hereinafter called “Borrower”) indicated in the BDS has applied for or received financing (hereinafter called “funds”) from the Inter-American Development Bank (hereinafter called "IDB" or “the Bank”) in the amount indicated **in the BDS** toward the cost of the project named in the BDS. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this bidding document is issued. 2. Payment by the Bank will be made only at the request of the Borrower and upon approval by the Bank, and will be subject, in all respects, to the terms and conditions of the Loan Contract. 3. The Loan Contract prohibits a withdrawal from the loan account for the purpose of any payment to persons or entities, or for any import of goods, equipment, plant, or materials, if such payment or import is prohibited by a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations. 4. No party other than the Borrower shall derive any rights from the Loan Contract or have any claim to the proceeds of the Loan. | |
| Prohibited Practices | | 1. The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, including members of its personnel, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, *inter alia*, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and representatives or agents, irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank[[4]](#footnote-5) all suspected acts of Prohibited Practices of which they have knowledge or become aware both, during the bidding process and throughout the negotiation or execution of a contract. Prohibited Practices are: (i) corrupt practices; (ii) fraudulent practices; (iii) coercive practices; (iv) collusive practices; (v) obstructive practices; and (vi) misappropriation of funds. The Bank has established mechanisms to report allegations of Prohibited Practices. Any allegation shall be submitted to the Bank’s Office of Institutional Integrity (OII) for the appropriate investigation. The Bank has adopted procedures to sanction those who have incurred in Prohibited Practices. The Bank also entered into an agreement with other International Financial Institutions (IFIs) to mutually recognize debarment decisions. | |
|  | | * + 1. For the purposes of this provision, the definitions of Prohibited Practices are as follows:   (i) “*corrupt practice*” is the offering, giving, receiving or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party;  (ii) “*fraudulent practice*” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation;  (iii) “*collusive practice*” is an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party;  (iv) “*coercive practice*” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;  (v) “*obstructive practice*” is  (i) destroying, falsifying, altering or concealing of evidence material to an IDB Group investigation, or making false statements to investigators with the intent to impede an IDB Group investigation;  (ii) threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to an IDB Group investigation or from pursuing the investigation, or  (iii) acts intended to impede the exercise of the IDB Group’s contractual rights of audit or inspection provided for under ITB 3.1(f) below or access to information; and  (vi) “*misappropriation*” is the use of IDB Group financing or resources for an improper or unauthorized purpose, committed either intentionally or through reckless disregard. | |
|  | | * + 1. If, the Bank determines that at any stage of the procurement or implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, *inter alia*, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires, (including their respective officers, employees and representatives or agents irrespective of whether the attribution is express or implied) engaged in a Prohibited Practice during the award or implementation of the contract, the Bank may:   (i) not finance any proposal to award a contract for works, goods or services, and consulting services;  (ii) suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has engaged in a Prohibited Practice;  (iii) declare Misprocurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, *inter alia*, providing adequate notice to the Bank upon learning of the Prohibited Practice) within a time period which the Bank considers reasonable;  (iv) issue the firm, entity or individual a reprimand in the form of a formal letter of censure for its behavior;  (v) declare that a firm, entity, or individual is ineligible, either permanently or for a stated period of time, to participate and/or be awarded additional contracts financed with IDB Group resources;  (vi) impose other sanctions that it deems to be appropriate, among others, the restitution of funds and of fines equivalent to the reimbursement for costs associated with investigations and proceedings contemplated in the Sanctions Procedures. Such other sanctions may be imposed in addition to or in lieu of the sanctions referred above (the “above-mentioned” sanctions are reprimand and debarment/ineligibility);  (vii) extend the sanctions imposed on any individual, entity or firm that, directly or indirectly, owns or controls a sanctioned entity, is owned or controlled by a sanctioned entity or is the object of common ownership or control with a sanctioned entity, as well as to officials, employees, affiliates or representatives or agents of a sanctioned entity who also own a sanctioned entity and / or exercise control over a sanctioned entity, even if it has not been concluded that those parties directly incurred in a Prohibited Practice; and/or  (viii) refer the matter to appropriate law enforcement authorities. | |
|  | | * + 1. The provisions of ITB 3.1 (b) (i) and (ii) shall also be applicable when such parties have been temporarily suspended from eligibility to be awarded additional contracts pending a final outcome of a sanction proceeding, or otherwise. | |
|  | | * + 1. The imposition of any action to be taken by the Bank pursuant to the provisions referred to above may be made public.     2. Pursuant to the Agreement for Mutual Enforcement of Debarment Decisions entered into with other IFIs, any firm, entity or individual bidding for or participating in a Bank-financed activity or acting as bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, concessionaires, personnel of the Borrower (including grant Beneficiaries), Executing Agencies or Contracting Agencies, (including their respective officers, employees, representatives and agents, irrespective of whether the attribution is expressed or implied) may be subject to a sanction. For purposes of this paragraph the term “sanction” shall mean any debarment, conditions on future contracting or any publicly-disclosed action taken in response to a violation of an IFI’s applicable framework for addressing allegations of Prohibited Practices. | |
|  | | * + 1. The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the submission of bids and contract performance as well as to have them audited by personnel appointed by the Bank. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its investigation. The Bank also requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires: (i) maintain all documents and records related to the Bank-financed activities for seven (7) years after completion of the work contemplated in the relevant contract; (ii) deliver any document necessary for the investigation of allegations of Prohibited Practices; and (iii) ensure that employees, representatives or agents of the applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers or concessionaires who have knowledge that the Bank financed the activities to respond to questions from Bank personnel or any properly designated investigator, agent, auditor or consultant relating to the investigation. If the applicant, bidder, supplier and its representative or agent, contractor, consultant, personnel, sub-contractor, sub-consultant, service provider or concessionaire fails to cooperate and/or comply with the Bank’s request, or otherwise obstructs the investigation, the Bank, discretionally, may take appropriate action against the applicant bidder, supplier and its agent or representative, contractor, consultant, personnel, sub-contractor, service provider or concessionaire. | |
|  | | * + 1. If the Borrower procures goods or services, works or consulting services directly from a specialized agency, all provisions regarding Prohibited Practices and to the correspondent sanctions shall apply in their entirety to applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, and concessionaires, (including their respective officers, employees, and representatives or agents, irrespective of whether the agency is express or implied), or to any other entities that signed contracts with such specialized agency to supply such goods, works, or non-consulting services in connection with the Bank-financed activities. The Bank will retain the right to require the Borrower to invoke remedies such as contract suspension or termination. Specialized agencies shall consult the Bank’s list of suspended or debarred firms and individuals. In the event a specialized agency signs a contract or purchase order with a firm or an individual suspended or debarred by the Bank, the Bank will not finance the related expenditures and will apply other remedies as appropriate. | |
|  | | 3.2 By submitting bids, bidders represent and warrant: | |
|  | | * + 1. that they have read and understood the Bank’s definition of Prohibited Practices and the applicable sanctions pursuant to the Sanctions Procedures; | |
|  | | * + 1. that they have not engaged in any Prohibited Practice as set forth herein during the selection, negotiation, adjudication or execution of this contract; | |
|  | | * + 1. that they have not misrepresented or concealed any material facts during the procurement or contract negotiation processes or during the performance of the contract; | |
|  | | * + 1. that neither they nor their representatives or agents, sub-contractors, sub-consultants, directors, key personnel or principal shareholders have been declared ineligible to be awarded a contract by the Bank; | |
|  | | * + 1. that all commissions, representative or agents’ fees, facilitating payments or revenue-sharing agreements related to the Bank-financed activities have been disclosed; and     2. that they acknowledge that the breach of any of these representations may constitute a basis for the adoption by the Bank of one or more of the measures set forth in ITB 3.1 (b). | |
| Excluded Activities  Eligible Bidders | | 1. The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, inter alia, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires will not knowingly engage, directly or indirectly through Financial Intermediaries, in the production, trade, or use of the products and substances or the activities listed in the Annex 1 of the IDB Environmental and Social Policy Framework.[[5]](#footnote-6) Additional exclusions may apply. 2. If, the Bank determines that at any stage of the implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, inter alia, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires used IDB resources to engage in an Excluded Activity during the implementation of the contract, the Bank may: 3. Suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has used IDB resources to engage in an Excluded Activity. 4. Declare Mis-procurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, inter alia, providing adequate notice to the Bank upon learning of the Excluded Activity) within a time period which the Bank considers reasonable. 5. Refer the matter to appropriate law enforcement authorities. 6. The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the contract performance as well as to have them audited by personnel appointed by the Bank. 7. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its monitoring and supervision   5.1 A Bidder, all personnel and all parties constituting the Bidder, shall be nationals from member countries of the Bank. Bidders from other countries shall be disqualified from participating in contracts intended to be financed in whole or in part from Bank loans. Section IV, “Eligible Countries” of this document establishes the Bank’s member countries, as well as the criteria to determine the nationality of the Bidders and the country of origin of goods and services. The Bidders with the nationality of a Bank’s member country and the goods to be supplied under the Contract are not eligible:   * 1. if as a matter of law or official regulation, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the supply of goods and works required; or   2. by an act of compliance with a decision of the United nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any imports of goods from that country or any payments to persons or entities in that country.   5.2 A Bidder, included in all cases, the directors, key personnel, principal shareholders, proposed personnel and agents should not have conflicts of interest unless the conflict has been resolved in a manner acceptable to the Bank. All bidders found to have conflict of interest shall be disqualified. Bidders may be considered to have a conflict of interest with one or more parties in this bidding process, if they:   1. directly or indirectly controls[[6]](#footnote-7) another Bidder, is controlled directly or indirectly by another Bidder, or is controlled together with another Bidder by a natural or legal entity in common; or 2. receives or has received any direct or indirect subsidy from another Bidder; or 3. has the same legal representative as another Bidder; for the purpose of this bidding process; or | |
|  | | 1. has a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the Bid of another Bidder, or influence the decisions of the Employer regarding this Bidding process; or 2. any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the works that are the subject of the Bid; or | |
|  | | 1. or any of its affiliates has been hired (or is proposed to be hired) by the Employer or Borrower as Project Manager for the Contract implementation; or 2. would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS in reference to ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; or 3. has a close[[7]](#footnote-8) family or financial relationship or past or future employment with a professional staff of the Borrower (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the bidding document or specifications of the Contract, and/or the Bid evaluation process of such Contract; or (ii) would be involved in the implementation or supervision of such contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to the Bank throughout the bidding process and execution of the Contract. | |
|  | | 5.3 A Bidder is not eligible whose subcontractors, suppliers, consultants, manufacturers or service providers that intervene in any part of the Contract (including, in all cases, the respective directors, key personnel, principal shareholders, proposed personnel and agents) are subject to a temporary suspension or disqualification imposed by the IDB, or a disqualification imposed by the IDB pursuant to an agreement for the recognition of disqualification decisions signed by the IDB and other development banks. The list of such ineligible firms and individuals is indicated **in the BDS.** | |
|  | | 5.4 A firm that is a Bidder (either individually or as a Joint Venture, Consortium or Association (“JVCA”) member) shall not participate as a Bidder or as JVCA member in more than one Bid except for permitted alternative Bids. Such participation shall result in the disqualification of all Bids in which the firm is involved. However, this does not limit the participation of a Bidder as subcontractor in another Bid or of a firm as a subcontractor in more than one Bid. Unless specified **in the BDS**, there is no limit on the number of members in a JVCA.  5.5 Government-owned entities in the Borrower’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under the principles of commercial law, and (iii) are not dependent agencies of the Employer or the Borrower. | |
|  | | 5.6 Bidder shall not be under suspension from Bidding by the Employer as the result of the operation of a Bid–Securing Declaration. | |
|  | | 5.7 A Bidder shall provide such documentary evidence of eligibility satisfactory to the Employer, as the Employer shall reasonably request. | |
|  | | 5.8 This Bidding is open only to prequalified Bidders if so specified **in the BDS**. | |
| Eligible Materials, Equipment, and Services | | 6.1 The materials, equipment and services to be supplied under the Contract and financed by the Bank may have their origin in any country subject to the restrictions specified in Section V, “Eligible Countries,” and all expenditures under the Contract will be limited to such materials, equipment, and services. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment and services. | |
|  | | 6.2 For purposes of ITB 5.1 above, “origin” means the place where the materials and equipment are mined, grown, produced or manufactured, and from which the services are provided. Materials and equipment are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that is substantially different in its basic characteristics or in purpose or utility from its components. | |
| **B. Contents of Bidding Document** | | | |
| Sections of Bidding Document | | 7.1 The bidding document consists of Parts 1, 2, and 3, which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 9.  **PART 1 Bidding Procedures**   * Section I. Instructions to Bidders (ITB) * Section II. Bid Data Sheet (BDS) * Section III. Evaluation and Qualification Criteria * Section IV. Bidding Forms * Section V. Eligible Countries   **PART 2 Works and Services’ Requirements**   * Section VI - Specifications for Works and Services   **PART 3 Conditions of Contract and Contract Forms**   * Section VII. General Conditions * Section VIII. Particular Conditions * Section IX. Contract Forms | |
|  | | 7.2 The Specific Procurement Notice for this Request for Bids (RFB) or the notice to the prequalified Bidders, as the case may be, issued by the Employer is not part of the bidding document. | |
|  | | 7.3 Unless obtained directly from the Employer, the Employer is not responsible for the completeness of the bidding document, responses to requests for clarification, the minutes of the pre-Bid meeting (if any), or Addenda to the bidding document in accordance with ITB 9. In case of any contradiction, documents obtained directly from the Employer shall prevail. | |
|  | | 7.4 The Bidder is expected to examine all instructions, forms, terms, and specifications in the bidding document and to furnish with its Bid all information and documentation as is required by the bidding document. Failure by the Bidder to submit all the information or documentation required in the bidding document may result in the rejection of its bid. | |
| Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | | 8.1 A Bidder requiring any clarification of the bidding document shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise its enquiries during the pre-Bid meeting if provided for in accordance with ITB 8.4. The Employer will respond in writing to any request for clarification, provided that such request is received no later than the period specified **in the BDS** prior to the deadline for submission of Bids. The Employer shall forward copies of its response to all Bidders who have acquired the bidding document in accordance with ITB 7.3, including a description of the inquiry but without identifying its source. If so specified **in the BDS**, the Employer shall also promptly publish its response at the web page identified **in the BDS.**  Should the Employer deem it necessary to amend the bidding document as a result of a request for clarification, it shall do so following the procedure under ITB 9 and ITB 23.2. | |
|  | | 8.2 The Bidder is advised to visit and examine the Site of the Roads and its surroundings and obtain for itself and on its own responsibility all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site of the Roads shall be at the Bidder’s own expense. | |
|  | | 8.3 The Bidder and any of its personnel or agents will be granted permission by the Employer to visit the Roads and surrounding lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. | |
|  | | 8.4 If so provided in the BDS, the Bidder’s designated representative is required to attend a pre-Bid meeting and/or a Site of the Roads’ visit. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. | |
|  | | 8.5 The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer not later than one week before the meeting. | |
|  | | 8.6 Minutes of the pre-Bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the bidding document in accordance with ITB 7.3. Any modification to the bidding document that may become necessary as a result of the pre-Bid meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to ITB 9 and not through the minutes of the pre-Bid meeting. Nonattendance at the pre-Bid meeting will not be a cause for disqualification of a Bidder. | |
| Amendment of Bidding Document | | 9.1 At any time prior to the deadline for submission of Bids, the Employer may amend the bidding document by issuing addenda. | |
|  | | 9.2 Any addendum issued shall be part of the bidding document and shall be communicated in writing to all who have obtained the bidding document from the Employerin accordance with ITB 7.3. The Employer shall also promptly publish the addendum on the Employer’s web page in accordance with ITB 8.1. | |
|  | | 9.3 To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Employer may, at its discretion, extend the deadline for the submission of Bids, pursuant to ITB 23.2. | |
| **C. Preparation of Bids** | | | |
| Cost of Bidding | | 10.1 The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall not be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. | |
| Language of Bid | | 11.1 The Bid, as well as all correspondence and documents relating to the Bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the languag**e** specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. | |
| Documents Comprising the Bid | | 12.1 The Bid shall comprise the following:   1. **Letter of Bid** prepared in accordance with ITB 13; 2. **Schedules**, including priced Bills of Quantities completed in accordance with ITB 13 and ITB 15; 3. **Bid Security or Bid-Securing Declaration**, in accordance with ITB 20.1; 4. **Alternative Bid**, if permissible, in accordance with ITB 14; 5. **Authorization**: written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 21.3; 6. **Qualifications**: documentary evidence in accordance with ITB 18 establishing the Bidder’s qualifications, or continued qualified status, as the case may be, to perform the Contract if its Bid is accepted; 7. **Conformity:** a technical proposal in accordance with ITB 17; and 8. any other document required **in the BDS**.   12.2 In addition to the requirements under ITB 12.1, Bids submitted by a Joint Venture, Consortium or Association (“JVCA”) shall include a copy of the Joint Venture Agreement entered into by all members. Alternatively, a Letter of Intent to execute a Joint Venture Agreement in the event of a successful Bid shall be signed by all members and submitted with the Bid, together with a copy of the proposed agreement.  12.3 The Bidder shall furnish in the Letter of Bid information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Bid. | |
| Letter of Bid, and Schedules | | 13.1 The Letter of Bid and Schedules, including the Bills of Quantities*,* shall be prepared using the relevant form*s* furnished in Section IV, “Bidding Forms.” The forms must be completed without any alterations to the text, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested. | |
| Alternative Bids | | 14.1 Unless otherwise indicated in the BDS, alternative Bids shall not be considered. | |
|  | | 14.2 When alternative times for reaching the required Service Levels or for the completion of Rehabilitation or Improvement Works are explicitly invited, a statement to that effect will be included in the BDS, and, in Section III, “Evaluation and Qualification Criteria” shall describe the method of evaluating different times for completion. | |
|  | | 14.3 Except as provided under ITB 14.4 below, Bidders wishing to offer technical alternatives to the requirements of the bidding document must first price the Employer’s design as described in the bidding document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. Only the technical alternatives, if any, of the Bidder with the lowest evaluated bid conforming to the basic technical requirements shall be considered by the Employer. | |
|  | | 14.4 When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the Rehabilitation and/or Improvement Works, and such parts will beidentified in the BDS, described in Section VI, “Specifications for Works and Services,” and Section III, “Evaluation and Qualification Criteria” shall describe the method for their evaluating. | |
| Bid Prices and Discounts | | 15.1 The prices and discounts quoted by the Bidder in the Letter of Bid and in the Bills of Quantities shall conform to the requirements specified below. | |
|  | | 15.2 The Bidder shall fill in rates and prices for all items of the Works and Services described in the Bills of Quantities. Items against which no rate or price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bills of Quantities and will not be paid for separately by the Employer. An item not listed in the priced Bill of Quantities shall be assumed to be not included in the Bid, and provided that the Bid is determined substantially responsive notwithstanding this omission, the average price of the item quoted by substantially responsive Bidders will be added to the Bid price and the equivalent total cost of the Bid so determined will be used for price comparison. | |
|  | | 15.3 The price to be quoted in the Letter of Bid, in accordance with ITB 13.1, shall be the total price of the Bid, excluding any discounts offered. | |
|  | | 15.4 The Bidder shall quote any discounts and the methodology for their application in the Letter of Bid, in accordance with ITB 13.1. | |
|  | | 15.5 Unless otherwise provided in the BDS and the Contract, the rates and prices quoted by the Bidder are subject to adjustment during the performance of the Contract in accordance with the provisions of the Conditions of Contract. In such a case, the Bidder shall furnish the indices and weightings for the price adjustment formulae in the Schedule of Adjustment Data and the Employer may require the Bidder to justify its proposed indices and weightings. | |
|  | | 15.6 If so indicated in ITB 1.1, Bids are being invited for individual lots (contracts)or for any combination of lots (packages). Bidders wishing to offer any price reduction for the award of more than one Contract shall specify in their bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package. Discounts shall be submitted in accordance with ITB 15.4, provided the Bids for all lots (contracts) are submitted and opened at the same time. | |
|  | | 15.7 All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of Bids, shall be included in the rates and prices and the total Bid Price submitted by the Bidder. | |
| Currencies of Bid and Payment | | 16.1 The currency(ies) of the Bid and the currency(ies) of payments shall be the same and shall be as specified in the BDS.  17.2 Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the unit rates and prices and shown in the Summary of Payment Currency Schedule, in which case a detailed breakdown of the foreign currency requirements shall be provided by Bidders. | |
| Documents Comprising the Technical Proposal | | 17.1 The Bidder shall furnish a technical proposal including a statement of work methods, equipment, personnel, schedule, an Environmental and Social Management Plan Strategies and Implementation Plans (MSIP) (if required), and any other information as stipulated in Section IV, Bidding Forms, in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work and services’ requirements and the completion time. | |
| Documents Establishing the Qualifications of the Bidder | | 18.1 To establish Bidder’s eligibility in accordance with ITB 5, Bidders shall complete the Letter of Bid, included in Section IV, “Bidding Forms.”  18.2 In accordance with Section III, “Evaluation and Qualification Criteria,” to establish its qualifications to perform the Contract the Bidder shall provide the information requested in the corresponding information sheets included in Section IV, “Bidding Forms.” | |
| Period of Validity of Bids | | 19.1 Bids shall remain valid for the period specified in the BDS. The Bid Validity period starts from the date fixed for the Bid submission deadline (as prescribed by the Employer in accordance with ITB 23). A Bid valid for a shorter period shall be rejected by the Employer as nonresponsive. | |
|  | | 19.2 In exceptional circumstances, prior to the expiration of the Bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a Bid Security is requested in accordance with ITB 20, it shall also be extended for twenty-eight (28) days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its Bid Security. A Bidder granting the request shall not be required or permitted to modify its Bid, except as provided in ITB 19.3. | |
|  | | 19.3 If the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial Bid validity period, the Contract price shall be determined as follows:   1. in the case of fixed price contracts, the Contract price shall be the Bid price adjusted by the factor specified **in the BDS**; 2. in the case of adjustable price contracts, no adjustment shall be made; or 3. in any case, bid evaluation shall be based on the Bid price without taking into consideration the applicable correction from those indicated above. | |
| Bid Security | | 20.1 The Bidder shall furnish as part of its Bid, either a Bid-Securing Declaration or a Bid Security as specified **in the BDS**, in original form and, in the case of a Bid security, in the amount and currency specified in the BDS. | |
|  | | 20.2 A Bid-Securing Declaration shall use the form included in Section IV, “Bidding Forms.”  20.3 If a Bid Security is required pursuant to ITB 20.1, the Bid Security shall be a demand guarantee at the Bidder’s option, in any of the following forms:   * + 1. an unconditional bank guarantee issued by a bank or non-bank financial institution (such as an insurance, bonding or surety company);     2. an irrevocable letter of credit;     3. a cashier’s or certified check; or     4. another security specified **in the BDS**,   from a reputable source from an eligible country. If the unconditional guarantee is issued by a non-bank financial institution located outside the Employer’s Country, the issuing non-bank financial institution shall have a correspondent financial institution located in the Employer’s Country to make it enforceable unless the Employer has agreed in writing, prior to Bid submission, that a correspondent financial institution is not required. In the case of a bank guarantee, the Bid Security shall be submitted either using the Bid Security Form included in Section IV, “Bidding Forms,” or in another substantially similar format approved by the Employer prior to Bid submission. The Bid Security shall be valid for twenty-eight (28) days beyond the original validity period of the Bid, or beyond any period of extension if requested under ITB 19.2. | |
|  | | 20.4 If a Bid Security or Bid-Securing Declaration is specified pursuant to ITB 20.1, any Bid not accompanied by a substantially responsive Bid Security or Bid-Securing Declaration shall be rejected by the Employer as non-responsive. | |
|  | | 20.5 If a Bid Security is specified pursuant to ITB 19.1, the Bid Security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s signing the Contract and furnishing the Performance Security and if required **in the BDS**, the Environmental, Social, Health and Safety (ESHS) Performance Security pursuant to ITB 44. | |
|  | | 20.6 The Bid Security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required Performance Security and if required **in the BDS**, the Environmental, Social, Health and Safety (ESHS) Performance Security. | |
|  | | 20.7 The Bid Security may be forfeited, or the Bid-Securing Declaration executed:   * + 1. if a Bidder withdraws its Bid during the period of Bid validity specified by the Bidder on the Letter of Bid or any extension thereto provided by the Bidder; or     2. if the successful Bidder fails to:  (i) sign the Contract in accordance with ITB 43; or(ii) furnish a performance security and if required in the BDS, the Environmental, Social, Health and Safety (ESHS) Performance Security in accordance with ITB 44. | |
|  | | 20.8 The Bid Security or the Bid Securing Declaration of a JVCA shall be in the name of the JVCA that submits the Bid. If the JVCA has not been legally constituted at the time of Bidding, the Bid Security or the Bid-Securing Declaration shall be in the names of all future members as named in the letter of intent referred to in ITB 12.2*.*  20.9 If a Bid Security or a Bid-securing Declaration is not required in the BDS, pursuant to ITB 20.1**,** and   * + 1. if a Bidder withdraws its Bid during the period of Bid validity specified by the Bidder on the Letter of Bid, or     2. if the successful Bidder fails to:  (i) sign the Contract in accordance with ITB 43; or(ii) furnish a performance security and if required in the BDS, the Environmental, Social, Health and Safety (ESHS) Performance Security in accordance with ITB 44, the Borrower may, if provided for in the BDS, declare the Bidder ineligible to be awarded a contract by the Borrower for a period of time as stated in the BDS. | |
| Format and Signing of Bid | | 21.1 The Bidder shall prepare one original of the documents comprising the Bid as described in ITB 12 and clearly mark it “ORIGINAL.” Alternative Bids, if permitted in accordance with ITB 14, shall be clearly marked “ALTERNATIVE.” In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS and clearly mark them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. | |
|  | | 21.2 Bidders shall mark as “CONFIDENTIAL” all information in their Bids which is confidential to their business. This may include proprietary information, trade secrets, or commercial or financially sensitive information. | |
|  | | 21.3 The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid where entries or amendments have been made shall be signed or initialed by the person signing the Bid. | |
|  | | 21.4 In case the Bidder is a JVCA, the Bid shall be signed by an authorized representative of the JVCA on behalf of the JVCA, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives. | |
|  | | 21.5 Any inter-lineation, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. | |
| **D. Submission and Opening of Bids** | | | |
| Sealing and Marking of Bids | | 22.1 The Bidder shall deliver the Bid in a single, sealed envelope (one-envelope Bidding process). Within the single envelope the Bidder shall place the following separate, sealed envelopes: | |
|  | | 1. in an envelope marked “ORIGINAL”, all documents comprising the Bid, as described in ITB 12; and 2. in an envelope marked “COPIES”, all required copies of the Bid; and 3. if alternative Bids are permitted in accordance with ITB 14, and if relevant: 4. in an envelope marked “ORIGINAL –ALTERNATIVE BID”, the alternative Bid; and 5. in the envelope marked “COPIES - ALTERNATIVE BID”, all required copies of the alternative Bid. | |
|  | | 22.2 If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the Bid. | |
| Deadline for Submission of Bids | | 23.1 Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. When so specified in the BDS, Bidders shall have the option of submitting their Bids electronically. Bidders submitting Bids electronically shall follow the electronic Bid submission procedures specified in the BDS. | |
|  | | 23.2 The Employer may, at its discretion, extend the deadline for the submission of Bids by amending the bidding document in accordance with ITB 9, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. | |
| Late Bids | | 24.1 The Employer shall not consider any Bid that arrives after the deadline for submission of Bids, in accordance with ITB 23. Any Bid received by the Employer after the deadline for submission of Bids shall be declared late, rejected, and returned unopened to the Bidder. | |
| Withdrawal, Substitution, and Modification of Bids | | 25.1 A Bidder may withdraw, substitute, or modify its Bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 21.3, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the Bid must accompany the respective written notice. All notices must be:   1. prepared and submitted in accordance with ITB 20 and ITB 22 (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” “Substitution,” “Modification;” and 2. received by the Employer prior to the deadline prescribed for submission of Bids, in accordance with ITB 23. | |
|  | | 25.2 Bids requested to be withdrawn in accordance with ITB 25.1 shall be returned unopened to the Bidders. | |
|  | | 25.3 No Bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of Bids and the expiration of the period of Bid validity specified by the Bidder on the Letter of Bid Form or any extension thereof. | |
| Bid Opening | | 26.1 Except in the cases specified in ITB 24 and ITB 25.2, the Employer shall publicly open and read out in accordance with this ITB all Bids received by the deadline, at the date, time and place specified in the BDS, in the presence of Bidders’ designated representatives and anyone who chooses to attend. Any specific electronic Bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1, shall be as specified **in the BDS**. | |
|  | | 26.2 First, envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding Bid shall **not be** opened but **returned** to the Bidder. No Bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at Bid opening. | |
|  | | 26.3 Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding Bid being substituted, and the substituted Bid shall not be opened, but returned to the Bidder. No Bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at Bid opening. | |
|  | | 26.4 Next, envelopes marked “Modification” shall be opened and read out with the corresponding Bid. No Bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at Bid opening. | |
|  | | 26.5 Next, all remaining envelopes shall be opened one at a time, reading out: the name of the Bidder and whether there is a modification; the total Bid Price, per lot (contract) if applicable, including any discounts and alternative Bids; the presence or absence of a Bid Security or Bid-securing Declaration, if required; and any other details as the Employer may consider appropriate. | |
|  | | 26.6 Only Bids, alternative Bids and discounts that are opened and read out at Bid opening shall be considered further. The Letter of Bid andtheBill of Quantitiesare to be initialed by representatives of the Employer attending Bid opening in the manner specified **in the BDS**. | |
|  | | 26.7 The Employer shall neither discuss the merits of any Bid nor reject any Bid (except for late Bids, in accordance with ITB 24.1). | |
|  | | 26.8 The Employer shall prepare a record of the Bid opening that shall include, as a minimum:   1. the name of the Bidder and whether there is a withdrawal, substitution, or modification; 2. the Bid Price, per lot (contract) if applicable, including any discounts; 3. any alternative Bids; 4. the presence or absence of a Bid Security or Bid-securing Declaration, if one was required. | |
|  | | 26.9 The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders. | |
| **E. Evaluation and Comparison of Bids** | | | |
| Confidentiality | | 27.1 Information relating to the evaluation of Bids and recommendation of contract award shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on the Intention to Award of the Contract is transmitted to all Bidders in accordance with ITB 42. | |
|  | | 27.2 Any effort by a Bidder to influence the Employer in the evaluation of the Bids or Contract award decisions may result in the rejection of its Bid. | |
|  | | 27.3 Notwithstanding ITB 27.2, from the time of Bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the Bidding process, it may do so in writing. | |
| Clarification of Bids | | 28.1 To assist in the examination, evaluation, and comparison of the Bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the prices or substance of the Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Bids, in accordance with ITB 32. | |
|  | | 28.2 If a Bidder does not provide clarifications of its Bid by the date and time set in the Contracting Agency’s request for clarification, its Bid may be rejected. | |
| Deviations, Reservations, and Omissions | | 29.1 During the evaluation of Bids, the following definitions apply:   1. “*Deviation*” is a departure from the requirements specified in the bidding document; 2. “*Reservation*” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the bidding document; and 3. “*Omission*” is the failure to submit part or all of the information or documentation required in the bidding document. | |
| Determination of Responsiveness | | 30.1 The Employer’s determination of a Bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 12. | |
|  | | 30.2 A substantially responsive Bid is one that meets the requirements of the bidding document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that:  (a) if accepted, would: (i) affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or(ii) limit in any substantial way, inconsistent with the bidding document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or (b) if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. | |
|  | | 30.3 The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 17, Technical Proposal, in particular, to confirm that all requirements of Section VI, “Specifications for Works and Services” have been met without any material deviation, reservation or omission. | |
|  | | 30.4 If a Bid is not substantially responsive to the requirements of the bidding document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. | |
| Nonmaterial Nonconformities | | 31.1 Provided that a Bid is substantially responsive, the Employer may waive any nonconformities in the Bid*.* | |
|  | | 31.2 Provided that a Bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. | |
|  | | 31.3 Provided that a Bid is substantially responsive, the Employer shall rectify nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or nonconforming item or component in the manner specified **in the BDS.** | |
| Correction of Arithmetical Errors | | 32.1 Provided that the Bid is substantially responsive, the Employer shall correct arithmetical errors in the lump-sums and parts of the Bid with unit prices and quantities on the following basis:  (a) if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of theEmployer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected;  (b) if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail, and the total shall be corrected; and  (c) if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. | |
|  | | 31.2 Bidders shall be requested to accept correction of arithmetical errors. Failure to accept the correction in accordance with ITB 32.1, shall result in the rejection of the Bid. | |
| Conversion to Single Currency | | 33.1 For evaluation and comparison purposes, the currency(ies) of the Bid shall be converted into a single currency as specified in the BDS**.** | |
| Margin of Preference | | 34.1 A margin of preference for domestic Bidders shall not apply. | |
| Evaluation of Bids | | 35.1 The Employer shall use the criteria and methodologies listed in this ITB and Section III, “Evaluation and Qualification Criteria.” No other evaluation criteria or methodologies shall be permitted. By applying the criteria and methodologies the Employer shall determine the Most Advantageous Bid in accordance with ITB 41.  35.2 To evaluate a Bid, the Employer shall consider the following:  (a) the Bid price, excluding Provisional Sums and the provision, if any, for contingencies in the Summary Bill of Quantities;  (b) price adjustment for correction of arithmetic errors in accordance with ITB 32.1;  (c) price adjustment due to discounts offered in accordance with ITB 15.4;  (d) converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 33;  (e) price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 31.3;  (f) the Best and Final Offer in the evaluation of bids if specified in BDS in reference to ITB 38.; and  (g) the additional evaluation factors specified **in the BDS** and Section III, “Evaluation and Qualification Criteria.” | |
|  | | 35.3 The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. | |
|  | | 35.4 If this bidding document allows Bidders to quote separate prices for different lots (contracts), and the award to a single Bidder of multiple lots (contracts), the methodology to determine the lowest evaluated cost of the lot (contract) combinations, including any discounts offered in the Letter of Bid, is specified in Section III, “Evaluation and Qualification Criteria.” | |
|  | | 35.5 The price of the Rehabilitation and Improvement Works included in each Bid shall not be higher than the threshold indicated **in the BDS**. If the Bidder estimates that its costs for the Rehabilitation and Improvement Works are higher than the threshold indicated **in the BDS**, it shall include the portion above the threshold in its price for the Maintenance Services. If the Bid price in the Most Advantageous Bid is above the threshold indicated **in the BDS** for the Rehabilitation and Improvement Works, the Employer may reject the Bid. | |
| Comparison of Bids | | 36.1 The Employer shall compare the evaluated costs of all substantially responsive Bids in accordance with ITB 35.2 to determine the Bid that has the lowest evaluated cost.  36.2 After application of the criteria established in ITB 35.1 to ITB 34.5, the Evaluated Bid Price for comparison of Bids will be:   1. the lump-sum price offered by the Bidder for the Maintenance Services; plus 2. the lump-sum price offered by the Bidder for the Rehabilitation Works, if the bidding document requires prices for this type of works; plus 3. the total price of the priced Bill of Quantities for the Improvement Works, if the bidding document requires prices for this type of works; plus   (d) the total price of the priced Bill of Quantities for the Emergency Works. | |
| Abnormally Low Bids | | 37.1 An Abnormally Low Bid is one where the Bid price, in combination with other constituent elements of the Bid, appears unreasonably low to the extent that the Bid price raises material concerns as to the capability of the Bidder to perform the Contract for the offered Bid price. | |
|  | | 37.2 In the event of identification of a potentially Abnormally Low Bid, the Employer shall seek written clarifications from the Bidder, including detailed price analyses of its Bid price in relation to the subject matter of the contract, scope, proposed methodology, schedule, allocation of risks and responsibilities and any other requirements of the bidding document. | |
|  | | 37.3 After evaluation of the price analyses, in the event that the Employer determines that the Bidder has failed to demonstrate its capability to perform the Contract for the offered Bid Price, the Employer shall reject the Bid. | |
| Best Final Offer or Negotiations | | 38.1 If so specified **in the BDS** the Employer will use the Best and Final Offer method, the Bidders who submitted bids substantially responsive to the requirements will be invited to present their Best and Final Offer in accordance with ITB 38.3 to ITB 38.6 reducing prices, clarifying or modifying the bid or providing additional information, as appropriate.  38.2 If so specified **in the BDS** the Employer will use Negotiations after evaluation of bids and before final award of Contract, the Bidder who submitted the Most Advantageous Bid will be invited to negotiations in accordance with ITB 43.2 and following instructions.  38.3 Bidders are not required to submit a Best and Final Offer. There shall be no Negotiations after Best and Final Offer.  38.4 To observe and report on the application of the Best and Final Offer, the Employer may, and in the case of Negotiations shall, appoint the Independent Probity Assurance Authority indicated **in the BDS**.  38.5 The Employer shall specify **in the BDS** a new deadline and details for the submission of the Best and Final Offer or to initiate Negotiations. Instructions in ITB 21 to ITB 28 shall apply to the presentation, opening and clarifications of the Best and Final Offer of the Bidders.  38.6 On receipt of the Best and Final Offer from each Bidder, the Employer shall proceed with the evaluation and comparison of the bids again in accordance with ITB 29 to ITB 36 and then shall proceed with ITB 39 and following instructions. | |
| Qualification of the Bidder | | 39.1 The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated cost and substantially responsive Bid meets the qualifying criteria specified in Section III, “Evaluation and Qualification Criteria” or, if prequalification has taken place, continues to be eligible and continues to meet the qualifying criteria. | |
|  | | 39.2 The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 18.2. The determination shall not take into consideration the qualifications of other firms such as the Bidder’s subsidiaries, parent entities, affiliates, subcontractors (other than Specialized Subcontractors, if permitted **in BDS** when prequalification has not taken place) or any other firm(s) different from the Bidder. | |
|  | | 39.3 An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the Bid, in which event the Employer shall proceed to the next lowest evaluated Bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. | |
| Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | | 40.1 The Employer reserves the right to accept or reject any Bid, and to annul the Bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all Bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. | |
| Standstill Period | | 41.1 The Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITB 44. The Standstill Period commences when the Employer has transmitted to each Bidder the Notification of Intention to Award the Contract. Where only one Bid is submitted, or if this contract is in response to an emergency situation recognized by the Bank, the Standstill Period shall not apply. | |
| Notification of Intention to Award | | 42.1 The Employer shall send to each Bidder the Notification of Intention to Award the Contract to the successful Bidder. The Notification of Intention to Award shall contain, at a minimum, the following information: | |
|  | | 1. the name and address of the Bidder submitting the successful Bid; 2. the Contract price of the successful Bid; 3. the names of all Bidders who submitted Bids, and their Bid prices as readout, and as evaluated; 4. a statement of the reason(s) the Bid (of the unsuccessful Bidder to whom the notification is addressed) was unsuccessful, unless the price information in c) above already reveals the reason; 5. if in the evaluation of bids was used the method BAFO, if applicable; 6. the expiry date of the Standstill Period; and 7. instructions on how to request a debriefing and/or submit a complaint during the Standstill Period. | |
| **F. Award of Contract** | | | |
| Award Criteria | | 43.1 Subject to ITB 40, The Employer shall award the Contract to the successful Bidder. This is the Bidder whose Bid has been determined to be the lowest evaluated bid. | |
|  | | 43.2 If the Employer has not used the Best and Final Offer method in the Bid evaluation and if in the BDS in reference to ITB 38.1 it is specified that the Employer will use Negotiations with the Bidder with the Most Advantageous Bid, the selected Bidder shall be invited to Negotiations before the final adjudication of the Contract. The Negotiations se will be performed in the presence of the probity entity established in the BDS in reference to ITB 38.4. | |
|  | | 43.3 Once the Employer has determined the Bidder with the Most Advantageous Bid, the Employer shall promptly notify the selected Bidder the terms to initiate Negotiations in accordance with BDS in reference to ITB 38.5. Negotiations may include terms and conditions, price or social, environmental, innovative and cybersecurity aspects, provided that the minimum requirements of the bid are not modified. | |
|  | | 43.4 The Employer will first negotiate with the Bidder that has submitted the Most Advantageous Bid. If the result is not satisfactory or an agreement is not reached, the Employer will notify the Bidder that the Negotiations concluded without agreement and may then notify the Bidder with the following Most Advantageous Bid on the list, and so on until a satisfactory result is achieved. | |
| Notification of Award | | 44.1 Prior to the expiration of the Bid Validity Period and upon expiry of the Standstill Period or any extension thereof, and upon satisfactorily addressing any complaint that has been filed within the Standstill Period, the Employer shall notify the successful Bidder, in writing, that its Bid has been accepted. The notification of award (hereinafter and in the Contract Forms called the “Letter of Acceptance”) shall specify the sum that the Employer will pay the Supplier in consideration of the execution of the Contract (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”). | |
|  | | 44.2 Within ten (10) Business Days  after the date of transmission of the Letter of Acceptance, the Employer shall publish the Contract Award Notice which shall contain, at a minimum, the following information:   1. name and address of the Employer; 2. name and reference number of the contract being awarded, and the selection method used; 3. names of all Bidders that submitted Bids, and their Bid prices as read out at Bid opening, and as evaluated; 4. names of all Bidders whose Bids were rejected either as nonresponsive or as not meeting qualification criteria, or were not evaluated, with the reasons therefor; 5. if Negotiations were used in the final award, if applicable; 6. the name of the successful Bidder, the final total contract price, the contract duration and a summary of its scope; and 7. successful Bidder’s Beneficial Ownership Disclosure Form, if specified in BDS in reference to ITB 46.1. | |
|  | | 44.3 The Contract Award Notice shall be published on the Employer’s website with free access if available, or in at least one newspaper of national circulation in the Employer’s Country, or in the official gazette. The Employer shall also publish the contract award notice in UNDB online. | |
|  | | 44.4 Until a formal Contract is prepared and executed, the Letter of Acceptance shall constitute a binding Contract. | |
| Debriefing by the Employer | | 45.1 On receipt of the Employer’s Notification of Intention to Award referred to in ITB 42.1, an unsuccessful Bidder has three (3) Business Days to make a written request to the Employer for a debriefing on the reasons why its Bid was not selected. The Employer shall provide a debriefing to all unsuccessful Bidders whose request is received within this deadline. | |
|  | | 45.2 Where a request for debriefing is received within the deadline, the Employer shall provide a debriefing within five (5) Business Days, unless the Employer decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Employer shall promptly inform, by the quickest means available, all Bidders of the extended standstill period. | |
|  | | 45.3 Where a request for debriefing is received by the Employer later than the three (3)-Business Day deadline, the Employer should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of Public Notice of Award of contract. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period. | |
|  | 45.4 Debriefing of unsuccessful Bidders may be done in writing or through an information meeting, or both, at the option of the Employer. The Bidders shall bear their own costs of attending such a meeting. | | |
| Signing of Contract | | 46.1 Immediately after sending the Notification of Award, the Employer shall send to the successful Bidder the Letter of Acceptance including the Contract Agreement included in Section X, “Contract Forms”, and, if specified **in the BDS**, a request to submit the Beneficial Ownership Disclosure Form providing additional information on its beneficial ownership. The Beneficial Ownership Disclosure Form, if so requested, shall be submitted within eight (8) Business Days of receiving this request. |
|  | | 46.2 The successful Bidder shall sign, date and return to the Employer, the Contract Agreement included in Section IX, “Contract Forms” within twenty-eight (28) days of its receipt. |
| Performance Security | | 47.1 Within twenty-eight (28) days of the receipt of the Letter of Acceptance from the Employer, the successful Bidder shall furnish the Performance Security and if required **in the BDS**, the Environmental, Social, Health and Safety (ESHS) Performance Security in accordance with the Conditions of Contract using for that purpose the Performance Security and ESHS Performance Security Forms included in Section IX, “Contract Forms,” or another form acceptable to the Employer. If the Performance Security furnished by the successful Bidder is in the form of a bond, it shall be issued by a bonding or insurance company that has been verified by the successful Bidder to be acceptable to the Employer. A foreign institution providing a bond shall have a correspondent financial institution located in the Employer’s Country, unless the Employer has agreed in writing that a correspondent financial institution is not required. |
|  | | 47.2 Failure of the successful Bidder to submit the above-mentioned Performance Security and, if required in the BDS, the Environmental, Social, Health and Safety (ESHS) Performance Security, or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the Bid Security. In that event the Employer may award the Contract to the Bidder offering the next lowest evaluated Bid. |
| Procurement Related Complaint | | 48.1 The procedures for making a Procurement-related Complaint are as specified **in the BDS**. |

Section II - Bid Data Sheet (BDS)

The following specific data for the Works and Services to be procured shall complement, supplement, or amend the provisions in the Instructions to Bidders (ITB). Whenever there is a conflict, the provisions herein shall prevail over those in ITB.

*[Where an e-procurement system is used, modify the relevant parts of the BDS accordingly to reflect the e-procurement process.]*

*[Instructions for completing the Bid Data Sheet are provided, as needed, in the notes in italics mentioned for the relevant ITB.]*

|  |  |
| --- | --- |
| **ITB Reference** | **A. General** |
| **ITB 1.1** | The reference number of the Bidding is : \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[Insert number of the bidding]***  The Employer is: ***[insert name of the Employer]***  The name of the Bidding is: ***[insert name of the bidding]***  ***[The following text is to be included and the corresponding information inserted only if the contract is to be bid simultaneously with other contracts on a “slice and package” basis. Otherwise omit.]***  The number and identification of lots (contracts)comprising this Bidding is:  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert number and identification of lots (contracts)]***  The Roads are: **\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert identification of the Roads covered under the contract]***  Rehabilitation Works are \_\_\_\_\_\_\_\_\_ ***[insert “are” or “are not” as appropriate]*** required.  The sections of the Road(s) subject to Rehabilitation Works are**: \_*\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [If Rehabilitation Works are required, insert identification of the sections of the Road(s) covered under the contract; otherwise, insert “Not Applicable”]***  Improvement Works are \_\_\_\_ ***[insert “are” or “are not” as appropriate]*** required |
| **ITB 1.3 Electronic – Procurement System** | The Employer [***insert "shall use a" or "shall not use any"*** ] electronic-procurement system to manage this RFB:  ***[If an e/procurement system is used, insert name of the e-system and url address or link; if not used delete this and the next text]***  The electronic-procurement system shall be used to manage the following aspects of the procurement process:  ***[list the aspects here and modify the relevant parts of the BDS accordingly e.g., issuing Bidding document, issuing amendments to the bidding documents, submissions of Bids, opening of Bids, etc.]*** |
| **ITB 2.1** | The Borrower is: ***[insert name of the Borrower]*** |
| **ITB 2.1** | The name of the Project is: \_\_\_\_\_\_\_\_\_ ***[insert name of the project]*** |
| **ITB 5.3** | The Bank's website (www.iadb.org/integridad) provides information on companies and sanctioned persons. |
| ITB 5.4 | [***Delete if not applicable or, in case that a prequalification has taken place, if this limit was already established in the prequalification***]  Maximum number of members in the JVCA shall be: ***[insert a number]*** *\_\_\_\_\_\_\_* |
| ITB 5.8 | This Bidding is open only for prequalified Bidders*.* ***[In cases where prequalification has not taken place, indicate that Bidding is open to all eligible, interested Bidders.]*** |
| **B. Bidding Document** | |
| **ITB 8.1** | For **Clarification of Bid purposes** only, the Employer’s address is:  ***[insert the corresponding information as required below. This address may be the same as or different from that specified under provision ITB 24.1 for Bid submission]***  Attention: ***[insert full name of person, if applicable****]*  Address: *[****insert street address and number****]*  Floor/ Room number*: [****insert floor and room number, if applicable****]*  City:*] [****insert name of city or town****]*  ZIP Code:[***insert postal (ZIP) code, if applicable****]*  Country: : *[****insert name of country****]*  Telephone: *[****insert telephone number, including country and city codes****]*  Electronic mail address: *[****insert email address, if applicable****]*  Requests for clarification should be received by the Employer no later than: ***[insert no. of days]*** before the deadline for bid submission.  The Employer shall respond to the request of clarifications until: ***[insert no. of days]*** before the deadline for bid submission.  ***[Note: Requests for clarification sent via email must be sent on a company's letterhead, signed and stamped by the company's legal representative and preferably in pdf format.]*** |
| **ITB 8.4** | A Pre-Bid meeting \_\_\_\_\_\_\_\_\_\_\_ ***[insert “will” and insert the date, time and place information in the spaces provided below if a pre-Bid meeting will take place, taking into consideration that the meeting should take place no later than four weeks before the deadline for Bid submission. Otherwise, insert “will not” and insert “Not Applicable” in the spaces provided below for the date, time and place]***take place at the following date, time and place:  Date: \_\_\_\_\_\_\_\_\_ ***[insert date]***  Time: \_\_\_\_\_\_\_\_ ***[insert time]***  Place: \_\_\_\_\_\_\_\_ ***[insert place]***  A site visit conducted by the Employer\_\_\_\_\_\_\_\_\_\_\_ ***[insert “will be” or “will not be”****, as appropriate]* organized. |
| **C. Preparation of Bids** | |
| ITB 11.1 | The language of the Bid is: ***[insert “English” or” Spanish” or “French” or “Portuguese]****.*  All correspondence exchange shall be in \_\_\_\_\_\_\_\_\_\_\_\_ ***[insert language]*** language.  Language for translation of supporting documents and printed literature is \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[Specify one language]****.* |
| ITB 12.1 (h) | The Bidder shall submit the following additional documents in its Bid: ***[list any additional document not already listed in ITB 12.1 that must be submitted with the Bid. The list of additional documents should include the following:]***  **Code of Conduct (ESHS)**  The Bidder shall submit its Code of Conduct that will apply to and be properly communicated to the Contractor’s employees and subcontractors’ employees, to ensure compliance with its Environmental, Social, Health and Safety (ESHS) obligations under the contract.  In addition, the Bidder shall detail how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, how it will be communicated to personnel, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches.  The Contractor and its subcontractors shall be required to implement the agreed Code of Conduct upon contract award.  **Management Strategies and Implementation Plans (MSIP) to manage the (ESHS) risks and impacts.**  The Bidder shall submit for approval, and subsequently implement Management Strategies and Implementation Plans (MSIP) to manage the key Environmental, Social, Health and Safety (ESHS) risks and impacts, that are collectively referred to as the Contractor’s Environmental and Social Management Plan (C-ESMP) and are to be developed according to the Project’s Environmental and Social Assessment (ESA), the Project Specific Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan ESPF (ESAP), in accordance with the Particular Conditions of Contract Sub-Clause 10.1, that includes the agreed Management Strategies and Implementation Plans described here. .  ( |
| **ITB 14.1** | ***[The following provision should be included and the required corresponding information inserted only if alternative Bids will be considered. Otherwise omit.]***  Alternative Bids \_\_\_\_\_\_\_\_\_\_\_***[insert “shall be”]***permitted. |
| ITB 14.2 | Alternative times for reaching the required Service Levels and for the completion of the Rehabilitation and/or Improvement Works\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert “will be” or “will not be”, as appropriate****]* permitted. ***[Alternative times for completion should be permitted when the Employer sees potential net benefits in different times for completion; they also have merit for contracts bid on a “slice and package” basis.]***  If alternative times for completion are permitted, the evaluation method will be as specified in Section III, “Evaluation and Qualification Criteria.” |
| ITB 14.4 | Alternative technical solutions for the Rehabilitation and/or Improvement Works shall be permitted for the following parts of the Works: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[List the parts of the Works]*.**  If alternative technical solutions are permitted, the evaluation method will be as specified in Section III, “Evaluation and Qualification Criteria.” |
| **ITB 15.5** | ***[Price adjustment is mandatory for contracts expected to last more than 18 months. The following provision should be included and the required corresponding information inserted only if the prices quoted by the Bidder are not subject to price adjustment. Otherwise omit.]***  The prices quoted by the Bidder shall be: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_***[insert “fixed; consequently, the Bidder is not required to furnish the indices and weightings for the price adjustment formulae in the Schedule of Adjustment Data”.]*** |
| **ITB 16.1** | The currency(ies) of the Bid and the payment currency(ies) shall be in accordance with Alternative \_\_\_\_\_\_\_\_\_ as described below:  **Alternative A: (Bidders to quote entirely in local currency):**  (a) The unit rates and the prices shall be quoted by the Bidder in the Bill of Quantities, entirely in ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[Insert the name of the currency of the Employer’s country,]*** and further referred to as “the local currency”. A Bidder expecting to incur expenditures in other currencies for inputs to the Works supplied from outside the Employer’s country (referred to as “the foreign currency requirements”) shall indicate in the Appendix to Bid - Table C, the percentage(s) of the Bid Price (excluding Provisional Sums), needed by the Bidder for the payment of such foreign currency requirements, limited to no more than three foreign currencies.  (b) The rates of exchange to be used by the Bidder in arriving at the local currency equivalent and the percentage(s) mentioned in (a) above shall be specified by the Bidder in the Appendix to Bid - Table C, and shall apply for all payments under the Contract so that no exchange risk will be borne by the successful Bidder.  **Alternative B: (Bidders allowed to quote in local and foreign currencies):**   * + 1. The unit rates and prices shall be quoted by the Bidder in the Bill of Quantities separately in the following currencies – using Table: Alternative B in Section IV:   (i) for those inputs to the Works that the Bidder expects to supply from within the Employer’s country, in ***\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[Insert the name of the currency of the Employer’s country],*** and further referred to as “the local currency”; and  (ii) for those inputs to the Works that the Bidder expects to supply from outside the Employer’s country (referred to as “the foreign currency requirements”), in up to any three foreign currencies. |
| **ITB 19.1** | The Bid validity period shall be \_\_\_\_\_\_\_***[insert a number of days that is a multiple of seven counting as of the deadline for Bid submission]*** days. |
| **ITB 19.3 (a)** | The Bid price shall be adjusted by the following factor(s):\_\_\_\_\_\_\_\_  ***[The local currency portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.]*** |
| **ITB 20.1** | ***[If a Bid Security shall be required, a Bid-Securing Declaration shall not be required, and vice versa.]***  A Bid Security ***\_\_\_\_\_\_\_\_ [insert “shall be” or “shall not be”*]** required.  A Bid-Securing Declaration \_\_\_\_\_\_\_\_ ***[insert “shall be” or “shall not be”]*** required.  If a Bid Security shall be required, the amount and currency of the Bid Security shall be: \_\_\_\_\_\_\_ ***[preferably insert fixed amount and currency]***  ***[If a Bid Security is required, insert amount and currency of the Bid Security. Otherwise insert “Not Applicable”.]******[In case of lots, please insert amount and currency of the Bid Security for each lot]***  ***Note: Bid Security is required for each lot as per amounts indicated against each lot. Bidders have the option of submitting one Bid Security for all lots (for the combined total amount of all lots) for which Bids have been submitted, however if the amount of Bid Security is less than the total required amount, the Employer will determine for which lot or lots the Bid Security amount shall be applied]*** |
| **ITB 20.3 (d)** | Other types of acceptable securities:  ***[Insert names of other acceptable securities. Insert “None” if no Bid Security is required under provision ITB 20.1 or if Bid Security is required but no other forms of Bid securities besides those listed in ITB 20.3 (a) through (c) are acceptable.]*** |
| **ITB 20.9** | ***[The following provision should be included and the required corresponding information inserted only if a Bid Security is not required under provision ITB 20.1 and the Employer wishes to declare the Bidder ineligible for a period of time should the Bidder perform any of the actions mentioned in provision ITB 20. 9 (a) or (b), Otherwise omit]***  If the Bidder performs any of the actions prescribed in ITB 20.9 (a) or (b), the Borrower will declare the Bidder ineligible to be awarded contracts by the Employer for a period of \_\_\_\_\_\_ ***[insert number of years]*** years. |
| **ITB 21.1** | In addition to the original of the Bid, the number of copies is: ***[insert***  ***number of copies]*** |
| **ITB 21.3** | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: \_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert the form the written confirmation of authorization should consist of.]*** |
| **D. Submission and Opening of Bids** | |
| **ITB 23.1** | For **Bid submission purposes** only, the Employer’s address is: ***[This address may be the same as or different from that specified under provision ITB 7.1 for clarifications]***  Attention: *[****insert full name of person, if applicable]***  Street Address: *[****insert street address and number****]*  Floor/Room number: *[****insert floor and room number, if applicable****]*  City: [***insert name of city or town***]  ZIP Code: [***insert postal (ZIP) code, if applicable***]  Country: [***insert name of country***]  **The deadline for Bid submission is:**  Date: ***[insert day, month, and year, e.g. 19 December 2017]***  Time: *[****insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.****]*  ***[The date and time should be the same as those provided in the Request for Bids, unless subsequently amended pursuant to ITB 24.2*]**  Street Address: *[****insert street address and number****]*  Floor/Room number: *[****insert floor and room number, if applicable****]*  City: [***insert name of city or town***]  Country: [***insert name of country***]  Date: ***[insert day, month, and year, e.g. 19 December 2017]***  Time: *[****insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.****]* |
| **ITB 26.1** | The Bid opening shall take place at: *[insert the corresponding information as required below]*  Street Address: *[****insert street address and number****]*  Floor/Room number: *[****insert floor and room number, if applicable****]*  City: [***insert name of city or town***]  Country: [***insert name of country***]  Date: ***[insert day, month, and year, e.g. 19 December 2017]***  Time: *[****insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.****]* ***[Date and time should be the same as those given for the deadline for submission of Bids ITB 23]***  ***[The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their Bids electronically. Otherwise omit.]***  The electronic Bid opening procedures shall be: ***[insert a description of the electronic Bid opening procedures.]*** |
| **ITB 26.6** | The Letter of Bid and priced Bills of Quantities \_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert “shall” or “shall not”]*** be initialed by representatives of the Employer attending Bid opening.  If initialization is required, it shall be conducted as follows: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[if “shall” is inserted above, insert a description of the manner in which the Letter of Bid and Bill of Quantities are to be initialed, e.g., pages (all or some) to be initialed and number of Employer representatives attending Bid opening that shall initial the Letter of Bid and Bill of Quantities. Otherwise insert “Not Applicable”.]*** |
| **E. Evaluation and Comparison of Bids** | |
| **ITB 31.3** | The adjustment shall be based on **the \_\_\_\_\_\_\_ *[insert “average” or “highest”]*** price of the item or component as quoted in other substantially responsive Bids. If the price of the item or component cannot be derived from the price of other substantially responsive Bids, the Employer shall use its best estimate. |
| **ITB 33.1** | The currency that shall be used for Bid evaluation and comparison purposes to convert at the selling exchange rate all Bid prices expressed in various currencies into a single currency is: \_\_\_\_\_\_\_\_\_\_\_\_*[****insert name of currency]***  The date for the exchange rate shall be*:\_\_\_\_\_\_\_* ***[insert day, month and year, e.g. 19 December 2017 not earlier than 28 days prior to the deadline for submission of the Bids, nor later than the original date for the expiry of Bid validity period].*** |
| **ITB 35.2 (f)** | **[*Delete this section if not applicable*]**  Additional requirements apply. These are detailed in the evaluation criteria in Section III, “Evaluation and Qualification Criteria.” |
| **ITB 35.5** | The combined price for the Rehabilitation and Improvement Works may not exceed the following threshold: *[select one of the two options below]*  Option 1: \_\_\_\_\_\_\_% of the total contract price excluding provisional sums *[insert percentage], or*  Option 2: The amount of *\_\_\_\_\_\_\_\_\_* ***[insert amount and currency]*** |
| **ITB 38.1**  **BAFO** | [Delete if not applicable,]  The evaluation will use the Best and Final Offer (BAFO) method. |
| **ITB 38.2**  **Negotiations** | [***Delete if not applicable or if BDS ITB 38.1 specifies that BAFO is used***]  The final award will use Negotiations. |
| **ITB 38.4**  Independent Probity Assurance Authority | [***Delete if not applicable***]  If Negotiations are used, the Independent Probity Assurance Authority shall be: [*indicate: name and address*]. |
| **ITB 38.5 Address for submission of BAFO** | [***Delete if not applicable***]  For the purpose of presenting the BAFO, the Employer's address is: ***[This address may be the same as in relation to the provision of ITB 7.1 for clarification or a different one]***  Attention: ***[insert full name of person, if applicable****]*  Address: *[****insert street address and number****]*  Floor/Room number*: [****insert floor and room number, if applicable****]*  City:*] [****insert name of city or town****]*  ZIP Code: [***insert postal (ZIP) code, if applicable****]*  Country: *[insert name of country]* |
| **ITB 38.5**  **Deadline for submission of BAFO** | **[*Delete if not applicable*]**  The deadline for the presentation of the Best and Final Offer is:  Date: ***[insert day, month, and year, e.g. 19 December, 2019]***  Time: *[****insert time, and identify if a.m. or p.m. e.g. 10:30 a.m.****]* ***[Date and time should be the same as those given for the deadline for submission of Bids (ITB 23)]***  *[Note: The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their Bids electronically. Otherwise omit.]*  Bidders **[*insert “shall” or “shall not”*]** have the option of submitting their BAFO Bids electronically.  The electronic Bid opening procedures shall be: ***[insert a description of the electronic Bid opening procedures]*** |
| **ITB 38.5**  **Address for Negotiations and submission of Negotiated Bid** | [***Delete if not applicable***]  For the purpose of starting Negotiations and presenting the negotiated bid, the Employer's address is: ***[This address may be the same as in relation to the provision of ITB 8.1 for clarification or a different one]***  Attention: ***[insert full name of person, if applicable****]*  Address: *[****insert street address and number****]*  Floor/Room number*: [****insert floor and room number, if applicable****]*  City:*] [****insert name of city or town****]*  ZIP Code: [***insert postal (ZIP) code, if applicable****]*  Country: :*[****insert name of country****]* |
| **ITB 38.5**  **Deadline for submission of Negotiated Bid** | [***Delete if not applicable***]  The deadline for the presentation of the negotiated Bid will be defined in a Notification of the Employer certified by the Independent Probity Assurance Authority.  [***The time allowed to present the negotiated bid will be determined by giving due consideration to the particular circumstances of the Project and the magnitude and complexity of the purchase. The period allowed must be at least five business days from the end of the negotiations***]  [*The following provision will be included and the corresponding information required will be indicated only if Bidders have the option to submit the Negotiated Offer electronically. Delete if not applicable*].  Selected Bidder **[*insert “shall” or “shall not”*]** have the option of submitting its negotiated Bid electronically.  The procedures for submitting the negotiated bid electronically will be the following: *[****describe the procedures for submitting bids electronically****]* \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| **ITB 39.2** | Where prequalification has not taken place, the Employer \_\_\_\_\_\_\_\_\_ ***[insert “shall” or shall not”]*** permit that specific experience for parts of the Works and Service may be met by Specialized Subcontractors. |
| **F. Award of Contract** | |
| **ITB 47.1** | The successful Bidder ***[shall] or [shall not]*** submit the Beneficial Ownership Disclosure Form. |
| **ITB 47.1 and 48.2** | ***[Delete the following if not applicable]***  The successful Bidder shall be required to submit an Environmental, Social, Health and Safety (ESHS) Performance Security.  ***[Note: The ESHS Performance Security shall normally be required where ESHS risks are significant.]*** |
| **ITB 49**  **Complaints regarding Procurement** | The procedures for making a Procurement-related Complaint are detailed in the Procurement Policies for Goods and Works financed by the Inter-American Development Bank GN-2349-15.  If a Bidder wishes to make a Procurement-related Complaint, the Bidder should submit its complaint following these procedures, in writing (by the quickest means available, e.g., by email), to:  **For the attention**: *[insert full name of person receiving complaints]*  **Title/position**: *[insert title/position]*  **Employer**: *[insert name of Employer]*  **Email address***: [insert email address]* |

|  |
| --- |
| Section III - Evaluation and Qualification Criteria (Following Prequalification) |

This section contains the criteria that the Employer shall use to evaluate Bids and qualify Bidders. No other factors, methods or criteria shall be used other than specified in this bidding document.. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

**1. Evaluation**

In addition to the criteria listed in ITB 35.2 (a) – (e) the following criteria shall apply:

* 1. **Assessment of adequacy of Technical Proposal with Requirements**

……………………………………………………………………………………………………………………………………………………………………

* 1. **Alternative Completion Times**

If permitted under ITB 14.2, will be evaluated as follows: ……………………………………………………………………………………………………………………………………………………………………

* 1. **Technical alternatives**

If permitted under ITB 14.4, will be evaluated as follows: ……………………………………………………………………………………………………………………………………………………………………

* 1. **Sustainable procurement**

……………………………………………………………………………………………………………………………………………………………………

*[If specific****sustainable procurement technical requirements****have been specified in Section VI, “Specifications for Works and Services”* ***either****state that (i) those requirements will be evaluated on a pass/fail (compliance basis)****or****otherwise (ii) in addition to evaluating those requirements on a pass/fail (compliance basis), if applicable, specify the monetary adjustments to be applied to Bid prices for comparison purposes on account of Bids that exceed the specified minimum sustainable procurement technical requirements.]*

* 1. **BAFO**

If specified in the BDS in reference to ITB 38.1, after determining among the bids substantially meeting the requirements, the bid presenting the lowest evaluated cost in accordance to ITB 36, and, if applicable, evaluating any abnormally low bid (in accordance with ITB 37), the Employer may invite Bidders to submit their Best Final Offer in accordance with ITB 38, using only the following requirements: \_\_\_\_\_\_\_\_\_\_\_\_ [*indicate requirements such as price, type of clarifications or modifications, additional information, social, environmental, innovative or cybersecurity aspects*].

**2. Qualification**

**2.1 Update of Information**

The Bidder shall continue to meet the criteria used at the time of prequalification. The bidder shall use the relevant forms in Section IV to provide any updates to the information it provided at the time of prequalification.

**2.2 Financial Resources**

Using the relevant Financial Forms in Section IV, Bidding Forms, the Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:

(i) the following cash-flow requirement:

……………………………………………………………………………………………………………………………………………………………………

and

(ii) the cash flow requirements for works currently in progress and for future contract commitment.

**2.3 Personnel**

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements:

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Position** | **Total Work Similar**  **Experience (years)** | **In Similar Works Experience**  **(years)** |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
|  |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Information Forms included in Section IV, Bidding Forms.

**2.4 Equipment**

The Bidder must demonstrate that it has the key equipment listed hereafter:

|  |  |  |
| --- | --- | --- |
| **No.** | **Equipment Type and Characteristics** | **Minimum Number required** |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
|  |  |  |
|  |  |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV, “Bidding Forms.”

|  |
| --- |
| Section III - Evaluation and Qualification Criteria(Without Prequalification) |

This section contains the criteria that the Employer shall use to evaluate Bids and qualify Bidders. No other factors, methods or criteria shall be used other than specified in this bidding document.. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

**1. Evaluation**

In addition to the criteria listed in ITB 35.2 (a) – (e) the following criteria shall apply:

* 1. **Assessment of adequacy of Technical Proposal with Requirements:**

……………………………………………………………………………………………………………………………………………………………………

* 1. **Slice and Package**

If permitted under ITB 35.4, will be evaluated as follows:

Award Criteria for Multiple Contracts [ITB 35.4]:

Lots

Bidders have the option to Bid for any one or more lots. Bids will be evaluated lot-wise, taking into account discounts offered, if any, after considering all possible combinations of lots, the contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined lots, subject to the selected Bidder(s) meeting the required qualification criteria for lot or combination of lots as the case may be.

Packages

Bidders have the option to Bid for any one or more packages and for any one or more lots within a package. Bids will be evaluated package-wise, taking into account discounts offered, if any, for combined packages and/or lots within a package. The contract(s) will be awarded to the Bidder or Bidders offering the lowest evaluated cost to the Employer for combined packages, subject to the selected Bidder(s) meeting the required qualification criteria for combination of packages and or lots as the case may be.

**Qualification Criteria for Multiple Contracts**

The criteria for qualification is aggregate minimum requirement for respective lots as specified under items 3.1, 3.2, 4.2(a) and 4.2(b). However, with respect to the specific experience under item 4.2 (a) of Section III, the Employer will select any one or more of the options as identified below:

N is the minimum number of contracts

V is the minimum value of a single contract

**(a) For one Contract**:

**Option 1:**

(i) N contracts, each of minimum value V;

Or

**Option 2:**

(i) N contracts, each of minimum value V; or

(ii) Less than or equal to N contracts, each of minimum value V, but with total value of all contracts equal or more than N x V.

**(b) For multiple Contracts**

**Option 1:**

(i) Minimum requirements for combined contract(s) shall be the aggregate requirements for each contract for which the Bidder has submitted Bids as follows, and N1, N2, N3, etc. shall be different contracts:

Lot 1: N1 contracts, each of minimum value V1;

Lot 2: N2 contracts, each of minimum value V2;

Lot 3: N3 contracts, each of minimum value V3;

----etc.

Or

**Option 2:**

(i) Minimum requirements for combined contract(s) shall be the aggregate requirements for each contract for which the Bidder has submitted Bids as follows, and N1, N2, N3, etc. shall be different contracts:

Lot 1: N1 contracts, each of minimum value V1;

Lot 2: N2 contracts, each of minimum value V2;

Lot 3: N3 contracts, each of minimum value V3;

----etc., **or**

(ii) Lot 1: N1 contracts, each of minimum value V1; or number of contracts less than or equal to N1, each of minimum value V1, but with total value of all contracts equal or more than N1 x V1.

(iii) Lot 2: N2 contracts, each of minimum value V2; or number of contracts less than or equal to N2, each of minimum value V2, but with total value of all contracts equal or more than N2 x V2.

(iv) Lot 3: N3 contracts, each of minimum value V3; or number of contracts less than or equal to N3, each of minimum value V3, but with total value of all contracts equal or more than N3 x V3.

----etc.

Or

**Option 3:**

(i) Minimum requirements for combined contract(s) shall be the aggregate requirements for each contract for which the Bidder has bid for as follows, and N1, N2, N3, etc. shall be different contracts:

Lot 1: N1 contracts, each of minimum value V1;

Lot 2: N2 contracts, each of minimum value V2;

Lot 3: N3 contracts, each of minimum value V3;

----etc., **or**

(ii) Lot 1: N1 contracts, each of minimum value V1; or number of contracts less than or equal to N1, each of minimum value V1, but with total value of all contracts equal or more than N1 x V1.

Lot 2: N2 contracts, each of minimum value V2; or number of contracts less than or equal to N2, each of minimum value V2, but with total value of all contracts equal or more than N2 x V2.

Lot 3: N3 contracts, each of minimum value V3; or number of contracts less than or equal to N3, each of minimum value V3, but with total value of all contracts equal or more than N3 x V3.

----etc., **or**

(iii) Subject to compliance as per (ii) above with respect to minimum value of single contract for each lot, total number of contracts is equal or less than N1 + N2 + N3 +--but the total value of all such contracts is equal or more than N1 x V1 + N2 x V2 + N3 x V3 +---.

* 1. **Alternative Completion Times**, (if permitted under ITB 14.2, will be evaluated as follows: ……………………………………………………………………………………………………………………………………………………………………
  2. **Technical alternatives** , if permitted under ITB 14.4, will be evaluated as follows: ……………………………………………………………………………………………………………………………………………………………………
  3. **Sustainable procurement**

……………………………………………………………………………………………………………………………………………………………………

*[If specific****sustainable procurement technical requirements****have been specified in Section VI, “Specifications for Works and Services,”****either****state that (i) those requirements will be evaluated on a pass/fail (compliance basis)****or****otherwise (ii) in addition to evaluating those requirements on a pass/fail (compliance basis), if applicable, specify the monetary adjustments to be applied to Bid prices for comparison purposes on account of Bids that exceed the specified minimum sustainable procurement technical requirements.]*

* 1. **BAFO**

If specified in the BDS in reference to ITB 38.1, after determining among the bids substantially meeting the requirements, the bid presenting the lowest evaluated cost in accordance to ITB 36, and, if applicable, evaluating any abnormally low bid (in accordance with ITB 37), the Employer may invite Bidders to submit their Best Final Offer in accordance with ITB 38, using only the following requirements: \_\_\_\_\_\_\_\_\_\_\_\_ [*indicate requirements such as price, type of clarifications or modifications, additional information, social, environmental, innovative or cybersecurity aspects*].

**2. Qualification**

| **Eligibility and Qualification Criteria** | | | **Compliance Requirements** | | | | **Document** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **No.** | **Subject** | **Requirement** | **Single Entity** | **Joint Venture (existing or intended)** | | | **Submission Requirements** |
| **All Members Combined** | **Each Member** | **One Member** |
| **2.1. Eligibility** | | | | | | | |
| **1.1** | **Nationality** | Nationality in accordance with ITB 5.1 and Section V | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Forms ELI – 1.1 and 1.2, with attachments |
| **1.2** | **Conflict of Interest** | No conflicts of interest in accordance with ITB 5.2 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| **1.3** | **Bank Eligibility** | Not be on the list of parties sanctioned by the Bank, in accordance with  ITB 5.3. | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| **1.4** | **State-owned Enterprise or Institution of the Borrower country** | Meets conditions of ITB 5.5 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Forms ELI – 1.1 and 1.2, with attachments |
| **1.5** | **United Nations resolution or Borrower’s country law** | Not having been excluded as a result of prohibition in the Borrower’s country laws or official regulations against commercial relations with the Bidder’s country, or by an act of compliance with UN Security Council resolution, both in accordance with ITB 5.1 (a) and (b). | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Forms ELI – 1.1 and 1.2, with attachments |
| **2.2. Historical Contract Non-Performance** | | | | | | | |
| **2.1** | **History of Non-Performing Contracts** | Non-performance of a contract[[8]](#footnote-9) did not occur as a result of contractor default since 1st January [*insert year]*. | Must meet requirement | Must meet requirements | Must meet requirement[[9]](#footnote-10) | N/A | Form CON-2 |
| **2.2** | **Suspension Based on Execution of Bid/Proposal Securing Declaration by the Employer** | Not under suspension based on-execution of a Bid/Proposal Securing Declaration pursuant to ITB 5.6 or withdrawal of the Bid. pursuant ITB 20.9. | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| **2.3** | **Pending Litigation** | Bid’s financial position and prospective long-term profitability still sound according to criteria established in 3.1 below and assuming that all pending litigation will be resolved against the Bidder | Must meet requirement | N/A | Must meet requirement | N/A | Form CON– 2 |
| **2.4** | **Litigation History** | No consistent history of court/arbitral award decisions against the Bidder[[10]](#footnote-11) since 1st January *[insert year]* | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Form CON– 2 |
| **2.5** | **Declaration: Environmental, Social, Health, and Safety (ESHS) past performance** | Declare any civil work contracts that have been suspended or terminated and/or performance security called by an employer for reasons related to the non-compliance of any environmental, social, health and safety (including labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, gender and sexual and gender-based violence (SGBV) requirements or safeguard in the past five years[[11]](#footnote-12). | Must make the declaration. Where there are Specialized Sub-contractor/s, the Specialized Sub-contractor/s must also make the declaration. | N/A | Each must make the declaration. Where there are Specialized Sub-contractor/s, the Specialized Sub-contractor/s must also make the declaration. | N/A | Form CON-3 ESHS Performance Declaration |
| **2.3. Financial Situation and Performance** | | | | | | | |
| **3.1** | **Financial Capabilities** | (i) The Bidder shall demonstrate that it has access to, or has available, liquid assets, , lines of credit, and other financial means (independent of any contractual advance payment) sufficient to meet the construction cash flow requirements estimated as USD $ *[insert amount]* for the subject contract(s) net of the Bidder’s other commitments  (ii) The Bidders shall also demonstrate, to the satisfaction of the Employer, that it has adequate sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments.  (iii) The audited balance sheets or, if not required by the laws of the Bidder’s country, other financial statements acceptable to the Employer, for the last *[insert number of years]* years shall be submitted and must demonstrate the current soundness of the Bidder’s financial position and indicate its prospective long-term profitability. | Must meet requirement  Must meet requirement  Must meet requirement | Must meet requirement  Must meet requirement  N/A | N/A  N/A  Must meet requirement | N/A  N/A  N/A | Form FIN – 3.1, with attachments |
| **3.2** | **Average Annual Construction Turnover** | Minimum average annual construction turnover of US$ *[insert amount]*, calculated as total certified payments received for contracts in progress and/or completed within the last *[insert of year]* years, divided by *[insert number of years]* years | Must meet requirement | Must meet requirement | Must meet *[insert number]* %, *[insert percentage in words]* of the requirement | Must meet *[insert number]* %, *[insert percentage in words]* of the requirement | Form FIN – 3.2 |
| **2.4. Experience** | | | | | | | |
| **4.1 (a)** | **General Construction Experience** | Experience under construction contracts in the role of prime contractor, JVCA member, sub-contractor, or management contractor for at least the last *[insert number of years]* years, starting 1st January *[insert year]*. | Must meet requirement | N/A | Must meet requirement | N/A | Form EXP – 4.1 |
| **4.2 (a)** | **Specific Construction & Contract Management Experience** | (i) A minimum number of *[state the number]* similar contracts specified below that have been satisfactorily and substantially[[12]](#footnote-13) completed as a prime contractor, joint venture member[[13]](#footnote-14), management contractor or sub-contractor6 between 1st January [insert year] and bid submission deadline:  (i) N contracts, each of minimum value V;  Or  (ii) Less than or equal to N contracts, each of minimum value V, but with total value of all contracts equal or more than N x V; [insert values of N & V, delete (ii) above if not applicable].  [*In case the Works are to be bid as individual contracts under a slice and package (multiple contract) procedure, the minimum number of contracts required for purposes of evaluating qualification shall be selected from the options in accordance with ITB 35.4]*  The similarity of the contracts shall be based on the following: [*Based on Section VI, Specifications for Works and Services, specify the minimum key requirements in terms of physical size, complexity, construction method, technology and/or other characteristics including part of the requirements that may be met by specialized subcontractors, if permitted in accordance with ITB BDS 39.2]* | Must meet requirement | Must meet requirement[[14]](#footnote-15) | N/A | Must meet the following requirements for the key activities listed below [list key activities and the corresponding minimum requirements to be met by one member otherwise state: “N/A”] | Form EXP 4.2(a) |
|  |
| **4.2 (b)** |  | For the above and any other contracts [substantially completed and under implementation] as prime contractor, joint venture member, or sub-contractor between 1st January *[insert year]* and Application submission deadline, a minimum construction experience in the following key activities successfully completed[[15]](#footnote-16): *[list key activities indicating volume, number or rate of production as applicable.*  *Under 4.2(a), specified requirements define similarity of contracts, whereas the key activities or production rates to be specified under 4.2 (b) define the required capability of the Applicant to execute the Works. There shall not be any inconsistency or repetition of requirement between 4.2(a) and 4.2(b).For the rate of production, specify that the rate of production shall be on the basis of either the average during the entire specified period OR the rate of annual production in any 12-month period in the specified period****,*** *][[16]](#footnote-17)* | Must meet requirements  *[Specify activities that may be met through a specialized subcontractor, if permitted in accordance with ITB BDS 39.2]* | Must meet requirements *[Specify activities that may be met through a Specialized Subcontractor, if permitted in accordance with ITB BDS 39.2*] | N/A | Must meet the following requirements for key activities listed below *[****if applicable, out of the key activities in the first column of this 4.2 b),*** *list key activities (volume, number or rate of production as applicable) and the corresponding minimum requirements that have to be met by one member,* ***otherwise this cell should state: “N/A”.]*** | Form EXP – 4.2 (b) |

***Note: [For Multiple lots (contracts) specify financial and experience criteria for each lot under Sub-Factors 3.1, 3.2, 4.2(a) and 4.2(b)]***

**2.5 Key Personnel**

[***Note: Insert in the following table the minimum key specialists required to execute the contract, taking into account the nature, scope, complexity and risks of the contract****.]*

The Bidder must demonstrate that it will have a suitably qualified (and in adequate numbers) minimum Key Personnel, as described in the table below, that are required to perform the Contract.

The Bidder shall provide details of the Key Personnel and such other Personnel that the Bidder considers appropriate, together with their academic qualifications and work experience. The Bidder shall complete the relevant Forms in Section IV, Bidding Forms.

The Contractor shall require the Employer’s consent to substitute or replace the Key Personnel (reference the Particular Conditions of Contract 19.1).

**Key Personnel**

|  |  |  |  |
| --- | --- | --- | --- |
| **Item No.** | **Position/specialization** | **Relevant academic qualifications** | **Minimum years of relevant work experience** |
| 1 | *[Road Manager]* |  |  |
| 2 | *…* |  |  |
| **Suitable experts in the following specializations** | | | |
| 3 | [*Environmental*] | e.g. degree in relevant environmental field. | e.g. *[number of years]* working in road contracts in similar work environments |
| 4 | [*Health and Safety*] |  |  |
| 5 | [*Social*] |  | e.g. [number of *years*] of monitoring and managing risks related to SGBV |
| 6 | [*add others as appropriate*] |  |  |

* 1. **Equipment**

The Bidder must demonstrate that it has the key equipment listed hereafter:

|  |  |  |
| --- | --- | --- |
| **No.** | **Equipment Type and Characteristics** | **Minimum Number required** |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
|  |  |  |
|  |  |  |

The Bidder shall provide further details of proposed items of equipment using Form EQU in Section IV, “Bidding Forms.”

|  |
| --- |
| Section IV - Bidding Forms |

**Table of Forms**

Letter of Bid 66

Appendix to Bid 70

Bills of Quantities 74

Bill of Quantities for Maintenance Services 75

Bill of Quantities for Rehabilitation and Improvement Works 78

Bills of Quantities for Emergency Works 82

Technical Proposal 87

Bidder’s Qualification Forms 101

Form of Bid Security 117

Form of Bid-Securing Declaration 119

|  |
| --- |
| Letter of Bid |

|  |
| --- |
| *INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE DOCUMENT*  *The Bidder must prepare this Letter of Bid on stationery with its letterhead clearly showing the Bidder’s complete name and business address.*  *In respect to the statement on commissions, bonuses or fees, services it may be for example, payments to, or through, individuals or entities that are authorized to act on behalf of the Bidder to advance the interests of the Bidder in relation to this process of bidding or execution of the Contract.*  *Note: All italicized text in is to help Bidders in preparing this form.* |

**Date of this Bid submission**: [*insert date (as day, month and year) of Bid submission*]

**Request for Bid No**.: [*insert identification*]

**Alternative No.**:[*insert identification No if this is a Bid for an alternative*]

To: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_[*insert name of Employer*]

We, the undersigned, declare that:

1. **No reservations**: We have examined and have no reservations to the bidding document, including Addenda issued in accordance with ITB 9;
2. **Eligibility:** We meet the eligibility requirements and have no conflict of interest in accordance with ITB 5; and in case of detecting that any of the named parties are in any conflict of interest, we will notify this circumstance in writing to the Employer, either during the selection process, the negotiations or the execution of the Contract;
3. **Bid-Securing Declaration:** We have not been suspended nor declared ineligible by the Employer based on execution of a Bid-Securing Declaration in the Employer’s Country in accordance with ITB 5.6.
4. **Conformity:** We offer to execute in conformity with the bidding document and in accordance with the construction or service schedule the following Works: .

*[Insert one of the options below as appropriate]*

1. **Bid Price:** The total price of our Bid, excluding any discounts offered in item (f) below is:

| **Description** | **Amount**  **(in numbers)** |
| --- | --- |
| (a) Maintenance Services in an amount of *[amount in words] [name of currency]*.  (b) Rehabilitation Works in an amount of *[amount in words] [name of currency]*.  (c) Improvement Works in an amount of *[amount in words] [name of currency]*. |  |
| **A. SUB-TOTAL = (a) + (b) + (c)** |  |
| (d) Emergency Works in an amount of *[amount in words] [name of currency]*. |  |
| **B. TOTAL = A + (d)** |  |

1. **Combined Price:** We hereby confirm that our combined price for Rehabilitation Works and Improvement Works does not exceed the threshold given in the BDS ITB 35.5 which is *[insert amount or percentage of the total contract price].*

or

(e ) **Bid Price**: The total price, excluding any discounts offered in item (f) below is:

| **Description** | **Amount (in numbers and words)** | | |
| --- | --- | --- | --- |
|  | **Lot 1** | **Lot 2** | **Lot 3** |
| **(a) Maintenance Services** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |
| **(b) Rehabilitation Works** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |
| **(c) Improvement Works** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |
| **A. SUB-TOTAL = (a) + (b) + (c)** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |
| (d ) **Emergency Works** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |
| **B. TOTAL = A + (d)** *[amount in numbers, name of currency]* |  |  |  |
| *[amount in words]* |  |  |  |

(f) Combined Price: We hereby confirm that our combined price for Rehabilitation Works and Improvement Works does not exceed the threshold given in the BDS ITB 35.5, which is *[insert amount or percentage of the total contract price].*

1. **Discounts**: The discounts offered and the methodology for their application are:

(i) The discounts offered are: *[Specify in detail each discount offered.]*

(ii) The exact method of calculations to determine the net price after application of discounts is shown below: [*Specify in detail the method that shall be used to apply the discounts*];

1. **Bid Validity Period**: Our Bid shall be valid for a period specified in BDS 19.1 (or as amended if applicable) from the date fixed for the Bid submission deadline specified in BDS 23.1 (or as amended if applicable), and it shall remain binding upon us and may be accepted at any time before the expiration of that period;
2. **Performance Security**: If our Bid is accepted, we commit to obtain a Performance Security [*and an Environmental, Social, Health and Safety (ESHS) Performance Security,* ***Delete if not applicable***] in accordance with the bidding document;
3. **One Bid per Bidder:** We are not submitting any other Bid(s) as an individual Bidder, and weare not participating in any other Bid(s) as a Joint Venture member, and meet the requirements of ITB 5.4, other than alternative Bids submitted in accordance with ITB 14;
4. **Suspension and Debarment**: We, along with any of our subcontractors, suppliers, consultants, manufacturers, or service providers for any part of the contract, are not subject to, and not controlled by any entity or individual that is subject to, a temporary suspension or a debarment imposed by IDB or a debarment imposed by IDB in accordance with the Agreement for Mutual Enforcement of Debarment Decisions between the IDB and other development banks.

Further, we are not ineligible under the Employer’s Country laws or official regulations or pursuant to a decision of the United Nations Security Council;

1. **State-owned enterprise or institution:** [*select the appropriate option and delete the other*] *[We are not a state-owned enterprise or institution*] / [*We are a state-owned enterprise or institution but meet the requirements of ITB 5.5*];
2. **Commissions, gratuities and fees:** We have paid, or will pay the following commissions, gratuities, or fees with respect to the Bidding process or execution of the Contract: *[insert complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity]*

| Name of Recipient | Address | Purpose of the commission or gratuity | Amount |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

*(If none has been paid or is to be paid, indicate “none.”)*

1. **Beneficial Ownership Form:** [*Applies in the event that the Bidder must provide the Form*]. We understand that in the event that our offer is accepted we will be providing the information required in the Beneficial Ownership Disclosure Form or, if applicable, we will indicate the reasons why it is not possible to provide the required information. The Borrower will publish the Beneficial Ownership Disclosure Form as part of the Notification of the Award of the Contract, for which we express our authorization.
2. **Binding Contract:** We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us, until a formal contract is prepared and executed;
3. **Not Bound to Accept**: We understand that the Employer is not bound to accept the lowest evaluated cost Bid, the Most Advantageous Bid or any other Bid that you may receive;
4. **Best Final Offer or Negotiations**: We understand that the Employer will use the Best Final Offer method in the evaluation of bids if specified in BDS in reference to ITB 37.1 or Negotiations in the final adjudication if specified in BDS in reference to ITB 37.2, and that there will be an Independent Probity Assurance Authority hired by the Employer to observe and report on this process.
5. **Prohibited Practices:** We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf engages in any type of Prohibited Practices.
6. Excluded Activities: We, and our subcontractors or suppliers for any component of the contract have read and understood the definitions of the excluded activities contained in Annex I “IDB Environmental and Social Exclusion List” to the Bank’s Environmental and Social Policy Framework (ESPF)[[17]](#footnote-18), and will under the terms of the awarded contract not knowingly engage directly or indirectly in the production, trade or use of the products, substance or participate in the activities listed in said list

**Name of the Bidder**:\*[*insert complete name of person signing the Bid*]

**Name of the person duly authorized to sign the Bid on behalf of the Bidder**:\*\*[*insert complete name of person duly authorized to sign the Bid*]

**Title of the person signing the Bid**: [*insert complete title of the person signing the Bid*]

**Signature of the person named above**: [*insert signature of person whose name and capacity are shown above*]

**Date signed** [*insert date of signing*] **day of** [*insert month*], [*insert year*]

Name In the capacity of \_

Signed

Duly authorized to sign the Bid for and on behalf of

Dated on \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_

|  |
| --- |
| Appendix to Bid |

**Schedule of Adjustment Data**

[In Tables A, B, and C, below, the Bidder shall (a) indicate its amount of local currency payment, (b) indicate its proposed source and base values of indices for the different foreign currency elements of cost, (c) derive its proposed weightings for local and foreign currency payment, and (d) list the exchange rates used in the currency conversion. In the case of very large and/or complex contracts, it may be necessary to specify several families of price adjustment formulae corresponding to the different works involved.]

**Table A. Local Currency**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Index code\*** | **Index description\*** | **Source of index\*** | **Base value**  **and date\*** | **Bidder’s**  **related currency amount** | **Bidder’s**  **proposed**  **weighting** |
|  | Nonadjustable | — | — | — | A: \*  B:  C:  D:  E: |
|  |  |  | **Total** |  | **1.00** |

[\* To be entered by the Employer]

**Table B. Foreign Currency**

**State type:** ....................... [If the Bidder wishes to quote in more than one foreign currency, this table should be repeated for each foreign currency.]

| **Index code** | **Index description** | **Source of index** | **Base value and date** | **Bidder’s related source currency in type/amount** | **Equivalent in FC1** | **Bidder’s proposed weighting** |
| --- | --- | --- | --- | --- | --- | --- |
|  | Nonadjustable | **—** | **—** | **—** |  | **A: \_\_\_\_\_\_\_\_\***  **B:**  **C:**  **D:**  **E:** |
|  |  |  |  | **Total** |  | **1.00** |

[\* To be entered by the Employer]

**Table C. Summary of Payment Currencies**

For ………………………..[insert name of Section of the Works]

[Separate tables may be required if the various sections of the Works (or of the Bill of Quantities) will have substantially different foreign and local currency requirements. The Employer should insert the names of each Section of the Works.]

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Name of payment currency** | **A**  **Amount of currency** | **B**  **Rate of exchange**  **(local currency per unit of foreign)** | **C**  **Local currency equivalent**  **C = A x B** | **D**  **Percentage of  Net Bid Price (NBP)**  **100xC**  **NBP** |
| **Local currency** |  | **1.00** |  |  |
| **Foreign currency #1** |  |  |  |  |
| **Foreign currency #2** |  |  |  |  |
| **Foreign currency #** |  |  |  |  |
| **Net Bid Price** |  |  |  | **100.00** |
| **Provisional sums expressed in local currency** | *[To be entered by the Employer]* |  | *[To be entered by the Employer]* |  |
| **BID PRICE** |  |  |  |  |

**Table: Alternative B**

***To be used only with Alternative B Prices directly quoted in the currencies of payment.*** *(ITB 15.1)*

Summary of currencies of the Bid for \_\_\_\_\_\_\_\_\_\_\_ *[insert name of Section of the Works]*

|  |  |
| --- | --- |
| *Name of currency* | *Amounts payable* |
| Local currency: |  |
| Foreign currency #1: |  |
| Foreign currency #2: |  |
| Foreign currency #3: |  |
| Provisional sums expressed in local currency \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | *[To be entered by the Employer]* |

|  |
| --- |
| Bills of Quantities |

The bid includes the following Bills of Quantities:

* **Bill of Quantities for Maintenance Services**
* **Bill of Quantities for Rehabilitation Works** (if those are required under the contract)
* **Bill of Quantities for Improvement Works** (if those are required under the contract)
* **Bill of Quantities for Emergency Works**

*[*Samples *of the above Bills of Quantities are presented on the following pages.]*

|  |
| --- |
| Bill of Quantities for Maintenance Services |

1. The Bill of Quantities for Maintenance Services shall be read in conjunction with the Instructions to Bidders, Conditions of Contract, Specifications and the Drawings.

2. This Bill of Quantities is the basis for payment of maintenance services that are to be provided on a lump sum per km basis for maintaining the roads covered under the contract, at the Service Levels defined in the Specifications. The rates given by the Bidder shall, except insofar as is otherwise provided under the Contract, include all plant, equipment, labor, management and supervision, materials, erection, maintenance, insurance, profit, taxes and duties, together with all general risks, liabilities and obligations set out or implied in the Contract.

3. Payment shall be made in accordance with the actual performance of the Contractor and compliance with the Service Level criteria given in the Specifications for each road. Failure to meet the Service Levels will result in payment reductions in accordance with Clause 47 of the General Conditions and the Performance Specifications.

4. The unit rates and prices shall be quoted entirely in local currency but payment will be made in the proportions and currencies quoted in the Schedule of Adjustment Data.

5. A unit rate or price shall be entered by the Bidder against each item in the Bill of Quantities. The cost of items against which the Bidder has failed to enter a unit rate or price shall be deemed to be covered by other unit rates and prices entered in the Bill of Quantities.

6. General directions and descriptions of work and materials are not repeated or summarized in the Bill of Quantities. References to the relevant sections of the Contract documentation shall be made before entering rates or prices against each item in the Bill of Quantities.

7. The method of measurement of completed work for payment shall be in accordance with the measurement and payment provisions of the relevant section in the Performance Specifications.

8. Arithmetical errors discovered prior to award of the Contract will be corrected by the Employer pursuant to the Instructions to Bidders.

**Bill of Quantities and Unit Prices for Maintenance Services**

*[To be completed by the bidder]*

|  |  |  |
| --- | --- | --- |
| **Price N°** | **Description of Service and Price** | Unit Price |
|  |  | In Local Currency |
| **1.** | Unit Price per kilometer and month |  |
|  | This price is the full remuneration to the Contractor to carry out the services and works required in order to reach and maintain the service levels described in the Specifications and elsewhere in the contract. It further includes the activities of the Contractor related to self-control, quality assurance and material testing.  The Unit Price per kilometer and month is:   * Road section a: ………………………………….. * Road section b: ………………………………….. * Road section c: …………………………………. * Etc.………..   *[Note: There may either be one-unit price for all roads or road sections included in the contract, or different prices for different roads.]* | …………  …………  ………… |

**Bill of Quantities for Maintenance Services and their Prices**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | **Unit Price per kilometer and month** | **Total Price** | |
| **Price N°** | **Road or road section** | **Length**  **(km)** | **Service Level** |  |  | |
| **2** | Monthly lump-sum payment |  |  |  |  | |
| 2a  2b  2c  … | *[Indicate Roads or Road Sections]* | km | *[indicate Service Level for each road or road section]* |  |  | |
|  |  |  |  |  |  | |
| **SUB-TOTAL per month**: | | | | |  |  |
| Multiply by number of month (duration of contract) | | | | | *[Number of months]* | |
| **Total for contract period** | | | | |  | |

|  |
| --- |
| Bill of Quantities for Rehabilitation  and Improvement Works |

1. The Bills of Quantities for Rehabilitation Works and for Improvement Works shall be read in conjunction with the Instructions to Bidders, Conditions of Contract, Specifications and the Drawings.

**Bill of Quantities for Rehabilitation Works**

2. The Bill of Quantities for Rehabilitation Works presents a number of explicit activities considered necessary to rehabilitate particular road sections before some or all of the Service Level criteria for performance-based maintenance defined in the Specifications can be applied. The Bidder shall undertake a detailed assessment of road conditions at the time of Bid. The location and extent of the particular rehabilitation works considered necessary to reach required Service Levels shall be indicated by the Bidder in his Bid submission.

3. Although the bidding document may show estimated quantities of Rehabilitation Works, it is the responsibility of the Bidder to prepare his own estimate for the quantity of work required for each rehabilitation activity, and he shall indicate these quantities in the Bill of Quantities.

4. The Employer may in some cases indicate fixed quantities for some specific Rehabilitation Works, such as asphalt resurfacing. Those cases are clearly indicated as such by the Employer in the Bid Data Sheet, the Specifications and the Bill of Quantities for Rehabilitation Works.

5. Payment for Rehabilitation Works shall be made in relation to the work outputs satisfactorily completed in conformity with the Specifications as measured by the Contractor and verified by the Project Manager, and valued at the unit rates and prices stated in the priced Bill of Quantities. The total price for Rehabilitation Works and Improvement Works, if any, shall not exceed the threshold value or percentage given by the Employer in the Bid Data Sheet.

**Bill of Quantities for Improvement Works**

6. The Bill of Quantities for Improvement Works lists a set of interventions to be carried out by the contractor that add new characteristics to the Road in response to existing or new traffic, safety or other conditions, as defined in the Bid Data Sheet and the Specifications.

7. Payment for Improvement Works shall be made in relation to the work items satisfactorily completed in conformity with the Specifications, as measured by the Contractor and verified by the Project Manager, and valued at the unit rates and prices stated in the priced Bill of Quantities for Improvement Works.

**General**

8. The unit rates and prices Bid in the priced Bill of Quantities shall, except insofar as is otherwise provided under the Contract, include all plant, equipment, labor, supervision, materials, erection, maintenance, insurance, profit, taxes and duties, together with all general risks, liabilities and obligations set out or implied in the Contract. Unit rates and prices shall also include the cost of engineering design services, and measures needed to prevent or mitigate environmental impacts and safety measures.

9. The unit rates and prices shall be quoted entirely in local currency but payment will be made in the proportions and currencies quoted in the Schedule of Adjustments.

10. A quantity, unit rate or price shall only be entered against those work items considered necessary to attain the required Service Levels and sustain such Service Levels thereafter through execution of maintenance services that are provided for separately.

11. General directions and descriptions of work and materials are not repeated or summarized in the Bill of Quantities. References to the relevant sections of the Contract documentation shall be made before entering rates or prices against each item in the Bill of Quantities.

12. The method of measurement of completed work for payment shall be in accordance with the measurement and payment provisions of the relevant section of the Specifications.

13. Arithmetical errors discovered prior to award of the Contract will be corrected by the Employer pursuant to the Instructions to Bidders.

**Sample**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bill of Quantities for Rehabilitation Works** | | | | | |
| Activity | Quantity | Unit | Unit Price | Write in Full | Total Price |
| Milling and Replacement |  |  |  |  |  |
| * Lane |  | Km |  |  |  |
| * Shoulder |  | Km |  |  |  |
| Retrofiling |  |  |  |  |  |
| * Lane |  | Km |  |  |  |
| * Shoulder |  | Km |  |  |  |
| Asphalt Slurry |  |  |  |  |  |
| * Lane |  | Km |  |  |  |
| * Shoulder |  | Km |  |  |  |
| Etc. |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total Price for Rehabilitation Works | | | | |  |

Sample

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Bill of Quantities for Improvement Works** | | | | | |
| Activity | Quantity | Unit | Unit Price | Write in Full | Total Price |
| Additional Lane between Km 50 and 80 | 30 | Km |  |  |  |
| Shoulder paving between Km 50 and 80 | 30 | Km |  |  |  |
| Construction of Bus stops in 5 cities | 5 | Bus Stop type A |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total Price for Improvement Works | | | | |  |

|  |
| --- |
| Bills of Quantities for Emergency Works |

**GENERAL**

1. The Bill of Quantities for Emergency Works shall be read in conjunction with the Instructions to Bidders, Conditions of Contract, Specifications and the Drawings.

2. The quantities given in the Bill of Quantities are hypothetical and provisional, and are given to provide a common basis for Bidding. Actual quantities for Emergency Works will be specified in Work Orders, issued by the Project Manager in accordance with the General Conditions. The basis of payment for Emergency Works will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Project Manager and valued at the unit rates and prices Bid in the priced Bill of Quantities, where applicable, and otherwise at such unit rates and prices as may be agreed or determined by the Project Manager under the provisions of the Contract.

3. The unit rates and prices Bid in the priced Bill of Quantities shall, except insofar as is otherwise provided under the Contract, include all plant, equipment, labor, supervision, materials, erection, maintenance, insurance, profit, taxes and duties, together with all general risks, liabilities and obligations set out or implied in the Contract.

4. The unit rates and prices shall be quoted entirely in local currency, but payment will be made in the proportions and currencies quoted in the Schedule of Adjustments.

5. A unit rate or price shall be entered against each item in the Bill of Quantities. The cost of items against which the Contractor has failed to enter a unit rate or price shall be deemed to be covered by other unit rates and prices entered in the Bill of Quantities.

6. General directions and descriptions of work and materials are not repeated or summarized in the Bill of Quantities. References to the relevant sections of the Contract documentation shall be made before entering rates or prices against each item in the Bill of Quantities.

7. The method of measurement of completed work for payment shall be in accordance with the measurement and payment provisions of the relevant section of the Specifications.

8. Arithmetical errors discovered prior to award of the Contract will be corrected by the Employer pursuant to ITB 31

**Sample**

**Bill of Quantities for Emergency Works**

**Work Items**

1. The Bill of Quantities usually contains the following part Bills, which have been grouped according to the nature or timing of the work:

Bill No. 1—General Items

Bill No. 2—Earthworks

Bill No. 3—Culverts and Bridges

Bill No. 4—etc., as required

and

Summary Bill of Quantities

2. Bidders shall price the Bill of Quantities in local currency only and shall indicate in the Schedule of Adjustments the percentage expected for payment in foreign currency or currencies.

**Sample**

**Bill of Quantities for Emergency Works**

#### Bill No. 1: General Items

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Item no.* | *Description* | *Unit* | *Quantity* | *Rate* | *Amount* |
| 101 | Provide diversion road with gravel surfacing | km | 5 |  |  |
| 102 | Provide for traffic control and maintenance of diversion road | Km/day | 30 |  |  |
| 103 | Transport of material for fill or improved subgrade layers | m3 x km | 2500 |  |  |
| 104 | Transport of material for gravel wearing course | m3 x km | 1400 |  |  |
| 105 | —etc.— |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total for Bill No. 1  (carried forward to Summary, p. ) | | | | |  |

Sample

**Bill of Quantities for Emergency Works**

#### Bill No. 2: Earthworks

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Item no.* | *Description* | *Unit* | *Quantity* | *Rate* | *Amount* |
| 201 | Excavate topsoil to maximum depth 25 cm and stockpile for reuse, maximum haul distance 1 km | m3 | 95,000 |  |  |
| 202 | Excavate topsoil to maximum depth 25–50 cm, and dispose | m3 | 15,000 |  |  |
| 203 | —etc.— |  |  |  |  |
| 206 | Excavate fill material from cuttings or approved borrow pits, haul up to 1 km, deposit, shape, and compact to fill | m3 | 258,000 |  |  |
| 207 | Excavate rock in cuttings and dispose, any depth | m3 | 25,000 |  |  |
| 208 | —etc.— |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| Total for Bill No. 2  (carried forward to Summary, p. ) | | | | |  |

Summary of Specified Provisional Sums

|  |  |  |  |
| --- | --- | --- | --- |
| *Bill no.* | *Item no.* | *Description* | *Amount* |
| 1 |  |  |  |
|  |  |  |  |
|  |  |  |  |
| 2 |  |  |  |
|  |  |  |  |
|  |  |  |  |
| 3 |  |  |  |
|  |  |  |  |
|  |  |  |  |
| 4 |  |  |  |
|  |  |  |  |
|  |  | [*To be entered by the Employer; Delete if not applicable:]* Provisional sums for additional ESHS outcomes. |  |
|  |  | [*To be entered by the Employer; Delete if not applicable:]* Provisional sum for sexual and gender -based violence (SGBV) awareness and sensitization training. |  |
| etc. |  |  |  |
|  |  |  |  |
| Total for Specified Provisional Sums  (carried forward to Grand Summary (B), p. ) | | |  |

|  |
| --- |
| Technical Proposal |

The Bidder’s Technical Proposal shall include the following elements:

SCHEDULE A. Projected Cash Flow

SCHEDULE B. Site Organizations

SCHEDULE C. Subcontractors

SCHEDULE D. Contractor’s Equipment

SCHEDULE E. Initial Tentative Program of Performance

SCHEDULE F. Key Personnel Proposed

SCHEDUEL G. ESHS Management Strategies and Implementation Plans

SCHEDUEL H. Code of Conduct (ESHS)

Instructions on how to present the various schedules of the Technical Proposal are given on the following pages.

**SCHEDULE A**

**Projected Cash Flow**

(1) Bidders shall tabulate below estimates, based on their preliminary work programme, of:

(a) On the expenditure side, the value of the work which will be carried out;

(b) On the revenue side, the net payments to which they will become entitled with due allowance for the advance payment and repayment, materials prepayments, and retention money, but excluding price adjustments for rise and fall and provisional sums for emergency works.

(c) The projected net cash flow during the contract period.

(2) The prospective successful Bidder may be required to submit full details to substantiate his estimates.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Period (Months) | Cost/Value of Rehabilitation and Improvement Works *[indicate* ***amount*** *and* ***currency****]* | Cost/Value of Maintenance Services *[indicate* ***amount*** *and* ***currency****]* | Net Payments to be received *[indicate* ***amount*** *and* ***currency****]* | Net Cash Flow |
| Start Date |  |  |  |  |
| 1 to 6 |  |  |  |  |
| 6 to 12 |  |  |  |  |
| 12 to 18 |  |  |  |  |
| 18 to 24 |  |  |  |  |
| 24 to 30 |  |  |  |  |
| 30 to 36 |  |  |  |  |
| 36 to 42 |  |  |  |  |
| 42 to 48 |  |  |  |  |
| 48 to 54 |  |  |  |  |
| 54 to 60 |  |  |  |  |
| … etc. |  |  |  |  |
| Total |  |  |  |  |

**SCHEDULE B**

**Site Organization**

Bidders shall give below full particulars of the organization they propose to establish, direct, and administer the performance of the Contract. In particular, Bidders shall indicate the location of site camps and the resources they intend to allocate to Self-Control Units for planning and monitoring purposes.

**1. SITE ORGANIZATION CHART**

**2. NARRATIVE DESCRIPTION OF SITE ORGANISATION CHART**

**SCHEDULE C**

**SUBCONTRACTORS / PARTNERS**

Bidders shall list below those parts of the Works and Services which they propose to subcontract, and state the approximate value of those parts and the names and addresses of the proposed subcontractors, if those are known at Bidding stage. Bidders shall also list other business partners involved in the execution of the contract and their respective roles and responsibilities.

Part of Works / Services:

Approximate value:

Name and address of

proposed subcontractor / partner:

Part of Works / Services:

Approximate value:

Name and address of

proposed subcontractor / partner:

Part of Works / Services:

Approximate value:

Name and address of

proposed subcontractor / partner:

Part of Works / Services:

Approximate value:

Name and address of

proposed subcontractor / partner:

**SCHEDULE D**

**Contractor’s Equipment**

**Form EQU**

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III, Evaluation and Qualification Criteria. A separate Form shall be prepared for each item of equipment listed (with a current new purchase price exceeding US$ 5.000).

|  |  |  |
| --- | --- | --- |
| Item of equipment | | |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location | |
|  | Details of current commitments | |
|  |  | |
| Source | Indicate source of the equipment  o Owned o Rented o Leased o Specially manufactured | |

Omit the following information for equipment owned by the Bidder.

|  |  |  |
| --- | --- | --- |
| Owner | Name of owner | |
|  | Address of owner | |
|  |  | |
|  | Telephone | Contact name and title |
|  | Telephone | E-mail |
| Agreements | Details of rental / lease / manufacture agreements specific to the project | |
|  |  | |
|  |  | |

**SCHEDULE E**

**Initial Tentative Program of Performance**

To demonstrate a clear understanding of the requirements of the Contract, Bidders shall provide the following:

i) a bar chart sub-divided into sections for each road showing the major activities to be carried out for Maintenance Services, Rehabilitation Works and Improvement Works, if any. The activities shall be shown against time, with linkages shown between related/sequential activities as far as possible and appropriate.

ii) a bar chart or schedule showing the usage of major plant, including those listed in Schedule D (Contractor’s Equipment).

**SCHEDULE F**

**Form PER -1**

**Key Personnel**

**Schedule**

Bidders should provide the names and details of the suitably qualified Key Personnel to perform the Contract. The data on their experience should be supplied using the Form PER-2 below for each candidate.

**Key Personnel**

|  |  |  |
| --- | --- | --- |
| **1.** | **Title of position: Road Manager** | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **2.** | **Title of position: …** | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **3.** | **Title of position:** | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **4.** | **Title of position:** *[Environmental Specialist]* | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **5.** | **Title of position:** *[Health and Safety Specialist]* | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **6.** | **Title of position:** *[Social Specialist]* | |
|  | **Name of candidate:** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |
| **7.** | **Title of position:** *[insert title]* | |
|  | **Name of candidate** | |
|  | **Duration of appointment:** | [*insert the whole period (start and end dates) for which this position will be engaged*] |
|  | **Time commitment: for this position:** | [*insert the number of days/week/months/ that has been scheduled for this position*] |
|  | **Expected time schedule for this position:** | [*insert the expected time schedule for this position (e.g. attach high level Gantt chart*] |
|  | **Country of Citizenship or residence** | *[insert name of country]* |
|  | **Education** | *[insert professional and technical education, name of institutions, dates and titles]* |

**Form PER-2**

Resume and Declaration

Key Personnel

|  |
| --- |
| **Name of Bidder** |

|  |  |  |
| --- | --- | --- |
| **Position [#*1*]: [*title of position from Form PER-1*]** | | |
| **Personnel information** | **Name:** | **Date of birth:** |
|  | **Address:** | **E-mail:** |
|  |  |  |
|  | **Professional qualifications:** | |
|  | **Academic qualifications:** | |
|  | **Language proficiency:***[language and levels of speaking, reading and writing skills]* | |
| **Details** |  | |
|  | **Address of employer:** | |
|  | **Telephone:** | **Contact (manager / personnel officer):** |
|  | **Job title:** | **Years with present employer:** |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

|  |  |  |  |
| --- | --- | --- | --- |
| **Project** | **Role** | **Duration of involvement** | **Relevant experience** |
| *[main project details]* | *[role and responsibilities on the project]* | *[time in role]* | *[describe the experience relevant to this position]* |
|  |  |  |  |
|  |  |  |  |

**Declaration**

I, the undersigned Key Personnel, certify that to the best of my knowledge and belief, the information contained in this Form PER-2 correctly describes myself, my qualifications and my experience.

I confirm that I am available as certified in the following table and throughout the expected time schedule for this position as provided in the Bid:

|  |  |
| --- | --- |
| **Commitment** | **Details** |
| **Commitment to duration of contract:** | *[insert period (start and end dates) for which this Key Personnel is available to work on this contract]* |
| **Time commitment:** | *[insert the number of days/week/months/ that this Key Personnel will be engaged]* |

I understand that any misrepresentation or omission in this Form may:

1. be taken into consideration during Bid evaluation;
2. my disqualification from participating in the Bid;
3. my dismissal from the contract.

**Name of Key Personnel: [*insert name*]**

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Countersignature of authorized representative of the Bidder:**

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**SCHEDULE G**

ESHS Management Strategies and Implementation Plans

(ESHS-MSIP)

#### [The Bidder shall submit for approval, and subsequently implement the Management Strategies and Implementation Plans (MSIP) to manage the key Environmental, Social, Health and Safety (ESHS) risks and impacts, including risks related to labor, occupational and community health and safety, disaster and climate change, Iindigenous Ppeoples, vulnerable groups, gender, sexual and gender-based violence (SGBV) and stakeholder engagement, that are collectively referred to as the Contractor’s Environmental and Social Management Plan (C-ESMP). The MSIPs are to be developed according to the Project’s Environmental and Social Assessment (ESA), Project-specifc Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan (ESAP) as well as the Particular Conditions of Contract Sub-Clause 4.1, as required by ITB 121.1 (h) of the Bid Data Sheet. In developing these strategies and plans, the Bidder shall have regard to the ESHS provisions fully described in Section VI, “Specifications for Works and Services]

These strategies and plans shall describe in detail the actions, materials, equipment, management processes etc. that will be implemented by the Contractor, and its subcontractors and suppliers, which may include but are not limited to the following:]

• [e.g. Contractor’s Environmental Social Health and Safety Framework]

• [e.g. Occupational Health and Safety Plan to provide a safe and healthy environment to the Contractor’s workforce]

• [e.g. Labor Management Procedures to manage labor risks and working conditions including the prevention of child and forced labor in the project workforce];

• [e.g. Emergency Response Plan in case of natural disaster or public emergencies];

• [e.g. Traffic Management Plan to ensure safety of local communities from construction traffic];

• [e.g. Water Resource Protection Plan to prevent contamination of drinking water];

• [e.g. Solid and Hazardous Waste Management Plan to prevent pollution];

• [e.g. Boundary Marking and Protection Strategy for mobilization and construction to prevent offsite adverse impacts];

• [e.g. Strategy for obtaining Consents/Permits prior to the start of relevant works such as opening a quarry or borrow pit];

• [e.g. Biodiversity Action Plan to protect and restore ecosystems];

• [e.g. Resettlement or Livelihood Restauration Plans to minimize and mitigate impacts on livelihoods];

• [e.g. Sociocultural Analysis to, among other aspects, identify risks and impacts on Indigenous Peoples, and a respective Plan to prevent, minimize and/or compensate these risks and impacts and propose culturally appropriate measures]

• [e.g. Chance Find Procedure to define actions if cultural heritage resources are encountered];

• [e.g. Sexual and Gender Based Violence (SGBV) prevention and response action plan].

• [e.g. Stakeholder Engagement Plan (SEP) including procedures to implement the project’s stakeholder grievance mechanism (GRM) to ensure effective and continuous engagement with local communities].

PAYMENT FOR ESHS REQUIREMENTS

The Employer’s ESHS and procurement specialists should consider how the Contractor will cost the delivery of the ESHS requirements. In the majority of cases, the payment for the delivery of ESHS requirements shall be a subsidiary obligation of the Contractor covered under the prices quoted for other Bill of Quantity items. For example, normally the cost of implementing workplace safe systems of work, including the measures necessary for ensuring traffic safety, shall be covered by the Bidder’s rates for the relevant works. Alternatively, provisional sums could be set aside for activities for example for HIV counselling service and SGBV awareness and sensitization or to encourage the contractor to deliver additional ESHS outcomes beyond the requirement of the Contract.

**SCHEDULE H**

Code of Conduct: Environmental, Social, Health and Safety (ESHS)

#### The Bidder shall submit the Code of Conduct defining rules of behavior for all workers related to prevention and management measures for environmental, labor, and social risks of the Project, including health and safety risks, sexual and gender- based violence, discrimination, and sexual abuse and exploitation of children and other individuals or vulnerable groups that will apply to the Contractor’s employees and subcontractors as required by ITB 11.1 (h) of the Bid Data Sheet. The Code of Conduct shall ensure compliance with the ESHS provisions of the contract, including those as may be more fully described in Section VI, “Specifications for Works and Services.”

#### In addition, the Bidder shall submit an outline of how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement,how it will be provided and properly communicated to all workers, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches.

#### The Code of Conduct should be written in plain language, in a manner that is clear, understandable and accessible, be provided and properly communicated to all workers and should, where possible, be signed by each worker to indicate that they have:

#### received a copy of the code;

#### had the code explained to them;

#### acknowledged that adherence to this Code of Conduct is a condition of employment; and

#### understood that violations of the Code can result in serious consequences, up to and including dismissal, or referral to legal authorities.

#### A copy of the Code shall be displayed throughout project implementation in a location easily accessible to the workers, community and project affected persons. It shall be provided in languages comprehensible to the local community, Contractor’s Personnel, Employer’s Personnel, and affected persons.

Bidder’s Qualification Forms

|  |
| --- |
| Form ELI -1.1 |
| Bidder Information Form |
| Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* Page *\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages |
| |  | | --- | | Bidder's name | | In case of Joint Venture (JVCA), name of each member: | | Bidder's actual or intended country of registration:  *[indicate country of Constitution]* | | Bidder's actual or intended year of incorporation: | | Bidder's legal address [in country of registration]: | | Bidder's authorized representative information  Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Address: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Telephone numbers: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  E-mail address: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* | | 1. Attached are copies of original documents of  🞎 Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above.  🞎 In case of JVCA, letter of intent to form JVCA or JVCA agreement, in accordance with ITB 12.2  🞎 In case of state-owned enterprise or institution, in accordance with ITB 5.5, documents establishing:   * Legal and financial autonomy * Operation under commercial law * Establishing that the Bidder is not a dependent agency of the Employer or the Borrower   2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. *[If required under BDS ITB 43.1, the successful Bidder shall provide additional information on beneficial ownership, using the Beneficial Ownership Disclosure Form.]* | |

Form ELI -1.2

Bidder's JVCA Information Form  
(to be completed for each member of Bidder’s JVCA)

Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* of *\_\_\_\_\_\_\_\_\_\_\_\_* pages

|  |
| --- |
| Bidder’s JVCA name: |
| JVCA member’s name: |
| JVCA member’s country of registration: |
| JVCA member’s year of constitution: |
| JVCA member’s legal address in country of constitution: |
| JVCA member’s authorized representative information  Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Telephone number: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  E-mail address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| 1. Attached are copies of original documents of  🞎 Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above.  🞎 In case of a state-owned enterprise or institution, documents establishing legal and financial autonomy, operation in accordance with commercial law, and that they are not a dependent agency of the Employer or the Borrower, in accordance with ITB 5.5.  2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership. *[If required under BDS ITB 43.1, the successful Bidder shall provide additional information on beneficial ownership for each JVCA member using the Beneficial Ownership Disclosure Form.]* |

Form CON – 2

Historical Contract Non-Performance, Pending Litigation and Litigation History

Bidder’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*JVCA Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

|  |  |  |  |
| --- | --- | --- | --- |
| Non-Performed Contracts in accordance with Section III, “Evaluation and Qualification Criteria” | | | |
| 🞎 Contract non-performance did not occur since 1st January *[insert year]* specified in Section III, Evaluation and Qualification Criteria, Sub-Factor 2.1.  🞎 Contract(s) not performed since 1st January *[insert year]* specified in Section III, “Evaluation and Qualification Criteria,” requirement 2.1 | | | |
| **Year** | **Non- performed portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for nonperformance: *[indicate main reason(s)]* | *[insert amount]* |
| Pending Litigation, in accordance with Section III, “Qualification Criteria and Requirements” | | | |
| 🞎 No pending litigation in accordance with Section III, “Evaluation and Qualification Criteria,” Sub-Factor 2.3. | | | |
| 🞎 Pending litigation in accordance with Section III, “Evaluation and Qualification Criteria,” Sub-Factor 2.3 as indicated below. | | | |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Year of dispute** | | **Amount in dispute (currency)** | | **Contract Identification** | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |
|  | |  | | Contract Identification: \_\_\_\_\_\_\_\_\_  Name of Employer: \_\_\_\_\_\_\_\_\_\_\_\_  Address of Employer: \_\_\_\_\_\_\_\_\_\_  Matter in dispute: \_\_\_\_\_\_\_\_\_\_\_\_\_\_  Party who initiated the dispute: \_\_\_\_  Status of dispute: *\_\_\_\_\_\_\_\_\_\_\_* |  |
|  | |  | | Contract Identification:  Name of Employer:  Address of Employer:  Matter in dispute:  Party who initiated the dispute:  Status of dispute: |  |
| Litigation History in accordance with Section III, “Evaluation and Qualification Criteria” | | | | | |
| 🞎 No Litigation History in accordance with Section III, “Evaluation and Qualification” Criteria, Sub-Factor 2.4.  🞎 Litigation History in accordance with Section III, “Evaluation and Qualification Criteria,” Sub-Factor 2.4 as indicated below. | | | | | |
| **Year of award** | **Outcome as percentage of Net Worth** | | **Contract Identification** | | **Total Contract Amount (currency), USD Equivalent (exchange rate)** |

**Form CON – 3**

Environmental, Social, Health, and Safety Performance Declaration

*[The following table shall be filled in for the Bidder, each member of a Joint Venture and each Specialized Subcontractor]*

**Bidder’s Name: *[insert full name]*Date: *[insert day, month, year]*Joint Venture Member’s or Specialized Subcontractor’s Name: *[insert* *full name]***Bidding No. and title: *[insert Bidding number and title]*Page *[insert page number]* of *[insert total number]* pages

| **Environmental, Social, Health, and Safety Performance Declaration**  in accordance with Section III, “Evaluation and Qualification Criteria”  (In case of prequalification, Section III Qualification Criteria, and Requirements of the Prequalification document) | | | |
| --- | --- | --- | --- |
| 🞎 **No suspension or termination of contract**: An employer has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental, Social, Health, or Safety (ESHS) performance including labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, sexual and gender-based violence (SGBV), stakeholder engagement, since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5.  🞎 **Declaration of suspension or termination of contract**: The following contract(s) has/have been suspended or terminated and/or Performance Security called by an employer(s) for reasons related to Environmental, Social, Health, or Safety (ESHS) performance including labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, sexual and gender-based violence (SGBV), stakeholder engagement, since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 2.5. Details are described below: | | | |
| **Year** | **Suspended or terminated portion of contract** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and US$ equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for suspension or termination: *[indicate main reason(s) e.g. for GBV/ SEA breaches]* | *[insert amount]* |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: [indicate complete contract name/ number, and any other identification]  Name of Employer: [insert full name]  Address of Employer: [insert street/city/country]  Reason(s) for suspension or termination: [indicate main reason(s)] | *[insert amount]* |
| *…* | *…* | *[list all applicable contracts]* | *…* |
| **Performance Security called by an employer(s) for reasons related to ESHS performance** | | | |
| *Year* | Contract Identification | | Total Contract Amount (current value, currency, exchange rate and US$ equivalent) |
| *[insert year]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for calling of performance security: *[indicate main reason(s) e.g. for SGBV breaches or incidents of child or forced labor.* | | *[insert amount]* |
|  |  | |  |

Form FIN – 3.1:

**Financial Situation and Performance**

Bidder’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*JVCA Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

**1. Financial data**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Type of Financial information in**  **(currency)** | **Historic information for previous** *\_\_\_\_\_\_\_\_\_years,*  *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  **(amount in currency, currency, exchange rate\*, USD equivalent)** | | | | |
|  | Year 1 | Year 2 | Year 3 | Year4 | Year 5 |
| Statement of Financial Position (Information from Balance Sheet) | | | | | |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Total Equity/Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Working Capital (WC) |  |  |  |  |  |
| Information from Income Statement | | | | | |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |
| Cash Flow Information | | | | | |
| Cash Flow from Operating Activities |  |  |  |  |  |

**2. Sources of Finance**

Specify sources of finance to meet the cash flow requirements on works currently in progress and for future contract commitments.

|  |  |  |
| --- | --- | --- |
| **No.** | **Source of finance** | **Amount (US$ equivalent)** |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
|  |  |  |

**2. Financial documents**

The Bidder and its parties shall provide copies of financial statements for *\_\_\_\_\_\_\_\_\_\_\_*years pursuant Section III, Evaluation and Qualifications Criteria, Sub-factor 3.1. The financial statements shall:

(a) reflect the financial situation of the Bidder or in case of JVCA member, and not an affiliated entity (such as parent company or group member).

(b) be independently audited or certified in accordance with local legislation.

(c) be complete, including all notes to the financial statements.

(d) correspond to accounting periods already completed and audited.

🞎 Attached are copies of financial statements[[18]](#footnote-19) for the *\_\_\_\_\_\_\_\_\_\_\_\_*years required above; and complying with the requirements

Form FIN – 3.2:

**Average Annual Construction Turnover**

Bidder’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*JVCA Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

|  |  |  |  |
| --- | --- | --- | --- |
| **Annual turnover data** | | | |
| **Year** | **Amount**  **Currency** | **Exchange rate** | **USD equivalent** |
| *[indicate year]* | *[insert amount and indicate currency]* |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| Average Annual Construction Turnover \* |  |  |  |

\* See Section III, “Evaluation and Qualification Criteria,” Sub-Factor 3.2.

Form FIN – 3.4:

**Current Contract Commitments / Works in Progress**

Bidders and each member to a JVCA should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

|  |
| --- |
| **Current Contract Commitments** |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Name of Contract | Employer’s  Contact Address, Tel. | Value of Outstanding Work  [Current US$ Equivalent] | Estimated Completion Date | Average Monthly Invoicing Over Last Six Months [US$/month)] |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
|  |  |  |  |  |  |

Form EXP - 4.1

General Construction Experience

Bidder’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*JVCA Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

|  |  |  |  |
| --- | --- | --- | --- |
| Starting  Year | Ending  Year | Contract Identification | Role of  Bidder |
|  |  | Contract name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Brief Description of the Works and Services performed by the  Bidder: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Amount of contract: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Name of Employer: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Address: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* |  |
|  |  | Contract name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Brief Description of the Works and Services performed by the  Bidder: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Amount of contract: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Name of Employer: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Address: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* |  |
|  |  | Contract name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Brief Description of the Works and Services performed by the  Bidder: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Amount of contract: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Name of Employer: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*  Address: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_* |  |

Form EXP - 4.2(a)

**Specific Construction and Contract Management Experience**

Bidder’s Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*JVCA Member’s Name\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Similar Contract No.** | **Information** | | | | |
| Contract Identification |  | | | | |
| Award date |  | | | | |
| Completion date |  | | | | |
| Role in Contract | Prime Contractor 🞎 | | Member in  JVCA  🞎 | Management Contractor  🞎 | Sub-contractor 🞎 |
| Total Contract Amount |  | | | US$ | |
| If member in a JVCA or sub-contractor, specify participation in total Contract amount |  |  | |  | |
| Employer's Name: |  | | | | |
| Address:  Telephone number  E-mail: |  | | | | |

**Form EXP - 4.2(a) (cont.)**

**Specific Construction and Contract Management Experience (cont.)**

|  |  |
| --- | --- |
| **Similar Contract No.** | **Information** |
| Description of the similarity in accordance with Sub-Factor 4.2(a) of Section III: |  |
| 1. Amount |  |
| 2. Physical size of required Works and Services items |  |
| 3. Complexity |  |
| 4. Methods/Technology |  |
| 5. Construction rate for key activities |  |
| 6. Other Characteristics |  |

Form EXP - 4.2(b)

Construction Experience in Key Activities

Bidder's Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Bidder's JVCA Member Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Sub-contractor's Name[[19]](#footnote-20) (as per ITB 39.2): *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*Bidding No. and title: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Page *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*pages

All Sub-contractors for key activities must complete the information in this form as per ITB 39.2 and Section III, Qualification Criteria and Requirements, Sub-Factor 4.2.

1. Key Activity No One: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

|  | **Information** | | | | |
| --- | --- | --- | --- | --- | --- |
| Contract Identification |  | | | | |
| Award date |  | | | | |
| Completion date |  | | | | |
| Role in Contract | Prime Contractor  🞎 | Member in  JVCA  🞎 | | Management Contractor  🞎 | Sub-contractor  🞎 |
| Total Contract Amount |  | | | US$ | |
| Quantity (Volume, number or rate of production, as applicable) performed under the contract per year or part of the year | Total quantity in the contract  (i) | | Percentage  participation  (ii) | | Actual Quantity Performed  (i) x (ii) |
| Year 1 |  | |  | |  |
| Year 2 |  | |  | |  |
| Year 3 |  | |  | |  |
| Year 4 |  | |  | |  |
| Employer’s Name: |  | | | | | |
| Address:  Telephone number  E-mail: |  | | | | | |

|  |  |
| --- | --- |
|  | **Information** |
| Description of the key activities in accordance with Sub-Factor 4.2(b) of Section III: |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |

2. Activity No. Two

3. …………………

|  |
| --- |
| Form of Bid Security |

**Demand Guarantee**

**Beneficiary:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Request for Bids No:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Date:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**BID GUARANTEE No.:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**Guarantor:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Applicant") has submitted or will submit to the Beneficiary its Bid (hereinafter called "the Bid") for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ under Request for Bids No. \_\_\_\_\_\_\_\_\_\_\_ (“the Bidding”).

Furthermore, we understand that, according to the Beneficiary’s conditions, Bids must be supported by a Bid guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_  (\_\_\_\_\_\_\_\_\_\_\_\_) upon receipt by us of the Beneficiary’s complying demand, supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying or identifying the demand, stating that either the Applicant:

(a) has withdrawn its Bid during the period of Bid validity set forth in the Applicant’s Letter of Bid (“the Bid Validity Period”), or any extension thereto provided by the Applicant; or

(b) having been notified of the acceptance of its Bid by the Beneficiary during the Bid Validity Period or any extension thereto provided by the Applicant, (i) has failed to execute the contract agreement, or (ii) has failed to furnish the Performance Security, and, if required, the Environmental, Social, Health and Safety (ESHS) Performance Security, in accordance with the Instructions to Bidders (“ITB”) of the Beneficiary’s Bidding document.

This guarantee will expire: (a) if the Applicant is the successful Bidder, upon our receipt of copies of the contract agreement signed by the Applicant and the performance Security and, if required, the Environmental, Social, Health and Safety (ESHS) Performance Security, issued to the Beneficiary in relation to such contract agreement; or (b) if the Applicant is not the successful Bidder, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the Bidding process; or (ii)twenty-eight days after the end of the Bid Validity Period.

Consequently, any demand for payment under this guarantee must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

*[signature(s)]*

Form of Bid-Securing Declaration

Date: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Bidding No.: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Alternative No.: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

To: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

We, the undersigned, declare that:

We understand that, according to your conditions, Bids must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for Bidding or submitting Proposals in any contract with the Employer for the period of time of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,* starting on *\_\_\_\_\_\_\_\_\_\_\_\_,* if we are in breach of our obligation(s) under the Bid conditions, because we:

(a) have withdrawn our Bid during the period of Bid validity specified in the Letter of Bid; or

(b) having been notified of the acceptance of our Bid by the Employer during the period of Bid validity, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security and, if required, the Environmental, Social, Health and Safety (ESHS) Performance Security, in accordance with the ITB.

We understand this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight days after the expiration of our Bid.

Signed: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

In the capacity of *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Name: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Duly authorized to sign the Bid for and on behalf of: *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Dated on \_\_\_\_\_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_\_\_ *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

Corporate Seal (where appropriate)

Section V - Eligible Countries

**Eligibility to provide goods, Works construction and render services for Bank financed procurement**

***Note:*** *In these documents references to Bank include the IDB, the Bid Lab and any fund administered by the Bank.*

*Next, 2 options of number 1) are shown, for the User to choose the one that is appropriate, according to the source of financing. This source may be the Inter-American Development Bank (IDB), the Bid Lab or, occasionally, contracts can be financed by special funds that could include different criteria for eligibility to a particular group of member countries. When the last option is selected, the eligibility criteria should be mentioned therein:*

**(1) *Member Countries when the financing source is the Inter-American Development Bank****.*

Germany, Argentina, Austria, the Bahamas, Barbados, Belgium, Belize, Bolivia, Brazil, Canada, Chile, Colombia, Costa Rica, Croatia, Denmark, Ecuador, El Salvador, Slovenia, Spain, United States, Finland, France, Guatemala, Guyana, Haiti, Honduras, Israel, Italy, Jamaica, Japan, Mexico, Nicaragua, Norway, The Netherlands, Panama, Paraguay, Peru, Portugal, United Kingdom, Republic of Korea, Dominican, People's Republic of China, Sweden, Switzerland, Suriname, Trinidad and Tobago, Uruguay, and Venezuela.

***Eligible Territories***

1. Guadeloupe, French Guyana, Martinique, Reunion – French Departments.
2. U.S. Virgin Islands, Puerto Rico, Guam – U.S.A. Territory.
3. Aruba – as country of the Kingdom of the Netherlands; and Bonaire, Curacao, Saint Maarten, Saint Eustatius – as departments of the Kingdom of The Netherlands
4. Hong Kong – Special Administrative Region of the People's Republic of China.

*--------------------------------------*

**(1) *List of Countries according to the Administered Fund Agreement:***

*(Include the list of countries)*]

*--------------------------------------*

**(2) Criteria to determine Nationality and the country of origin of goods and services**

To make a determination of: (a) the nationality of companies and individuals eligible to partake in Bank financed contracts and (b) the country of origin of goods and services, the following criteria shall be used:

**(A) Nationality**

(a) **An individual** holds the nationality of a Bank member country when he/she meets the following requirements;

* 1. Is a citizen of a member country; or
  2. Has established domicile in a member country as a “bonafide” resident and is legally authorized to work in that country.

(b) **A company** holds the nationality of a member country if two of the following requirements are met:

1. Is legally constituted or incorporated according to the laws of a Bank member country; and
2. More than fifty percent (50%) of the company capital is owned by individuals or companies of Bank member countries.

All partners in a partnership, consortium or association (JVCA) with joint and severally responsibility and all the subcontractors shall have to comply with the requirements set above.

**B) Origin of Goods**

Goods have their origin in a member country of the Bank if they have been mined, grown, harvested, or produced in a member country of the Bank. A good has been produced when through manufacture, processing or assembly another commercially recognized article results that differs substantially in its basic characteristics, function or purpose of utility from its parts or components.

For a good consisting of several individual components that need to be interconnected (either by the supplier, the purchaser or by a third party) to make the good operative and regardless of the complexity of the interconnection, the Bank considers that such good is eligible for financing if the assembly of the components took place in a member country, regardless of the origin of the components. When the good is a set of several individual goods that are normally packaged and sold commercially as a single unit, the good is considered to originate in the country where the set was packaged and shipped to the purchaser.

For purpose of origin, goods labeled “made in the European Union” shall be eligible without the need to identify the corresponding specific country of the European Union.

The origin of materials, parts or components of the goods or the nationality of the firm that produces, assembles, distributes or sells the goods, does not determine the origin of the goods.

**C) Origin of Services**

The country of origin of services is that of the individual or firm providing the services as determined under the nationality criteria set forth above. These criteria apply to services ancillary to the supply of goods (such as transportation, insurance, erection, assembly, etc.), to construction services and to consulting services.

PART 2 – Works and Services’ Requirements

|  |
| --- |
| Section VI - Specifications for Works and Services |

**Notes for preparing Specifications for Output- and Performance-based Road Contracts**

*Any additional sustainable procurement technical requirements (beyond the ESHS requirements stated in the Environmental, Social, Health and Safety Requirements section below) shall be clearly specified. Please refer to the Bank’s Procurement Regulations and Sustainable procurement guidance notes/tool kit for further information. The requirements to be specified shall be specific enough to not demand evaluation based on rated criteria/merit point system. The sustainable procurement requirements shall be specified to enable evaluation of such a requirement on a pass/fail basis. To encourage Bidders’ innovation in addressing sustainable procurement requirements, as long as the Bid evaluation criteria specify the mechanism for monetary adjustments for the purpose of Bid comparisons, Bidders may be invited to offer Road Works that exceed the specified minimum sustainable procurement requirements.*

Precise and clear Specifications are a prerequisite for Bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their Bids. In the context of bidding document for the **Output - and Performance-based Road Contracts**, the Specifications must cover different areas (performance criteria, general technical aspects, organization, ESHS regulations, etc.) and must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards to be complied with. Specifications must be written specially by the Employer to suit the specific conditions of each country and of the roads included in the contract. Recognizing that there cannot be mandatory standard specifications for universal application in all countries, this document does not include any sample texts for specifications. However, for the guidance and convenience of its clients and other users of this document, the Bank has prepared in Annex of this document **“Sample Specifications for OPBRC”** which provides sample texts and technical guidance for the preparation of Section VI - Specifications for Works and Services These can be applied, with the necessary adjustments, for different types of roads ranging from low-volume unpaved rural roads to multi-lane paved highways. The Bank suggests the use of these sample texts as appropriate; these nevertheless still need adaptation to the specific conditions of the road networks under contract. The sample Specifications provided reflect the basic principles which have been adopted under this bidding document for Output- and Performance-Based Road Contracts. They should also help to prevent conflicts which could derive from contradictions between the administrative sections of the bidding document and the Specifications.

Section VI of the bidding document should include as a minimum the following parts:

**Part A: Performance Specifications**

This part should include a detailed description of (i) the concepts on which the Output- and Performance-Based Road Contracts are based; (ii) the Service Levels required on the roads included in the contract; (iii) the methods and procedures to be applied for measuring compliance with Service Levels; (iv) the payment reductions or liquidated damages applied in case of non-compliance, (v) the Rehabilitation Works and the Improvement Works the contractor will have to carry out in addition to the Services of Management and Maintenance, and (vi) other aspects, such as the internal organization of the contractor, etc.

**Part B: General Specifications for Roadworks**

This part is very country-specific and should present the norms and specifications generally applied for roadworks in a specific country, mainly in terms of quality and workmanship. Part B is applicable mainly for specific Rehabilitation and Improvement Works described in Part A, but some parts of it may also be applicable for Maintenance Services and Emergency Works.

**Part C: Specifications for Emergency Works**

This part must describe the procedures and other rules to be applied if Emergency Works are to be carried out within the contract. Use of the sample text would help to ensure that the concept of Emergency Works is not misused.

**Part D: Environmental and Social Specifications**

This part would provide a set of rules to be followed by the contractor in order to manage ESHS impacts and risks.

Other Specifications may be needed concerning the use of materials, plant and equipment by the contractor, if the provisions included in the General Conditions (GC, Section VII) and complemented in the Particular Conditions (PC, Section VIII) are deemed insufficient by the Employer. However, these issues may already be covered in the General Specifications for Roadworks.

Only if the various parts of the Specifications are completed adequately and included in the bidding document, will the objectives of economy, efficiency, and equality in procurement be realized, responsiveness of Bids be ensured, and the subsequent task of Bid evaluation facilitated.

The use of metric units is encouraged by IDB.

Care must be taken in drafting Specifications to ensure that they are not too restrictive. In the specification of standards for materials, plant, other supplies, and workmanship, recognized international standards should be used as much as possible.

These **Notes for Preparing Specifications** are intended only as information for the Employer or the person drafting the bidding document. They should **not** be included in the final bidding document.

**Environmental, social, health and safety requirements**

*The Employer should use the services of a suitably qualified environmental, social, health and safety specialist/s to prepare the specifications for Management Strategies and Implementation Plans (MSIP) to manage the key Environmental, Social, Health and Safety (ESHS) risks and impacts, including risks related to labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, gender, sexual and gender-based violence (SGBV) and stakeholder engagement, that are collectively referred to as the Contractor’s Environmental and Social Management Plan (C-ESMP), working with a procurement specialist/s.*

*The Employer should attach or refer Project’s Environmental and Social Assessment (ESA), Project-specifc Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan (ESAP). .*

*The Employer in this section shall refer to the IDB’s Environmental and Social Policy Framework that shall apply to the projects: [Select those that apply:*

1. *Environmental and Social Policy Framework[[20]](#footnote-21)*
2. *Access to information Policy*

*These specifications for the C-ESMP shall describe in detail the actions, materials, equipment, management processes etc. that will be implemented by the Contractor, and its subcontractors and suppliers, which may include but are not limited to the following:*

* [*e.g. Contractor’s Environmental Social Health and Safety Framework*]
* [*e.g. Occupational Health and Safety Plan to provide a safe and healthy environment to the Contractor’s workforce*]
* [*e.g. Labor Management Procedures to manage labor risks and working conditions including the prevention of child and forced labor in the project workforce*];
* [*e.g. Emergency Response Plan in case of natural disaster or public emergencies*];
* [*e.g. Traffic Management Plan to ensure safety of local communities from construction traffic*];
* [*e.g. Water Resource Protection Plan to prevent contamination of drinking water*];
* [*e.g. Solid and Hazardous Waste Management Plan to prevent pollution*];
* [*e.g. Boundary Marking and Protection Strategy for mobilization and construction to prevent offsite adverse impacts*];
* [*e.g. Strategy for obtaining Consents/Permits prior to the start of relevant works such as opening a quarry or borrow pit];*
* [*e.g. Biodiversity Action Plan to protect and restore ecosystems*];
* [*e.g. Resettlement or Livelihood Restauration Plans to minimize and mitigate impacts on livelihoods*];
* *[e.g. Sociocultural Analysis to, among other aspects, identify risks and impacts on Indigenous Peoples, and a respective Plan to prevent, minimize and/or compensate these risks and impacts and propose culturally appropriate measures]*
* [*e.g. Chance Find Procedure to define actions if cultural heritage resources are encountered*];
* *[e.g. Sexual and Gender Based Violence (SGBV) prevention and response action plan].*
* *[e.g. Stakeholder Engagement Plan (SEP) including procedures to implement the project’s stakeholder grievance mechanism (GRM) to ensure effective and continuous engagement with local communities].*

**Minimum Content of ESHS requirements**

*In preparing detailed specifications for C-ESMP requirements, the specialists should refer to and consider:*

* *project assessments and plans e.g. the project’s Environmental and Social Action Plan (ESAP) and its Environmental and Social Assessment (ESA), Project-specifc Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) including specific thematic plans such as the project’s Stakeholder Engagement Plan (SEP).*
* *consent/permit conditions*
* *required standards of the IDB’s Environmental and Social Policy Framework (ESPF)*
* *relevant international conventions or treaties etc., national legal and/or regulatory requirements and standards (where these represent higher standards than the IDB ESPF and its Environmental and Social Performance Standards (ESPS))*
* *relevant international standards e.g. WHO Guidelines for Safe Use of Pesticides*
* *relevant good industry practice e.g. WBG EHS Guidelines*
* *relevant sector standards e.g. EU Council Directive 91/271/EEC Concerning Urban Waste Water Treatment*
* *grievance redress mechanism including types of grievances to be recorded and how to protect confidentiality e.g. of those reporting allegations of SGBV and protect from reprisal.*
* *SGBV prevention and management.*
* *Assessment of risks and impacts on Indigenous Peoples, and a culturally appropriate engagement process, that requires FPIC under certain circumstances.*

*The detail specification for ESHS should, to the extent possible, describe the intended outcome rather than the method of working.*

*The ESHS requirements should be prepared in manner that does not conflict with the relevant General Conditions of Contract and Particular Conditions of Contract, and in particular:*

*General Conditions of Contract*

*Sub-clause 1.13 Compliance with Laws*

*Sub-clause 2.2 Assistance (Permits, Licenses and Approvals)*

*Sub-clause 4.1 Contractor’s General Obligations*

*Sub-clause ~~4.4~~ 5.1 Subcontractors*

*Sub-clause 4.8 Health and Safety Obligation*

*Sub-clause 4.14 Avoidance of Interference*

*Sub-clause 4.18 Protection of the Environment*

*Sub-clause 4.22 Contractor’s Operations on the Site*

*Sub-clause 4.23 Archeological anf Geological Finding*

*Section 6 Staff and Labour (includes health and safety)*

*Sub-clause 7.1 Manner of Execution*

*Sub-clause 11.11 Clearance of Site*

*Sub-clause 12.3 Valuation of Work (reference ITB 14.2 “Items against which no rate or price is entered by the Bidder shall be deemed to be covered by the rates for other items in the Bill of Quantities and will not be paid separately by the Employer.”)*

**minimun content for a Contractor ESHS Framework**

*In preparing detailed specifications for the Contractor’s ESHS Framework requirements, the specialists should refer to and consider:*

*At a minimum the Contractor ESHS Framework, should state the works’ policy goal to integrate environmental and social protection, labor and working conditions, occupational and community health and safety, gender equality, Indigenous Peoples issues, equality, child protection, vulnerable groups (including those with disabilities), sexual and gender based violence (SGBV), discrimination, and sexual abuse and exploitation of children and other individuals or vulnerable groups, HIV/AIDS awareness and prevention and wide and continuous stakeholder engagement (including the implementation of a grievance redress mechanism) in the planning processes, programs, and activities of the parties involved in the execution of the Works.*

*The Employer shall consult with the Bank to agree the issues to be included which may also address: climate adaptation, land acquisition and resettlement, indigenous people, etc. The Contractor ESHS Framework should set the frame for monitoring, continuously improving processes and activities and for reporting on the compliance with the policy.*

*It shall include a statement that, for the purpose of the framework, specific management plans and code of conduct applicable to workers, the term “child” / “children” means any person(s) under the age of 18 years.*

*The Contractor ESHS Framework should, as far as possible, be brief but specific and explicit, and measurable, to enable reporting of compliance with the framework in accordance with the Particular Conditions of the Contract Sub-Clause 4.20 and Part E of the Particular Conditions of Contract.*

*As a minimum, the Contractor ESHS Framework is set out to the commitments to:*

1. *apply good international industry practice to protect and conserve the natural environment and to minimize unavoidable impacts.*
2. *provide and maintain a healthy and safe work environment, safe systems of work and adequate working conditions.*
3. *protect the health and safety of local communities and users, with particular concern for those who have disabilities, are elderly, or otherwise vulnerable;*
4. *respect Indigenous Peoples rights to lands, territories and natural resources, and identify risks and impacts that could affect them, while ensuring their access to project benefits, and proposed mitigation and compensation measures, through a culturally appropiate participatory process, and a free prior and informed consent process, if required.*
5. *ensure that terms of employment and working conditions of all workers engaged in the Works meet the requirements of the IDB’s Environmental and Social Policy Framework (ESPF) and its Environmental and Social Performance Standard (ESPS) 2 on Labor and Working conditions, as well as the ILO labour conventions to which the host country is a signatory;*
6. *be intolerant of and enforce disciplinary measures for illegal activities. To be intolerant of, and enforce disciplinary measures for SGBV, discrimination, harassment, threats of violence, coercion, inhumane treatment and sexual activity with children; To be intolerant of, report and remedy any incidents of child and forced labor including in the workforce of contractors and sub-contractors.*
7. *incorporate a gender perspective and provide an enabling environment where persons of all genders, sexual orientations and gender identities have equal opportunity to participate in, and benefit from, planning and development of the Works;*
8. *work co-operatively, including with end users of the Works, relevant authorities, contractors and local communities;*
9. *engage with and listen to affected persons and organizations and be responsive to their concerns, with special regard for vulnerable, disabled, and elderly people;*
10. *provide an environment that fosters the exchange of information, views, and ideas that is free of any fear of retaliation, and protects whistleblowers;*
11. *minimize the risk of HIV transmission and to mitigate the effects of HIV/AIDS associated with the execution of the Works;*

*The Framework should be signed by the senior manager of the Employer. This is to signal the intent that it will be applied rigorously.*

**Minimum Requirements for the Bidder’s Code of Conduct**

*The Employer should use the services of a suitably qualified environmental, social, health and safety specialist/s to prepare the specifications for the Code of Conduct defining rules of behavior for all workers related to prevention and management measures for environmental, labor, and social risks of the Project, including health and safety risks, sexual and gender-based violence, discrimination, and sexual abuse and exploitation of children and other individuals or vulnerable groups that will apply to the Contractor’s employees and subcontractors’employees as required by ITB 12.1 (h) of the Bid Data Sheet. The Code of Conduct shall ensure compliance with the ESHS provisions of the contract, including those as may be more fully described in the Section VII, "Works Requirements."*

*The specifications shall require an outline of how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, how it will be provided and properly communicated to all workers, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches.*

*The Code of Conduct should be written in plain language, in a manner that is clear, understandable and accessible, will be provided and properly communicated to all workers and should, where possible, be signed by each worker to indicate that they have:*

* *received a copy of the code;*
* *had the code explained to them;*
* *acknowledged that adherence to this Code of Conduct is a condition of employment; and*
* *understood that violations of the Code can result in serious consequences, up to and including dismissal, or referral to legal authorities.*

*A copy of the Code shall be displayed throughout project implementation in a location easily accessible to the workers, community and project affected people. It shall be provided in languages comprehensible to the local community, Contractor’s Personnel, Employer’s Personnel, and affected persons.*

*A minimum requirement for the Code of Conduct should be set out by the Employer, taking into consideration the issues, impacts, and mitigation measures identified, for example, in:*

* *project assessments and plans e.g. the project’s Environmental and Social Action Plan (ESAP) and its Environmental and Social Assessment (ESA), Project Specific Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) inclduing labor management procedures, a commitment to zero tolerance of SGBV against community members and workers together with disciplinary measures for breach of conduct*
* *consent/permit conditions (regulatory authority conditions attached to any permits or approvals for the project)*
* *required standards of the IDB Environmental and Social Policy Framework (ESPF)*
* *relevant international conventions, standards or treaties, including core ILO conventions the country has ratified*
* *relevant national, legal and/or regulatory requirements and standards as well as applicable collective agreements*
* *relevant standards and good industry practice, e.g. World Bank EHS Guidelines, Workers’ Accommodation: Process and Standards (IFC and EBRD)*
* *workforce grievance redress mechanisms.*
* *Stakeholder grievance redress mechanism*
* *Relevant guidelines determined by Indigenous governance structure and decision-making process when works take place in areas with presence of Indigenous Peoples. Considerations must be included to ensure the engagement with Indigenous Peoples is culturally appropriate.*

*The types of issues identified could include. risks associated with: labor influx, spread of communicable diseases, SGBV, illicit behavior and crime, engaging with project affected communities (particularly Indigenous Peoples), non-discrimination and maintaining a safe environment etc.*

*A satisfactory code of conduct will contain obligations on all Contractor’s Personnel (including sub-contractors and day workers) that are suitable to address the following issues, as a minimum. Additional obligations may be added to respond to particular concerns of the region, the location and the project sector or to specific project requirements. The code of conduct shall contain a statement that the term “child” / “children” means any person(s) under the age of 18 years.*

*The issues to be addressed include:*

1. *Compliance with the IDB’s Environmental and Social Policy Framework (ESPF)*
2. *Compliance with applicable laws, rules, and regulations*
3. *Compliance with applicable health and safety requirements to protect the local community (including vulnerable and disadvantaged groups), the Employer’s Personnel, and the Contractor’s Personnel (including wearing prescribed personal protective equipment, preventing avoidable accidents and a duty to confidentially report conditions or practices that pose a safety hazard or threaten the environment)*
4. *The use of illegal substances*
5. *Non-Discrimination in dealing with the local community (including vulnerable and disadvantaged groups), the Employer’s Personnel, and the Contractor’s Personnel (for example on the basis of family status, ethnicity, race, gender, religion, language, marital status, age, disability (physical and mental), sexual orientation, gender identity, political conviction or social, civic, or health status)*
6. *Interactions with the local community(ies), members of the local community (ies), and any affected person(s) (for example to convey an attitude of respect, including to their culture and traditions)*
7. *Sexual harassment (for example to prohibit use of language or behavior, in particular towards women and/or children, that is inappropriate, harassing, abusive, sexually provocative, demeaning or culturally inappropriate)*
8. *Violence, including SGBV (for example acts that inflict physical, emotional, psychological or sexual harm or suffering, threats of such acts, coercion, and deprivation of liberty or resources.*
9. *Exploitation including sexual exploitation and abuse (for example the prohibition of the exchange of money, employment, goods, or services for sex, including sexual favors or other forms of humiliating, degrading behavior, exploitative behavior or abuse of power)*
10. *Protection of children (including prohibitions against sexual activity or abuse, or otherwise unacceptable behavior towards children, limiting interactions with children, and ensuring their safety in project areas)*
11. *Sanitation requirements (for example, to ensure workers use specified sanitary facilities provided by their employer and not open areas)*
12. *Avoidance of conflicts of interest (such that benefits, contracts, or employment, or any sort of preferential treatment or favors, are not provided to any person with whom there is a financial, family, or personal connection)*
13. *Respecting reasonable work instructions (including regarding ESHS norms)*
14. *Completion of relevant training courses for specific activities, non-discrimination or SGBV*
15. *Protection and proper use of property (for example, using personal protective equipment, to prohibit theft, carelessness or waste)*
16. *Respecting restrictions on the use of force (and where applicable firearms) of security forces and appropriate conduct towards workers and project-affected people*
17. *Duty to confidentially report violations of this Code*
18. *Procedures how grievances will be kept confidential, considered and addresses*
19. *Non-retaliation against workers who report violations of the Code or who makes use of the grievance mechanism for Contractor’s Personnel or the project’s Grievance Redress Mechanism, if that report is made in good faith.*
20. *Sanctions and Disciplinary measures proportional to violations of this Code consistent with national laws and regulations and applicable collective agreements.*

***Payment for ESHS Requirements***

*The Employer’s ESHS and procurement specialists should consider how the Contractor will cost the delivery of the ESHS requirements. In the majority of cases, the payment for the delivery of ESHS requirements shall be a subsidiary obligation of the Contractor covered under the prices quoted for other Bill of Quantity items. For example, normally the cost of implementing workplace safe systems of work, including the measures necessary for ensuring traffic safety, shall be covered by the Bidder’s rates for the relevant works. Alternatively, provisional sums could be set aside for activities for example for HIV counselling service, and SGBV awareness and sensitization or to encourage the contractor to deliver additional ESHS outcomes beyond the requirement of the Contract.*

PART 3 – Conditions of Contract and Contract Forms

|  |
| --- |
| Section VII - General Conditions |

**Table of Clauses**

[A. Contract and Interpretation 137](#_Toc454885041)

[1. Definitions 137](#_Toc454885042)

[2. Interpretation 140](#_Toc454885043)

[3. Documents Forming the Contract 141](#_Toc454885044)

[4. Language and Law 141](#_Toc454885045)

[5. Notices 141](#_Toc454885046)

[6. Settlement of Disputes (Alternative when using a Dispute Review Board) 142](#_Toc454885047)

[6. Settlement of Disputes (Alternative when using a Dispute Review Expert) 146](#_Toc454885048)

[B. Assignment of Responsibilities 148](#_Toc454885049)

[7. Scope of Works and Services 148](#_Toc454885050)

[8. Design Responsibility 149](#_Toc454885051)

[9. Copyright 152](#_Toc454885052)

[10. Start Date and Completion 152](#_Toc454885053)

[11. Contractor’s Responsibilities 152](#_Toc454885054)

[12. Subcontracting 154](#_Toc454885055)

[13. Assignment of Contract 155](#_Toc454885056)

[14. Employer’s Responsibilities 155](#_Toc454885057)

[15. Confidential Information 156](#_Toc454885058)

[C. Execution of Works and Services 157](#_Toc454885059)

[16. Representatives 157](#_Toc454885060)

[17. Work Program 159](#_Toc454885061)

[18. Execution of Works 160](#_Toc454885062)

[19. Staff and Labor 162](#_Toc454885063)

[20. Test and Inspection 165](#_Toc454885064)

[21. Rehabilitation Works 167](#_Toc454885065)

[22. Improvement Works 167](#_Toc454885066)

[23. Maintenance Services 167](#_Toc454885067)

[24. Performance Standards 167](#_Toc454885068)

[25. Contractor’s Self-Control of Quality and Safety 168](#_Toc454885069)

[26. Environmental and Safety Requirements 168](#_Toc454885070)

[27. Work Orders for Improvement Works and Emergency Works 170](#_Toc454885071)

[28. Taking Over Procedures 170](#_Toc454885072)

[29. Emergency Works 171](#_Toc454885073)

[30. Quality of materials used by Contractor 172](#_Toc454885074)

[31. Signalling and demarcation of work zones and bypasses 173](#_Toc454885075)

[D. Allocation of Risks 173](#_Toc454885076)

[32. Employer’s Risks 173](#_Toc454885077)

[33. Contractor’s Risks 174](#_Toc454885078)

[34. Loss of or Damage to Property; Accident or Injury to Workers; Indemnification 174](#_Toc454885079)

[35. Insurance 176](#_Toc454885080)

[36. Unforeseen Conditions 177](#_Toc454885081)

[37. Change in Laws and Regulations 178](#_Toc454885082)

[38. Force Majeure 179](#_Toc454885083)

[E. Guarantees and Liabilities 181](#_Toc454885084)

[39. Completion Time Guarantee and Liability 181](#_Toc454885085)

[40. Performance Guarantee and Liability 181](#_Toc454885086)

[41. Defect Liability 182](#_Toc454885087)

[42. Limitation of Liability 184](#_Toc454885088)

[43. Liability for Damages through Traffic Accidents and Traffic Interruptions 184](#_Toc454885089)

[F. Payment 184](#_Toc454885090)

[44. Contract Price 184](#_Toc454885091)

[45. Advance Payment 185](#_Toc454885092)

[46. Bill of Quantities 186](#_Toc454885093)

[47. Measurement 187](#_Toc454885094)

[48. Price Adjustments 187](#_Toc454885095)

[49. Monthly Statements and Payments 188](#_Toc454885096)

[50. Payments 189](#_Toc454885097)

[51. Retention and Reductions 189](#_Toc454885098)

[52. Taxes and Duties 190](#_Toc454885099)

[53. Securities 190](#_Toc454885100)

[54. Certificate of Completion 191](#_Toc454885101)

[55. Final Statement 191](#_Toc454885102)

[56. Discharge 192](#_Toc454885103)

[57. As Built Drawings and Manuals 192](#_Toc454885104)

[G. Remedies 192](#_Toc454885105)

[58. Suspension 192](#_Toc454885106)

[59. Termination 194](#_Toc454885107)

[H. Provisional Sum 200](#_Toc454885108)

[60. Provisional Sum 200](#_Toc454885109)

[61. Use of Provisional Sum for Emergency Works 200](#_Toc454885110)

[62. Use of Provisional Sum for Contingencies 200](#_Toc454885111)

[I. Change in Contract Elements 200](#_Toc454885112)

[63. Change in Assignments to Contractor 201](#_Toc454885113)

[64. Extension Time for Completion 205](#_Toc454885114)

[65. Release from Performance 206](#_Toc454885115)

A. Contract and Interpretation

|  |  |  |  |
| --- | --- | --- | --- |
| 1. Definitions | 1.1 Boldface type is used to identify defined terms.  **Bill of Quantities** means the priced and completed Bill of Quantities forming part of the Contractor’s Bid.  The **Certificate of Completion** is a document issued by the Project Manager upon completion of Rehabilitation Works, Improvement Works and Emergency Works, or parts thereof, as applicable, in accordance with GC 54.1  The **Completion Date** is the date of completion of the Services and Works as certified by the Project Manager, in accordance with Sub-Clause 10.2.  The **Contract** is the Contract between the Employer and the Contractor to perform the services to be provided by the Contractor, and to execute, complete, and maintain the Works. It consists of the documents listed in Clause 3 below.  The **Contractor** is a person or corporate body whose Bid to carry out the Works and Services has been accepted by the Employer.  The **Contractor’s Bid** is the completed bidding document submitted by the Contractor to the Employer.  The **Contract Price** is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.  **Days** are calendar days; **months** are calendar months.  A **Defect** is any part of the Works and Services not completed in accordance with the Contract.  The **Defects Liability Certificate** is the certificate issued by Project Manager upon correction of defects by the Contractor.  The **Defects Liability Period** is the period specified in the Contract and is applicable for Rehabilitation Works and Improvement Works, with exclusions identified in the PC, if any.  **Dispute Review Board (DRB)** is a board of three members selected and act in accordance with rules and procedures defined in the Contract to seek to resolve any dispute of any kind that may arise between the Employer and the Contractor in connection with or arising out of the Contract, as provided for in Clause 6 hereunder.  **Dispute Review Expert (DRE)** is one expert selected and acting in accordance with rules and procedures defined in the Contract to seek to resolve any dispute of any kind that may arise between the Employer and the Contractor in connection with or arising out of the contract, as provided for in Clause 6 hereunder.  **Drawings** include calculations and other information provided by the Contractor for the execution of the Contract.  **Emergency Works** is a set of necessary and sufficient activities to reinstate the Road and reconstruct its structure or right of way strip damaged as a result of natural phenomena with imponderable consequences, such as strong storms, flooding and earthquakes. The need for execution of Emergency Works is jointly identified by the Employer and the Contractor and for starting of execution of Emergency Works the Employer shall issue a Work Order.  The **Employer** is the party who employs the Contractor to carry out the Works and Services.  **Equipment** is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works and to carry out the Services.  **Improvement Works** consists of a set of interventions that add new characteristics to the Road in response to existing or new traffic, safety or other conditions, as defined in the Specifications.  **Rehabilitation Works** are specific and clearly defined civil works the Contractor is required to carry out under the conditions of the Contract, as defined in the Specifications. Rehabilitation Works quantities were estimated by the Contractor to achieve the performance standards defined by the Service Levels and offered at a Lump-Sum price.  The **Intended Completion Date** is the date on which it is intended that the Contractor shall complete the Works and Services. The Intended Completion Date is specified in the Particular Conditions (PC). The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time.  **Materials** are all supplies, including consumables, used by the Contractor for incorporation in the Works and for provision of Services.  The **Project Manager** is the person named in the PC who is responsible for the overall administration of the Contract on behalf of the Employer, and the supervision of works and services to be performed thereunder. The Project Manager may delegate through a written instrument some of his functions to any other competent person, retaining however the overall responsibility for the actions of that person. The Project Manager may not delegate the overall administrative control of the Contract.  **Road** means the road or network of roads for which the Works and Services are contracted under the Contract.  The **Road Management Office** is the location indicated by the Contractor from which the Road Manager operates, and where the Contractor shall receive notifications.  The **Road Manager** is a person appointed by the Contractor who is in charge of managing all activities of the Contractor under the Contract. He is also the Contractor’s Representative for the purposes of this contract.  **Services** means all interventions on the Road under the Contract and all activities related to the management and evaluation of the Road which shall be carried out by the Contractor in order to achieve and keep the Road Performance Standards as defined by the Service Levels, and to receive full payment of the monthly fee under the contract  **Service Levels** are the minimum performance standards for the level of quality of conditions of the Road defined in the Specifications which the Contractor shall comply with.  The **Site** is the area defined as such in the PC.  **Site Investigation Reports** are those that were included in the bidding document and are factual and interpretative reports about the surface and subsurface conditions at the Site.  The **Start Date** is the date when the Contractor has started the physical execution of the Works and Services on the site. It does not necessarily coincide with any of the Site Possession Dates.  A **Subcontractor** is a person or corporate body who has a contractual agreement with the Contractor to carry out certain activities related to the services to be provided under the contract, which may include work on the Site.  **Specifications** means the Specifications of the Works and Services included in the Contract and any modification or addition made or approved by the Project Manager.  A **Variation** is an instruction given by the Project Manager which varies the Works or Services.  The **Works** are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as covered under Rehabilitation Works, Improvement Works and Emergency Works.  **Work Order** is an order issued by the Project Manager to the Contractor authorizing the execution of Improvement Works and Emergency Works, as provided for in Clause 27 hereunder.  “ESHS” means environmental, social, health and safety (including labor, occupational and community health and safety, disaster and climate change, Indigenous People, vulnerable groups, gender, (SGBV), stakeholder engagement).  “SGBV” refers to any act that is perpetrated against a person’s will and is based on gender norms and unequal power relationships. It encompasses threats of violence, coercion, and harassment. It can be physical, emotional, psychological, or sexual in nature, and can take the form of a denial of resources or access to them. It includes sexual exploitation, abuse and harassment. It can affect persons at any age across the lifespan, and disproportionately affects women, | | |
| 2. Interpretation | 2.1 In interpreting these General Conditions (GC), singular also means plural, male also means female or neuter, and vice versa. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager will provide instructions clarifying queries about these General Conditions (GC). | | |
| 3. Documents Forming the Contract | 3.1 The documents forming the Contract shall be interpreted in the following order of priority:  (1) Agreement,  (2) Letter of Acceptance,  (3) Contractor’s Letter of Bid,  (4) Particular Conditions (PC),  (5) General Conditions (GC),  (6) Specifications,  (7) Drawings,  (8) Bill of Quantities, and  (9) any other document listed in the PC as forming part of the Contract. | | |
| 4. Language and Law | 4.1 The language of the Contract and the law governing the Contract are stated in the PC. | | |
| 5. Notices | 5.1 Unless otherwise stated in the Contract, all notices to be given under the Contract shall be in writing, and shall be sent by personal delivery, airmail post, special courier, or E-mail to the address of the relevant party set out in the PC, with the following provisions:  5.1.1 Any notice sent by E-mail shall be confirmed within two (2) days after dispatch by notice sent by airmail post or special courier, except as otherwise specified in the Contract.  5.1.2 Any notice sent by airmail post or special courier shall be deemed (in the absence of evidence of earlier receipt) to have been delivered ten (10) days after dispatch. In proving the fact of dispatch, it shall be sufficient to show that the envelope containing such notice was properly addressed, stamped and conveyed to the postal authorities or courier service for transmission by airmail or special courier.  5.1.3 Any notice delivered personally or sent by E-mail shall be deemed to have been delivered on date of its dispatch.  5.1.4 Either party may change its postal or E-mail address or addressee for receipt of such notices by ten (10) days’ notice to the other party in writing.   * 1. Notices shall be deemed to include any approvals, consents, instructions, orders and certificates to be given under the Contract.   5.3 The Contractor shall provide at its own cost, and maintain in operation permanently during the duration of the Contract, such communications equipment which ensures that both written (E-mail) and oral (voice) communications can be established at all times  (a) between the Road Manager and his senior field staff;  (b) between the Project Manager and the Road Manager;  (c) between the public telephone system and the Road Manager;  (d) The equipment to be provided and maintained includes the equipment located at the Project Manager’s office.  5.4 At the Start Date of the Contract, the Contractor must communicate to the Employer the address of his office, including the postal and E-mail address, which for the purposes of this contract is called the Road Management Office, where Notices will be addressed to. The Employer may require that the physical location of the Road Management Office is within the close geographical area of the Road. If the Contractor fails to communicate the address of his Road Management Office, and the Employer is otherwise unable to locate the Road Manager, all notifications to the Contractor shall be valid if they are deposited at a designated location within the office of the Project Manager, and if a copy is sent to the Contractor’s legal address. | | |
| 6. Settlement of Disputes (Alternative when using a Dispute Review Board) | 6.1 Dispute Review Board (DRB)  6.1.1 If any dispute of any kind whatsoever shall arise between the Employer and the Contractor in connection with or arising out of the Contract, including without prejudice to the generality of the foregoing, any question regarding its existence, validity or termination, or the execution of the Works and Services—whether during the progress of the execution or after completion and whether before or after the termination, abandonment or breach of the Contract—the parties shall seek to resolve any such dispute or difference by mutual consultation. If the parties fail to resolve such a dispute or difference by mutual consultation, then the matter in dispute shall, in the first place, be referred in writing by either party to the Disputes Review Board (‘the Board’), with a copy to the other party.  6.1.2 The Board shall be established when each of the three Board Members has signed a Board Member’s Declaration of Acceptance as required by the DRB’s Rules and Procedures (which, along with the Declaration of Acceptance form, are attached to the Contract). The Board shall comprise three Members experienced with the type of construction and services involved in the Contract and with the interpreta­tion of contractual documents. One Member shall be selected by each of the Employer and the Contractor and approved by the other. If either of these Members is not so selected and approved within 28 days of the date of the Letter of Acceptance, then upon the request of either or both parties such Member shall be selected as soon as practicable by the Appointing Authority specified in the PC. The third Member shall be selected by the other two and approved by the parties. If the two Members selected by or on behalf of the parties fail to select the third Member within 14 days after the later of their selections, or if within 14 days after the selection of the third Member, the parties fail to approve that Member, then upon the request of either or both parties such third Member shall be selected promptly by the same Appointing Authority specified in the PC who shall seek the approval of the proposed third Member by the parties before selection but, failing such approval, nevertheless shall select the third Member. The third Member shall serve as Chairman of the Board.  6.1.3 In the event of death, disability, or resignation of any Member, such Member shall be replaced in the same manner as the Member being replaced was selected. If for whatever other reason a Member shall fail or be unable to serve, the Chairman (or failing the action of the Chairman then either of the other Members) shall inform the parties and such nonserving Member shall be replaced in the same manner as the Member being replaced was selected. Any replacement made by the parties shall be completed within 28 days after the event giving rise to the vacancy on the Board, failing which the replacement shall be made by the Appointing Authority in the same manner as described above. Replacement shall be considered completed when the new Member signs the Board Member’s Declaration of Acceptance. Throughout any replace­ment process the Members not being replaced shall continue to serve and the Board shall continue to function and its activities shall have the same force and effect as if the vacancy had not occurred, provided, however, that the Board shall not conduct a hearing nor issue a Recommendation until the replacement is completed.  6.1.4 Either the Employer or the Contractor may refer a dispute to the Board in accordance with the provisions of the DRB’s Rules and Procedures, attached to the Contract. The Recommendation of the Board shall be binding on both parties, who shall promptly give effect to it unless and until the same shall be revised, as hereinafter provided, in an arbitral award. Unless the Contract has already been repudiated or terminated, the Contractor shall continue to proceed with the Works and Services in accordance with the Contract.  6.1.5 If either the Employer or the Contractor is dissatisfied with any Recommendation of the Board, or if the Board fails to issue its Recommendation within 56 days after receipt by the Chairman of the Board of the written Request for Recommendation, then either the Employer or the Contractor may, within 14 days after his receipt of the Recommendation, or within 14 days after the expiry of the said 56-day period, as the case may be, give notice to the other party of his intention to commence arbitration, as hereinafter provided, as to the matter in dispute. Such notice shall establish the entitlement of the party giving the same to commence arbitration, as hereinafter provided, as to such dispute and, subject to Sub-Clause 6.3, no arbitration in respect thereof may be commenced unless such notice is given.  6.1.6 If the Board has issued a Recommendation to the Employer and the Contractor within the said 56 days and no notice of intention to commence arbitration as to such dispute has been given by either the Employer or the Contractor within 14 days after the parties received such Recommendation from the Board, the Recommendation shall become final and binding upon the Employer and the Contractor.  6.1.7 Whether or not it has become final and binding upon the Employer and the Contractor, a Recommendation shall be admissible as evidence in any subsequent dispute resolution procedure, including any arbitration or litigation having any relation to the dispute to which the Recommendation relates.  6.1.8 All Recommendations that have become final and binding shall be implemented by the parties forthwith.  6.2 Arbitration  6.2.1 If either the Employer or the Contractor is dissatisfied with the Board’s decision, then either the Employer or the Contractor may, in accordance with Sub-Clause 6.1.5, give notice to the other party of its intention to commence arbitration, as hereinafter provided, as to the matter in dispute, and no arbitration in respect of this matter may be commenced unless such notice is given. The arbitral tribunal shall have full power to open up, review, and revise any decision, opinion, instruction, determination, certificate, and any Recommendation(s) of the Board.  6.2.2 Any dispute in respect of which a notice of intention to commence arbitration has been given, in accordance with GC Sub-Clause 6.2.1, shall be finally settled by arbitration. Neither party shall be limited in the proceedings before such arbitration tribunal to the evidence or arguments put before the Board for the purpose of obtaining his Recommendation(s) pursuant to Sub-Clause 6.2.1. No Recommendation shall disqualify the Board from being called as a witness and giving evidence before the arbitrator(s) on any matter whatsoever relevant to the dispute Arbitration may be commenced prior to or after completion of the Works and Services.  6.2.3 Arbitration proceedings shall be conducted in accordance with the rules of procedure designated in the PC.   * 1. Where neither the Employer nor the Contractor has given notice of intention to commence arbitration of a dispute within the period stated in Sub-Clause 6.1.5 and the related Recommendation has become final and binding, either party may, if the other party fails to comply with such Recommendation and without prejudice to any other right it may have, refer the failure to arbitration in accordance with Sub-Clause 6.2. The provisions of Sub-Clause 6.1 shall not apply to any such reference   6.4 Notwithstanding any reference to the Board or Arbitration herein,  (a) the parties shall continue to perform their respective obligations under the Contract unless they otherwise agree   1. the Employer shall pay the Contractor any monies due the Contractor. | | |
| 6. Settlement of Disputes (Alternative when using a Dispute Review Expert) | 6.1 Dispute Review Expert (DRE)  6.1.1 If any dispute of any kind whatsoever shall arise between the Employer and the Contractor in connection with or arising out of the Contract, including without prejudice to the generality of the foregoing, any question regarding its existence, validity or termination, or the execution of the Works and Services—whether during the progress of the execution or after completion and whether before or after the termination, abandonment or breach of the Contract—the parties shall seek to resolve any such dispute or difference by mutual consultation. If the parties fail to resolve such a dispute or difference by mutual consultation, then the matter in dispute shall, in the first place, be referred in writing by either party to the Disputes Review Expert (‘DRE’), with a copy to the other party.  6.1.2 The DRE shall take up his functions after having signed a DRE’s Declaration of Acceptance as required by the DRE’s Rules and Procedures (which, along with the Declaration of Acceptance form, are attached to the Contract). The DRE shall be a person experienced with the type of construction and services involved in the Contract and with the interpretation of contractual documents and shall be selected by agreement between the Employer and the Contractor. If the DRE is not selected within 28 days of the date of the Letter of Acceptance, then upon the request of either or both parties the DRE shall be selected as soon as practicable by the Appointing Authority specified in the PC.  6.1.3 In the event of death, disability, or resignation of the DRE, the latter shall be replaced by agreement between the Employer and the Contractor. Any replacement made by the parties shall be completed within 28 days after the event giving rise to the need for a replacement, failing which the replacement shall be made by the same Appointing Authority as above.  6.1.4 Either the Employer or the Contractor may refer a dispute to the DRE in accordance with the provisions of the DRE’s Rules and Procedures, attached to the Contract. The Recommendation of the DRE shall be binding on both parties, who shall promptly give effect to it unless and until the same shall be revised, as hereinafter provided, in an arbitral award. Unless the Contract has already been repudiated or terminated, the Contractor shall continue to proceed with the Works and Services in accordance with the Contract.  6.1.5 If either the Employer or the Contractor is dissatisfied with any Recommendation of the DRE, or if the DRE fails to issue his Recommendation within 56 days after he has received the written Request for Recommendation, then either the Employer or the Contractor may, within 14 days after his receipt of the Recommendation, or within 14 days after the expiry of the said 56-day period, as the case may be, give notice to the other party of his intention to commence arbitration, as hereinafter provided, as to the matter in dispute. Such notice shall establish the entitlement of the party giving the same to commence arbitration, as hereinafter provided, as to such dispute and, subject to Sub-Clause 6.3, no arbitration in respect thereof may be commenced unless such notice is given.  6.1.6 If the DRE has issued a Recommendation to the Employer and the Contractor within the said 56 days and no notice of intention to commence arbitration as to such dispute has been given by either the Employer or the Contractor within 14 days after the parties received such Recommendation from the DRE, the Recommendation shall become final and binding upon the Employer and the Contractor.  6.1.7 Whether or not it has become final and binding upon the Employer and the Contractor, a Recommendation shall be admissible as evidence in any subsequent dispute resolution procedure, including any arbitration or litigation having any relation to the dispute to which the Recommendation relates.  6.1.8 All Recommendations that have become final and binding shall be implemented by the parties forthwith.  6.2 Arbitration  6.2.1 If either the Employer or the Contractor is dissatisfied with the DRE’s decision, then either the Employer or the Contractor may, in accordance with Sub-Clause 6.1.5, give notice to the other party of its intention to commence arbitration, as hereinafter provided, as to the matter in dispute, and no arbitration in respect of this matter may be commenced unless such notice is given. The arbitral tribunal shall have full power to open up, review, and revise any decision, opinion, instruction, determination, certificate, and any Recommendation(s) of the DRE.  6.2.2 Any dispute in respect of which a notice of intention to commence arbitration has been given, in accordance with GC Sub-Clause 6.2.1, shall be finally settled by arbitration. Neither party shall be limited in the proceedings before such arbitration tribunal to the evidence or arguments put before the DRE for the purpose of obtaining his Recommendation(s) pursuant to Sub-Clause 6.2.1. No Recommendation shall disqualify the DRE from being called as a witness and giving evidence before the arbitrator(s) on any matter whatsoever relevant to the dispute Arbitration may be commenced prior to or after completion of the Works and Services.  6.2.3 Arbitration proceedings shall be conducted in accordance with the rules of procedure designated in the PC.  6.3 Where neither the Employer nor the Contractor has given notice of intention to commence arbitration of a dispute within the period stated in Sub-Clause 6.1.5 and the related Recommendation has become final and binding, either party may, if the other party fails to comply with such Recommendation and without prejudice to any other right it may have, refer the failure to arbitration in accordance with Sub-Clause 6.2. The provisions of Sub-Clause 6.1 shall not apply to any such reference.  6.4 Notwithstanding any reference to the DRE or Arbitration herein,   1. the parties shall continue to perform their respective obligations under the Contract unless they otherwise agree 2. the Employer shall pay the Contractor any monies due the Contractor. | | |
| B. Assignment of Responsibilities | | | |
| 7. Scope of Works and Services | 7.1 Unless otherwise expressly limited in the Specifications, the Contractor’s obligations cover the Design, the carrying out of all Works and the performance of all Services required for keeping the Road in accordance with the Service Levels defined in the Specifications, while at the same time respecting the plans, procedures, specifications, drawings, codes and any other documents as identified in the Specifications. Such specifications include, but are not limited to, the provision of supervision and engineering services; the supply of labor, materials, equipment; Contractor’s Equipment; construction utilities and supplies; temporary materials, structures and facilities; transportation (including, without limitation, unloading and hauling to, from and at the Site); and storage, except for those supplies, works and services that will be provided or performed by the Employer, if any, as set forth in the corresponding Specifications.  7.2 The Contractor shall, unless specifically excluded in the Contract, perform all such work, services and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining the Performance Standards (as specified in Clause 24 of GC) as if such work, services and/or items and materials were expressly mentioned in the Contract. | | |
| 8. Design Responsibility | 8.1 The Contractor shall be responsible for the design and programming of the Works and Services, and for the accuracy and completeness of the information used for that design and programming in accordance with the requirements established in the Specifications.  8.2 Specifications and Drawings  8.2.1 The Contractor shall execute the basic and detailed design and the engineering work in compliance with the provisions of the Contract and the Specifications, or where not so specified, in accordance with good engineering practice.  The Contractor shall be responsible for any discrepancies, errors or omissions in the specifications, drawings and other technical documents that it has prepared, whether such specifications, drawings and other documents have been approved by the Project Manager or not, provided that such discrepancies, errors or omissions are not because of inaccurate information furnished in writing to the Contractor by or on behalf of the Employer.  8.2.2 The Contractor shall be entitled to disclaim responsibility for any design, data, drawing, specification or other document, or any modification thereof, provided or designated by, or on behalf of, the Employer, by giving a notice of such disclaimer to the Project Manager.  8.3 Codes and Standards  Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of Bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied after approval by the Employer and shall be treated in accordance with GC Clause 63.  8.4 Approval/Review of Technical Documents by Project Manager  8.4.1 For those Works specified in the PC, the Contractor shall prepare (or cause its Subcontractors to prepare) and furnish to the Project Manager the documents listed in the Specifications (List of Documents for Approval or Review) for its approval or review.  Unless otherwise specified in the PC, the Contractor shall not be required to submit for the Employer’s approval the Design or other technical documents concerning the Maintenance Services remunerated through monthly lump-sum payments.  Any part of the Works covered by or related to the documents to be approved by the Project Manager shall be executed only after the Project Manager’s approval thereof.  GC Sub-Clauses 8.4.2 through 8.4.7 shall apply only to those documents requiring the Project Manager’s approval, but not to those furnished to the Project Manager for his information or review only.  8.4.2 Within fourteen (14) days after receipt by the Project Manager of any document requiring the Project Manager’s approval in accordance with GC Sub-Clause 8.4.1, the Project Manager shall either return one copy thereof to the Contractor with its approval endorsed thereon or shall notify the Contractor in writing of its disapproval thereof and the reasons therefore and the modifications that the Project Manager proposes.  If the Project Manager fails to take such action within the said fourteen (14) days, then the said document shall be deemed to have been approved by the Project Manager.  8.4.3 The Project Manager shall not disapprove any document, except on the grounds that the document does not comply with some specified provision of the Contract or that it is contrary to good engineering practice.  8.4.4 If the Project Manager disapproves the document, the Contractor shall modify the document and resubmit it for the Project Manager’s approval in accordance with GC Sub-Clause 8.4.2. If the Project Manager approves the document subject to modification(s), the Contractor shall make the required modification(s), whereupon the document shall be deemed to have been approved.  8.4.5 If any dispute or difference occurs between the Employer and the Contractor in connection with or arising out of the disapproval by the Project Manager of any document and/or any modification(s) thereto that cannot be settled between the parties within a reasonable period, then such dispute or difference may be referred to the DRB (or DRE) for determination in accordance with GC Sub-Clause 6.1 hereof. If such dispute or difference is referred to the DRB (or DRE), the Project Manager shall give instructions as to whether and if so, how, performance of the Contract is to proceed. The Contractor shall proceed with the Contract in accordance with the Project Manager’s instructions, provided that if the DRB (or DRE) upholds the Contractor’s view on the dispute and if the Employer has not given notice under GC Sub-Clause 6.1.5 hereof, then the Contractor shall be reimbursed by the Employer for any additional costs incurred by reason of such instructions and shall be relieved of such responsibility or liability in connection with the dispute and the execution of the instructions as the DRB (or DRE) shall decide, and the Time for Completion shall be extended accordingly.  8.4.6 The Project Manager’s approval, with or without modification of the document furnished by the Contractor, shall not relieve the Contractor of any responsibility or liability imposed upon it by any provisions of the Contract except to the extent that any subsequent failure results from modifications required by the Project Manager.  8.4.7 The Contractor shall not depart from any approved document unless the Contractor has first submitted to the Project Manageran amended document and obtained the Project Manager’s approval thereof, pursuant to the provisions of this GC Sub-Clause 8.4.  If the Project Manager requests any change in any already approved document and/or in any document based thereon, the provisions of GC Clause 63.2 shall apply to such request. | | |
| 9. Copyright | 9.1 The copyright in all drawings, documents and other materials containing data and information furnished to the Employer by the Contractor herein shall remain vested in the Contractor or, if they are furnished to the Employer directly or through the Contractor by any third party, including suppliers of materials, the copyright in such materials shall remain vested in such third party. | | |
| 10. Start Date and Completion | 10.1 The Contractor shall start the Works and Services within the period specified in the PC. Upon request from the Contractor, the Employer shall confirm in writing the Start Date, after verifying that works and services have started on the Site.  10.2 The Contractor shall attain the required Service Levels and the Completion of the Rehabilitation and Improvement Works (or of a part where a separate time for Completion of such part is specified in the Contract) within the time schedules included in the PC and the Specifications, or within such extended time to which the Contractor shall be entitled under GC Clause 64 hereof. | | |
| 11. Contractor’s Responsibilities | 11.1 The Contractor shall design and carry out the Works and Services (including associated purchases and/or subcontracting) necessary to comply with the requirements established in the Specifications with due care and diligence in accordance with the Contract.  11.2 The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Works and Services required, including any data and tests provided by the Employer, and on the basis of information that the Contractor could have obtained from a visual inspection of the Site and of other data readily available to it relating to the Road as of the date twenty-eight (28) days prior to Bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Works and Services.  11.3 The Contractor shall acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country of the Employer that are necessary for the performance of the Contract, including, without limitation, visas for the Contractor’s and Subcontractor’s personnel and entry permits for all imported Contractor’s Equipment. The Contractor shall acquire all other permits, approvals and/or licenses that are not the responsibility of the Employer under GC Sub-Clause 14.3 hereof and that are necessary for the performance of the Contract.   * 1. The Contractor shall comply with all laws in force in the country of the Employer and where the Works and Services are carried out. The laws will include all local, state, national or other laws that affect the performance of the Contract and bind upon the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such laws by the Contractor or its personnel, including the Subcontractors and their personnel, but without prejudice to GC Sub-Clause 14.1 hereof.   2. Any Plant, Material and Services that will be incorporated in or be required for the Works and Services and other supplies shall have their origin in an eligible Country as defined under the Bank’s procurement guidelines.   3. The Contractor shall keep, and shall make all reasonable efforts to cause its Subcontractors and subconsultants to keep, accurate and systematic accounts and records in respect of the Goods in such form and details as will clearly identify relevant time changes and costs.   4. Pursuant to paragraph 2.2 e. of Appendix A to the General Conditions, the Contractor shall permit and shall cause its subcontractors and subconsultants to permit, the Bank and/or persons appointed by the Bank to inspect the Site and/or the accounts and records relating to the procurement process, selection and/or contract execution, and to have such accounts and records audited by auditors appointed by the Bank if requested by the Bank. The Contractor’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 66.1 which provides, inter alia, that acts intended to materially impede the exercise of the Bank’s inspection and audit rights constitute a prohibited practice subject to contract termination (as well as to a determination of ineligibility pursuant to the Bank’s prevailing sanctions procedures). | | |
| 12. Subcontracting | * 1. The Contractor may subcontract activities listed in the PC. Any other activity under the Contract may be subcontracted only when approved by the Project Manager. The Contractor may not assign the entire Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations nor relieve the Contractor from any liability or obligation under the Contract and he shall be responsible for the acts, defaults and neglects of any Subcontractor, his agents, servants or workmen as fully as if they were the acts, defaults or neglects of the Contractor, his agents, servants or workmen.   2. Notwithstanding GC Sub-Clause 12.1, the Contractor may subcontract under his own responsibility and without prior approval of the Employer the small Works and Services also listed in the PC. | | |
| 13. Assignment of Contract | 13.1 Neither the Employer nor the Contractor shall, without the express prior written consent of the other party (which consent shall not be unreasonably withheld), assign to any third party the Contract or any part thereof, or any right, benefit, obligation or interest therein or thereunder, except that the Contractor shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract. | | |
| 14. Employer’s Responsibilities | 14.1 The Employer shall apply due diligence to ensure the accuracy of all information and/or data to be supplied to the Contractor as described in the Specifications, except when otherwise expressly stated in the Contract.  14.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the corresponding Specifications. The Employer shall give full possession of, and accord all rights of access thereto on or before the date(s) specified in the PC.  14.3 The Employer shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located, when such authorities or undertakings require the Employer to obtain them in the Employer’s name, are necessary for the execution of the Contract, and are specified in the corresponding Specifications.  14.4 If requested by the Contractor, the Employer shall use its best endeavors to assist the Contractor in obtaining in a timely and expeditious manner all permits, approvals and/or licenses necessary for the execution of the Contract from all local, state or national government authorities or public service undertakings that such authorities or undertakings require the Contractor or Subcontractors or the personnel of the Contractor or Subcontractors, as the case may be, to obtain.  14.5 The Employer shall be responsible for the continued operation of the Road after Completion, in accordance with GC Sub-Clause 28, and shall be responsible for facilitating the Guarantee Test(s) for the Road, in accordance with GC Sub-Clause 20.  14.6 All costs and expenses involved in the performance of the obligations under this GC Clause 14 shall be the responsibility of the Employer, save those to be incurred by the Contractor with respect to the performance of Guarantee Tests, in accordance with GC Sub-Clause 20. | | |
| 15. Confidential Information | 15.1 The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other party hereto, divulge to any third party any documents, data or other information furnished directly or indirectly by the other party hereto in connection with the Contract, whether such information has been furnished prior to, during or following termination of the Contract. Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor under this GC Clause 15.  15.2 The Employer shall not use such documents, data and other information received from the Contractor for any purpose other than the operation and maintenance of the Road. Similarly, the Contractor shall not use such documents, data and other information received from the Employer for any purpose other than the design, procurement of Plant and Equipment, construction or such Works and Services as are required for the performance of the Contract.  15.3 The obligation of a party under GC Sub-Clauses 15.1 and 15.2 above, however, shall not apply to that information which  (a) now or hereafter enters the public domain through no fault of that party;  (b) can be proven to have been possessed by that party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other party hereto;  (c) otherwise lawfully becomes available to that party from a third party that has no obligation of confidentiality.  15.4 The above provisions of this GC Clause 15 shall not in any way modify any undertaking of confidentiality given by either of the parties hereto prior to the date of the Contract in respect of the Works and Services or any part thereof.  15.5 The provisions of this GC Clause 15 shall survive termination, for whatever reason, of the Contract. | | |
| C. Execution of Works and Services | | | |
| 16. Representa­tives | 16.1 Project Manager  If the Project Manager is not named in the Contract, then within fourteen (14) days of the issuance of the Letter of Acceptance by the Employer, the Employer shall appoint and notify the Contractor in writing of the name of the Project Manager. The Employer may from time to time appoint some other person as the Project Manager in place of the person previously so appointed, and shall give a notice of the name of such other person to the Contractor without delay. No such appointment shall be made at such a time or in such a manner as to impede the progress of the Works and Services. Such appointment shall only take effect upon receipt of such notice by the Contractor. The Project Manager shall represent and act for the Employer at all times during the period of the Contract. All notices, instructions, orders, certificates, approvals and all other communications under the Contract shall be given by the Project Manager, except as herein otherwise provided.  All notices, instructions, information and other communications given by the Contractor to the Employer under the Contract shall be given to the Project Manager, except as herein otherwise provided.  The Project Manager may delegate any of his duties and responsibilities to other people, except to the DRB members or DRE, after notifying the Contractor, and may cancel any delegation after notifying the Contractor.  16.2 Road Manager  16.2.1 If the Road Manager is not named in the Contract, then the Contractor shall appoint the Road Manager before the Start Date and shall request the Employer in writing to approve the person so appointed. If the Employer makes no objection to the appointment within fourteen (14) days, the Road Manager shall be deemed to have been approved. If the Employer objects to the appointment within fourteen (14) days giving the reason therefore, then the Contractor shall appoint a replacement within fourteen (14) days of such objection, and the foregoing provisions of this GC Sub-Clause 16.2.1 shall apply thereto.  16.2.2 The Road Manager shall represent and act for the Contractor at all times during the period of the Contract and shall give to the Project Manager all the Contractor’s notices, instructions, information and all other communications under the Contract. The Road Manager shall be in charge of the day-to-day management of the works and services to be provided under the contract on behalf of the Contractor, and shall have legal and all other faculties to take all necessary decisions related to the execution of the contract.  All notices, instructions, information and all other communications given by the Employer or the Project Manager to the Contractor under the Contract shall be given to the Road Manager or, in its absence, its deputy, except as herein otherwise provided.  The Contractor shall not revoke the appointment of the Road Manager without the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, the Contractor shall appoint some other person as the Road Manager, pursuant to the procedure set out in GC Sub-Clause 16.2.1.  16.2.3 The Road Manager may, subject to the approval of the Employer (which shall not be unreasonably withheld), at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice to the Project Manager signed by the Road Manager, and shall specify the powers, functions and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Project Manager.  Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GC Sub-Clause 16.2.3 shall be deemed to be an act or exercise by the Road Manager.  16.2.4 From the Start Date until Completion, the Road Manager shall supervise all work and services done at the Site by the Contractor and shall be present at the Site throughout normal working hours except when on leave, sick or absent for reasons connected with the proper performance of the Contract. Whenever the Road Manager is absent from the Site, a suitable person shall be appointed to act as his or her deputy.  16.2.5 The Employer may by notice to the Contractor object to any representative or person employed by the Contractor in the execution of the Contract who, in the reasonable opinion of the Employer, may behave inappropriately, may be incompetent or negligent, or may commit a serious breach of the Site regulations provided under the Specifications. The Employer shall provide evidence of the same, whereupon the Contractor shall remove such person from the Site.  16.2.6 If any representative or person employed by the Contractor is removed in accordance with GC Sub-Clause 16.2.5, the Contractor shall, where required, promptly appoint a replacement. | | |
| 17. Work Program | 17.1 Contractor’s Organization  The Contractor shall supply to the Project Manager a chart showing the proposed organization to be established by the Contractor for carrying out the Works and Services. The chart shall include the identities of the key personnel together with the curricula vitae of such key personnel to be employed as included in the Contractor’s Bid. The Contractor shall promptly inform the Project Manager in writing of any revision or alteration of such an organization chart.  17.2 Program of Performance  Not later than the Start Date, the Contractor shall prepare and supply to the Project Manager a program of performance of the Contract, made in the form specified in the Specifications and showing the sequence in which it proposes to design and carry out the Works and Services, as well as the date by which the Contractor reasonably requires that the Employer shall have fulfilled its obligations under the Contract so as to enable the Contractor to execute the Contract in accordance with the program and to achieve Completion in accordance with the Contract. The Contractor shall update and revise the program as and when appropriate, but without modification in the Times for Completion given in the PC and any extension granted in accordance with GC Clause 64, and shall supply all such revisions to the Project Manager.  17.3 Progress Report  The Contractor shall monitor progress of all the activities specified in the program referred to in GC Sub-Clause 17.2 above, and supply a progress report to the Project Manager every month together with his Monthly Statement. The progress report shall be in a form acceptable to the Project Manager in accordance with the Specifications.  17.4 Progress of Execution  If at any time the Contractor’s actual progress falls behind the program referred to in GC Sub-Clause 17.2, or it becomes apparent that it will so fall behind, the Contractor shall prepare and supply to the Project Manager a revised program, taking into account the prevailing circumstances, and shall notify the Project Manager of the steps being taken to expedite progress so as to attain Completion of the Works and Execution of Services activities within the Time for Completion under GC Sub-Clause 10.2, any extension thereof entitled under GC Sub-Clause 64, or any extended period as may otherwise be agreed upon between the Employer and the Contractor.  17.5 Work Procedures  The Contract shall be executed in accordance with the Contract Documents and the procedures given in the Specifications. | | |
| 18. Execution of Works | 18.1 Setting Out/Supervision/Labor  18.1.1 *Bench Mark.* The Contractor shall be responsible for the true and proper setting-out of the Works in relation to bench marks, reference marks and lines provided to it in writing by or on behalf of the Employer.  If, at any time during the progress of execution of the Works, any error shall appear in the position, level or alignment of the Works, the Contractor shall forthwith notify the Project Manager of such error and, at its own expense, immediately rectify such error to the reasonable satisfaction of the Project Manager. If such error is based on incorrect data provided in writing by or on behalf of the Employer, the expense of rectifying the same shall be borne by the Employer.  18.1.2 *Contractor’s Supervision.* The Contractor shall give or provide all necessary supervision during the execution of the Works, and the Road Manager or its deputy shall be on the Site to provide full-time supervision of the execution. The Contractor shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand.  18.2 Contractor’s Equipment  18.2.1 All Contractor’s Equipment brought by the Contractor onto the Site shall be deemed to be intended to be used exclusively for the execution of the Contract. The Contractor shall not remove the same from the Site without informing the Project Manager.  18.2.2 Unless otherwise specified in the Contract, upon completion of the Works and Services, the Contractor shall remove from the Site all Equipment brought by the Contractor onto the Site and any surplus materials remaining thereon.  18.2.3 The Employer will, if requested, use its best endeavors to assist the Contractor in obtaining any local, state or national government permission required by the Contractor for the export of the Contractor’s Equipment imported by the Contractor for use in the execution of the Contract that is no longer required for the execution of the Contract.  18.3 Site Regulations and Safety  The Employer and the Contractor shall establish Site regulations setting out the rules to be observed in the execution of the Contract at the Site and shall comply therewith. The Contractor shall prepare and submit to the Employer, with a copy to the Project Manager, proposed Site regulations for the Employer’s approval, which approval shall not be unreasonably withheld.  Such Site regulations shall include, but shall not be limited to, rules in respect of security, safety, traffic control, accident response, gate control, sanitation, medical care, fire prevention, waste management and closure of tailing pits.  18.4 Access to site for Other Contractors  18.4.1 The Contractor shall, upon written request from the Employer or the Project Manager, give site access to other contractors employed by the Employer on or near the site.  18.5 Site Clearance  18.5.1 *Site Clearance in Course of Execution*: In the course of carrying out the Contract, the Contractor shallkeep theSite reasonably free from all unnecessary obstruction, store or remove any surplus materials, clear away any wreckage, rubbish or temporary works from the Site, and remove any Contractor’s Equipment no longer required for execution of the Contract.  18.5.2 *Clearance of Site after Completion*: After Completion of all parts of the Works and Services, the Contractor shall clear away and remove all wreckage, rubbish and debris of any kind from the Site, and shall leave the Site and the Road clean and safe.  18.6 Watching and Lighting  The Contractor shall provide and maintain at its own expense alllighting, fencing, and watching when and where necessary for the proper execution and the protection of the Works and Services, for the protection of his own installations and his equipment, for the safety of the owners and occupiers of adjacent property and for the safety of the public.  18.7 Access to the Site  The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out.  18.8 Management Meetings  18.8.1 Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised by either the Contractor or the Employer.  18.8.2 The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either during or after the management meeting and stated in writing to all who attended the meeting. | | |
| 19. Staff and Labor | 19.1 The Contractor shall employ the key personnel named in the Contractor’s Bid, to carry out the functions stated in the Specifications or other personnel approved by the Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Contractor’s Bid.  19.2 Labor  (a) The Contractor shall provide and employ on the Site for the execution of the Works and Services such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. The Contractor is encouraged to use local labor that has the necessary skills.  (b) Unless otherwise provided in the Contract, the Contractor shall be responsible for the recruitment, transportation, accommodation and catering of all labor, local or expatriate, required for the execution of the Contract and for all payments in connection therewith.  (c) The Contractor shall be responsible for obtaining all necessary permit(s) and/or visa(s) from the appropriate authorities for the entry of all labor and personnel to be employed on the Site into the country where the Site is located.  (d) The Contractor shall at its own expense provide the means of repatriation to all of its and its Subcontractor’s personnel employed on the Contract at the Site to their various home countries. It shall also provide suitable temporary maintenance of all such persons from the cessation of their employment on the Contract to the date programmed for their departure. In the event that the Contractor defaults in providing such means of transportation and temporary maintenance, the Employer may provide the same to such personnel and recover the cost of doing so from the Contractor.  (e) The Contractor shall at all times during the progress of the Contract use its best endeavors to prevent any unlawful, riotous or disorderly conduct or behavior by or amongst its employees and the labor of its Subcontractors.  (f) The Contractor shall provide lodging, medical assistance, alimentation and sanitary installations for the employees living in the contractor’s base camps to comply with the Social, Sanitary and Health Conditions of Labor requirements established in the Specifications.  (g) The Contractor shall, in all dealings with its labor and the labor of its Subcontractors currently employed on or connected with the Contract, pay due regard to all recognized festivals, official holidays, religious or other customs and all local laws and regulations pertaining to the employment of labor.  (h) HIV-AIDS Prevention. If so indicated in the PC, the Contractor shall conduct an HIV-AIDS awareness programme via an approved service provider or specialized NGO, and shall undertake such other measures as are specified in this Contract to reduce the risk of the transfer of the HIV virus between and among the Contractor’s personnel (including Sub-Contractors) and the local community, to promote early diagnosis and to assist affected individuals. The Contractor shall throughout the contract: (i) conduct Information, Education and Consultation Communication (IEC) campaigns, at least every other month, addressed to all the Site staff and labor (including all the Contractor's employees, all Sub-Contractors and Consultants' employees working on the Site, and truck drivers and crew making deliveries to the Site for Works and Services executed under the contract, and to the immediate local communities, concerning the risks, dangers and impact, and appropriate avoidance behavior with respect to of Sexually Transmitted Diseases (STD)—or Sexually Transmitted Infections (STI) in general and HIV/AIDS in particular; (ii) provide male or female condoms for all Site staff and labor as appropriate; and (iii) provide for STI and HIV/AIDS screening, diagnosis, counseling and referral to a dedicated national STI and HIV/AIDS program, (unless otherwise agreed) of all Site staff and labor.  (i) If so indicated in the PC, the Contractor shall include in the program to be submitted for the execution of the Works and Services under Sub-Clause 17 a program for Site staff and labor and their families in respect of Sexually Transmitted Infections (STI) and Sexually Transmitted Diseases (STD) including HIV/AIDS. The STI, STD and HIV/AIDS alleviation program shall indicate when, how and at what cost the Contractor plans to satisfy the requirements of this Sub-Clause and the related specification. For each component, the program shall detail the resources to be provided or utilized and any related sub-contracting proposed. The program shall also include provision of a detailed cost estimate with supporting documentation. Payment to the Contractor for preparation and implementation this program shall not exceed the Provisional Sum dedicated for this purpose.  19.3 Removal of staff  If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract.  19.4 Work at Night and on Holidays  19.4.1 Unless otherwise provided in the Contract, if and when the Contractor considers it necessary to carry out work at night or on public holidays so as to meet the Service Levels and the Time for Completion, and requests the Employer’s consent thereto (if such consent is needed), the Employer shall not unreasonably withhold such consent. | | |
| 20. Test and Inspection | 20.1 The Contractor shall at its own expense carry out on the Site all such tests and/or inspections as are specified in the Specifications, and in accordance with the procedures described in the Specifications.  20.2 The Employer and the Project Manager or their designated representatives shall be entitled to attend the aforesaid test and/or inspection.  20.3 For tests to be carried out on the initiative of the Contractor, whenever the Contractor is ready to carry out any such test and/or inspection, he shall give a reasonable advance notice of such test and/or inspection and of the place and time thereof to the Project Manager. The Contractor shall provide the Project Manager with a signed report of the results of any such test and/or inspection.  20.4 If the Employer or Project Manager (or their designated representatives) fails to attend a scheduled test and/or inspection, or if it is agreed between the parties that such persons shall not attend, then the Contractor may proceed with the test and/or inspection in the absence of such persons, and may provide the Project Manager with a signed report of the results thereof.  20.5 The Project Manager may require the Contractor to carry out any test and/or inspection not required by the Contract, provided that the Contractor’s reasonable costs and expenses incurred in the carrying out of such test and/or inspection shall be added to the Contract Price. Further, if such test and/or inspection impedes the progress of the works and/or the Contractor’s performance of its other obligations under the Contract, due allowance will be made in respect of the Time for Completion and the other obligations so affected.  20.6 If Rehabilitation Works, Improvement Works or Emergency Works fail to pass any test and/or inspection, the Contractor shall either rectify or replace such works and shall repeat the test and/or inspection upon giving a notice under GC Sub-Clause 20.3.  20.7 If any dispute or difference of opinion shall arise between the parties in connection with or arising out of the test and/or inspection of the Works and Services, or part of them, that cannot be settled between the parties within a reasonable period of time, it may be referred to the RDB (or DRE) for determination in accordance with GC Sub-Clause 6.1.  20.8 The Contractor agrees that neither the execution of a test and/or inspection of the Works and Services or any part of them, nor the attendance by the Employer or the Project Manager, nor the issue of any test certificate pursuant to GC Sub-Clause 20.4, shall release the Contractor from any other responsibilities under the Contract.  20.9 No part or foundations shall be covered up on the Site without the Contractor carrying out any test and/or inspection required under the Contract. The Contractor shall give a reasonable notice to the Project Manager whenever any such part or foundations are ready or about to be ready for test and/or inspection; such test and/or inspection and notice thereof shall be subject to the requirements of the Contract.  20.10 The Contractor shall uncover any part of the Works or foundations, or shall make openings in or through the same as the Project Manager may from time to time require at the Site, and shall reinstate and make good such part or parts.  If any parts of the Works or foundations have been covered up at the Site after compliance with the requirement of GC Sub-Clause 20.9 and are found to be executed in accordance with the Contract, the expenses of uncovering, making openings in or through, reinstating, and making good the same shall be borne by the Employer, and the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been delayed or impeded in the performance of any of its obligations under the Contract. | | |
| 21. Rehabilitation Works | 21.1 If so indicated in the PC, specific Rehabilitation Works shall be carried out explicitly in accordance with the Specifications and as specified in the bidding document and in the Contractor’s Bid. Input quantities for Rehabilitation Works were estimated by the Contractor to achieve the performance criteria for Rehabilitation Works given in the Specifications. The specific Rehabilitation Works were offered by the Contractor at a Lump-Sum price. | | |
| 22. Improvement Works | * 1. If so indicated in the PC, Improvement Works are required and will consist of a set of interventions that add new characteristics to the roads in response to new traffic and safety or other conditions. Improvement Works quantities were offered at unit prices included in the Bill of Quantities.   2. The execution of Improvement Works shall be requested by the Project Manager, who will issue a Work Order defining the requested works to be carried out by the Contractor, based on the activities priced in the Bill of Quantities. The Work order shall specify the activities to be carried out and the corresponding price. The Road Manager shall confirm his acceptance by signing the Work Order. | | |
| 23. Maintenance Services | * 1. Maintenance Services are those activities necessary for keeping the Road in compliance with the Performance Standards pursuant to GC Clause 24. Maintenance Services shall include all activities required to achieve and keep the Road Performance Standards and Service Levels. These Services will be remunerated by Lump-Sum amount for the period of the contract paid in fixed monthly payments during the Maintenance Services period. | | |
| 24. Performance Standards | 24.1 The Contractor shall carry out the Maintenance Services to achieve and keep the Road complying with the Service Levels defined in the Specifications. He will carry out all Works in accordance with the performance standards indicated in the Specifications. | | |
| 25. Contractor’s Self-Control of Quality and Safety | * 1. The Contractor shall, throughout the execution and completion of the Works and Services, maintain a System which shall ensure that the work methods and procedures are adequate and safe at all times and do not pose any avoidable risks and dangers to the health, safety and property of the workers and agents employed by him or any of his subcontractors, of road users, of persons living in the vicinity of the roads under contract, and any other person who happens to be on or along the roads under contract.   2. Unless specified otherwise in the PC, the Contractor shall establish, within his own organizational structure, a specific Unit staffed with qualified personnel, whose task is to verify continuously the degree of compliance by the Contractor with the required Service Levels. That Unit will also be responsible for the generation and presentation of the information needed by the contractor for the documentation required as defined in the Specifications. The Unit will be responsible for maintaining a detailed and complete knowledge of the condition of the Road and to provide to the Road Manager all the information needed in order to efficiently manage and maintain the Road. The Unit shall also carry out, in close collaboration with the Project Manager, the verifications on the Service Levels.   3. The Contractor’s Self-Control Unit mentioned in GC Sub-Clause 25.2 shall report the level of compliance with the required Service Levels in the standard format presented in the Specifications. | | |
| 26. Environmental and Safety Requirements | 26.1 The Contractor shall, throughout the design, execution and completion of the Works and Services, and the remedying of any defects therein:   1. have full regard for the safety of all persons employed by him and his subcontractors and keep the Site (so far as the same is under his control) in an orderly state appropriate to the avoidance of danger to such persons; 2. provide and maintain at his own cost all guardrails, fencing, warning signs and watching, when and where necessary or required by Sub-Clause 18.3 of the Contract or by any duly constituted authority, for the protection of the Works and Services or for the safety and convenience of his workers and road users, the public or others; and 3. take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. | |
| 27. Work Orders for Improvement Works and Emergency Works | * 1. Improvement Works and Emergency Works shall be executed by the Contractor on the basis of Work Orders issued by the Project Manager.   2. Work Orders shall be issued in writing and shall include the date on which the Work Order was issued and the signature of the Project Manager. Two copies of the Work Order shall be transmitted by the Project Manager to the Contractor, who shall immediately countersign one copy, including the date of acceptance, and return it to the Project Manager.   3. If the Contractor has any objection to a Work Order, the Road Manager shall notify the Project Manager of his reasons for such objection within ten (10) days) of the date of issuing the Work Order. Within five (5) days of the Road Manager’s objection, the Project Manager shall cancel, modify or confirm the Work Order in writing. | | |
| 28. Taking Over Procedures | 28.1 When the whole of the Works and Services have been substantially completed and have satisfactorily passed any Tests on Completion prescribed by the Contract, the Contractor may give a notice to that effect to the Project Manager, accompanied by a written undertaking to finish with due expedition any outstanding work during the Defects Liability Period. Such notice and undertaking shall be deemed to be a request by the Contractor for the Project Manager to issue a Taking-Over Certificate in respect of the Works and Services. The Project Manager shall, within twenty-one (21) days of the date of delivery of such notice, either issue to the Contractor a Taking-Over Certificate, stating the date on which the Works and Services were substantially completed in accordance with the Contract, or give instructions in writing to the Contractor specifying all the conditions to be complied with and all the work which is required to be done by the Contractor before the issue of such Certificate. The Project Manager shall also notify the Contractor of any defects in the Works and Services affecting substantial completion that may appear after such instructions and before completion of Taking-Over Certificate within twenty-one (21) days of completion, to the satisfaction of the Project Manager, of the Works and Services so specified and remedying any defects so notified.  28.2 Similarly, in accordance with the procedure set out in Sub-Clause 28.1, the Contractor may request and the Project Manager shall issue a Taking-Over Certificate in respect of:  (a) any Section in respect of which a separate Time for Completion is provided in the contract,  (b) any substantial part of the Works and Services which both has been completed to the satisfaction of the Project Manager and, otherwise than as provided for in the Contract, occupied or used by the Employer, or  (c) any part of the Works and Services which the Employer has elected to occupy or use prior to completion (where such prior occupation or use is not provided for in the Contract or has not been agreed by the Contractor as a temporary measure). | | |
| 29. Emergency Works | 29.1 The need for execution of Emergency Works is jointly identified by the Employer and the Contractor and the starting of the execution of Emergency Works shall always require a Work Order issued by the Project Manager.  29.2 The execution of Emergency Works shall be requested by the Contractor based on losses or damages occurred as a result of natural phenomena (such as strong storms, flooding or earthquakes) with imponderable consequences, or on the possibility of damages or losses occurring, or the safety of individuals, works, services or equipment being at risk as result of the natural phenomena. In order to characterize the Emergency Works, the Contractor shall forward a Technical Report to the Project Manager requesting the execution of Emergency Works and characterizing the situation. On the basis of the said report, and of his own judgment of the situation, the Project Manager may issue a Work Order to the Contractor.  29.3 The Employer or even Government authorities may declare an Emergency Situation on the basis of local legislation. In those cases, the Project Manager may issue a Work Order for Emergency Works to the Contractor even without a request by the Contractor.   * 1. If the Contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine necessary in order to prevent damage to the Road. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Contractor in writing of such emergency, the work done and the reasons, therefore. If the work done or caused to be done by the Employer is work that the Contractor was liable to do at its own expense under the Contract, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Contractor to the Employer. Otherwise, the cost of such remedial work shall be borne by the Employer. | | |
| 30. Quality of materials used by Contractor | 30.1 The quality of materials used by the Contractor for the execution of the Contract shall be in compliance with the requirements of the Specifications. If the Contractor is of the opinion that materials of higher quality than those stated in the Specifications need to be used in order to ensure compliance with the Contract, he shall use such better materials, without being entitled to higher prices or remunerations.  30.2 Under no circumstances may the Contractor make any claim based on the insufficient quality of materials used by him, even if the material used was authorized by the Project Manager.  30.3 The Contractor shall carry out at his own cost the laboratory and other tests that he needs to verify if materials to be used comply with the Specifications, and shall keep records of such tests. If requested by the Project Manager, the Contractor shall hand over the results of the tests. | | |
| 31. Signaling and demarcation of work zones and bypasses | * 1. To ensure the safety of road users, including non-motorized road users and pedestrians, the Contractor is responsible to install and maintain at his cost the adequate signaling and demarcation of work sites, which in addition must comply with the applicable legislation.   2. If the execution of services and works under the contract is likely to interfere with traffic, the Contractor shall take at his cost the measures necessary to limit such interference to the strict minimum, or any danger to the workers or others. For that purpose, he is entitled to install, within the right-of-way of the road, temporary bypasses, structures or other modifications to be used by traffic during the execution of works and services. The Contractor shall notify the Project Manager of any such temporary installations.   3. If the execution of Works and Services by the Contractor makes it necessary to temporarily close a road section, and a traffic detour has to be implemented over other public roads or streets, the Contractor shall be responsible for the adequate signaling of the detour, under the same conditions as stated in GC Sub-Clause 31.1.   4. The Contractor shall inform the local authorities and the local police about such activities to be carried out by him which may cause any significant interruptions or changes to the normal traffic patterns. Such information shall be made in writing and at least seven (7) days before the beginning of such activities. Upon request from the Contractor, the Employer shall assist the Contractor in the coordination with the local authorities and the local police. | | |
| D. Allocation of Risks | | | |
| 32. Employer’s Risks | 32.1 From the Start Date until the Defects Correction Certificate has been issued, the following are Employer’s risks insofar as they directly affect the execution of the Works and Services included in this Contract:  (a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies;  (b) rebellion, revolution, insurrection, military or usurped power, or civil war;  (c) ionizing radiations, contamination by radioactivity from any nuclear fuel, or any nuclear waste from the combustion of nuclear fuel, radioactive toxic explosive or other hazardous properties of any explosive nuclear assembly or nuclear component thereof;  (d) riot, commotion or disorder, unless solely restricted to employees of the Contractor or of his Subcontractors and arising from the conduct of the Works and Services;  (e) loss or damage due to the use or occupation by the Employer of any unfinished Section or part of the Works, except as may be provided for in the Contract;  (f) any operation of the forces of nature against which an experienced contractor could not reasonably have been expected to take precautions. | | |
| 33. Contractor’s Risks | 33.1 The Employer carries the risks which this Contract states are Employer’s risks, and the remaining risks are the Contractor’s risks. | | |
| 34. Loss of or Damage to Property; Accident or Injury to Workers; Indemnifica­tion | 34.1 Subject to GC Sub-Clause 34.3, the Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property arising in connection with the execution and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents.  34.2 If any proceedings are brought or any claim is made against the Employer that might subject the Con tractor to liability under GC Sub-Clause 34.1, the Employer shall promptly give the Contractor a notice thereof and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim.  If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim.  The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing.  34.3 The Employer shall indemnify and hold harmless the Contractor and its employees, officers and Subcontractors from any liability for loss of or damage to property of the Employer, other than the Works not yet taken over, that is caused by fire, explosion or any other perils, in excess of the amount recoverable from insurances procured under GC Clause 35, provided that such fire, explosion or other perils were not caused by any act or failure of the Contractor.  34.4 The party entitled to the benefit of an indemnity under this GC Clause 34 shall take all reasonable measures to mitigate any loss or damage which has occurred. If the party fails to take such measures, the other party’s liabilities shall be correspondingly reduced. | | |
| 35. Insurance | 35.1 To the extent specified in the PC, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified in the said PC. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, who should not unreasonably withhold such approval.  (a) *Loss of or damage to the Plant and Materials*  Covering loss or damage occurring prior to Completion.  (b) *Third Party Liability Insurance*  Covering bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property occurring in connection with Works and Services.  (c) *Automobile Liability Insurance*  Covering use of all vehicles used by the Contractor or its Subcontractors (whether or not owned by them) in connection with the execution of the Contract.  (d) *Workers’ Compensation*  In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed.  (e) *Employer’s Liability*  In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed.  (f) *Other Insurances*  Such other insurances as may be specifically agreed upon by the parties.  35.2 The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 35.1, except for the Third-Party Liability, Workers’ Compensation and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 35.1 except for the Cargo Insurance During Transport, Workers’ Compensation and Employer’s Liability Insurances. All insurer’s rights of subrogation against such co-insured for losses or claims arising out of the performance of the Contract shall be waived under such policies.  35.3 The Contractor shall deliver to the Employer certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days’ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy.  35.4 The Contractor shall ensure that, where applicable, its Subcontractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Subcontractors are covered by the policies taken out by the Contractor.  35.5 If the Contractor fails to take out and/or maintain in effect the insurances referred to in GC Sub-Clause 35.1, the Employer may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Contractor under the Contract any premium that the Employer shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Contractor.  35.6 Unless otherwise provided in the Contract, the Contractor shall prepare and conduct all and any claims made under the policies effected by it pursuant to this GC Clause 35, and all monies payable by any insurers shall be paid to the Contractor. The Employer shall give to the Contractor all such reasonable assistance as may be required by the Contractor. With respect to insurance claims in which the Employer’s interest is involved, the Contractor shall not give any release or make any compromise with the insurer without the prior written consent of the Employer. With respect to insurance claims in which the Contractor’s interest is involved, the Employer shall not give any release or make any compromise with the insurer without the prior written consent of the Contractor. | | |
| 36. Unforeseen Conditions | 36.1 If, during the execution of the Contract, the Contractor shall encounter on the Site any physical conditions (other than climatic conditions) or artificial obstructions that could not have been reasonably foreseen prior to the date of the Contract Agreement by an experienced contractor on the basis of reasonable examination of the data relating to the Road (including any data and tests provided by the Employer), and on the basis of information that it could have obtained from a visual inspection of the Site or other data readily available to it relating to the Road, and if the Contractor determines that it will in consequence of such conditions or obstructions incur additional cost and expense or require additional time to perform its obligations under the Contract that would not have been required if such physical conditions or artificial obstructions had not been encountered, the Contractor shall promptly, and before performing additional work or using additional Plant and Equipment or Contractor’s Equipment, notify the Project Manager in writing of  (a) the physical conditions or artificial obstructions on the Site that could not have been reasonably foreseen;  (b) the additional work and/or Plant and Equipment and/or Contractor’s Equipment required, including the steps which the Contractor will or proposes to take to overcome such conditions or obstructions;  (c) the extent of the anticipated delay;  (d) the additional cost and expense that the Contractor is likely to incur.  On receiving any notice from the Contractor under this GC Sub-Clause 36.1, the Project Manager decide upon the actions to be taken to overcome the physical conditions or artificial obstructions encountered. Following such consultations, the Project Manager shall instruct the Contractor, with a copy to the Employer, of the actions to be taken.  36.2 Any reasonable additional cost and expense incurred by the Contractor in following the instructions from the Project Manager to overcome such physical conditions or artificial obstructions referred to in GC Sub-Clause 36.1 shall be paid by the Employer to the Contractor as an addition to the Contract Price.  36.3 If the Contractor is delayed or impeded in the performance of the Contract because of any such physical conditions or artificial obstructions referred to in GC Sub-Clause 36.1, the Time for Completion shall be extended in accordance with GC Clause 64. | | |
| 37. Change in Laws and Regulations | 37.1 If, after the date twenty-eight (28) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the PC. | | |
| 38. Force Majeure | 38.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, insofar as they directly affect the execution of the Services and Works included in this Contract and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following:  (a) war, hostilities or warlike operations (whether a state of war be declared or not), invasion, act of foreign enemy and civil war;  (b) rebellion, revolution, insurrection, mutiny, usurpation of civil or military government, conspiracy, riot, civil commotion and terrorist acts;  (c) confiscation, nationalization, mobilization, commandeering, requisition by or under the order of any government or de jure or de facto authority or ruler or any other act or failure to act of any local state or national government authority;  (d) strike, sabotage, lockout, embargo, import restriction, port congestion, lack of usual means of public transportation and communication, industrial dispute, shipwreck, shortage or restriction of power supply, epidemics, quarantine and plague;  (e) earthquake, landslide, volcanic activity, fire, flood or inundation, tidal wave, typhoon or cyclone, hurricane, storm, lightning, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster;  (f) shortage of labor, materials or utilities where caused by circumstances that are themselves Force Majeure.  38.2 If either party is prevented, hindered or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event.  38.3 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GC Clause 64.  38.4 The party or parties affected by the event of Force Majeure shall use reasonable efforts to mitigate the effect thereof upon its or their performance of the Contract and to fulfill its or their obligations under the Contract, but without prejudice to either party’s right to terminate the Contract under GC Sub-Clause 38.6.  38.5 No delay or nonperformance by either party hereto caused by the occurrence of any event of Force Majeure shall  (a) constitute a default or breach of the Contract;  (b) give rise to any claim for damages or additional cost or expense occasioned thereby;  if and to the extent that such delay or nonperformance is caused by the occurrence of an event of Force Majeure.  38.6 If the performance of the Contract is substantially prevented, hindered or delayed for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of one or more events of Force Majeure during the currency of the Contract, the parties will attempt to develop a mutually satisfactory solution, failing which either party may terminate the Contract by giving a notice to the other, but without prejudice to either party’s right to terminate the Contract under GC Clause 59.  38.7 In the event of termination pursuant to GC Sub-Clause 38.6, the rights and obligations of the Employer and the Contractor shall be as specified in GC Sub-Clauses 59.1.2 and 59.1.3.  38.8 Notwithstanding GC Sub-Clause 38.5, Force Majeure shall not apply to any obligation of the Employer to make payments to the Contractor herein. | | |
| E. Guarantees and Liabilities | | | |
| 39. Completion Time Guarantee and Liability | 39.1 The Contractor guarantees that it shall attain specified Service Levels and the Completion of Rehabilitation and Improvement Works (or a part for which a separate time for completion is specified in the PC) within the time schedules specified in the PC and the Specifications, pursuant to GC Sub-Clause 10.2, or within such extended time to which the Contractor shall be entitled under GC Clause 64 hereof.  39.2 If the Contractor fails to attain specified Service Levels within the contractually agreed time schedules as given in the Specifications, the contractor shall receive reduced payments for Maintenance Services, for such default and not as a penalty, in accordance with the Specifications.  39.3 If the Contractor fails to attain the Completion of Rehabilitation and Improvement Works (or a part for which a separate time for completion is specified in the PC clause 39.1) within the contractually required time schedules, the contractor shall pay to the Employer liquidated damages for such default and not as a penalty, in accordance with the PC and the Specifications.  39.4 The payment reductions and liquidated damages indicated in GC 39.2 and 39.3 shall be the only monies due from the Contractor for such defaults, and they will be applied for every day of delay, in accordance with the PC and the Specifications. The aggregate amount of such liquidated damages and payment reductions shall in no event exceed the “aggregate liability” in accordance with GC Clause 42. The payment or deduction of such sums shall not relieve the Contractor from his obligation to complete the Works and Services, or from any other of his obligations and liabilities under the Contract. | | |
| 40. Performance Guarantee and Liability | 40.1 The Contractor guarantees that during the Performance Tests or Inspections for Rehabilitation and Improvement Works, and for Emergency Works, the Road and all parts thereof shall attain the Performance Standards specified in the corresponding Specifications.  40.2 If, for reasons attributable to the Contractor, the minimum level of the Performance Standards specified in the corresponding Specifications are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications and/or additions to the Road or any part thereof as may be necessary to meet at least the minimum level of such Standards. The Contractor shall notify the Employer upon completion of the necessary changes, modifications and/or additions, and shall request the Employer to repeat the Test or Inspection until the minimum level of the Standards has been met. If the Contractor eventually fails to meet the minimum level of Performance Standard, the Employer may consider termination of the Contract, pursuant to GC Sub-Clause 59.2.2.  40.3 If, for reasons attributable to the Contractor, the Performance Standards relating to Rehabilitation and Improvement Works specified in the corresponding Specifications are not attained either in whole or in part, the Contractor shall, at the Contractor’s choice, either  (a) make such changes, modifications and/or additions to the Works and Services or any part thereof that are necessary to attain the Performance Standards at its cost and expense, and shall request the Employer to repeat the Test, or  (b) pay liquidated damages to the Employer in respect of the Works and Services which fail to meet the Performance Standards in accordance with the provisions in the corresponding Specifications.  40.4 The payment of liquidated damages under GC Sub-Clause 40.3, up to the limitation of liability specified in the PC, shall completely satisfy the Contractor’s guarantees under GC Sub-Clause 40.1, and the Contractor shall have no further liability whatsoever to the Employer in respect thereof. Upon the payment of such liquidated damages by the Contractor, the Project Manager shall issue the Certificate of Completion for the Works or any part thereof in respect of which the liquidated damages have been so paid. | | |
| 41. Defect Liability | 41.1 The Contractor warrants that the Works and Services or any part thereof shall be free from defects in the design, engineering, materials and workmanship of the Works and Services executed.  41.2 The Defect Liability Period shall be twelve (12) months from the date of Completion of the Contract, or eighteen (18) months from the date of Certificate of Completion of the Works (or any part thereof), whichever occurs first, unless specified otherwise in the PC.  If during the Defect Liability Period any defect should be found in the design, engineering, materials and workmanship of the Works and Services executed by the Contractor, the Contractor shall promptly, in consultation and agreement with the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace or otherwise make good (as the Contractor shall, at its discretion, determine) such defect as well as any damage to the Road caused by such defect. The Contractor shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Road arising out of or resulting from improper operation or maintenance of the Road by the Employer after taking over.  41.3 The Contractor’s obligations under this GC Clause 41 shall not apply to  (a) any works or materials that have a normal life shorter than the Defect Liability Period stated herein;  (b) any designs, specifications or other data designed, supplied or specified by or on behalf of the Employer or any matters for which the Contractor has disclaimed responsibility herein;  (c) any other materials supplied or any other work executed by or on behalf of the Employer, except for the work executed by the Employer under GC Sub-Clause 41.6.  41.4 The Employer shall give the Contractor a notice stating the nature of any such defect together with all available evidence thereof, promptly following the discovery thereof. The Employer shall afford all reasonable opportunity for the Contractor to inspect any such defect.  41.5 The Employer shall afford the Contractor all necessary access to the Site to enable the Contractor to perform its obligations under this GC Clause 41. The Contractor may remove from the Site any Plant and Equipment that are defective if the nature of the defect is such that repairs cannot be expeditiously carried out at the Site.  41.6 If the Contractor fails to commence the work necessary to remedy such defect or any damage to the Road caused by such defect within a reasonable time (which shall in no event be considered to be less than fifteen (15) days), the Employer may, following notice to the Contractor, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Contractor or may be deducted by the Employer from any monies due the Contractor or claimed under the Performance Security.  41.7 If the Road or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Road or such part, as the case may be, shall be extended by a period equal to the period during which the Road or such part cannot be used because of any of the aforesaid reasons.  41.8 Except as provided in GC Clauses 40 and 41, the Contractor shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, in respect of defects in the Road or any part thereof, the Plant and Equipment, design or engineering or work executed that appear after Completion of the Works and Services, except where such defects are the result of the gross negligence, fraud, criminal or willful action of the Contractor. | | |
| 42. Limitation of Liability | 42.1 Except in cases of criminal negligence or willful misconduct,  (a) the Contractor shall not be liable to the Employer, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and  (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the limit specified in the PC. | | |
| 43. Liability for Damages through Traffic Accidents and Traffic Interruptions | 43.1 The Contractor cannot be held liable for losses or damages of any kind arising out of traffic accidents on the roads included in the Contract, unless those traffic accidents have been caused directly by potholes or other major defects of the Road covered by the Contract he failed to repair in a timely manner, criminal acts, willful misconduct or gross negligence of the Contractor.  43.2 Under no circumstances can the Contractor be held liable for losses or damages of any kind and to anyone arising out of interruptions of traffic or traffic delays on the road included in the Contract, including any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs. | | |
| F. Payment | | | |
| 44. Contract Price | 44.1 The Contract Price shall be as specified in the Form of Contract Agreement to be paid in the currencies indicated in the PC.  44.2 Unless indicated otherwise in the PC, and except in the event of a Change as provided for in the Contract, the Contract Price shall be:   1. For Rehabilitation Works, a firm lump sum not subject to any alteration, to be paid according to work progress; 2. For Maintenance Services, a firm lump sum to be paid in monthly installments; 3. For Improvement Works, the total price stated in the Bill of Quantities for this item; 4. For Emergency Works, the Provisional Sum reserved for this purpose.   44.3 The Contractor shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract. | | |
| 45. Advance Payment | 45.1 The Employer shall make advance payment to the Contractor of the amounts and by the date stated in the PC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment.  45.2 The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for the execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager.  45.3 The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works and Services on a payment basis as indicated in the PC. | | |
| 46. Bill of Quantities | 46.1 The Bill of Quantities shall contain items for Groups of Activities which include the provision of Services (measured by performance standards) and Works(measured by unit of outputs or of products). The Bill of Quantities for Works shall include, where applicable, the lump-sum and unit price for Rehabilitation Works, and unit rates for Improvement Works and for Emergency Works.  46.2 Maintenance Services shall be measured and billed separately and will be remunerated by lump-sum amount for the period of the contract, and paid in fixed monthly payments during the entire Contract period. The values for remuneration of the Maintenance Services are those stated in the Bill of Quantities.  46.3 Rehabilitation Works will be remunerated by Lump-Sum amount for the period of the contract, however, indicating the quantities of measurable outputs to be executed in order that the Road achieves the performance standards specified in the bidding document. Payments will be made in accordance with the execution of those measured outputs paid by executed works output. The prices shall be those stated in the Bill of Quantities.  46.4 Improvement Works will be remunerated after acceptance by the Employer and shall be paid according to the product unit price using the prices included in the Bill of Quantities.  46.5 Each Emergency Work Order issued by the Project Manager will include a lump-sum price for the works to be performed. The Lump-Sum price for the Emergency Works will be submitted by the Contractor to the Project Manager in each emergency pursuant to GC Clauses 29 and 61 and will be prepared based on the Specifications and on the unit prices included in the Bill of Quantities for Emergency Works, and will remunerate all Emergency Activities. The prices include compliance with all Performance Indices described in the Specifications. Once approved, Emergency Works will be paid as lump sum in accordance with the schedule of payment proposed by the Contractor for the specific Emergency and approved by the Employer.  46.6 The Bill of Quantities is used to calculate the Contract Price. The amounts for Maintenance Services and Rehabilitation Works are the Lump-Sum prices offered in the Contractor’s Bid. The Improvement Works amount included in the Contract is an estimate on the basis of the unit prices included in the Contractor’s Bid. The Provisional Sum included in the Contract Price is an estimate for use when authorized by the Employer for Emergency Works and contingencies. | | |
| 47. Measurement | * 1. Maintenance Services will not be measured in volume; however, its payment will be affected by compliance with the Performance Standards pursuant to GC Clause 24. Maintenance Services shall be billed in fixed monthly amounts as per the Bill of Quantities Lump-Sum amount for Maintenance Services, beginning from the Start Date. Payments will be made with Reductions if the Performance Standards are not achieved, as defined in the Specifications. The Reductions for non-compliance with the Performance Standards will be applied on a daily basis for the period under which the Road does not achieve the Performance Standards, in accordance with the methodology specified in the Specifications.   47.2 Rehabilitation Works will be measured on the basis indicated in the PC, based on the quantity of actual work outputs as defined in the Specifications, concluded by the Contractor and approved by the Project Manager. The prices shall be those stated in the Bill of Quantities.  47.3 Improvement Works will be measured on the basis indicated in the PC and in accordance with the unit of measurement used for product unit price included in the Bill of Quantities. The prices shall be those stated in the Bill of Quantities.  47.4 Emergency Works will not be measured and shall be billed in accordance with the Schedule of Payments agreed for each specific Emergency Work as approved by the Employer. | | |
| 48. Price Adjustments | 48.1 Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the PC. If so provided, the amounts certified in each payment certificate, after deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency. A separate formula of the type indicated below applies to each Contract currency:  **Pc = Ac + Bc Imc/Ioc**  where:  Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c”  Ac and Bc are coefficients[[21]](#footnote-22) specified in the PC, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c”, and  Imc is the index prevailing at the end of the month being invoiced and Ioc is the index prevailing twenty-eight (28) days before Bid opening for inputs payable; both in the specific currency “c”.  48.2 If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs. | | |
| 49. Monthly Statements and Payments | 49.1 The Contractor shall submit to the Project Manager monthly statements in the format indicated in the Specifications, of the estimated value of Maintenance Services, Rehabilitation Works, Improvement Works, and Emergency Works in separated items covering the Works and Services for the corresponding month.  49.2 The Project Manager shall check the Contractor’s monthly statement and certify within fourteen (14) days the amount to be paid to the Contractor.  49.3 The value of Services executed shall be certified by the Project Manager taking into account the monthly amount included in the Bill of Quantities for Maintenance Services and the achievement of the Performance Standards for the Maintenance Services adjusted for any payment reductions in accordance with GC Sub-Clause 47.1.  49.4 The value of Works executed shall be certified by the Project Manager taking into account the value of the quantities of products executed and the prices in the Bill of Quantities.  49.5 The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. | | |
| 50. Payments | 50.1 Payments shall be adjusted for deductions for advance payments, retention, and reductions for not achieving Performance Standards for Maintenance Services. The Employer shall pay the Contractor the amounts certified by the Project Manager in accordance with GC Clause 49, within twenty-eight (28) days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made.  50.2 If an amount certified is increased in a later certificate or as a result of an award by the DRB or DRE or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. The interest rate shall be determined as per Sub-Clause 50.1.  50.3 Unless otherwise stated, all payments and deductions will be paid or charged in the proportions of currencies comprising the Contract Price.  50.4 Items of the Works for which no rate or price has been entered in the Bill of Quantities will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. | | |
| 51. Retention and Reductions | 51.1 The Employer shall retain the percentage indicated in the PC from each payment due to the Contractor for Rehabilitation Works and Improvement Works, except for the types of works specified in the PC. The regular monthly lump-sum payments for performance-based Maintenance Services will not be subject to retentions, unless indicated in the PC.  51.2 On completion of the Rehabilitation and Improvement Works, half the total amount retained shall be repaid to the Contractor and the other half after twelve (12) months have passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor have been corrected before the end of this period.   * 1. On completion of the whole Works and Services, the Contractor may substitute retention money with an “on demand” Bank guarantee.   2. Reduction of monthly payments for Maintenance Services due to non-compliance with the Service Levels will be made as indicated in GC Sub-Clause 47.1. The amount of Reduction for the days in which the Road was not complying with the Performance Standards will not be paid or repaid, even after the Contractor re-establishes the quality levels to the standards required by the contract. | | |
| 52. Taxes and Duties | 52.1 Except as otherwise specifically provided in the Contract, the Contractor shall bear and pay all taxes, duties, levies and charges assessed on the Contractor, its Subcontractors or their employees by all municipal, state or national government authorities in connection with the Works and Services in and outside of the country where the Site is located.  52.2 If any tax exemptions, reductions, allowances or privileges may be available to the Contractor in the country where the Site is located, the Employer shall use its best endeavors to enable the Contractor to benefit from any such tax savings to the maximum allowable extent.  52.3 For the purpose of the Contract, it is agreed that the Contract Price specified in the Form of Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date twenty-eight (28) days prior to the date of Bid submission in the country where the Site is located (hereinafter called “Tax”). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Contractor, Subcontractors or their employees in connection with performance of the Contract, an equitable adjustment of the Contract Price shall be made to fully take into account any such change by addition to the Contract Price or deduction therefrom, as the case may be, in accordance with GC Clause 37 hereof. | | |
| 53. Securities | 53.1 Issuance of Securities  The Contractor shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner and form specified below.  53.2 Advance Payment Security  53.2.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to the advance payment calculated in accordance with the corresponding PC to the Contract Agreement, and in the same currency or currencies.  53.2.2 The security shall be in the form provided in the bidding document or in another form acceptable to the Employer. The amount of the security shall be reduced in proportion to the value of the Works and Services executed by and paid to the Contractor from time to time, and shall automatically become null and void when the full amount of the advance payment has been recovered by the Employer. The security shall be returned to the Contractor immediately after its expiration.  53.3 Performance Security  53.3.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security for the due performance of the Contract in the amount specified in the PC.  53.3.2 The security shall be denominated in the currency or currencies of the Contract, or in a freely convertible currency acceptable to the Employer, and shall be in one of the forms of guarantees provided in the bidding document, as stipulated by the Employer in the PC, or in another form acceptable to the Employer.  53.3.3 The security shall automatically become null and void, twelve (12) months after Completion of all Works and Services under the Contract, provided however, that if the Defects Liability Period has been extended on any part of the Works pursuant to GC Sub-Clause 41.8 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration. | | |
| 54. Certificate of Completion | 54.1 The Contractor shall request the Project Manager to issue a Certificate of Completion of the Rehabilitation Works, Improvement Works and Emergency Works, or parts thereof, as applicable, and the Project Manager will do so upon deciding that the work is completed. | | |
| 55. Final Statement | 55.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within fifty-six (56) days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within fifty-six (56) days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. | | |
| 56. Discharge | 56.1 Upon submission of the Final Statement, the Contractor shall give to the Project Manager, a written discharge confirming that the total of the Final Statement represents full and final settlement of all monies due to the Contractor arising out of or in respect of the Contract. Provided that such discharge shall become effective only after payment due under the Final Payment Certificate issued pursuant to Sub-Clause 55 has been made and the performance security referred to in Sub-Clause 53.3, if any, has been returned to the Contractor. | | |
| 57. As Built Drawings and Manuals | 57.1 If “as built” Drawings and/or manuals are required, the Contractor shall supply them by the dates stated in the PC.  57.2 If the Contractor does not supply the Drawings and/or manuals by the dates stated in the PC, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the PC from payments due to the Contractor. | | |
| G. Remedies | | | |
| 58. Suspension | 58.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Site and Works) until ordered in writing to resume such performance by the Project Manager.  If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor’s default or breach of the Contract, the Contractor’s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in accordance with GC Sub-Clause 63.1, excluding the performance of the suspended obligations from the Contract.  If the Employer fails to do so within such period, the Contractor may, by a further notice to the Project Manager, elect to treat the suspension as termination of the Contract under GC Sub-Clause 59.1.  58.2 If  (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the Contract, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GC Sub-Clause 50.1, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, or fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice; or  (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site, or failure to obtain any governmental permit under the Employer’s responsibility and necessary for the execution and/or completion of the Works and Services,  then the Contractor may by fourteen (14) days’ notice to the Employer suspend performance of all or any of its obligations under the Contract, or reduce the rate of progress.  58.3 If the Contractor’s performance of its obligations is suspended or the rate of progress is reduced pursuant to this GC Clause 58, then the Time for Completion shall be extended in accordance with GC Sub-Clause 64, and any and all additional costs or expenses incurred by the Contractor as a result of such suspension or reduction shall be paid by the Employer to the Contractor in addition to the Contract Price, except in the case of suspension order or reduction in the rate of progress by reason of the Contractor’s default or breach of the Contract.  58.4 During the period of suspension, the Contractor shall not remove from the Site any Plant and Equipment or any Contractor’s Equipment, without the prior written consent of the Employer. | | |
| 59. Termination | 59.1 Termination for Employer’s Convenience  59.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GC Sub-Clause 59.1.  59.1.2 Upon receipt of the notice of termination under GC Sub-Clause 59.1.1, the Contractor shall either immediately or upon the date specified in the notice of termination  (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Works and Services already executed, or any work required to leave the Site in a clean and safe condition,  (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) below,  (c) remove all Contractor’s Equipment from the Site, repatriate the Contractor’s and its Subcontractors’ personnel from the Site, remove from the Site any wreckage, rubbish and debris of any kind, and leave the whole of the Site in a clean and safe condition.  (d) In addition, the Contractor, subject to the payment specified in GC Sub-Clause 59.1.3, shall  (i) deliver to the Employer the parts of the Works executed by the Contractor up to the date of termination,  (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Works and Services and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors  (iii) deliver to the Employer all non-proprietary drawings, specifications and other documents prepared by the Contractor or its Subcontractors as at the date of termination in connection with the Works.  59.1.3 In the event of termination of the Contract under GC Sub-Clause 59.1.1, the Employer shall pay to the Contractor the following amounts:  (a) the Contract Price, properly attributable to the parts of the works and services executed by the Contractor as of the date of termination,  (b) the costs reasonably incurred by the Contractor in the removal of the Contractor’s Equipment from the Site and in the repatriation of the Contractor’s and its Subcontractors’ personnel,  (c) any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges,  (d) the costs incurred by the Contractor in protecting and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GC Sub-Clause 59.1.2,  (e) the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (d) above.  59.2 Termination for Contractor’s Default  59.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GC Sub-Clause 59.2:  (a) if the Contractor becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Contractor is a corporation, a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Contractor takes or suffers any other analogous action in consequence of debt;  (b) if the Contractor assigns or transfers the Contract or any right or interest therein in violation of the provision of GC Clause 13;  (c) if Contractor, in the judgment of the Employer has engaged in Prohibited Practices in competing for or in executing the Contract, as established in the Policies of the Inter-American Development Bank, indicated in Clause 66.1 of these GCC; and  (d) if the Contractor substantially prevents the exercise of the Bank's rights to perform audits, notwithstanding the provisions of Subclause 66.1 (f) of this Contract.  59.2.2 If the Contractor  (a) has abandoned or repudiated the Contract  (b) has without valid reason failed to commence work on the Road promptly or has suspended (other than pursuant to GC Sub-Clause 58.2) the progress of Contract performance for more than twenty-eight (28) days after receiving a written instruction from the Employer to proceed,  (c) persistently fails to execute the Contract in accordance with the Contract, such failure being defined in the PC, or persistently neglects otherwise to carry out its obligations under the Contract without just cause,  (d) refuses or is unable to provide sufficient materials, services or labor to execute and complete the Works and Services in the manner specified in the program furnished under GC Clause 17 at rates of progress that give reasonable assurance to the Employer that the Contractor can attain completion of the works and services by the Time for Completion as extended,  then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GC Sub-Clause 59.2.  59.2.3 Upon receipt of the notice of termination under GC Sub-Clauses 59.2.1 or 59.2.2, the Contractor shall, either immediately or upon such date as is specified in the notice of termination,   1. cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Works and Services already executed, or any work required to leave the Site in a clean and safe condition   (b) terminate all subcontracts, except those to be assigned to the Employer based on the Employer’s written request,  (c) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Works and Services.  59.2.4 The Contractor shall be entitled to be paid the Contract Price attributable to the Works and Services executed as of the date of termination, and the costs, if any, incurred in protecting and in leaving the Site in a clean and safe condition pursuant to paragraph (a) of GC Sub-Clause 59.2.3. Any sums due the Employer from the Contractor accruing prior to the date of termination shall be deducted from the amount to be paid to the Contractor under this Contract.  59.3 Termination by Contractor  59.3.1 If  (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to GC Clause 50, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GC Sub-Clause 50.2, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice, or  (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas or failure to obtain any governmental permit under the Employer’s responsibility and necessary for the execution and/or completion of the Works and Services,  then the Contractor may give a notice to the Employer thereof, and if the Employer has failed to pay the outstanding sum, to approve the invoice or supporting documents, to give its reasons for withholding such approval, or to remedy the breach within twenty-eight (28) days of such notice, or if the Contractor is still unable to carry out any of its obligations under the Contract for any reason attributable to the Employer within twenty-eight (28) days of the said notice, the Contractor may by a further notice to the Employer referring to this GC Sub-Clause 59.3.1, forthwith terminate the Contract.  59.3.2 The Contractor may terminate the Contract forthwith by giving a notice to the Employer to that effect, referring to this GC Sub-Clause 59.3.2, if the Employer becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, being a corporation, if a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Employer takes or suffers any other analogous action in consequence of debt.  59.3.3 If the Contract is terminated under GC Sub-Clauses 59.3.1 or 59.3.2, then the Contractor shall immediately  (a) cease all further work, except for such work as may be necessary for the purpose of protecting that part of the Road already executed, or any work required to leave the Site in a clean and safe condition,  (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii),  (c) remove all Contractor’s Equipment from the Site and repatriate the Contractor’s and its Subcontractors’ personnel from the Site.  (d) In addition, the Contractor, subject to the payment specified in GC Sub-Clause 59.3.4, shall  (i) deliver to the Employer the parts of the Road executed by the Contractor up to the date of termination,  (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Road and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors,  (iii) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Works and Services.  59.3.4 If the Contract is terminated under GC Sub-Clauses 59.3.1 or 59.3.2, the Employer shall pay to the Contractor all payments specified in GC Sub-Clause 59.1.3, and reasonable compensation for all loss, except for loss of profit, or damage sustained by the Contractor arising out of, in connection with or in consequence of such termination.  59.3.5 Termination by the Contractor pursuant to this GC Sub-Clause 59.3 is without prejudice to any other rights or remedies of the Contractor that may be exercised in lieu of or in addition to rights conferred by GC Sub-Clause 59.3.  59.4 In this GC Clause 59, in calculating any monies due from the Employer to the Contractor, account shall be taken of any sum previously paid by the Employer to the Contractor under the Contract, including any advance payment paid pursuant to the Contract. | | |
| H. Provisional Sum | | | | |
| 60. Provisional Sum | | 60.1 “Provisional Sum” means a sum included in the Contract for use when authorized by the Employer for Emergency Works and for contingencies, which sum may be used, in whole or in part, or not at all, on the instructions of the Employer. The Contractor shall be entitled to only such amounts in respect of the work, supply or contingencies to which such Provisional Sums relate as the Project Manager shall determine in accordance with this Clause. | | |
| 61. Use of Provisional Sum for Emergency Works | | 61.1 After detecting a situation which in the opinion of the Contractor justifies the execution of Emergency Works or otherwise as defined in GC Clause 29, the Contractor shall submit a Technical Report to the Project Manager characterizing the situation, and state estimated works quantities to correct the emergency situation, and a Lump Sum price quotation for the Emergency Works to be carried out. The price quotation should be based on the Specifications stated in Section VI using the unit prices included in the Bill of Quantities.  61.2 If the execution of the Emergency Works requires any activity not priced in the Bill of Quantities, the Contractor will use the price breakdowns included in the Contractor’s Bid in order to form the unit prices of the unpriced items to be included in the Price Quotation of the Emergency Works, all in accordance with agreed methodology for approving new prices.  61.3 Upon receiving the request for Emergency Works including a Price Quotation, the Project Manager may issue a Work Order in accordance with GC Sub-Clause 29.2 for execution of the Emergency Works for a Lump-Sum amount with a payment Schedule agreed with the Contractor. The cost of these Works will be covered by the amounts included in the Provisional Sum. | | |
| 62. Use of Provisional Sum for Contingen­cies | | 62.1 The use of the Provisional Sum to cover for Contingencies will be done under the control and initiative of the Project Manager in accordance with the conditions of the Contract. | | |
| I. Change in Contract Elements | | | | |
| 63. Change in Assignments to Contractor | | 63.1 Introducing a Change  63.1.1 If so indicated in the PC, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Assignments to the Contractor (hereinafter called “Change”), provided that such Change falls within the general scope of the Assignment and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Works and Services and the technical compatibility of the Change envisaged with the nature of the Works and Services as specified in the Contract.  63.1.2 If so indicated in the PC, the Contractor may from time to time during its performance of the Contract propose to the Employer (with a copy to the Project Manager) any Change that the Contractor considers necessary or desirable to improve the quality, efficiency or safety of the Works and Services. The Employer may at its discretion approve or reject any Change proposed by the Contractor.  63.1.3 Notwithstanding GC Sub-Clauses 63.1.1 and 63.1.2, no change made necessary because of any default of the Contractor in the performance of its obligations under the Contract shall be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Completion.  63.1.4 The procedure on how to proceed with and execute Changes is specified in GC Sub-Clauses 63.2 and 63.3, further details and sample forms are provided in the Sample Forms and Procedures section in the bidding documents.  63.2 Changes Originating from Employer  63.2.1 If the Employer proposes a Change pursuant to GC Sub-Clause 63.1.1, it shall send to the Contractor a “Request for Change Proposal,” requiring the Contractor to prepare and furnish to the Project Manager, as soon as reasonably practicable, a “Change Proposal,” which shall include the following:  (a) brief description of the Change  (b) effect on the Time for Completion  (c) estimated cost of the Change  (d) effect on Functional Guarantees (if any)  (e) effect on any other provisions of the Contract  63.2.2 Prior to preparing and submitting the “Change Proposal,” the Contractor shall submit to the Project Manager an “Estimate for Change Proposal,” which shall be an estimate of the cost of preparing and submitting the Change Proposal.  Upon receipt of the Contractor’s Estimate for Change Proposal, the Employer shall do one of the following:  (a) accept the Contractor’s estimate with instructions to the Contractor to proceed with the preparation of the Change Proposal,  (b) advise the Contractor of any part of its Estimate for Change Proposal that is unacceptable and request the Contractor to review its estimate,  (c) advise the Contractor that the Employer does not intend to proceed with the Change.  63.2.3 Upon receipt of the Employer’s instruction to proceed under GC Sub-Clause 63.2.2 (a), the Contractor shall, with proper expedition, proceed with the preparation of the Change Proposal, in accordance with GC Sub-Clause 63.2.1.  63.2.4 The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If such rates and prices are inequitable, the parties thereto shall agree on specific rates for the valuation of the Change.  63.2.5 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith, and with all other Change Orders that have already become binding upon the Contractor under this GC Clause 63, would be to increase or decrease the Contract Price as originally set forth in the Contract Agreement by more than fifteen percent (15%), the Contractor may give a written notice of objection thereto prior to furnishing the Change Proposal as aforesaid. If the Employer accepts the Contractor’s objection, the Employer shall withdraw the proposed Change and shall notify the Contractor in writing thereof.  The Contractor’s failure to so object shall neither affect its right to object to any subsequent requested Changes or Change Orders herein, nor affect its right to take into account, when making such subsequent objection, the percentage increase or decrease in the Contract Price that any Change not objected to by the Contractor represents.  63.2.6 Upon receipt of the Change Proposal, the Employer and the Contractor shall mutually agree upon all matters therein contained. Within fourteen (14) days after such agreement, the Employer shall, if it intends to proceed with the Change, issue the Contractor with a Change Order.  If the Employer is unable to reach a decision within fourteen (14) days, it shall notify the Contractor with details of when the Contractor can expect a decision.  If the Employer decides not to proceed with the Change for whatever reason, it shall, within the said period of fourteen (14) days, notify the Contractor accordingly. Under such circumstances, the Contractor shall be entitled to reimbursement of all costs reasonably incurred by it in the preparation of the Change Proposal, provided that these do not exceed the amount given by the Contractor in its Estimate for Change Proposal submitted in accordance with GC Sub-Clause 63.2.2.  63.2.7 If the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters identified in the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order.”  Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal.  If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the DRB or DRE in accordance with the provisions of GC Sub-Clause 6.1.  63.3 Changes Originating from Contractor  63.3.1 If the Contractor proposes a Change pursuant to GC Sub-Clause 63.1.2, the Contractor shall submit to the Project Manager a written “Application for Change Proposal,” giving reasons for the proposed Change and including the information specified in GC Sub-Clause 63.2.1.  Upon receipt of the Application for Change Proposal, the parties shall follow the procedures outlined in GC Sub-Clauses 63.2.6 and 63.2.7. However, should the Employer choose not to proceed, the Contractor shall not be entitled to recover the costs of preparing the Application for Change Proposal.  Value Engineering   * + 1. The Contractor may prepare, at its own cost, a value engineering proposal at any time during the performance of the contract. The value engineering proposal shall, at a minimum, include the following;   (a) the proposed change(s), and a description of the difference to the existing contract requirements;  (b) a full cost/benefit analysis of the proposed change(s) including a description and estimate of costs (including life cycle costs) the Employer may incur in implementing the value engineering proposal; and  (c) a description of any effect(s) of the change on performance/functionality.  The Employer may accept the value engineering proposal if the proposal demonstrates benefits that:  (a) accelerates the delivery period; or  (b) reduces the Contract Price or the life cycle costs to the Employer; or  (c) improves the quality, efficiency, safety or sustainability of the Road; or  (d) yields any other benefits to the Employer,  without compromising the necessary functions of the Road and Services.  If the value engineering proposal is approved by the Employer and results in:  (a) a reduction of the Contract Price; the amount to be paid to the Contractor shall be the percentage specified in the PC of the reduction in the Contract Price; or  (b) an increase in the Contract Price; but results in a reduction in life cycle costs due to any benefit described in (a) to (d) above, the amount to be paid to the Contractor shall be the full increase in the Contract Price. | | |
| 64. Extension Time for Completion | | 64.1 The Time(s) for Completion specified in the PC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following:  (a) any Change in the Works and Services as provided in GC Clause 63,  (b) any occurrence of Force Majeure as provided in GC Clause 38 and unforeseen conditions as provided in GC Clause 36,  (c) any suspension order given by the Employer under GC Clause 58,  (d) any changes in laws and regulations as provided in GC Clause 37, or  (e) any default or breach of the Contract by the Employer, or any activity, act or omission of any other contractors employed by the Employer, or  (f) any other matter specifically mentioned in the Contract  by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor.  64.2 Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to an DRB or DRE, pursuant to GC Sub-Clause 6.1.  64.3 The Contractor shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract. | | |
| 65. Release from Performance | | 65.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. | | |
| 66. Prohibited Practices | | 1. The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, including members of its personnel, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, *inter alia*, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and representatives or agents, irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank[[22]](#footnote-23) all suspected acts of Prohibited Practices of which they have knowledge or become aware both, during the bidding process and throughout the negotiation or execution of a contract. Prohibited Practices are: (i) corrupt practices; (ii) fraudulent practices; (iii) coercive practices; (iv) collusive practices; (v) obstructive practices; and (vi) misappropriation of funds. The Bank has established mechanisms to report allegations of Prohibited Practices. Any allegation shall be submitted to the Bank’s Office of Institutional Integrity (OII) for the appropriate investigation. The Bank has adopted procedures to sanction those who have incurred in Prohibited Practices. The Bank also entered into an agreement with other International Financial Institutions (IFIs) to mutually recognize debarment decisions. | | |
|  | | * + 1. For the purposes of this provision, the definitions of Prohibited Practices are as follows:   (i) “*corrupt practice*” is the offering, giving, receiving or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party;  (ii) “*fraudulent practice*” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation;  (iii) “*collusive practice*” is an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party;  (iv) “*coercive practice*” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;  (v) “*obstructive practice*” is  (i) destroying, falsifying, altering or concealing of evidence material to an IDB Group investigation, or making false statements to investigators with the intent to impede an IDB Group investigation;  (ii) threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to an IDB Group investigation or from pursuing the investigation, or  (iii) acts intended to impede the exercise of the IDB Group’s contractual rights of audit or inspection provided for under GC Clause 66.1(f) below or access to information; and  (vi) “*misappropriation*” is the use of IDB Group financing or resources for an improper or unauthorized purpose, committed either intentionally or through reckless disregard. | | |
|  | | * + 1. If, the Bank determines that at any stage of the procurement or implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, *inter alia*, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires, (including their respective officers, employees and representatives or agents irrespective of whether the attribution is express or implied) engaged in a Prohibited Practice during the award or implementation of the contract, the Bank may:   (i) not finance any proposal to award a contract for works, goods or services, and consulting services;  (ii) suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has engaged in a Prohibited Practice;  (iii) declare Misprocurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, *inter alia*, providing adequate notice to the Bank upon learning of the Prohibited Practice) within a time period which the Bank considers reasonable;  (iv) issue the firm, entity or individual a reprimand in the form of a formal letter of censure for its behavior;  (v) declare that a firm, entity, or individual is ineligible, either permanently or for a stated period of time, to participate and/or be awarded additional contracts financed with IDB Group resources;  (vi) impose other sanctions that it deems to be appropriate, among others, the restitution of funds and of fines equivalent to the reimbursement for costs associated with investigations and proceedings contemplated in the Sanctions Procedures. Such other sanctions may be imposed in addition to or in lieu of the sanctions referred above (the “above-mentioned” sanctions are reprimand and debarment/ineligibility);  (vii) extend the sanctions imposed on any individual, entity or firm that, directly or indirectly, owns or controls a sanctioned entity, is owned or controlled by a sanctioned entity or is the object of common ownership or control with a sanctioned entity, as well as to officials, employees, affiliates or representatives or agents of a sanctioned entity who also own a sanctioned entity and / or exercise control over a sanctioned entity, even if it has not been concluded that those parties directly incurred in a Prohibited Practice; and/or  (viii) refer the matter to appropriate law enforcement authorities. | | |
|  | | * + 1. The provisions of GC Clause 66.1 (b) (i) and (ii) shall also be applicable when such parties have been temporarily suspended from eligibility to be awarded additional contracts pending a final outcome of a sanction proceeding, or otherwise. | | |
|  | | * + 1. The imposition of any action to be taken by the Bank pursuant to the provisions referred to above may be made public.     2. Pursuant to the Agreement for Mutual Enforcement of Debarment Decisions entered into with other IFIs, any firm, entity or individual bidding for or participating in a Bank-financed activity or acting as bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, concessionaires, personnel of the Borrower (including grant Beneficiaries), Executing Agencies or Contracting Agencies, (including their respective officers, employees, representatives and agents, irrespective of whether the attribution is expressed or implied) may be subject to a sanction. For purposes of this paragraph the term “sanction” shall mean any debarment, conditions on future contracting or any publicly-disclosed action taken in response to a violation of an IFI’s applicable framework for addressing allegations of Prohibited Practices. | | |
|  | | * + 1. The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the submission of bids and contract performance as well as to have them audited by personnel appointed by the Bank. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its investigation. The Bank also requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires: (i) maintain all documents and records related to the Bank-financed activities for seven (7) years after completion of the work contemplated in the relevant contract; (ii) deliver any document necessary for the investigation of allegations of Prohibited Practices; and (iii) ensure that employees, representatives or agents of the applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers or concessionaires who have knowledge that the Bank financed the activities to respond to questions from Bank personnel or any properly designated investigator, agent, auditor or consultant relating to the investigation. If the applicant, bidder, supplier and its representative or agent, contractor, consultant, personnel, sub-contractor, sub-consultant, service provider or concessionaire fails to cooperate and/or comply with the Bank’s request, or otherwise obstructs the investigation, the Bank, discretionally, may take appropriate action against the applicant bidder, supplier and its agent or representative, contractor, consultant, personnel, sub-contractor, service provider or concessionaire. | | |
|  | | * + 1. If the Borrower procures goods or services, works or consulting services directly from a specialized agency, all provisions regarding Prohibited Practices and to the correspondent sanctions shall apply in their entirety to applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, and concessionaires, (including their respective officers, employees, and representatives or agents, irrespective of whether the agency is express or implied), or to any other entities that signed contracts with such specialized agency to supply such goods, works, or non-consulting services in connection with the Bank-financed activities. The Bank will retain the right to require the Borrower to invoke remedies such as contract suspension or termination. Specialized agencies shall consult the Bank’s list of suspended or debarred firms and individuals. In the event a specialized agency signs a contract or purchase order with a firm or an individual suspended or debarred by the Bank, the Bank will not finance the related expenditures and will apply other remedies as appropriate. | | |
|  | | 1. The Contractor represents and warrants: | | |
|  | | * + 1. that has read and understood the Bank’s definition of Prohibited Practices and the applicable sanctions pursuant to the Sanctions Procedures; | | |
|  | | * + 1. that has not engaged in any Prohibited Practice as set forth herein during the selection, negotiation, adjudication or execution of this contract; | | |
|  | | * + 1. that has not misrepresented or concealed any material facts during the procurement or contract negotiation processes or during the performance of the contract; | | |
|  | | * + 1. that neither they nor their representatives or agents, sub-contractors, sub-consultants, directors, key personnel or principal shareholders have been declared ineligible to be awarded a contract by the Bank | | |
|  | | * + 1. that all commissions, representative or agents’ fees, facilitating payments or revenue-sharing agreements related to the Bank-financed activities have been disclosed; and     2. that he acknowledges that the breach of any of these representations may constitute a basis for the adoption by the Bank of one or more of the measures set forth in GC Clause 66.1 (b). | | |

**APPENDIX A**

**Environmental, Social, Health and Safety (ESHS)**

**Metrics for Progress Reports**

***[Note to Employer: the following metrics may be amended to reflect the Project’s Environmental and Social Assessment (ESA), Project-specifc Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan (ESAP). . The metrics that are required should be determined by the ESHS risks of the Works and not necessarily by the scale of the Works]***

*Metrics for regular reporting:*

1. environmental and social incidents or non-compliances with contract requirements, including contamination, pollution or damage to ground or water supplies; inadequate use of force of security forces or allegations of SGBV and/or reprisals against stakeholders
2. occupational and community health and safety incidents, accidents, injuries *that require treatment* and all fatalities;
3. social incidents or non-compliances with contract requirements, including inadequate resettlement compensation, economic displacement without resolution;
4. interactions with regulators: identify agency, dates, subjects, outcomes (report the negative if none);
5. status of all permits and agreements:
6. work permits: number required, number received, actions taken for those not received;
7. status of permits and consents including from labor inspectorates, if applicable::

* *list areas/facilities with permits required (quarries, asphalt & batch plants), dates of application, dates issued (actions to follow up if not issued), dates submitted to resident engineer (or equivalent), status of area (waiting for permits, working, abandoned without reclamation, decommissioning plan being implemented, etc.);*
* *list areas with landowner agreements required (borrow and spoil areas, camp sites), dates of agreements, dates submitted to resident engineer (or equivalent)* *including requirements for Free Prior Informed Consent (FPIC) of indigenous peoples and/or their representatives, if applicable;*
* *;*
* *identify major activities undertaken in each area in the reporting period and highlights of environmental and social protection (land clearing, boundary marking, topsoil salvage, traffic management, decommissioning planning, decommissioning implementation);*
* *for quarries: status of relocation and compensation (completed, or details of activities and current status in the reporting period).*

1. health and safety supervision:
2. safety officer: number days worked, number of full inspections & partial inspections, reports to construction/project management;
3. number of workers, work hours, metric of Personal Protective Equipment (PPE) use (percentage of workers with full PPE, partial, etc.), worker violations observed (by type of violation, PPE or otherwise), warnings given, repeat warnings given, follow-up actions taken (if any);
4. violations of Code of Conduct and disciplinary measures taken
5. worker accommodations:
6. number of expats housed in accommodations, number of locals; dissagreated by workforce characteristics such as gender, vulnerable groups, etc
7. date of last inspection, and highlights of inspection including status of accommodations’ compliance with national and local law and good practice, including including access to canteens, hygiene facilities, and appropriate areas for rest, , etc.;
8. actions taken to recommend/require improved conditions, or to improve conditions.
9. HIV/AIDS: provider of health services, information and/or training, location of clinic, number of non-safety disease or illness treatments and diagnoses (no names to be provided);
10. gender (for expats and locals separately): number of female workers, percentage of workforce, gender issues raised and dealt with (cross-reference grievances or other sections as needed);
11. training:
12. number of new workers, number receiving induction training, dates of induction training;
13. number and dates of toolbox talks, number of workers receiving Occupational Health and Safety (OHS), environmental and social training;
14. number and dates of HIV/AIDS sensitization and/or training, no. workers receiving training (in the reporting period and in the past); same questions for gender sensitization, flag person training.
15. number and date of SGBV sensitization and/or training, number of workers receiving training on code of conduct (in the reporting period and in the past), etc.
16. environmental and social supervision:
17. environmentalist: days worked, areas inspected and numbers of inspections of each (road section, work camp, accommodations, quarries, borrow areas, spoil areas, swamps, forest crossings, etc.), highlights of activities/findings (including violations of environmental and/or social best practices, actions taken), reports to environmental and/or social specialist/construction/site management;
18. sociologist: days worked, number of partial and full site inspections (by area: road section, work camp, accommodations, quarries, borrow areas, spoil areas, clinic, HIV/AIDS center, community centers, grievance redress offices, etc.), regular meeting with community representatives and/or members, highlights of activities (including violations of environmental and/or social requirements observed, actions taken), reports to environmental and/or social specialist/construction/site management; and
19. community liaison person(s): days worked (hours community center open), number *of* people met, number of meetings held with communities as part of stakeholder engagement plan, highlights of activities (issues raised, solutions agreed upon and implemented, etc.), reports to environmental and/or social specialist /construction/site management.
20. Grievances: list new grievances (e.g. allegations of SGBV received in the reporting period and unresolved past grievances by date received, complainant, how received, to whom referred to for action, resolution and date (if completed), data resolution reported to complainant, any required follow-up, including any allegations of threat of violence or other forms of reprisals, (Cross-reference other sections as needed):
21. Worker grievances;
22. Stakeholder grievances
23. Traffic and vehicles/equipment:
24. traffic accidents involving project vehicles & equipment: provide date, location, damage, cause, follow-up;
25. accidents involving non-project vehicles or property (also reported under immediate metrics): provide date, location, damage, cause, follow-up;
26. overall condition of vehicles/equipment (subjective judgment by environmentalist); non-routine repairs and maintenance needed to improve safety and/or environmental performance (to control smoke, etc.).
27. Environmental mitigations and issues (what have been done):
28. dust: number of working bowsers, number of waterings/day, number of complaints, warnings given by environmentalist, actions taken to resolve; highlights of quarry dust control (covers, sprays, operational status); % of rock/ spoil lorries with covers, actions taken for uncovered vehicles;
29. noise: level of noise compared to maximum levels;
30. erosion control: controls implemented by location, status of water crossings, environmentalist inspections and results, actions taken to resolve issues, emergency repairs needed to control erosion/sedimentation;
31. quarries, borrow areas, spoil areas, asphalt plants, batch plants: identify major activities undertaken *in the reporting period* at each, and highlights of environmental and social protection: land clearing, boundary marking, topsoil salvage, traffic management, decommissioning planning, decommissioning implementation;
32. blasting: number of blasts (and locations), status of implementation of blasting plan (including notices, evacuations, etc.), incidents of off-site damage or complaints (cross-reference other sections as needed);
33. spill cleanups, if any: material spilled, location, amount, actions taken, material disposal (report all spills that result in water or soil contamination;
34. waste management: types and quantities generated and managed, including amount taken offsite (and by whom) or reused/recycled/disposed on-site;
35. details of tree plantings and other mitigations required undertaken *in the reporting period*;
36. details of water and swamp protection mitigations required undertaken *in the reporting period*.
37. compliance:
38. compliance status for conditions of all relevant consents/permits, for the Work, including quarries, etc.): statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance;
39. compliance status of C-ESMP and its specific ESHS management plans, including but not limited to Occupational Health and Safety Plan, Stakeholder Engagement Plan and/or Indigenous Peoples Plan requirements: statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance
40. compliance status of SGBV prevention and response action plan, if applicable: statement of compliance or listing of issues and actions taken (or to be taken) to reach compliance
41. other unresolved issues from previous reporting periods related to ESHS requirements : continued violations, continued failure of equipment, continued lack of vehicle covers, spills not dealt with, continued compensation or blasting issues, etc. Cross-reference other sections as needed.

|  |
| --- |
| Section VIII - Particular Conditions of Contract |

The following Particular Conditions shall supplement the GC. They are to be completed by the Employer and presented as part of the bidding document. Whenever there is a conflict, the provisions herein shall prevail over those in the GC.

**Reference to GC Clauses**

|  |  |
| --- | --- |
| **1.** | The site is the area *[insert description of* ***site location****]*  The name of the Project Manager is *[insert the* ***name*** *of the person appointed by the Employer as Project Manager].* |
|  | The following is added at the end of GC 1.1  “ESHS” means environmental, social health and safety (including labor, occupational and community health and safety, disaster and climate change, Indigenous People, vulnerable groups, gender, (SGBV), stakeholder engagement). that shall apply to the projects:  (a) IDB’s Environmental and Social Policy Framework[[23]](#footnote-24);  (b) IDB Access to Information Policy  “SGBV” refers to any act that is perpetrated against a person’s will and is based on gender norms and unequal power relationships. It encompasses threats of violence, coercion, and harassment. It can be physical, emotional, psychological, or sexual in nature, and can take the form of a denial of resources or access to them. It includes sexual exploitation, abuse and harassment. It inflicts harm on people of all genders. It can affect persons at any age across the lifespan, and disproportionately affects women, |
| **3.** | The following documents also form part of the Contract: *[list the following and any other relevant documents]*   1. the ESHS Management Strategies and Implementation Plans; and 2. Code of Conduct (ESHS).   According to Seccion APPENDIX A and Section VI - ENVIRONMENTAL, SOCIAL, HEALTH AND SAFETY REQUIREMENTS. |
| **4.** | The language of the Contract and the law governing the Contract is *[insert* ***language****]* |
| **5.** | The address of the Employer is: *[insert exact* ***street address****, including* ***telephone******number****, and* ***E-Mail address****]*  The address of the Contractor is: *[insert exact* ***street address****, including* ***telephone******number****, and* ***E-Mail address****]* |
| **6.** | Dispute Resolution Method used: *[insert either* ***DRB*** *or* ***DRE****]* |
| **6.1.2** | The Appointing Authority is: *[insert* ***name****]* |
| 6.2.3 | Arbitration Proceedings shall be conducted in accordance with the following rules of procedure: *[insert which* ***set of rules*** *is to be used]* |
| **8.4.1** | The Contractor is obliged to prepare and to furnish to the Project Manager for Approval the following documents: *[list* ***documents****]*  ***Note****: The documents to be furnished and needing approval by the Project Manager will be related to Improvement Works and in some cases to Rehabilitation Works.* |
| **10.1** | The Start Date shall be not later than *[insert* ***number****]* days after the issuance of the Letter of Acceptance by the Employer.  *`*  *[The recommended number of days is between 45 and 60, depending on local circumstances.]* |
| **10.1** | **ESHS Management Strategies and Implementation Plans**  The following is inserted at the end of 10.1:  “ Notwithstanding the Start Date as specified in this Sub-Clause, the Contractor shall not carry out any Works, including mobilization and/or pre-construction activities (e.g. limited clearance for haul roads, site accesses and work site establishment, geotechnical investigations or investigations to select ancillary features such as quarries and borrow pits), unless the Project Manager is satisfied that appropriate measures are in place to address ESHS risks and impacts including labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, gender, and sexual and gender-based violence (SGBV) and stakeholder engagement .  At a minimum, the Contractor shall apply the Management Strategies and Implementation Plans and Code of Conduct, submitted as part of the Bid and agreed as part of the Contract.  These Management Strategies and Implementation Plans collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP) that the Contractor shall submit, on a continuing basis, for the Project Managers No-objection, to manage the ESHS risks and impacts of the ongoing Works.  ‘  The C-ESMP will include procedures to identify and monitor the risk of child and forced labor and human trafficking and to identify, investigate and remedy cases of child and forced labor and human trafficking in the workforce of the Contractor and Sub-Contractors.  The C-ESMP will include an Occupational Health and Sfety Plan shall be approved prior to the commencement of construction activities (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture).  The approved C-ESMP shall be reviewed, periodically (but not less than every six (6) months), and updated in a timely manner, as required, by the Contractor to ensure that it contains measures appropriate to the Works activities to be undertaken and the ESHS risks identified. The updated C-ESMP shall be subject to prior approval by the Project Manager.” |
| **10.2** | The Time Schedule for the achievement of specific Service Levels is: *[insert* ***date*** *or indicate in which section or annex of the Contract the Time Schedule is presented]* |
| **12.1** | The Contractor is specifically allowed to subcontract the following activities: *[list* ***specific major activities*** *or* ***works*** *required under the contract]”* |
| **12.2** | The Contractor may subcontract under his own responsibility and without prior approval of the Employer the following Works and Services provided they do not represent more than *[insert* ***number****]* percentage of the contract value: *[list the* ***generic description of Works and Services*** *allowed to be subcontracted]*  ***Note:*** *Under normal circumstances, the Contractor should be allowed to subcontract without prior approval of the Employer all the small works related to normal and recurrent maintenance services. However, the Contractor should normally not be allowed to subcontract the management and self-control activities.* |
| **14.2** | The Employer shall give full possession of and access to the Site on *[insert* ***date*** *here]* |
| **17.3** | **ESHS Reporting**  Inserted at the end of GC 17.3:  “In addition to the progress report, the Contractor shall also provide a report on the Environmental, Social, Health and Safety (ESHS) metrics set out in Appendix A. In addition to Appendix A reports, the Contractor shall also provide immediate notification to the Project Manager of incidents in the following categories. Full details of such incidents shall be provided to the Project Manager within the timeframe agreed with the Project Manager.   * + 1. confirmed or likely violation of any law or international agreement;     2. any fatality, serious (lost time) injury; or significant health and safety risk     3. any cases of child or forced labor or human trafficking in the project workforce including those of Sub-Contractors     4. significant adverse effects or damage to private property (e.g. vehicle accident, damage from fly rock, working beyond the boundary).     5. significant adverse impact on the environment, including, without limitation, explosions, spills, pollution of drinking water aquifer or damage or destruction of rare or endangered habitat including protected areas or species. or     6. any allegation of SGBV, including but no limited to sexual exploitation or abuse, sexual harassment or sexual misbehavior, rape, sexual assault, child abuse, or defilement, or other violations involving children.     7. any allegation of threat of violence or other forms of reprisal against project stakeholders or the Contractor’s and Sub-contractor’s Personnel,      * + 1. any other event or circumstance having, or which could reasonably be foreseen to have, a material adverse impact on the implementation or operation of the Project in accordance with the ESHS Requirements.   Furthermore, the Contractor must digitize and systematize all progress reports of the work and shall deploy technology for the execution and monitoring of the Works and Services through a participatory digital platform that allows traceability and transparency of the Work and services (e.g.., drones, BIM, etc). |
| **19.1** | **Key Personnel**  The term “key personnel” in GC 19.1 is replaced by “Key Personnel”. Key Personnel are defined as the Contractor’s personnel named in the Particular Conditions of Contract.  [insert the name/s of each Key Personnel agreed by the Employer prior to Contract signature. |
| **19.2 (h) and (i)** | The provisions concerning HIV-AIDS prevention … *[insert “apply” or “do not apply”].*  *Note: The provisions should normally apply, except for very small contracts and/or under otherwise particular conditions.* |
| **19.3** | **Code of Conduct (ESHS)**  The following is inserted at the end of GC 19.3:  “The reasons to remove a person include behavior which breaches the Code of Conduct (ESHS) (e.g., SGBV, child abuse, illicit activity or crime).” |
| **21.** | The Contractor shall carry out the following Rehabilitation Works, which are detailed in the Specifications: *[insert* ***listing of Rehabilitation Works****]* |
| 22. | The Contractor shall carry out the following Improvement Works, which are detailed in the Specifications and Bill of Quantities: *[insert* ***listing of Improvement Work****s]* |
| 25.2 | The Contractor shall establish a Self-Control Unit *[insert “not” after “shall” if this Unit is not required]*  *[Note: The Self-control Unit should always be required, except for very small contracts.]* |
| **35.1** | The Contractor shall take out and maintain in effect the following insurances in the sums and deductibles shown below: *[insert* ***list of insurances****, including* ***sums*** *and* ***deductibles*** *of each insurance]* |
| **39.1** | The Time for Completion are the following: *[insert* ***dates*** *or* ***periods*** *for completion of specific activities required by the contract]*  ***Note****: Besides the date for completion of the entire contract, there may be specific times for the completion of Improvement or Rehabilitation Works.* |
| **39.3** | For **Rehabilitation Works**, the liquidated damages are *[insert* ***percentage****]* per calendar day of delay, of the payment normally due for the specific Works for which completion is delayed.  For **Improvement Works**, the liquidated damages are *[insert* ***percentage****]* per calendar day of delay, of the payment normally due for the specific Works for which completion is delayed. |
| **42.1** | The aggregate liability of the Contractor to the Employer, excluding payment reductions defined in GC 47.1, shall not exceed the amount of *[insert* ***fixed amount****, or* ***percentage of contract amount****]* |
| **44.1** | The payment of the Contract Price will be made in the following currencies*: [insert* ***currencies*** *and the* ***percentage of each currency****]* |
| 45.1 | The amount of the Advance Payment is *[insert* ***amount*** *or* ***percentage of Contract Price*** *as specified in the Form of Contract]*  The Advance payment will be made by [*insert* ***date*** *or* ***event****]* |
| 45.3 | The Advance payment will be repaid during the *[insert* ***number of payments****]* initial monthly payments at the rate of *[insert* ***percentage****]* percent of the amount advanced in each monthly payment until the repayment of the total amount. |
| **47.2** | Rehabilitation Works will be measured on the following basis: *[indicate]*  ***Note:*** *Rehabilitation Works should normally be measured on the basis of work outputs.* |
| **47.3** | Improvement Works will be measured on the following basis: *[indicate]*  ***Note:*** *Depending on their nature, Improvement Works may be measured on the basis of work outputs or work inputs.* |
| **48.** | Price adjustment *[indicate if applies / does not apply]*  The coefficients are:  Ac =  Bc = |
| **49.5**  **(add new 49.6)** | Add new GC 49.6:  “49.6 if the Contractor was, or is, failing to perform any ESHS obligations or work under the Contract, the value of this work or obligation, as determined by the Project Manager, may be withheld until the work or obligation has been performed, and/or the cost of rectification or replacement, as determined by the Project Manager, may be withheld until rectification or replacement has been completed. Failure to perform includes, but is not limited to the following:   1. failure to comply with any ESHS obligations or work described in the Works’ Requirements which may include: working outside site boundaries, excessive dust, failure to keep public roads in a safe usable condition, damage to offsite vegetation, pollution of water courses from oils or sedimentation, contamination of land e.g. from oils, human waste, damage to archeology or cultural heritage features, air pollution as a result of unauthorized and/or inefficient combustion; incidents of child or forced labor and human trafficking, inappropriate use of force of security forces, incidents of SGBV; 2. failure to regularly review C-ESMP and/or update it in a timely manner to address emerging ESHS issues, or anticipated risks or impacts; 3. failure to implement the C-ESMP e.g. failure to provide required training or sensitization; 4. failing to have appropriate consents/permits prior to undertaking Works or related activities; 5. failure to submit ESHS report/s (as described in Appendix A), or failure to submit such reports in a timely manner; 6. failure to implement remediation as instructed by the Project Manager within the specified timeframe (e.g. remediation addressing non-compliance/s). |
| **51.** | The retention for Rehabilitation and Improvement Works is fixed at *[indicate* ***percentage****]* percent.  The retention is not applicable to the following types of Rehabilitation and Improvement Works: *[list* ***types of works****, if any, such as regravelling].* |
| **53.2.1** | The amount of the Advance payment security is the same of the advance payment amount. |
| **53.3.1** | Replace GC 53.3.1 with the following  An Environmental, Social, Safety and Health (ESHS) Performance Security [‘*shall’ or ‘shall not’, choose either option consistent with the BDS*] be provided to the Employer.  [If an ESHS Security is required, replace GC 53.3.1 with the following otherwise delete.]  “GC 53.3.1 is replaced with the following  The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a Performance Security and an Environmental, Social, Safety and Health (ESHS) Performance Security for the due performance of the Contract in the amount specified in the Particular Conditions of Contract GC 53.3.1.” |
| **53.3.1** | The Performance Security amount is *[insert amount(s) denominated in the types and proportions of the currencies in which the Contract Price is payable, or in a freely convertible currency acceptable to the* Employer*]*  (a) Bank Guarantee: *[insert percentage and amount(s)]*.  (b) Performance Bond: *[insert percentage and amount(s)]*.  **[*Delete this provision if ESHS Performance Security is not required*]**  The ESHS Performance Security will be in the form of a “*demand guarantee”* in the amount(s) of *[insert % figure(s) normally in an amount of 1% to 3%* of the Accepted Contract Amount and in the same currency(ies) of the Accepted Contract Amount.  **[*The sum of the total “demand guarantees” (Performance Security and ESHS Performance Security) shall normally not exceed 10% of the Accepted Contract Amount.*]**  *[A* ***Bank Guarantee*** *shall be unconditional (on demand) (see Section X, Contract Forms). An amount of 5 to 10 percent of the Contract Price is commonly specified for Performance Bank Guarantees. A* ***Performance Bond*** *is an undertaking by a bonding or insurance company (surety) to complete the construction in the event of default by the Contractor, or to pay the amount of the Bond to the* Employer*. An amount of 30 percent of the Contract Price is commonly used internationally for this type of security (see Section X, Contract Forms).]* |
| **53.3.2** | The performance security will be in the form of a \_\_\_\_ *[insert either one of “demand guarantee” or “performance bond”]*  The ESHS Performance Security will be in the form of a “*demand guarantee” [delete if not applicable]* |
| **57.1** | The following Drawings and/or Manuals are required at the following dates: *[If applicable, specify* ***type of document*** *and* ***date*** *by which they are to be supplied. If not applicable, state “****none****”.]* |
| 57.2 | If the required documents are not supplied in accordance with PC 57.1, the amount to be withheld is *[state* ***amount****].* |
| **59.2.2(c)** | The condition of persistent failure to execute the contract is given if and when the total amount of payment reductions and liquidated damages applied under the contract reaches *[insert* ***number****]* percent of the total contract amount.  *[Depending on the type of roads and the structure of the contract, the recommended number could be in the order of 10 – 15 percent of the total contract amount.]* |
| **63.1.1** | The Employer has the right to propose a change in the contract: Yes or No *[Indicate if applicable or not by deleting* ***Yes*** *or* ***No*** *as applicable].* |
| **63.1.2** | Contractor’s right to propose a change in the contract: Yes or No *[Indicate if applicable or not by deleting* ***Yes*** *or* ***No*** *as applicable].* |
| **63.2.1** | Sub-Clause 63.2.1(e) is replaced with the following, and the original 63.2.1(e) is renumbered as 63.2.1(f):  “sufficient ESHS information to enable an evaluation of ESHS risks and impacts of the Change.” |
| 63.3.2 | **Value Engineering**  In the first paragraph, after Sub-Paragraph *“(c) a description of any effect(s) of the change on performance/functionality.”* the following is added:  “; and   1. sufficient ESHS information to enable an evaluation of ESHS risks and impacts of the Change.” |
| 63.3.2 | Value Engineering  If the value engineering proposal is approved by the Employer the amount to be paid to the Contractor shall be \_\_\_% (insert appropriate percentage. The percentage is normally up to 50%) of the reduction in the Contract Price. |

|  |
| --- |
| Section IX - Contract Forms |

**Table of Forms**

[Beneficial Ownership Disclosure Form 226](#_Toc535747981)

[Letter of Acceptance 228](#_Toc535747982)

[Contract Agreement 229](#_Toc535747983)

[Performance Security 231](#_Toc535747984)

[Environmental, Social, Health and Safety (ESHS) Performance Security 235](#_Toc535747985)

[Advance Payment Security 237](#_Toc535747986)

[Retention Money Security 239](#_Toc535747987)

Notification of Intention to Award

**[*This Notification of Intention to Award shall be sent to each Bidder that submitted a Bid.*]**

**[*Send this Notification to the Bidder’s Authorized Representative named in the Bidder Information Form*]**

* For the attention of Bidder’s Authorized Representative
* Name: *[insert Authorized Representative’s name]*
* Address: *[insert Authorized Representative’s Address]*
* Telephone number: *[insert Authorized Representative’s telephone number]*
* Email Address: *[insert Authorized Representative’s email address]*

***[IMPORTANT: insert the date that this Notification is transmitted to Bidders. The Notification must be sent to all Bidders simultaneously. This means on the same date and as close to the same time as possible.]***

**DATE OF TRANSMISSION**: This Notification is sent by: [*email*] on [*date*] (local time)

**Notification of Intention to Award**

**Employer:** *[insert the name of the Employer]*

**Project:***[insert name of project]*

**Contract title:** *[insert the name of the contract]*

**Country:** *[insert country where RFB is issued]*

**Loan No.** *[insert reference number for loan]*

**RFB No:** *[insert RFB reference number from Procurement Plan]*

This Notification of Intention to Award (Notification) notifies you of our decision to award the above contract. The transmission of this Notification begins the Standstill Period. During the Standstill Period, you may:

1. request a debriefing in relation to the evaluation of your Bid, and/or
2. submit a Procurement-related Complaint in relation to the decision to award the contract.
3. **The successful Bidder**

|  |  |
| --- | --- |
| **Name:** | [*insert name* *of successful Bidder*] |
| **Address:** | [*insert address* *of the successful Bidder*] |
| **Contract price:** | [*insert contract price* *of the successful Bid*] |

1. **Other Bidders *[INSTRUCTIONS: insert names of all Bidders that submitted a Bid. If the Bid’s price was evaluated include the evaluated price as well as the Bid price as read out.]***

|  |  |  |
| --- | --- | --- |
| **Name of Bidder** | **Bid price** | **Evaluated Bid price**  **(if applicable)** |
| [*insert name*] | [*insert Bid price*] | [*insert evaluated price*] |
| [*insert name*] | [insert Bid price] | [*insert evaluated price*] |
| [*insert name*] | [insert Bid price] | [*insert evaluated price*] |
| [*insert name*] | [insert Bid price] | [*insert evaluated price*] |
| [*insert name*] | [insert Bid price] | [*insert evaluated price*] |

1. **Reason/s why your Bid was unsuccessful**

|  |
| --- |
| ***[INSTRUCTIONS: State the reason/s why this Bidder’s Bid was unsuccessful. Do NOT include: (a) a point by point comparison with another Bidder’s Bid or (b) information that is marked confidential by the Bidder in its Bid.]*** |

1. **Best and Final Offer or Negotiations**

|  |
| --- |
| Pursuant to ITB 38.1 in the evaluation of bids or pursuant to ITB 38.2, in the final award of this Contract, the following method was used:  🞎 Best and Final Offer  🞎 Negotiations  🞎 Neither method  ***[Delete if not applicable]***  The name of the Independent Probity Assurance Authority is:*[insert the name of the* Independent Probity Assurance Authority*]* |

1. **How to request a debriefing**

|  |
| --- |
| **DEADLINE: The deadline to request a debriefing expires at midnight on [*insert date*] (local time).**  You may request a debriefing in relation to the results of the evaluation of your Bid. If you decide to request a debriefing your written request must be made within three (3) Business Days of receipt of this Notification of Intention to Award.  Provide the contract name, reference number, name of the Bidder, contact details; and address the request for debriefing as follows:  **Attention**: [*insert full name of person, if applicable*]  **Title/position**: [*insert title/position*]  **Agency**: [*insert name of Employer*]  **Email address**: [*insert email address*]  If your request for a debriefing is received within the 3 Business Days deadline, we will provide the debriefing within five (5) Business Days of receipt of your request. If we are unable to provide the debriefing within this period, the Standstill Period shall be extended by five (5) Business Days after the date that the debriefing is provided. If this happens, we will notify you and confirm the date that the extended Standstill Period will end.  The debriefing may be in writing, by phone, video conference call or in person. We shall promptly advise you in writing how the debriefing will take place and confirm the date and time.  If the deadline to request a debriefing has expired, you may still request a debriefing. In this case, we will provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract Award Notice. |

1. **How to make a complaint**

|  |
| --- |
| **Period: Procurement-related Complaint challenging the decision to award shall be submitted by midnight, [*insert date*] (local time).**  Provide the contract name, reference number, name of the Bidder, contact details; and address the Procurement-related Complaint as follows:  **Attention**: [*insert full name of person, if applicable*]  **Title/position**: [*insert title/position*]  **Agency**: [*insert name of Employer*]  **Email address**: [*insert email address*]  At this point in the procurement process, you may submit a Procurement-related Complaint challenging the decision to award the contract. You do not need to have requested, or received, a debriefing before making this complaint. Your complaint must be submitted within the Standstill Period and received by us before the Standstill Period ends.  In summary, there are four essential requirements:   1. You must be an ‘interested party’. In this case, that means a Bidder who submitted a Bid in this bidding process, and is the recipient of a Notification of Intention to Award. 2. The complaint can only challenge the decision to award the contract. 3. You must submit the complaint within the period stated above. 4. You must include, in your complaint, all of the information pursuant to paragraphs 2.77 to 2.81 of the Bank´s Procurement Policies and Appendices 1 and 3. |

1. **Standstill Period**

|  |
| --- |
| **DEADLINE: The Standstill Period is due to end at midnight on [*insert date*] (local time).**  The Standstill Period lasts ten (10) Business Days after the date of transmission of this Notification of Intention to Award.  The Standstill Period may be extended as stated in Section 5 above. |

If you have any questions regarding this Notification, please do not hesitate to contact us.

On behalf of the Employer:

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title/position: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Telephone: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Email: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Beneficial Ownership Disclosure Form

*INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM*

*This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the successful Bidder. In case of joint venture, the Bidder must submit a separate Form for each member. The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.*

*For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:*

* *directly or indirectly holding 25% or more of the shares*
* *directly or indirectly holding 25% or more of the voting rights*
* *directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder*

**Bidding No.:** [*insert number of Bidding process*]

**Request for Bid No**.: [*insert identification*]

To: **[*insert complete name of Employer*]**

In response to your request in the Letter of Acceptance *dated [insert date of letter of Acceptance]* to furnish additional information on beneficial ownership: *[select one option as applicable and delete the options that are not applicable]*

(i) we hereby provide the following beneficial ownership information.

**Details of beneficial ownership**

|  |  |  |  |
| --- | --- | --- | --- |
| Identity of Beneficial Owner | Directly or indirectly holding 25% or more of the shares  (Yes / No) | Directly or indirectly holding 25 % or more of the Voting Rights  (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder  (Yes / No) |
| *[include full name (last, middle, first), nationality, country of residence]* |  |  |  |

***OR***

(ii) *We declare that there is no Beneficial Owner meeting one or more of the following conditions:*

* directly or indirectly holding 25% or more of the shares
* directly or indirectly holding 25% or more of the voting rights
* directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder

**OR**

*(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]*

* directly or indirectly holding 25% or more of the shares
* directly or indirectly holding 25% or more of the voting rights
* directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

**Name of the Bidder**: \*[*insert complete name of the Bidder*]\_\_\_\_\_\_\_\_\_

**Name of the person duly authorized to sign the Bid on behalf of the Bidder**: \*\*[*insert complete name of person duly authorized to sign the Bid*]\_\_\_\_\_\_\_\_\_\_\_

**Title of the person signing the Bid**: [*insert complete title of the person signing the Bid*]\_\_\_\_\_\_

**Signature of the person named above**: [*insert signature of person whose name and capacity are shown above*]\_\_\_\_\_

**Date signed** [*insert date of signing*] **day of** [*insert month*], [*insert year*]\_\_\_\_\_

\* In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

\*\* Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.

\*\*\* It is understood that any false or misleading information that has been provided in relation to this requirement may result in actions or sanctions by the Bank in accordance with its rules and policies.

Letter of Acceptance

*[letterhead paper of the Employer]*

*[date]*

To: *[name and address of the Contractor]*

This is to notify you that your Bid dated *[date]* for execution of the *[name of the Contract and identification number, as given in the Contract Data]* for the Accepted Contract Amount of the equivalent of *[amount in numbers and words] [name of currency]*, as corrected and modified in accordance with the Instructions to Bidders, is hereby accepted by our Agency.

You are requested to furnish (i) the Performance Security and an Environmental, Social, Health and Safety Performance Security ***[Delete ESHS Performance Security if it is not required under the contract]*** within 28 days in accordance with the Conditions of Contract, using for that purpose one of the Performance Security and the ESHS Performance Security Form, ***[Delete reference to the ESHS Performance Security Form if it is not required under the contract]*** and (ii) the additional information on beneficial ownership in accordance with BDS ITB 46.1, within eight (8) Business days using the Beneficial Ownership Disclosure Form, included in Section IX, Annex to the Particular Conditions - Contract Forms, of the bidding document.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

**Attachment: Contract Agreement**

|  |
| --- |
| Contract Agreement |

THIS AGREEMENT made the \_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, \_\_\_\_\_, between \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter “the Employer”), of the one part, and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works and Services known as \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1. In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2. The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

1. the Letter of Acceptance
2. the Letter of Bid (the last if BAFO or Negotiations were used)
3. the addenda Nos \_\_\_\_\_\_\_\_(if any)
4. the Particular Conditions
5. the General Conditions;
6. the Specification
7. the Drawings*;*
8. the completed Schedules, and
9. any other document listed in the PC as forming part of the Contract; including but not limited to:
   * + 1. *project assessments and plans e.g. the project’s Environmental and Social Action Plan (ESAP) and its Environmental and Social Assessment (ESA), Project specific Environmental and Social Management Framework (ESF) and Environmental and Social Management Plan (ESMP) inclduing specific thematic plans such as the project’s Stakeholder Engagement Plan (SEP).*
       2. *Code of Conduct for Contractor’s Personnel*

3. In consideration of the payments to be made by the Employer to the Contractor as indicated in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and Services, and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4. The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and Services, and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ on the day, month and year indicated above.

Signed by \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (for the Employer)

Signed by \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (for the Contractor)

|  |
| --- |
| Performance Security |

**Option 1: Demand Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[insert name and Address of* Employer*]*

**Date:** \_ *[Insert date of issue]*

**PERFORMANCE GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:** *[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Applicant") has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ),[[24]](#footnote-25)1 such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the …. Day of ……, 2… [[25]](#footnote-26)2, and any demand for payment under it must be received by us at this office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

**Performance Security**

**Option 2: Performance Bond**

By this Bond\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ as Principal (hereinafter called “the Contractor”) and\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_] as Surety (hereinafter called “the Surety”), are held and firmly bound unto\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_] as Obligee (hereinafter called “the Employer”) in the amount of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, for the payment of which sum well and truly to be made in the types and proportions of currencies in which the Contract Price is payable, the Contractor and the Surety bind themselves, their heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Contractor has entered into a written Agreement with the Employer dated the day of , 20 , for \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ in accordance with the documents, plans, specifications, and amendments thereto, which to the extent herein provided for, are by reference made part hereof and are hereinafter referred to as the Contract.

NOW, THEREFORE, the Condition of this Obligation is such that, if the Contractor shall promptly and faithfully perform the said Contract (including any amendments thereto), then this obligation shall be null and void; otherwise, it shall remain in full force and effect. Whenever the Contractor shall be, and declared by the Employer to be, in default under the Contract, the Employer having performed the Employer’s obligations thereunder, the Surety may promptly remedy the default, or shall promptly:

(1) complete the Contract in accordance with its terms and conditions; or

(2) obtain a Bid or Bids from qualified Bidders for submission to the Employer for completing the Contract in accordance with its terms and conditions, and upon determination by the Employer and the Surety of the lowest responsive Bidder, arrange for a Contract between such Bidder and Employer and make available as work progresses (even though there should be a default or a succession of defaults under the Contract or Contracts of completion arranged under this paragraph) sufficient funds to pay the cost of completion less the Balance of the Contract Price; but not exceeding, including other costs and damages for which the Surety may be liable hereunder, the amount set forth in the first paragraph hereof. The term “Balance of the Contract Price,” as used in this paragraph, shall mean the total amount payable by Employer to Contractor under the Contract, less the amount properly paid by Employer to Contractor; or

(3) pay the Employer the amount required by Employer to complete the Contract in accordance with its terms and conditions up to a total not exceeding the amount of this Bond.

The Surety shall not be liable for a greater sum than the specified penalty of this Bond.

Any suit under this Bond must be instituted before the expiration of one year from the date of the issuing of the Taking-Over Certificate.

No right of action shall accrue on this Bond to or for the use of any person or corporation other than the Employer named herein or the heirs, executors, administrators, successors, and assigns of the Employer.

In testimony whereof, the Contractor has hereunto set his hand and affixed his seal, and the Surety has caused these presents to be sealed with his corporate seal duly attested by the signature of his legal representative, this day of 20 .

SIGNED ON on behalf of

By in the capacity of

In the presence of

SIGNED ON on behalf of

By in the capacity of

In the presence of

|  |
| --- |
| Environmental, Social, Health and Safety (ESHS) Performance Security |

**ESHS Demand Guarantee**

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[insert name and Address of* Employer*]*

**Date:** \_ *[Insert date of issue]*

**ESHS PERFORMANCE GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:** *[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Applicant") has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ),[[26]](#footnote-27)1 such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its Environmental, Social, Health and/or Safety (ESHS) obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire, no later than the …. Day of ……, 2… [[27]](#footnote-28)2, and any demand for payment under it must be received by us at this office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

|  |
| --- |
| Advance Payment Security  Demand Guarantee |
|  |

*[Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** *[Insert name and Address of* Employer*]*

**Date:** *[Insert date of issue]*

**ADVANCE PAYMENT GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor:** *[Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called “the Applicant”) has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment in the sum \_\_\_\_\_\_\_\_\_\_\_ ( )is to be made against an advance payment guarantee.

At the request of the Applicant, we as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ ( ) *[[28]](#footnote-29)1* upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating either that the Applicant:

* + 1. has used the advance payment for purposes other than the costs of mobilization in respect of the Works; or
    2. has failed to repay the advance payment in accordance with the Contract conditions, specifying the amount which the Applicant has failed to repay.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the advance payment referred to above has been credited to the Applicant on its account number \_\_\_\_\_\_\_\_\_\_\_ at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_..

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Applicant as specified in copies of interim statements or payment certificates which shall be presented to us. This guarantee shall expire, at the latest, upon our receipt of a copy of the interim payment certificate indicating that ninety (90) percent of the Accepted Contract Amount, less provisional sums, has been certified for payment, or on the \_\_\_ day of \_\_\_\_\_, 2\_\_\_,[[29]](#footnote-30)2 whichever is earlier. Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date..

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

|  |
| --- |
| Retention Money Security |

**Demand Guarantee**

*\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ [Guarantor letterhead or SWIFT identifier code]*

**Beneficiary:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[Insert name and Address of* Employer*]*

**Date:** \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*[Insert date of issue]*

**RETENTION MONEY GUARANTEE No.:** *[Insert guarantee reference number]*

**Guarantor: [***Insert name and address of place of issue, unless indicated in the letterhead]*

We have been informed that \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name of Contractor, which in the case of a joint venture shall be the name of the joint venture]* (hereinafter called "the Applicant") has entered into Contract No. \_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert reference number of the contract]* dated \_\_\_\_\_\_\_\_\_\_\_\_ with the Beneficiary, for the execution of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name of contract and brief description of* Works*]* (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, the Beneficiary retains moneys up to the limit set forth in the Contract (“the Retention Money”), and that when the Taking-Over Certificate has been issued under the Contract and the first half of the Retention Money has been certified for payment, payment of *[*insert the second half of the Retention Money *or* *if* *the amount guaranteed under the Performance Guarantee when the Taking-Over Certificate is issued is less than half of the Retention Money,* the difference between half of the Retention Money and the amount guaranteed under the Performance Security*]* and, if required, the ESHS Performance Security*]* is to be made against a Retention Money guarantee.

At the request of the Applicant, we, as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of \_\_\_\_\_\_\_\_\_\_\_ *[insert amount in figures]* ( ) *[amount in words][[30]](#footnote-31)1* upon receipt by us of the Beneficiary’s complying demand supported by the Beneficiary’s statement, whether in the demand itself or in a separate signed document accompanying or identifying the demand, stating that the Applicant is in breach of its obligation(s) under the Contract, without your needing to prove or show grounds for your demand or the sum specified therein.

A demand under this guarantee may be presented as from the presentation to the Guarantor of a certificate from the Beneficiary’s bank stating that the second half of the Retention Money as referred to above has been credited to the Applicant on its account number \_\_\_\_\_\_\_\_\_\_\_ at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ *[insert name and address of Applicant’s bank]*.

This guarantee shall expire no later than the …. day of ……, 2… [[31]](#footnote-32)2, and any demand for payment under it must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_   
*[signature(s)]*

***Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.***

Annex

Sample Specifications

**Output and Performance** **Based Road Contracts**

Precise and clear Specifications are a prerequisite for bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their bids. In the context of bidding document for the Output- and **Performance-based Road Contracts**, the Specifications must cover different areas (performance criteria, general technical aspects, organization, environmental regulations, etc.) and must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards to be complied with. Specifications must be written specially by the Employer to suit the specific conditions of each country and of the roads included in the contract. Recognizing that there are no standard specifications for universal application in all countries, the Bank has prepared and provides below sample texts for (i) Output and Performance Specifications, to be applied for Management and Maintenance Services, and for Rehabilitation and Improvement works, and (ii) Specifications on Procedures for Emergency Works. The Bank suggests the use of these sample texts, which nevertheless still need adaptation to the specific conditions of the road networks under contract. The sample Specifications provided reflect the basic principles which have been adopted under this sample bidding document for Output- and Performance-Based Road Contracts, and they have been prepared to ensure that they correspond to the definitions and provisions of the Sample bidding document. They should also help to prevent conflicts which could derive from potential contradictions between the different parts of the bidding document.

The completed “Section VI – Specifications for Works and Services” of the finalized bidding document should include as a minimum the following parts:

**Part A: Output and Performance Specifications** (see sample text starting on page 1)

This part includes a detailed description of (i) the concepts on which the Output- and Performance-Based Road Contracts is prepared; (ii) the Service Levels required on the roads included in the contract; (iii) the methods and procedures to be applied for measuring compliance with Service Levels; (iv) the payment reductions and/or liquidated damages applied in case of non-compliance, (v) the initial rehabilitation works and the improvement works the contractor will have to carry out in addition to the general Management and Maintenance Services and Works, and (vi) other aspects, such as the internal organization of the contractor, etc. *This document provides sample text for this part.*

It is important that the performance criteria cover all aspects of the contract and take account of the fact that different roads within the contract area might require different service levels. In setting the measures various criteria (both technical and practical) need to be carefully considered, such as (i) traffic volume and composition, (ii) urban vs. rural roads (iii) flat, hilly or mountainous terrain, (iv) subgrade quality and type, (v) quality of available construction materials, (vi) capacity of available contractors, (vii) any environmental constraints, such as protected areas, parks, forest reserves, etc. **However, probably the most important criterion is the question of what service level can be afforded and economically justified for the road in question.**

The tables presented on the following two pages give an indication of the range of values that may be considered:

**Typical Service Levels for Unpaved Roads**

|  | **Fair** | **Good** | **Very Good** |
| --- | --- | --- | --- |
| **Typical Traffic Volumes (Vehicles/day)** | **Less than 50** | **50 – 150** | **150 - plus** |
| Average operational Traffic Speed (km/h) | 40 | 60 | 70 |
| Surface Degradation - Maximum diameter of any single degradation | 45cm | 35cm | 25cm |
| Surface Degradation - Max Number greater than nominated diameter in any 100m | 20/30cm | 10/25cm | 2/25cm |
| Cleanliness of pavement surface and shoulders response time for safety related matters | 24 hrs | 10 hrs | 6 hours |
| Cleanliness of pavement surface and shoulders response time for all other matters | 14 days | 7 days | 4 days |
| Road Corrugation Amplitude | 4.5cm | 3.5cm | 2.5cm |
| Rut Depth | 10.0 cm | 7.0 cm | 5.0 cm |

***Typical Service Levels for Paved Roads***

|  | **Fair** | **Good** | **Very Good** | **Excellent** |
| --- | --- | --- | --- | --- |
| **Typical Traffic Volumes (Vehicles/day)** | **Less than 250** | **250 - 1000** | **1000 – 5000** | **5000 plus** |
| Potholes (Max Dia of any single pothole) | 40 cm | 30cm | 15cm | No potholes allowed |
| Potholes (Max number in any 1000m with diameter greater than 10 cm | 12 | 8 | 4 | None allowed |
| Patching (Response time) | 28 days | 28 days | 14 days | 7 days |
| Cracking (Response time) | 28 days | 28 days | 28 days | 28 days |
| Cleanliness of the pavement surface and shoulders for safety related matters (Response time) | 10 hrs | 8 hrs | 6 hrs | 3 hr |
| Cleanliness of pavement surface and shoulders response time for all other matters (Response time) | 14 days | 7 days | 5 days | 3 days |
| Rutting | 4.0 cm | 4.0 cm | 3.0 cm | 2.0 cm |
| Rutting (Response time) | 56 days | 56 days | 28 days | 28 days |
| Raveling (Response time) | 56 days | 56 days | 28 days | 28 days |
| Loose Pavement Edges (Response time) | 56 days | 56 days | 28 days | 28 days |
| Height of Shoulders vs. Height of pavement | 7.5 cm | 5.0 cm | 5.0 cm | 5.0 cm |
| Height of Shoulders vs. Height of pavement (Response time) | 56 days | 56 days | 28 days | 14 days |
| Paved Shoulders (Response time) | 56 days | 56 days | 28 days | 28 days |

When using response times as part of the performance criteria, it is important to select them carefully as they have a significant influence on the cost of undertaking the work. Consideration needs to be given to the time needed to:

* 1. Identify the fault
  2. Schedule the necessary work
  3. Mobilizing the necessary resources
  4. Undertaking the work

and to the available technology – very short response times often dictate the need for “real time” technology which may not be really necessary or appropriate in many instances.

**Part B: General Specifications for Roadworks** (no sample text provided in this document)

This part is very country-specific and should present the norms and specifications generally applied for road works in a specific country, mainly in terms of quality and workmanship. Part B is applicable mainly for specific Rehabilitation and Improvement Works described in Part A, but at least parts of it may also be applicable for Maintenance Services and Emergency Works. Note: *This document provides no sample text for this part.*

Care should be taken to not make unnecessary references to method-based specifications that unduly limit the contractor’s ability to provide innovative solutions.

**Part C: Specifications for Emergency Works** (see sample text starting from page 55)

This part must describe the procedures and other rules to be applied if Emergency Works are to be carried out within the contract. Note: *This document provides sample text for this section*. Use of the sample text would help to ensure that the concept of Emergency Works is not misused.

**Part D: Environmental and Social Specifications** (no sample text provided in this document)

This part would provide a set of rules to be followed by the contractor to manage ESHS impacts and risks. Note: *This document provides no sample text for this part.*

Other Specifications may be needed concerning the use of materials, plant and equipment by the contractor, if the provisions included in the General Conditions (GC, Section VII) and complemented in the Particular Conditions (PC, Section VIII) are deemed insufficient by the Employer. Also, these issues may already be covered in the General Specifications for Roadworks.

Only if the various parts of the Specifications are completed adequately and included in the bidding document, will the objectives of economy, efficiency and equality in procurement be realized, and the responsiveness of bids be ensured, and the subsequent task of bid evaluation facilitated.

It is nevertheless important to remember again that this sample bidding document should not be used for roads or road networks in poor condition which require a very substantial and costly upgrading and/or rehabilitation before they can be maintained. It is suggested that whenever the initial upgrading and/or rehabilitation or improvement works are estimated to cost more than 40 to 50 percent of the total contract amount, it should be considered to undertake those works under a traditional contract model based on a bill of quantities and unit prices.

The use of metric units is encouraged by IBRD.

Care must be taken in drafting Specifications to ensure that they are not too restrictive. In the specification of standards for materials, plant, other supplies, and workmanship, recognized international standards should be used as much as possible.

These **Notes for Preparing Technical Specifications** are intended only as information for the Employer or the person drafting the bidding document. They should **not** be included in the final bidding document.

**Sample text for Section VI, Part A**

**Output and Performance Specifications**

[Part A1. Basic Concepts of Output- and Performance-Based Road Contracts 248](#_Toc454885821)

[Part A2. Description of Services to be Provided 248](#_Toc454885822)

[Proposed sample text for Section VI, Part C 294](#_Toc454885823)

Part A1. Basic Concepts of Output- and Performance-Based Road Contracts

*[Note: The basic concept of Output- and Performance-based Road Contracts is presented in the Foreword of the Bidding Document. It should simply be copied and inserted here, starting with the third paragraph of the Foreword, and ending just before the last paragraph.]*

Part A2. Description of Services to be Provided

2.1 General Specifications (for unpaved and paved roads)

2.1.1 Scope of Services to be provided

Notwithstanding the provisions of Clause 7 of the contract, the services to be provided by the Contractor include all activities, physical or others, which the Contractor needs to, carry out, in order to comply with the Service Levels and other output and performance criteria indicated under the contract, or with any other requirements of the contract. In particular, they include management tasks and physical works associated with the following road-related assets and items:

*[Note: List the extent of* ***specific road related assets and items*** *that are to be maintained under the contract. The list may include:*

* *Pavements (paved roads)*
* *Road surface (unpaved roads)*
* *Signaling and road safety furniture*
* *Drainage structures*
* *Vegetation control*
* *Slopes (cuts and embankments)*
* *Structures*
* *Traffic Management*
* *Data Collection*
* *etc.]*

2.1.2 Description of the project area

**The project roads are in the** *….[provide a* ***brief overview of the region****, including its economy, climate, geography, and the transportation network].*

2.1.3 Description of the Roads included in Contract

The road sections included in the contract are the following: *[provide* ***detailed listing of roads*** *and/or road sections included in the contract, with precise description of the beginning and end of each section].*

2.1.4 Reference Information

As a general reference, the information shown below is provided to the Bidder. The Employer provides this information to the best of his knowledge, but does not guarantee its correctness, and the Contractor may not make any claim based on potential errors or omissions in the information provided.

*[Provide* ***information*** *which may be useful to the bidder for the preparation of his bid, such as*

* *Traffic volumes for each road section*
* *Traffic composition*
* *Rainfall quantities and patterns*
* *Technical information of each road, such as original design, previous works executed, etc.*
* *Any maintenance history that is available*
* *Other information as available.]*

2.1.5 Design Criteria for Rehabilitation and Improvement Works

All Rehabilitation Works and Improvement Works shall be designed to meet the following minimum design criteria:

[*insert here the* ***minimum design criteria*** *to be used in the design of any rehabilitation and/or improvement works that may be required during the term of the contract. It is important to ensure that the works have the appropriate residual life at the end of the contract period. Criteria should be included for*

* *Pavements (for paved roads)*
* *Road surfacing (for unpaved roads)*
* *Structures*
* *Drainage structures – (including the design period of the storm event culverts are to pass without overtopping)*
* *Signage]*

2.1.6 Rehabilitation Works to be carried out by Contractor

*[Note: It is recommended to keep any mandatory explicit rehabilitation works to a minimum. Any detailed specification of substantial physical rehabilitation works at precise locations, based on a detailed design provided by the employer, would be contrary to the underlying concept of a lump-sum price included in this contract. If the Employer intends to do so, the document should be modified and prices should be asked for a unit price “inputs” based on a bill of quantities similar to the one used for Emergency Works.*

*However, it may well be appropriate to mandate minimum quantities of work to be undertaken throughout the contract and include them within the lump sum. For example:*

*For* ***unpaved roads****, it may be useful to make mandatory certain minimum physical quantities, such as, for example, a certain number of cubic meters of gravel or other materials to be added to the road during the contract period, without necessarily specifying the exact locations of where the materials are to be added. The quantity could be based on a technical study, or on qualified estimates made by the technical staff of the Employer.*

*For* ***paved roads****, it could be mandated that the Contractor applies a certain minimum quantity (in cubic meters or metric tons) of asphalt concrete to the roads during the contract period. Alternatively, the minimum length of pavement rehabilitation or strengthening required in each year during the contract could be specified and the contractor left to define of the most appropriate location for each year’s program for pavement rehabilitation and strengthening. The minimum quantities could be defined based on a technical study, or on qualified estimates made by the technical staff of the Employer.*

*For* ***culverts and other structures*** *there could be an obligation to build, for example, a certain number of culverts of a certain capacity, or the construction of a certain number of linear meters of retaining walls.*

*The main purpose of making this type of works mandatory is to ensure that an appropriate level of rehabilitation work is carried out during the contract and to avoid a gross miscalculation by any of the bidders as to the quantity of works necessary. The definition of mandatory minimum rehabilitation works thus reduces the risk that a bidder wins the contract based on a very low bid, but is then unable to comply. They also ensure that the contractor does not just rely on routine maintenance activities to meet the service levels in the last year or two of the contract period and so create a new backlog of rehabilitation work.*

*There are two possible options for the design of rehabilitation works. One is for the Employer to provide the detailed design to the Contractor and the second is for the Contractor to undertake the design to the Employer’s design criteria and satisfaction. The second option is preferred as it allows the contractor to introduce more innovation.]*

2.1.6.1 Description of the Rehabilitation Works

The Contractor will have to carry out the following minimum quantity of Rehabilitation Works:

*[Present a list showing* ***quantities and types*** *of works, including* ***drawings and technical documents*** *(if applicable) provided by the Employer and the* ***time frame*** *for the execution of the Rehabilitation Works. Items on the list may include light reshaping and gravelling, heavy reshaping and gravelling, embankment works, asphalt overlays, culvert repairs and culvert extensions, installation of new culverts, repairs to wooden bridge decks, drift construction, road sign installation, etc ]*

The Contractor is to make an independent estimate of the rehabilitation works which in his view are necessary to bring the roads to the required service levels, and include the cost for those works either in the item for Initial Rehabilitation Works (up to the ceiling given by the Employer in the Bidding Data) or in the price for Maintenance Services. However, only those works defined under the item for Rehabilitation Works will be paid for specifically and separately under the contract. Other works needed to bring roads up to the required service levels, but which are not included in the item for Rehabilitation Works, shall be included by the bidders in the lump sum price for Maintenance Services. Contractors are solely responsible for estimating the type and quantity of Rehabilitation Works needed to meet the requirements of the contract. During the execution of the contract the Contractor shall not be entitled to make claims for any Rehabilitation Works not foreseen at the time of bid preparation or not included in the bidding document.

The time for completion of the Rehabilitation Works varies from road to road in relation to the schedule for compliance with service level criteria as shown in the compliance timetables in *[insert* ***clause*** *number e.g.2.3.3 for unpaved roads]*.

The Rehabilitation Works indicated above may not be interpreted as to be sufficient in order to assure compliance with any of the Service Levels required by the contract.

2.1.6.2 List of Documents Related to Rehabilitation Works for Approval or Review

The following documents are specified in accordance with sub-clause 8.4.1 of the GC:

*[insert here a* ***list of documents*** *related to Rehabilitation Works to be provided by the Contractor, such as linear diagrams, as-built drawings, etc. Indicate which of the documents listed need approval and who is to provide such approval.]*

2.1.6.3 Payment for Rehabilitation Works

The Rehabilitation Works indicated above will be priced through a separate lump-sum amount included in the Contract Price. The Contractor will invoice Rehabilitation Works in Monthly Statements and in accordance with the Rehabilitation Works actually carried out and measured by Product Unit Price as stated in the Bill of Quantities. *[Note: Product Unit Prices are different from the input unit prices typically used in Works contracts. They are the prices for completed products, such as a culvert of a certain type, the re-establishment of a certain shoulder width per one-km section of road, etc.]*

2.1.7 Improvement Works to be carried out by Contractor

*[Note: It is recommended to keep Improvement Works to a minimum. It is important that the focus of the contract is Management and Maintenance of the roads and not the construction of new works.]*

2.1.7.1 Description of Improvement Works

The contractor will have to carry out the following Improvement Works:

*[Indicate* ***quantities and type*** *of works, and the* ***time frame*** *for their execution.]*

2.1.7.2 List of Documents Related to Improvement Works for Approval or Review

The following documents are specified in accordance with sub-clause 8.4.1 of the GC:

*[Insert here a* ***list of documents*** *related to Improvement Works to be provided by the Contractor, such as design plans, as-built drawings, etc. Indicate which of the documents listed need approval and who is to provide such approval.]*

2.1.7.3 Payment for Improvement Works

The Improvement Works indicated above will be remunerated based on the unit prices shown in the Bill of Quantities. The Contractor will invoice Improvement Works as part of the Monthly Statements and in accordance with the Improvement Works actually carried out and measured by unit price as stated in the Bill of Quantities.

2.1.8 Quality of Materials to be used

Notwithstanding the provisions of Clause 30 of the General Conditions, the materials used by the Contractor shall comply with or exceed the following quality criteria:

*[Indicate a* ***list of different types of materials*** *likely to be needed by the Contractor such as for concrete and steel used in structures, gravel, laterites, asphalt, paint, etc., and the minimum* ***quality criteria*** *for each of those materials]*

The Contractor is informed of the existence of the following borrowing pits and or extraction sites which may be used to extract materials:

*[Provide a* ***list including site plans*** *of gravel borrowing pits and other sites where suitable materials are known to exist which may be extracted by contractor. If available, indicate* ***qualitie****s of materials, with disclaimer. Indicate the* ***conditions for extraction,*** *especially the type of additional permits needed, if any, and payments to be made, if any.]*

Prior to the extraction of materials for use on the roads included in the contract, the contractor is obliged (i) to carry out the laboratory tests necessary to determine the quality of the materials, and (ii) to satisfy himself that the quality of the materials is sufficient for the purpose intended.

The Contractor may also utilize materials from other sources, in conformity with the GC, provided that (i) the extraction is in conformity with the legislation, (ii) he has informed the Employer of his intention to utilize the material, and (iii) he has satisfied himself as to the sufficiency of the technical characteristics and the quality of the materials he intends to use for the intended purposes. Under no circumstances may the Contractor make any claims based on the insufficient quality of any of the materials he has used.

2.1.9 Self-Control Unit of Contractor

In conformity with sub-clause 25.2 of the GC, the Contractor is obliged to establish, within his own organizational structure, a specific Unit staffed with qualified personnel, whose task is to verify continuously the degree of compliance by the Contractor with the required Service Levels. The Self Control Unit is also responsible for undertaking the quality control testing required for Rehabilitation Works, Improvement Works and Emergency Works.

The Unit is responsible for the generation and presentation of the information needed by the Contractor for the documentation required for the Monthly Statement. In general terms, the Unit will be responsible to maintain at all times a detailed and complete knowledge of the condition of the roads or road sections included in the contract and to provide to the management of the Contractor all the information needed in order to efficiently manage and maintain the roads included in the contract. The Self-control Unit is also obliged to carry out, in close collaboration with the Project Manager, the formal and scheduled inspections of Service Levels which will take place regularly.

The compliance (non-compliance) of the Contractor with service level requirements will be reported by the Self-Control Unit to the Project Manager in the form of tables as specified in 2.2.2.

2.1.10 Communications Equipment

*[Note: In accordance with sub-clause 5.3 of the GC, the Contractor is obliged to provide and maintain in operation permanently certain communications equipment. Depending on the country conditions, it may be useful to specify here the type of equipment and the number and location of units. The equipment may consist of cellular phones, satellite phones, radio equipment, computers with E-Mail access, and/or similar.]*

2.1.11 Site Regulations and Work Procedures

*[Insert* ***Site Regulations*** *in accordance with sub-clause 18.3 GC, if any]*

*[Insert* ***Work Procedures*** *in accordance with sub-clause 17.5 GC, if any. These should however not introduce too many constraints on the Contractor, who should be able to carry out his work the way he thinks is best suited to ensure compliance with service levels.]*

2.1.12 Functions of Key Personnel

*[If needed, insert here a list of required key positions within contractor’s staff and their functions.]*

2.1.13 Specification of Service Quality Criteria

For the purposes of this contract, different service levels are required for individual roads or road sections. The following service levels will be applied:

*[insert a* ***list*** *of the service levels applicable to the contract e.g. Fair, Good, Very Good, and for paved and unpaved roads.]*

The service level applicable to each road or road section is given below.

*[insert* ***table*** *listing road or road section identification, lengths, and the applicable service level. Include an appropriate summary of the information at the bottom of the table as per the* ***Sample Table*** *below.]*

| ***Road or Road section*** | ***Length (km)*** | ***Required Service Level*** |
| --- | --- | --- |
| *Road A* | *33.34* | *Fair* |
| *Road B* | *58.35* | *Fair* |
| *Road C* | *18.02* | *Very Good* |
| *Road D* | *71.97* | *Good* |
| *Road E* | *16.77* | *Very Good* |
| *Road F* | *15.13* | *Good* |
| *Road G* | *7.77* | *Fair* |
| ***Total*** | ***221.46*** |  |
| ***Length at Very Good Service Level***  ***Length at Good Service Level***  ***Length at Fair Service Level*** | *34.79*  *87.1*  *99.57* |  |

2.1.14 Methods of Inspection of Service Levels

2.1.14.1 Formal Inspections of Service Levels

Formal inspections are those scheduled in advance by the Project Manager, and carried out by the Contractor (through his self-control Unit) under the supervision of the Project Manager. The main purpose of the formal inspections is to enable the Project Manager to verify the information presented in the Contractor’s monthly statement and to issue the Interim Payment Certificate. The Project Manager must inform the Contractor of his intention to carry out a formal inspection at least 48 hours in advance, indicating the exact date, hour and location where the formal inspection is to begin. The Contractor is obliged to be present at the date, hour and location specified by the Project Manager, providing the physical means needed for the inspection as indicated further below. Formal inspections will normally, but not necessarily, be scheduled to begin within less than five (5) days after the presentation by the Contractor of the Monthly Statement to the Project Manager; and they should normally be completed within a maximum of three (3) days. The formal inspections allow the comparison of the information on compliance provided by the Contractor in the standard tables which are part of his Monthly Statement, with actual measurements taken in locations to be determined by the Project Manager. During the formal inspections, the Project Manager will prepare a brief Memorandum describing (i) the general circumstances of the site visit, including date, road sections visited, persons present, etc., (ii) any non-compliance which may have been detected, and (iii) the time granted by the Project Manager to the Contractor to remedy the detected defects. Based on the outcome of the formal inspection, the Project Manager will immediately correct any possible errors or misrepresentations in the Contractor’s statement, countersign it and present it to the Employer for payment, and to the Contractor for information.

Formal inspections will also be scheduled for the follow-up site visits, whose purpose is to verify if the Contractor has remedied the causes of earlier non-compliance, within the time frame granted by the Project Manager and specified in the Memorandum.

2.1.14.2 Informal Inspections of Service Levels

The Project Manager may carry out informal inspections of Service Levels as part of his general mandate given to him by the Employer. He may do so on his own initiative, at anytime and anywhere on the roads included in the contract. He must use his own means for those inspections. If he detects any road sections where the Service Level criteria are not met, he is obliged to inform the Contractor within 24 hours in writing, in order to enable the Contractor to take remedial action as soon as possible. The results of informal inspections may not be used by the Project Manager for purposes of correcting the Contractor’s monthly statements or applying penalties or liquidated damages, except for cases in which the road has been completely interrupted and the criteria of Road Usability has not been met.

2.2 Specification for the Provision of Road Management Information

The following Service Level criteria will be applied to all the deliverables required for the ongoing management of the contract and the road network.

2.2.1 Longitudinal Profile (applicable for unpaved roads only)

In accordance with sub-clause 18.1.1 of the GC, at the time of commencement of works, the Contractor will immediately start to carry out a **topographical survey** of all the roads or road sections included in the contract, and based thereon:

* Establish the **actual longitudinal profile** of the roads at the time of commencement of works, and
* Determine the **required longitudinal profile** which in the opinion of the Contractor will be necessary in order to ensure not only the compliance with the service level required under the contract, but also the long-term durability of the road. In the determination of the required longitudinal profile, the Contractor must (i) take into consideration any Rehabilitation and/or Improvement Works which may be required by the contract, (ii) pay particular attention to adequate drainage and protection from flooding, and (ii) collaborate closely with the Project Manager. In particular, he must provide to the Project Manager all the information utilized, and the criteria applied, in the determination of the required longitudinal profile.

If the survey for actual longitudinal profile for some or all of the roads exists already and has been provided to the Contractor by the Employer, the Contractor will nevertheless take all the measures which are necessary to satisfy himself and the Project Manager as to the correctness of the survey data on the actual longitudinal profile at the time of commencement of works.

In the topographic survey, as well as in the preparation of the actual and required longitudinal profiles, the Contractor will closely cooperate with the Project Manager. In particular, he will ensure that the Project Manager has access to all information gathered by the Contractor and used in the preparation of the longitudinal profile.

In any case, the Contractor will complete and formally transmit to the Project Manager the completed longitudinal profiles (actual and required) within *[indicate* ***number*** *of days]* days after the start date. The Project Manager may reject the required longitudinal profiles presented by the Contractor if (i) there is clear evidence that the required longitudinal profile as presented by the Contractor is insufficient to reasonably assure all of the service levels required by the contract, or (ii) if it does not comply with requirements concerning Rehabilitation and/or Improvement Works indicated in the contract. A rejection by the Project Manager must be accompanied by clear and detailed explanations of the reasons for the rejection, and suggestions for modifications which would remedy the reasons for rejection. If the Project Manager does not reject the required longitudinal profile presented by the Contractor within twenty (28) calendar days after receipt, providing at the same time the reasons for rejection, it will automatically become the benchmark for compliance with the criteria of durability, as described elsewhere in this contract.

Nevertheless, the Contractor cannot make any claim based on actual or potential insufficiencies in the height or other characteristics of the required longitudinal profile, even (i) if a case arises in which a non-compliance with service level criteria can directly be related to such insufficiency, or (ii) if the Project Manager has approved, or failed to reject, the required longitudinal profile proposed by the Contractor.

2.2.2 Monthly Statement

The Monthly Statement to be submitted in accordance with sub-clause 49.1 shall have the following format:

*[insert* ***sample format for Monthly Statement****. A sample from a contract for an unpaved network has been included on the following page]*

The compliance (or non-compliance) of the Contractor will be reported by the Self-control Unit to the Project Manager in the form of tables for which a mandatory standard format is adopted. There is one table for each road or road section. The tables are part of the Contractor’s monthly statement, and they may be complemented by comments for which a specific format is not required. The format of the mandatory standard table is as follows:

*[Insert* ***samples of mandatory standard tables*** *for unpaved or for paved roads, or for both if applicable.* *A sample from a contract for an unpaved network has been included after the sample monthly statement.]*

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Monthly Statement for Contract** | | | | | *Contract Name* | | | Contract Month: 12 (September 2005) | | | |
| Road or road section: | | | | | *Road A and Road B* | | |
| Required Service Level | | | | | Very Good | | |
| Length of road at required service level (km) | | | | | 34.8 | | |
| Service Level Criteria | Required  compliance | | Actual compliance | | | | | | Non-compliance | | Payment Reduction |
| Target | Km 1 | Compliance criteria | Road A | | Road B | Total length compliant (km) 2 | | Length non- compliant (3)  (1-2) | % Payment reduction (4) | Km  (5 = 3x4) |
| 1. Road Usability | 100% | 34.8 | Interruption to traffic (km days) | 100% | | 100% | 34.8 | | 0 | 1%  Sub total | 0  0 |
| 2 Average Traffic Speed | 60 kph |  | Average speed (per 5 kph below target) | 60 kph | | 60 kph | 34.8 | | 0 | 1%  Sub total | 0  0 |
| 3. Road User Comfort | 43% | 15.0 | Corrugation amplitude  Rut depth  Individual degradations  Total area of degradations  Road signs | 12  8  18  18  25% | | 14  6  16.8  16.8  30% | 26  14  24.8  34.8  9.5 | | 0.00  0.96  0.00  0.00  5.46 | 50%  50%  50%  10%  25%  Sub-total | 0  0.48  0  0  1.37  1.85 |
| 4. Durability | 38% | 13.2 | Vegetation height  Vegetation clearance  Useable road width  Longitudinal profile  Drainage | 18  18  6  Not evaluated  12 | | 16.8  16.8  3  this month  7 | 34.8  34.8  9  34.8  19 | | 0.00  0.00  4.22  0.00  0.00 | 25%  25%  10%  10%  50%  Sub total | 0  0  0.42  0  0  0.42 |
|  | | | | | | | | | | TOTAL | 2.27 |
|  | | | | | | | | | | | |
|  | | | | | Length in km for payment at this service level this month: 32.53 | | | | | | |

|  |  |  |  |
| --- | --- | --- | --- |
| Payment Summary – Contract OPBRC/1 | | | |
| Contract month: 12 | | | |
| Service Level | Network  km | Penalty  km | Km for payment this month |
| VERY GOOD | 34.8 | 2.27 | 32.53 |
| GOOD | 87.1 | 5.62 | 81.48 |
| FAIR | 99.6 | 7.30 | 92.3 |
| TOTAL | 221.5 | 16.19 | 206.31 |
| Total payment due this month | Rate per km x km for payment | | |

**STANDARD REPORTING TABLE FOR COMPLIANCE WITH SERVICE LEVELS (for unpaved roads)**

Contract No.: …………………….. Date of inspection: …………….

**INSPECTION OF SERVICE LEVELS FOR THE MONTH OF …………………….20…**

Contractor : …………………….. Persons present :

Road section : ……………………..

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | **CRITERIA** | | | |  |
| SECTIONS | | **ROAD USER COMFORT** | | **DURABILITY OF THE ROAD** | | SUB-CRITERION |
| From | To | Complied with | Not complied with | Complied with | Not complied with | NOT COMPLIED WITH |
|  |  |  |  |  |  |  |
| *[specify]* | *[specify]* | [*insert cross "X" or leave empty*] | [*insert cross "X" or leave empty*] | [*insert cross "X" or leave empty*] | [*insert cross "X" or leave empty*] | *[specify sub-criterion not complied with]* |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

**Usability of the Road**: ………………. [*insert "complied with" or "not complied with"*] **Traffic Speed**: ……….……. [*Insert "complied with" or "not complied with"*]

…. …..km/h [*insert average speed measured, if available*]

Prepared by Contractor’s Self-Control Unit Certified by Employer or his agent

………………………………….………. [*Signature*] ………………………………………………. [*Signature*]

2.2.3 Program of Performance

In accordance with clause 17.2 of the General Conditions (GC), the Contractor shall submit a Program of Performance within twenty-eight (28) days after the signing the contract agreement. The program shall include, but not be limited, to the following items:

2.2.3.1 Contractor’s Quality Assurance Plan

The purpose of the Contractor’s Quality Assurance Plan is to integrate the requirements of the contract and the Contractor’s quality assurance systems to deliver the Services.

The Contractor’s Quality Assurance Plan describes the methods and procedures which the Contractor will apply for the execution of the Contract, including how the contractor will:

1. identify the quality requirements specific to the contract,
2. plan and execute the work to satisfy those requirements
3. inspect and/or test the work to ensure compliance with the quality requirements
4. record and monitor the results as evidence of compliance, and
5. ensure that prompt action is taken to correct non-compliance.

The Contractor’s Quality Assurance Plan must clearly describe the systems, procedures and methods that will be used to deliver and monitor compliance of the Services.

2.2.3.2 Health and Safety Management Plans

If required in the Special Conditions of Contract (PC) the Program of Performance shall include a Health and Safety Management Plan.

The purpose of the Health and Safety Management Plan is to foster a responsible attitude towards occupational health and safety and to comply with the provisions of the ***[****insert* ***relevant act/regulations****].*

Because of the nature of the Services, the Contractor may occasionally be exposed to hazardous situations which could involve risk of various degrees of harm, to the contracting staff and/or the public.

Situations will arise when it is not practical to eliminate or isolate significant hazards. In these situations, the hazards must be minimized by ensuring planned protection systems (e.g. equipment, clothing) are actually used.

The Health and Safety Management Plan must be complied with by the Contractor’s personnel and all subcontractors at all times.

The Health and Safety Management Plan shall, when implemented in accordance with the plan requirements:

1. Ensure the systematic identification of existing and new hazards on the work site(s)
2. Ensure the minimization of significant hazards, where elimination and isolation are both impractical
3. Ensure the provision and use of appropriate protective measures
4. Include emergency procedures for dealing with accidental spillage, pollution or imminent danger
5. Ensure regular review and assessment of each hazard identified and monitor employees exposure to these hazards
6. Ensure reporting and recording of work site safety incidents so health and safety problems can be addressed quickly and regularly. It is a requirement of this Contract that any such incident be advised promptly to the Project Manager.

The Delivery Time for the initial Health and Safety Program shall be not later than *[indicate* ***number*** *of days]* days after the Start Date.

2.2.3.3 Emergency Procedures and Contingency Plan

If required in the Particular Conditions (PC) the Program of Performance shall include an Emergency Procedures and Contingency Plan which shall establish the roles, practices and procedures during specific types of emergency events identified in the plans and contingency plans associated with the closure of roads. The Emergency Procedures and Contingency Plan must be developed by the Contractor and agreed with the Project Manager and any other stakeholders the Project Manager may identify.

The purpose of the Emergency Procedures and Contingency Plan is to ensure the safety of the Contractor’s personnel and road users in the case of emergency and/or road closure. It should include:

* an effective communication and event recording system
* the name, contact number and specific duties of the Contractor’s personnel nominated to respond to an emergency event
* the contact number of other parties who need to be notified in cases of emergency events, e.g. police
* detailed response procedures for all emergency events
* possible detour routes in the event of road closure

The Delivery Time for the initial Emergency Procedures and Contingency Plan shall be not later than *[indicate* ***number*** *of days]* days after the Start Date.

2.2.3.4 Traffic Management Plan

If required in the Particular Conditions (PC) the Program of Performance shall include a Traffic Management Plan. The Traffic Management Plan establishes the practices for traffic management at work sites. The Traffic Management Plan must be developed by the Contractor and agreed with the Project Manager.

The objectives of the Traffic Management Plan are to:

1. clearly define and document the responsibilities and chain of command for the development, implementation and management of traffic control measures and systems
2. establish the minimum requirements for temporary traffic control
3. establish the minimum geometric, cross section and surfacing standards for temporary works
4. provide appropriate transitions and enable safe and efficient traffic flow into, through and out of work sites
5. protect the Contractor’s personnel at all times
6. protect the Assets and the Contractor’s resources at all times.
7. meet the operational requirements for the road

The Traffic Management Plan must include at least the following:

* + A documented process for preparation, review and approval of the Traffic Management Plan
  + A document tracking and control system to ensure that only the latest operative copy of the Traffic Management Plan is in circulation
  + Contact details for Contractor, Principal, emergency services and other stakeholders
  + Layout diagrams, method statements etc for implementation of traffic control while undertaking each aspect of the Services (including site specific layout diagrams and method statements if the Services require traffic control measures not covered by standard codes of practice)

2.2.4 Updating of Road Administration Databases

The Road Administration currently operates the following data associated with the assets being maintained under this contract, either electronically or on paper.

[*insert* ***list –*** *as a minimum this should include the data collected by the consultant for the preparation of the OPBRC Bidding Document.]*

The Contractor shall supply all information necessary to maintain this data in a condition of accuracy, currency and completeness appropriate to the users for which the data is intended.

The Contractor shall provide hard and/or electronic copies of the information to the Road Administrator as reasonably requested.

The delivery times and updating frequencies shall be [*insert appropriate* ***time frames****, updates at three monthly intervals are recommended]*

2.2.5 Handover Report

Immediately prior to the completion of the contract the Contractor shall prepare a *Handover Report*. The purpose of the Handover Report is to provide a smooth transition to the next contract and ensure that the next contractor is aware of any outstanding issues. .The Report will:

1. Summarize any unresolved issues;
2. Include the most recent complete set of data on the roads covered by the contract, and
3. Provide the following details:
   1. A schedule of outstanding defects and liabilities
   2. Any unresolved issues, especially those that may impact on the next Contractor
   3. Details of any sensitive issues
   4. Any ongoing special monitoring/maintenance needs.

2.3 Specification of Service Level Criteria for *Unpaved Roads*

The following Service Level criteria will be applied for all unpaved roads included in the contract. This section specifies the quality levels to be complied with within two overall criteria:

* Road User Service and Comfort
* Durability measures

2.3.1 Road User Service and Comfort Measures for Unpaved Roads

2.3.1.1 Usability of the Road

The Contractor will have to ensure that the road is open to traffic and free of interruptions at all times. **Permitted exceptions are:** *[specify* ***exceptions****, if any]*

*[Note: Permitted exceptions will have to be specified depending on the local conditions of each road. They may vary between two extremes: from a minimum of a few hours closure after severe road accidents, to a maximum of several months per year for roads which are subject to regular flooding during the rainy season. Roads in mountainous areas may be subject to landslides and require more exceptions than roads in flat areas. For countries with pronounced rainy seasons, permitted exceptions may vary between the rainy season and the dry season. In some other countries, the Contractor may be allowed to install rain barriers which may remain closed during rains and up to a certain number of hours afterwards. If the contract covers a road network which includes several different classes of roads, there may also be several classes of exceptions. In general, when defining exceptions, it is very important to closely look into the local conditions and to avoid excessively restrictive conditions.]*

2.3.1.2 Average Traffic Speed

The Contractor has to ensure that a vehicle of the type defined further below is able to circulate in a safe manner (i) at a certain average speed defined below, and (ii) that road surface conditions never constrain the vehicle speed below a certain minimum.

**Vehicle:** *[indicate vehicle, including* ***brand and model****]*

*[Note: The vehicle selected should be the most typical vehicle used by road users on the road in question. The purpose of this is to allow road users to participate, at least informally, in the inspection of compliance of the Contractor with this Service Level criterion.]*

**Average traffic speed:** *[insert* ***average******speed****]*

*[Note: (i) There may be more than one speed defined, if there are different requirements for different classes of roads in the network. (ii) The speed requirement may increase over time, if the Contractor is expected to gradually improve the Service Level of the road. (iii) In area with very pronounced rainy seasons and difficult soil conditions, it may be advisable to reduce the average speed requirement during the rainy season. Also, the concept of constrained minimum speed could be used in some cases, which is the lowest speed a user might be forced to slow down to because of road surface deficiencies.]*

2.3.1.3 Road User Comfort

The road user must be able to circulate at a certain level of comfort and safety, which depends on several criteria which are defined below. The enforcement of the criteria for road user comfort is gradual, in the sense that it is applied to a certain percentage of the network which is growing according to the timetable shown further below, until a 100% compliance is reached after some time.

*[Note: In most cases, the initial condition of the roads under contract is such that it would not be realistic to expect full compliance with the road user comfort criteria from the very beginning of the contract. It is recommended to use a timetable for compliance, a sample of which is shown further below.]*

|  |  | Fair | Good | Very Good |
| --- | --- | --- | --- | --- |
| Road Corrugation Amplitude | Permitted maximum value at any single point of road:  *[insert* ***value*** *for each service level, the recommended maximum is between 2.5 cm and 4.5 cm]* |  |  |  |
| Rut Depth | Permitted maximum value at any single point of road:  *[insert* ***value*** *for each service level, the recommended maximum is between 3.5 and 5 cm]* |  |  |  |
| Other Surface Degradations (potholes, erosions and similar types of degradations, other than corrugation and rutting) | Permitted maximum dimension of any single degradation:  *[insert* ***values for each service level****, the suggested value is between 30 cm to 45 cm]*  Permitted maximum number of accumulated degradations with any dimension greater than [*insert value, the suggested value is between 15 cm and 30 cm]* in any 1000 m section: |  |  |  |
| **Cleanliness of the pavement surface and shoulders.** | The road surface must always be clean and free of soil, debris, trash and other objects.  Dirt, debris and obstacles must be removed:   * Within *[insert value, the recommended time is between 1 hr and 24 hours]* if they pose a danger to traffic safety. * Within [*insert value, the recommended value is between 3 days and 14 days*] if they do not pose any danger to traffic safety. |  |  |  |

2.3.2 Durability Measures for Unpaved Roads

The activities of management and maintenance of the road carried out by the Contractor during the entire period of the contract must not endanger the long-term sustainability of the road, which depends of several criteria defined below.

*[Note: “Durability of the Road” is a group of criteria most of which do not directly and immediately affect the usage of the road in the short term, but which are nevertheless very important for the long-term “survival” of the substance of the road. In most cases, the initial condition of the roads under contract is such that it would not be realistic to expect full compliance with the durability criteria from the very beginning of the contract. It is recommended to use a timetable for compliance, a sample of which is shown further below.]*

|  |  |
| --- | --- |
| Required longitudinal profile | Accepted maximum negative vertical tolerance:  *[insert* ***value,*** *recommended value is minus three centimeters (3.0 cm below the height of the required longitudinal profile); no limit on the positive side]* |
| Useable Road Surface width | Road 1: ……*[insert* ***value****]* meters  Road 2: *……[insert* ***value****]* meters  Road …………Accepted maximum negative tolerance:  *[insert* ***value****, recommended is a value in the order of minus 20 centimeters (20 cm less than the width of the useable road surface]* |

2.3.3 Variations and Gradual Compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria is not expected until: *[insert* ***number*** *of days after signature or full legal notification of contract, recommended are between 60 and 90 days]*

The following table summarizes the variations and gradual compliance requirements with service levels over time: *[insert* ***table****]*

*[Note: The following table is an example from a 4-year contract which may be adapted to the Special Conditions of the contract and the roads included therein.]*

**SAMPLE TIMETABLE for unpaved roads***(for illustration purposes only)*

|  | **Timetable of compliance with Service Level requirements** | | | |
| --- | --- | --- | --- | --- |
| No. months since beginning of Contract | **Usability of the road(s)**  Compliance required on  *(% of total length of roads under contract)* | **Average Traffic Speed**  Minimum safe traffic speed which can be maintained  *(in Km/h)* | **Road User Comfort**  Compliance required on  *(% of total length of roads under contract)* | **Durability of the road(s)**  Compliance required on  *(% of total length of roads under contract)* |
| 1 and 2 | No minimum set | No minimum set | No minimum set | No minimum set |
| 3 | 100 | 40 | 3 | 2 |
| 4 | 100 | 40 | 8 | 4 |
| 5 | 100 | 50 | 13 | 7 |
| 6 | 100 | 50 | 18 | 11 |
| 7 | 100 | 50 | 24 | 15 |
| 8 | 100 | 60 | 30 | 20 |
| 9 | 100 | 60 | 36 | 25 |
| 10 | 100 | 60 | 42 | 30 |
| 11 | 100 | 60 | 50 | 35 |
| 12 | 100 | 60 | 60 | 40 |
| 13 | 100 | 60 | 70 | 45 |
| 14 | 100 | 60 | 80 | 51 |
| 15 | 100 | 60 | 90 | 57 |
| 16 | 100 | 60 | 100 | 63 |
| 17 | 100 | 60 | 100 | 69 |
| 18 | 100 | 60 | 100 | 75 |
| 19 | 100 | 60 | 100 | 81 |
| 20 | 100 | 60 | 100 | 87 |
| 21 until End of contract period | 100 | 60 | 100 | 100 |

*[Note: If the contract includes several groups of roads with different Service Level requirements, a separate table must be presented for each group. In countries with very pronounced rainy seasons, it may not be reasonable to request full compliance with all criteria during the rainy season, and different tables may be presented for the dry and rainy seasons. In particular, it might be necessary to suspend any increase in the percentage of the network where the Contractor must comply with User Comfort and Durability requirements. These and other potential limitations must be carefully evaluated by those preparing the Technical Specifications.]*

2.3.4 Means used for Inspection of Service Levels for *Unpaved Roads*

For the formal inspections of compliance with Service Levels, the Contractor’s Self-control Unit will work in close collaboration with, and under supervision of the Project Manager. The physical means needed for the inspections will be provided by the Contractor; they are the same which are normally used by the Self-control Unit for the continuous self-evaluation of the Contractor’s compliance, in particular:

1. Vehicles of the following type: *[specify* ***number*** *and* ***type*** *of vehicle].* The vehicle(s) must be in good condition and must be in conformity with its original factory specifications, without any alterations which would change its driving characteristics. *[Note: The vehicle(s) should be of the type most typically used by road users. Different types of vehicles may need to be specified for different groups of roads].*
2. Qualified and support staff *[specify number and type of staff, normally it should include as a minimum the qualified staff of the Self-control Unit plus two helpers].*
3. All tools and instruments needed, as indicated in the paragraphs describing the methodologies for inspection.

2.3.5 Methodologies to be used for Assessing Service Levels on Unpaved Roads

**(a) Usability of the Road(s)**: There is no particular testing method for the usability of a road, other than driving on the road in a normal manner, utilizing the type of vehicle indicated in the previous paragraph. The condition is not complied with if the road is interrupted at any point. The condition is however complied with if it is possible to continue to drive on the road, and without the vehicle suffering any damage caused by the bad condition of the road.

*[Note: For example, if the vehicle hits an obstacle on the road surface which causes damage to the exhaust system, the conditions is obviously not complied with. On the other hand, if there is a landslide which covers one half of the road, but it is easily possible to pass the area on the other side of the road, the condition is complied with.]*

**(b) Average Traffic Speed:** When verifying the Average Traffic Speed, the first step is to define the road sections to be tested. The lengths of the test sections should be equivalent to at least one-half hour driving time (e.g. 30 km lengths for a required average speed of 60 km/h). The second step is to travel on the defined test section in a normal and safe fashion, in the vehicle provided by the Contractor and driven by a driver provided by the Contractor. The driver must at all times respect the traffic regulation, in particular speed limits. The time of unforeseen stops which are unrelated to the road condition (such as checkpoints, breakdowns or other incidents) is to be deducted from the overall travel time. Except for normal and obligatory slowdowns and stops (at intersections, speed limits, stop signs, pedestrian crossings, village crossings, etc.), the travel speed should never be constrained by road conditions to less than a certain minimum speed given in the contract, and the average travel speed which can be maintained on the defined road section should be above the threshold value which is given in the Summary Table further below in the Technical Specifications.

In any case, the safety of the passengers of the test vehicle, as well as the safety of other road users, must never be put in danger. The judgment of whether a speed is safe or not is left to the Project Manager.

At the end of the test, the vehicle used must not have suffered any mechanical damage due to the speed of travel, which may have been excessive given the condition of the tested road section. If the vehicle has suffered such damages, the test is negative and the service level has not been complied with.

**(c) Road corrugation amplitude:** The road corrugation amplitude is one of the criteria for “Road User Comfort”. It will be checked at road sections selected by the Project Manager based on visual appearance. Measurement is carried out by placing a ruler or straight edge (three meters long) on the road, parallel to the road axis, at a place determined by the Project Manager, and measuring the space between the ruler/straight edge and the lowest point of the corrugation wave.

The maximum amplitude of the corrugation will be recorded and if this exceeds the value for corrugation height stated in the Summary Table below the one-kilometer section in which the corrugations are located will be judged non-compliant.

**(d) Rut depth:** Rut depth is one of the criteria for “Road User Comfort”. It will be checked at road sections selected by the Project Manager based on visual appearance. Measurement is carried out by placing a ruler or straight edge (three meters long) on the road surface, perpendicularly to the road axis, at a place determined by the Project Manager, and measuring the space between the ruler/straight edge and the lowest point of the rut.

The maximum rut depth will be recorded and if this exceeds the criteria for rut depth stated in the Summary Table below the one-kilometer section in which the ruts are located will be judged non-compliant.

**(e) Other surface degradations:** Other surface degradations are part of the criteria for “Road User Comfort”. They will be measured at road sections selected by the Project Manager based on their visual appearance. Individual surface degradations (such as potholes) are measured by using a standard ruler. The “equivalent diameter” is defined as the average of the greatest dimension of the degradation and a second measurement taken at right angles to the first.

For any one km of road, compliance with this criterion requires that (i) no individual surface degradation (other than ruts and corrugation) has an “equivalent diameter” of more than the maximum value specified and (ii) the number of individual degradations on a one km section is less than the threshold specified value shown in the Summary Table below.

**(f) Useable road surface width:** The useable road surface width is part of the criteria for the “Durability of the Road”. It will be measured at road sections selected by the Project Manager based on their visual appearance, in particular at places where erosions or other degradations exist which restrict the useful width of the road. The useful width is measured by using a measuring tape and/or rulers.

For any one km section of the road, the Project Manager will select one 50-meter subsection where the measurement will take place. Within that subsection, the Project Manager will select on each side of the road the individual degradation which constitutes the largest restriction of the useable surface. For each of those two points, he will then measure the distance (L) between the theoretical edge of the useable road surface (based on the useable road width specified in the contract) and the innermost point of the degradation, obtaining two values (L1 and L2). The actual useable road surface width is obtained by subtracting (L1 + L2) from the theoretical road surface width specified in the contract. (refer to diagram below). If either of these criteria is exceeded the one-kilometer section in which they are located will be judged non-compliant.



For any one km section of road, compliance with this criterion requires that there is no sub-section of 50 meters in which the actual useful width (shown as W in the drawing) is less than the width specified in the Summary Table below (clause 2.3.6), minus the tolerance allowed as indicated in the Summary Table.

**(g) Required longitudinal profile:** The required longitudinal profile is part of the criteria for the “Durability of the Road”. It will be measured at road sections selected by the Project Manager. During the initial period in which the Contractor carries out works destined to gradually increase the percentage of the road network in compliance, frequent measurements will be carried out, and their location will be based on the location of the works carried out by the Contractor. Once the 100% compliance is reached, the Project Manager may choose, during the remaining duration of the contract, to limit inspections to zones he considers “critical”. Nevertheless, towards the end of the contract period, the entire longitudinal profile of all roads included in the contract must be verified. Measurements will be taken at the same points which were used for the establishment of the original longitudinal profile at the beginning of the contract. The pieces of equipment to be used are the instruments normally used in topographical surveys.

To be representative of a one km section, five (5) measurements must be taken which are spaced 200 meters apart from each other (distance between profiles of 200 meters).

Compliance with this criterion requires that not more than one (1) profile shows a negative tolerance superior of the value specified in the contract. Positive tolerances are accepted, unless otherwise stated in the technical specifications.

2.3.6 Summary Table for Maximum and Threshold Values

*[Note: the following table is an example from a contract for unpaved roads which must be adapted to the specific requirements of the contract.]*

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Road** | **Required**  **Service**  **Level** | **Traffic Speed** | **Road User Comfort** | | | | **Durability** | | | | |
| **Average Speed (km\h)** | **Max Corrugation amplitude**  **(cm)** | **Max**  **Rut**  **Depth (cm)** | **Other Surface Degradations** | | **Vegetation** | | **Useable road width** | | **Longitudinal**  **profile** |
| **Max Dimension for single degradation (cm)** | **Max Number for 1 km long section** | **Min clearance above road surface (m)** | **Permitted maximum height (cm)** | **Reqd**  **Width (m)** | **Tolerance**  **(cm)** | **Tolerance (cm)** |
| Road A | Fair | 40 | 5.0 | 10.0 | 45.0 | 20 | 4.5 | 30 | 5.0 | 20 | 3 |
| Road B | Fair | 40 | 5.0 | 10.0 | 45.0 | 20 | 4.5 | 30 | 5.0 | 20 | 3 |
| Road C | Very Good | 60 | 2.5 | 5.0 | 30.0 | 2 | 4.5 | 30 | 6.0 | 20 | 3 |
| Road D | Good | 50 | 3.5 | 7.0 | 40.0 | 10 | 4.5 | 30 | 5.0 | 20 | 3 |
| Road E | Very Good | 60 | 2.5 | 5.0 | 30.0 | 2 | 4.5 | 30 | 6.0 | 20 | 3 |
| Road F | Good | 50 | 3.5 | 7.0 | 40.0 | 10 | 4.5 | 30 | 5.0 | 20 | 3 |
| Road G | Fair | 40 | 5.0 | 10.0 | 45.0 | 20 | 4.5 | 30 | 5.0 | 20 | 3 |

2.4 Specification of Service Level Criteria for *Paved Roads*

This section specifies the Service Levels to be complied with in the case of paved roads. There are three overall criteria:

* Road Usability
* Road User Service and Comfort Measures
* Durability Performance Measures

2.4.1 Usability of the Road

The Contractor will have to ensure that the road is open to traffic and free of interruptions at all times. **Permitted exceptions are:** *[specify exceptions, if any]*

*[Note: Permitted exceptions will have to be specified depending on the local conditions of each road. They may vary between two extremes: from a minimum of a few hours closure after severe road accidents, to a maximum of several months per year for roads which are subject to regular flooding during the rainy season. Roads in mountainous areas may be subject to landslides and require more exceptions than roads in flat areas. For countries with pronounced rainy seasons, permitted exceptions may vary between the rainy season and the dry season. In some other countries, the Contractor may be allowed to install rain barriers which may remain closed during rains and up to a certain number of hours afterwards. If the contract covers a road network which includes several different classes of roads, there may also be several classes of exceptions. In general, when defining exceptions, it is very important to closely look into the local conditions and to avoid excessively restrictive conditions.]*

2.4.2 Road User Service and Comfort Measures for Paved Roads

The service level criteria for road user service and comfort on paved roads are defined as follows:

*[Note: The table below is a sample which may be used as a basis for the actual table to be prepared for the bidding document. Modifications and additions may be needed in order to take into consideration the specific conditions of any given country or road network. Additional text may need to be added in order to explain in more detail any specific criteria, if deemed necessary.]*

| **Item** | **Service Level** | **Measurement/**  **Detection** | **Time allowed for repairs or Tolerance permitted** |
| --- | --- | --- | --- |
| **Potholes -** | Permitted maximum dimension of any single pothole  *[insert* ***value****, the suggested value is between zero and 40 c]).*  Permitted maximum number of accumulated potholes with an equivalent diameter greater than 100 mm in any continuous 1,000m section.  *[Insert* ***value****, suggested value is between zero and 10 per km of road)].* | Visual inspection.  Ruler | No tolerance allowed |
| **Patching** | Patches (i) shall be square or rectangular, (ii) shall be level with surrounding pavement, (iii) shall be made using materials similar to those used for the surrounding pavement, and (iv) shall not have cracks wider than three (3) mm. | * Visual inspection (for detection of shape and material used * Ruler (to check if patch is level with surrounding pavement * Small transparent ruler (for cracks) | Non-complying patches must be repaired within days after their detection  *[insert* ***value*** *for each service level – a period between 7and 28 days is recommended]*. |
| **Cracking in pavement**  (A crack is a linear opening in pavement with a width of more than 3 mm.) | There shall not be any cracks more than 3 mm wide. | Crack widths measured with small transparent ruler.  For **isolated cracks**, the “cracked area” includes 0.5 m on each side of the crack, multiplied by the length of the crack plus 0,5 m at each end. | Cracks more than 3 mm wide must be sealed within [insert ***Value****– a period of 28 days is recommended]*days after their detection. |
| **Multiple cracks in the pavement** | For any 50m section of the pavement, the cracked area cannot be more than ten (10) percent of the pavement surface. | For **multiple cracks** and cracks crossing each other, the “cracked area” is equivalent to a square area, parallel to the lanes, which fully encloses the cracks, and where the closest crack is at least 0.25 m away from the sides of the square. | Areas with multiple cracks must be sealed within [insert ***Value****– a period of 28 days is recommended]* days after their detection. |
| **Cleanliness of the pavement surface and shoulders.** | The road surface must always be clean and free of soil, debris, trash and other objects. | Visual inspection | Dirt, debris and obstacles must be removed:   * within *[insert* ***value*** *for each type of service level,* *the recommended time is between 1 and 8 hours]* if they pose a danger to traffic safety * Within *[insert* ***value*** *for each service level the recommended value is between 3 days and 14 days]* if they do not pose any danger to traffic safety. |
| **Rutting** | There shall not be ruts deeper than *[insert* ***value****]* mm.  Rutting of more than ten (10) mm shall not be present in more than 5 percent of any of the road sections defined in the contract.  *[Note: A maximum allowable rut depth of between 20 and 40 mm is recommended]* | Measured with 2 rulers (horizontal ruler of three 3 m length placed perpendicularly across lane; rut depth measured as space between horizontal ruler and lowest point of rut, using a small ruler with scale in mm) | Rutting above threshold value must be eliminated within *[insert* ***number*** *a period between 28 - 56 days is recommended]* of days. |
| **Raveling** | Raveled areas must not exist. | Visual inspection. | Raveled areas must be sealed within [*insert* **value** for each service level, the recommended value is between 28 – 56 days]) days after their detection. |
| **Loose Pavement edges** | There shall not be loose pavement edges, or pieces of pavement breaking off at the edges. | Visual inspection | Repairs must be completed within days after the detection of the defect.  [*insert* ***Valu****e for each service level – a period between 28 and 56 days is recommended)* |
| **Height of shoulders vs. height of pavement** | Difference in height at edge of pavement shall not be more than *[insert* ***value****]* mm.  *[Note: A maximum of 75 mm should not be exceeded.]* | Measured with ruler, with scale in mm. | Repairs must be [*insert* ***Value*** *for each service level – a period between 28 and 56 days is recommended*] completed within days after the detection of the defect. |
| **Paved shoulders** | Must always be   * sealed to avoid water penetration * without deformations and erosions * free of potholes and erosions | Visual inspection | Repairs must be completed within days *[insert* ***Value*** *for each service level– a period between 28 and 56 days is recommended]* after the detection of the defect. |

* + 1. Durability measures for paved roads
       1. Road Roughness

The Contractor is responsible for ensuring that the road roughness is below the threshold values given in the table below: *[insert* ***table****, see sample table below.]*

*[Note: Although road roughness could also be considered a Road User Comfort Measure, for the purposes of this contract it is considered to be a Road Durability Measure.]*

*[Note: There are three threshold values:*

* *Average for complete road(s) or road section(s) - - indicate maximum acceptable IRI for each road or road section]*
* *Maximum allowed average for any one-km section within road or road section - - indicate maximum one-km average IRI for each road or road section*
* *Maximum allowed average for any new pavement constructed as part of the rehabilitation works.]*

| **Item** | **Service Level** | **Measurement/Detection** | **Time allowed for repairs or tolerance permitted** |
| --- | --- | --- | --- |
| **Maximum IRI for any one-km section of existing pavement** | Average value for any one-km road section must be less than the threshold value given below (in IRI average)  Road 1: ……… IRI  Road 2: ……… IRI  Road 3: ……… IRI  Road …. | Measured with calibrated equipment (Bump Integrator). | No tolerance allowed. |
| **Maximum IRI for any length of new pavement** | Average value for any one-km road section must be less than the threshold value given below (in IRI average)  Road 1: ……… IRI  Road 2: ……… IRI  Road 3: ……… IRI  Road …. | Measured with calibrated equipment (Bump Integrator). | No tolerance allowed. |
| **Average Pavement roughness for entire road** | Average value for entire road or road section must be less than the threshold value given below (in IRI average)  Road 1: ……… IRI  Road 2: ……… IRI  Road 3: ……… IRI  Road …. | Measured with calibrated equipment (Bump Integrator). | No tolerance allowed. |

2.4.2.2 Road Deflection

The Contractor is responsible for ensuring that the average road deflection of any one-km road section is below the threshold values given in the table below: *[insert* ***table****, see sample table]*

| **Item** | **Service Level** | **Measurement/Detection** | **Time allowed for repairs or tolerance permitted** |
| --- | --- | --- | --- |
| **Deflection** | Average of section must be below the threshold values indicated for each road section.  Road 1: .……  Road 2: ……..  Road 3: …….  Road ... | Measured with Benkelman beam every 50 meters. Threshold value is average for sections of ………meters. | No tolerance allowed. |

2.4.2.3 Pavement Width

The Contractor is responsible for ensuring that the pavement width is at least as wide as specified below *[insert* ***table;*** *the minimum pavement width should be defined for each section of road in the contract]*

|  |  |  |  |
| --- | --- | --- | --- |
| **Item** | **Service Level** | **Measurement/Detection** | **Time allowed for repairs or tolerance permitted** |
| **Pavement Width** | Pavement width must be at least wide as specified in the contract | Manual measurement using a metallic measuring tape | No tolerance allowed |

2.4.3 Variations and gradual compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria is not expected until: *[insert* ***number of days*** *after the Start Date]*

*[Note: the following table is an example which must be adapted to the specific requirements of the contract]*

**SAMPLE TIMETABLE for paved roads***(for illustration purposes only)*

| **Timetable of compliance with Service Level requirements** | | | |
| --- | --- | --- | --- |
| No. months since beginning of Contract | **Usability of the road(s)**  Compliance required on  *(% of total length of roads under contract)* | **Road User Comfort**  Compliance required on  *(% of total length of roads under contract)* | **Durability of the road(s)**  Compliance required on  *(% of total length of roads under contract)* |
| 1 and 2 | No minimum set | No minimum set | No minimum set |
| 3 | 100 | 3 | 2 |
| 4 | 100 | 8 | 4 |
| 5 | 100 | 13 | 7 |
| 6 | 100 | 18 | 11 |
| 7 | 100 | 24 | 15 |
| 8 | 100 | 30 | 20 |
| 9 | 100 | 36 | 25 |
| 10 | 100 | 42 | 30 |
| 11 | 100 | 50 | 35 |
| 12 | 100 | 60 | 40 |
| 13 | 100 | 70 | 45 |
| 14 | 100 | 80 | 51 |
| 15 | 100 | 90 | 57 |
| 16 | 100 | 100 | 63 |
| 17 | 100 | 100 | 69 |
| 18 | 100 | 100 | 75 |
| 19 | 100 | 100 | 81 |
| 20 | 100 | 100 | 87 |
| 21 | 100 | 100 | 93 |
| 22 until End of contract period | 100 | 100 | 100 |

*[Note: If the contract includes several groups of roads with different Service Level requirements, a separate table must be presented for each group. In countries with very pronounced rainy seasons, it may not be reasonable to request full compliance with all criteria during the rainy season, and different tables may be presented for the dry and rainy seasons. In particular, it might be necessary to suspend any increase in the percentage of the network where the Contractor must comply with Road User Comfort and Durability requirements. These and other potential limitations must be carefully evaluated by those preparing the Technical Specifications.]*

2.4.4 Means used for Assessing of Service Levels forPaved Roads

For the formal inspections of compliance with Service Levels, the Contractor’s Self-control Unit will work in close collaboration with, and under supervision of the Project Manager. The physical means needed for the inspections will be provided by the Contractor; they are the same which are normally used by the Self-control Unit for the continuous self-evaluation of the Contractor’s compliance, in particular:

1. Vehicles of the following type: *[specify* ***number and type*** *of vehicle]*
2. *[Note: The vehicle(s) should be of the type most typically used by road users. Different types of vehicles may need to be specified for different groups of roads.]*
3. Qualified and support staff: *[specify* ***number and type*** *of staff, normally it should include as a minimum the qualified staff of the Self-control Unit plus two helpers.]*
4. All equipment, tools and instruments needed, as indicated in the paragraphs describing the methodologies for inspection.

2.4.5 Methodologies and Procedures to Be Used for Measurement of Service Levels on Paved Roads

2.4.5.1 Methodologies for Durability Measures

The methodologies to be used for inspections of Service Levels are as follows:  *[Identify* ***methods****; if needed, give details in annexes]*

*[Note: This section must be complemented by a detailed description of the methodologies to be used for measuring Service Levels for paved roads in particular. The following general guidance should be taken into consideration:*

***Roughness***

*A range of devices are available to measure the ride quality of a road as indicated by the roughness statistic. While variations exist, these different devices can broadly be categorised into one of the following two types:*

* *Response type meters*
* *Profilometers*

*The former of the two yields an estimate of the road roughness directly from the movement of the vehicle along the road. These need to be calibrated against a reference roughness. Examples of this approach include the Bump Integrator.*

*The second grouping of devices record the elevation profile of the road surface and this is used to establish the roughness. Within this class of devices are simple hand pushed devices, through to vehicle mounted systems.*

*For flexibility in the use of the data, outputs should be expressed both in International Roughness Index (IRI in m/km) plus any local variations in use (NAASRA counts, Bump Index etc).*

*The reporting interval for the roughness data should be such that it is both sufficiently long to include all the wavelengths of road profile that make up roughness, but also sufficiently short that the maintenance contractor can identify the discrete defects that are adding to the overall roughness. Often these two competing demands will result in two separate values being provided, one summarised at 50 or 100m intervals, and the other at 10 or 20m intervals.*

*In deciding what method to use to record roughness, a number of factors should be considered, including:*

* *The required accuracy of measurements. Typically, if there are financial consequences (bonuses or penalties) involved, then more accurate information is required.*
* *The robustness of the equipment in comparison to the operating conditions likely to be experienced. While often of a lower accuracy, the response type meters are often more robust than the high technology devices.*
* *The technology to be used in maintaining and rehabilitating the road network. There is little point in measuring the roughness to the nth degree, if the work is then undertaken to a relatively low standard using low technology methods.*

*Typically, response-type meters are used when the roughness is > 6 m/km IRI or the roads are unsealed. Profilometers are used when high precision is required.*

*Regardless of what device is used, it must be calibrated/validated over the range of road conditions and vehicle speeds reasonably expected during the surveys. Such calibration/validation should be undertaken during the data collection phase as per the manufacturer’s recommendations and from observations during previous use.*

***Deflection***

*The deflection of a road is taken to be an indication of its load carrying capacity. Like roughness, various methods exist to determine the strength of the pavement, with the more common being the Falling Weight Deflectometer (FWD) and the Benkelman Beam (BB). With both of these devices, a weight is applied to the road and then the resulting deflection of the road surface measured. The magnitude and shape of the deflections at various distances from the load are then used to infer the structural capacity.*

*The interval of testing for network management is generally lesser than that required for pavement design. While results at 10m or 20m intervals may be required for pavement design purposes, for network management intervals of several hundred meters are quite common. The more uniform the construction methods and subgrade conditions, then the greater the interval of testing can be without a substantial loss in confidence in the results.*

*Moisture and other factors can play a significant part in the deflections measured and hence in determining the remaining life of the pavement. It is necessary to document what methodology will be utilized to normalize results from one survey to the next. This is particularly so when bonus/penalty payments are at risk based on the estimated remaining life of the pavement.*

*There is a strong body of evidence that indicates deflections do not change greatly from one year to the next, until nearing the time of pavement structural failure. On this basis, a rolling programme of testing may well provide sufficient results for the management of the assets.]*

2.4.5.1.2 Procedures for Inspection

The formal inspections of Service Levels on paved roads will be carried out following the procedures presented in this section.

1. *Usability of Road*

There is no particular testing method for the usability of a road, other than driving on the road in a normal manner, utilizing the type of vehicle indicated in the previous paragraph. The condition is not complied with if the road is interrupted at any point. The condition is however complied with if it is possible to continue to drive on the road, and without the vehicle suffering any damage caused by the bad condition of the road.

*(b) Road User Comfort Measures and Pavement Width*

Procedures for the inspections of operation measures and pavement width aspects of the road shall be in accordance with Clause 2.1.14.1.and Clause 2.4.2

***(c) Road Roughness***

Every year and each time a pavement has been modified through rehabilitation, overlay or similar works, the road roughness will be measured by the Contractor under supervision of the Project Manager. The methodology to be used for measurement is presented in the corresponding annex of the Specifications.

If the measurement reveals that the road roughness is above the threshold established, the Project Manager will establish a time frame for the Contractor to take the measures necessary correct the defect. That time frame should normally ensure that the corresponding works are completed within four months and before the next measurement is due to be carried out. The Project Manager may however grant a longer period if, in the opinion of the Project Manager, the circumstances warrant such longer period.

The criteria for “Road User Service and Comfort” will be checked at road sections selected by the Project Manager based on visual appearance. If the measured value exceeds the specified maximum value the one-kilometer section in which the defect occurs will be judged non-compliant.

The liquidated damages for non-compliance with the Service Level requirement on road roughness, beyond the time limit determined by the Project Manager, is set at *[insert* ***amount and unit****].*

*[Note: It is recommended to set an amount per 100 meter section of each non-complying travel lane; suggested amount is US$ 4 per day of non-compliance. For example, for a non-complying section of 5,000 meter of a two-lane road, the liquidated damages would be US$400 per day.]*

***(d) Road Deflection***

The Contractor is required to guarantee that the pavement deflection of the roads under contract is below the threshold values indicated in the Technical Specifications, at a certain point of time during the contract. That point of time is: *[insert* ***point of time****]*

*[Note: The main purpose of this Service Level criterion is that the roads under contract are in a sound structural condition at the end of the contract period. This criterion must be safeguarded through an adequate warranty, such as a performance guarantee. The point of time for compliance should be determined in such a way as to enable the Contractor to carry out the necessary strengthening works before the end of the contract. The suggested point of time is one year before the end of the contract. For contracts covering larger road networks, a staggered timetable could be set in which different points of time are set for separate parts of the network. For example, 40% of the network must comply 18 months before the end of the contract, another 40% must comply 12 month before the end of the contract, and the remaining 20% must comply 6 month before the end of the contract.]*

The methodology to be used for measuring road deflection is described in the corresponding annex to the Specifications.

For each road under contract, the Contractor is obliged to measure pavement deflection at least once a year, as part of his normal activities of monitoring and evaluation. He will inform the Project Manager at least one week in advance about the time and location of pavement deflection measurements to be carried out, in order to enable the Project Manager to assist the process and verify the results. If during any of those measurements it is revealed that the pavement deflection is above the threshold established, the Project Manager will establish a time frame for the Contractor to take the measures necessary to correct the defect, and to have completed those measures at the point of time established for compliance. The Project Manager may however grant a longer period if, in the opinion of the Project Manager, the circumstances warrant such longer period.

The Employer is entitled to retain the performance guarantee provided by the Contractor until all the roads under contract comply with the pavement deflection criteria. If at the end of the contract period, the Contractor has not complied with the Service Level criteria on pavement deflection, the Employer is further entitled to employ other contractors to carry out the works necessary to ensure compliance with pavement deflection criteria, and use the amount of the performance guarantee, wholly or in part, to pay for those works. In any case, if at the end of the contract period, the Contractor has failed to carry out the works necessary to remedy any non-compliance with the pavement deflection criteria, the Contractor forfeits any right to obtain reimbursement of the performance guarantee.

2.5 Signaling and Road Safety

2.5.1 Service Levels Measures for Signaling and Road Safety

The Contractor is responsible for ensuring that all horizontal and vertical signaling, as well as guardrails and other road safety devices fully comply with *[insert either a complete inventory for the roads under contract, or a certain national or international standard which may have been adopted.]*.

The Service Level requirements for signaling and road safety devices are as shown in the following table:  *[see sample table below]*

| **Item** | **Service Level** | **Measurement/**  **Detection** | **Time allowed for repairs or Tolerance permitted** |
| --- | --- | --- | --- |
| Information signs | Signal has to be present, complete, clean, legible, and structurally sound | Visual inspection | Absent or defect signs must be replaced within fourteen (14) days.  Guardrails damaged by accidents must be replaced within seven (7) days |
| Warning signs | | Signal has to be present, complete, clean, legible and structurally sound; and clearly visible at night ° | Visual inspection |  |
| Traffic ruling signs | | Signal has to be present, complete, clean, legible and structurally sound; and clearly visible at night. | Visual inspection |
| Horizontal demarcation: and/or pavement paint | | Have to be present, legible and firmly attached to pavement. Micro spheres must be firm and visible. | Visual inspection |
| Mileposts and guidance posts | | Have to be present, complete, clean, legible and structurally sound; surface painted or otherwise covered. | Visual inspection |
| Guardrails | | Have to be present, clean, without any significant damage, without corrosion. | Visual inspection |

2.5.2 Variations and gradual compliance with Service Levels for Signaling and Road Safety

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria shall be in accordance with the timetable for Road User Service and Comfort Levels.

Other limitations to the compliance requirement are:

2.5.3 Procedures for Inspection

The visual inspection will be undertaken as part of the Formal and Informal inspectionsThe criteria for Signaling and Road Safety will be checked at sections selected by the Project Manager based on visual appearance. The Project Manager shall be the sole judge of compliance. If a specified criterion is not meet, the one-kilometer section in which the deficit occurs will be judged non-compliant**.**

2.6 Drainage

2.6.1 Service Levels

In general terms, the Contractor must ensure that all drainage elements and structures are without any obstructions which may reduce their normal cross-section and impede the free flow of water.

The Service Level requirements for drainage structures or devices are as shown in the following table:  *[see sample table below]*

| **Item** | **Service Level** | | **Measurement**  **Detection** | **Time allowed for repairs or Tolerance permitted** |
| --- | --- | --- | --- | --- |
| Ditches and vertical drains with lining | Must be clean and lining without any significant damage of the lining. | Visual Inspection | | Tolerance permitted:  Obstructions equivalent to less than 10% of capacity of item.  Obstructions must be cleared within seven (7) days after detection.  Damages must be repaired within three weeks after detection. |
| Ditches and vertical drains without lining | Must be clean and free of obstacles. |  | |  |
| Collectors | Must be clean and free of obstacles, and without structural damage. Must be firmly contained by surrounding soil or material. |  |
| Culverts and similar | Must be clean and free of obstacles, and without structural damage. Must be firmly contained by surrounding soil or material. |  |

2.6.2 Variations and Gradual Compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria shall be in accordance with the timetable for Road Durability Criteria specified in *[*insert **clause** number***].***

2.6.3 Procedures for Inspection

The cleanliness and condition of drainage structures (including ditches, Irish crossings and all other types of drainage devices) is part of the criteria for the “Durability of the Road”. It is verified on a regular basis, in particular before and during the rainy season. The drainage structures to be verified are determined by the Project Manager. Inspection is done visually.

The basic principle used to determine the cleanliness of drainage structures or devices is “the percentage of the theoretical cross-section of the structure or device which is unobstructed”. This percentage is specified in the Summary Table above. For a one km road section, the cleanliness of drainage ditches must be verified at least on two subsections of 50 meters each.

For any one km section of the road, compliance with this criterion requires that (i) all drainage structures are clean in the sense defined above; (ii) all structures and devices are structurally sound, based on the judgment of the Project Manager.

2.7 Vegetation

2.7.1 Service Levels

This section specifies the Service Levels to be complied will in the case of vegetation growing within the road right-of-way:

Vegetation is to be controlled to the heights, at the locations and with the restrictions as set out in the table and diagram below.

*[insert* ***table and associated diagram*** *to define criteria].*

*[Note: the following table and diagram is an example which must be adapted to the specific requirements of the contract*

**Table 1: Vegetation Control Types**

| **Type** | **Height (mm)** | **Features Applied To:** |
| --- | --- | --- |
| 1 | 25 – 75 | Urban highway shoulders, medians, traffic islands and highway verges, grass in rest areas (including around rest area furniture). |
| 2 | 25 – 300 | Non-urban roads and large vegetated areas, including surface water channels with longitudinal gradient ≥ 3%. |
| 3 | Vegetation Free or Near Vegetation Free1 [Note vegetation up to 200 mm high may be acceptable in these zones] | Vegetation control around:   * Edge marker posts * Signposts * Bridge end and culvert markers * Guardrails * Sight rails * Lighting Columns * Bridge abutments |
| 4 | Vegetation Free or Near Vegetation Free1 | Applies to vegetation control around:   * Culvert ends * Culvert headwalls * Side drains * Culvert waterways * Surface water channels with gradient < 3% (except where nominated for mowing in the specific contract requirements) * Weigh pits * Kerb and channel * Lined channels * All sealed surfaces * Metalled shoulders * Bridge decks. |
| 5 | Growth removed when it encroaches into the Vegetation Free Zone from the side or top. | Applies to vegetation control of vegetation in the envelope, including trees, scrub or branches hanging into the Vegetation Free Zone (within 0.5m of the line of the edge marker posts or to within 6.0m above the pavement)  (See Diagrams 6 and 7) |

2.7.2 Variations and Gradual Compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria shall be in accordance with the timetable for Road User Service and Comfort Measures specified above. *[Insert* ***Clause*** *number]*

Other limitations to the compliance requirement are:

*[Note: Limitations may vary between one road and other and may include limitations on the use of herbicides etc]*

2.7.3 Means used for Assessing Compliance with Service Levels

The height of vegetation, and its clearance above the road surface, is part of the criteria for the “Road User Comfort”. They will be measured at road sections selected by the Project Manager based on their visual appearance. The height is measured by using a ruler; it is defined as the vertical distance between the ground and the highest point of the vegetation. Clearance is also measured with a ruler; it is defined as the distance between the lowest point of the tree (or other plant) above the road surface.

The average height of vegetation in a one km section will be equal to the average of five values measured in at sections selected by the Project Manager.

For any one km section of road, compliance with this criterion requires that the average vegetation height measured within the section of one km is below the maximum value stated in the contract.

2.8 Structures

The Contractor is responsible for the routine maintenance of all bridges and similar structures along the roads and road sections included in the contract. In particular, he will be responsible for the correct functioning of the structures (paint of metallic structures, road surface on structures, condition and presence of guardrails) and the safety and comfort of road users while using the structures at normal speeds. Nevertheless, the reconstruction and improvement of bridges and similar structures is excluded from the Contractor’s obligations, unless specified elsewhere in the Technical Specifications.

2.8.1 Service Levels

The Service Level requirements for bridges and retaining walls and similar structures are as shown in the following table:

*[Note: The table below is a sample which may be used as a basis for the actual table to be prepared for the bidding document and the contract. Modifications and additions may be needed in order to take into consideration the specific conditions of any given country or road network. Additional text may need to be added in order to explain in more detail any specific criteria, if deemed necessary.]*

| **Item** | **Service Level** | **Measurement/ Detection** | **Time allowed for repairs or Tolerance permitted** |
| --- | --- | --- | --- |
| **Steel or other metal structures** | Guardrails must be present and not deformed. All metal parts of overall structure shall be painted or otherwise protected and free of corrosion. Drainage system in good condition and fully functional. | Visual inspection | Contractor must immediately notify Project Manager in case of any condition which threatens structural integrity of the structure |
| **Concrete structures** | Guardrails must be present and painted. Beams and all other structural parts must be in good conditions and fully functional. Drainage system in good condition and fully functional. | Visual inspection | Contractor must immediately notify Project Manager in case of any condition which threatens structural integrity of the structure |
| **Expansion joints** | Clean and in good condition | Visual inspection | Damages and defects must be repaired within seven (7) days. |
| **Retention walls** | Contractor must control presence and adequate condition of retention walls and their drainage. | Visual inspection |  |
| Riverbeds | Contractor must ensure free flow of water under bridge and up to 100 meters upstream. Contractor must maintain design clearance under bridge. The Contractor shall take all reasonable measures to control erosion around bridge abutments and piers. | Visual inspection | Causes for non-compliance must be eliminated within fourteen (14) days after water has sufficiently receded to allow minimum working conditions. |

2.8.2 Variations and gradual compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria is not expected until *[insert* ***number of days*** *after signature or full legal notification of contract recommended are between 60 and 90 days]*

Other limitations to the compliance requirement are:

*[Note: Limitations may vary between one road and other. In some cases, it may be convenient to prepare a table similar in structure to the table used for unpaved roads]*

2.8.3 Procedures for Inspection

The visual inspections will be undertaken as part of the Formal and Informal InspectionsThe criteria for Structures will be checked at points selected by the Project Manager based on visual appearance. The Project Manager shall be the sole judge of compliance. If a specified criterion is not meet, the one-kilometer section in which the deficit occurs will be judged non-compliant**.** *[Note: If so desired by the Road Administration the specification may stipulate an annual inspection of all structures by a qualified structural engineer or Bridge Inspector. Alternatively, this inspection may be part of the terms of reference of the Supervising Engineer]*

2.9 Slopes – Cuts and Embankments

The Contractor is responsible for the maintenance of all embankment and cut slopes along the roads sections included in the contract. In particular he is responsible for ensuring they are stable, without deformations and erosions. Nevertheless, the reconstruction and major improvements to retaining structures and slope stabilization is excluded from the Contractor’s obligations, unless specified elsewhere in the Technical Specifications.

2.9.1 Service Levels

The Service Level requirements are shown in the following table. *[Note: The table below is a sample which may be used as a basis for the actual table to be prepared for the bidding document and the contract. Modifications and additions may be needed in order to take into consideration the specific conditions of any given country or road network. Additional text may need to be added in order to explain in more detail any specific criteria, if deemed necessary.]*

|  |  |  |  |
| --- | --- | --- | --- |
| **Item** | **Service Level** | **Measurement/Detection** | **Time allowed for repairs or Tolerance Permitted** |
| **Embankment slopes** | Without deformations and erosions. | Visual inspection | Repairs must be completed within seven (7) days after the detection of the defect. |
| **Removal of slides** | Slides of slope material onto the road are considered an Emergency if   * the quantity of the material is above 500 m3, or * If the slide blocks all lanes and the road traffic is completely interrupted, and quantity is above 50 m3. | If the contractor intends to invoke the contract provisions for emergencies, he estimates the quantities and immediately informs Project Managers, who them verifies. | Traffic flow to be reestablished within a maximum of 6 hours.  Period for removal of other slide material is set by Project Manager as specified under provisions for emergencies. |
| **Slopes in cuts** | Slopes in cuts must be stable and/or adequate retaining walls and slope stabilization measures must be in place. | Visual inspection for slope material on shoulders or pavement | Fallen slope material must be removed  Quantities below 50 m3:   * from pavement within 4 hours after detection * From shoulders within 48 hours after detection.   Between 50 m3 and 500 m3   * from pavement within 24 hours after detection * from shoulders within 96 hours after detection   Note: For landslides classified as “emergency” different rules apply. |

2.9.2 Variations and gradual compliance with Service Levels

In order to respect the Contractor’s initial mobilization period, compliance with any of the service level criteria shall be in accordance with the timetable for Road Durability Criteria specified above in [Insert **clause number)**.

2.9.3 Procedures for Inspection

The visual inspection will be undertaken as part of the Formal and Informal inspectionsThe criteria for Slopes will be checked at sections selected by the Project Manager based on visual appearance. The Project Manager shall be the sole judge of compliance. If a specified criterion is not meet, the one-kilometer section in which the deficit occurs will be judged non-compliant**.**

2.10 Payment Reductions and Liquidated Damages

In accordance with the relevant clauses of the GC, Payment Reductions are applied in case of non-compliance with Service Level requirements, while Liquidated Damages are applied in the case of non-compliance with required Rehabilitation and Improvement Works.

2.10.1 Determination of Payment Reductions

The results of each formal inspection of the Service Levels and other performance criteria will be recorded by the Project Manager in the form of a Memorandum. The Memorandum will state the type and location of any non-compliance detected, in particular those non-compliances already shown in the standard tables provided by the Contractor as part of their monthly statement. For each individual case of non-compliance, the Project Manager will determine a date by which the Contractor must have completed the necessary measures in order to remedy the cause of the non-compliance. A follow-up site visit is therefore necessary at the date fixed by the Project Manager, or soon thereafter, in order to verify that the Contractor has indeed remedied the cause of non-compliance.

If at the date indicated in the Memorandum, the Contractor has not remedied the cause for non-compliance, independent of the reason given for their failure to do so, the Contractor is subject to Payment Reductions in accordance with the relevant clauses of the GC.

Payment Reductions are variable over time. If the Contractor fails to remedy a cause of non-compliance for which a payment reduction has already been applied, the amount of the payment reduction increases month by month for that particular cause of non-compliance, without a ceiling being applied, until compliance is established.

The calculation of the initial (first month) amounts of payment reductions, and the formula for their adjustment over time, is to be based on the following rules:

For unpaved roads: The following table applies:

*[insert* ***Table*** *for calculation of Payment Reductions.]*

*[Note: The following Table is provided as a sample for unpaved roads taken from an existing contract. It may provide some guidance to the staff preparing specific Bidding Document. It goes without saying that it needs to be adjusted for the specific situation of the area in which the roads under contract are located****. The preparation of this table is probably the most difficult and delicate part of the overall preparation of the bidding document.*** *If the unit rates of the penalties are too high, the potential bidders will perceive a high risk and offer high prices, or not present an offer at all. It the unit rates are too low, the Contractor will have an insufficient incentive to comply with the requirements of the contract. It is strongly advised to carry out a number of simulations taking into consideration likely situations of partial non-compliance which may occur.]*

| **CRITERIA** | **CONDITIONS FOR APPLICATION OF PAYMENT REDUCTIONS** | **UNIT RATES FOR NON COMPLIANCE** | **Reference to Technical Specifications**  **(Paragraph No.)** | **Reference to inspection methodology**  **(Paragraph No)** |
| --- | --- | --- | --- | --- |
| **Road Usability** | Interruption of motorized traffic (light and/or heavy vehicles) anywhere along a new road or road section. | 20% of monthly lump sum for the entire road and all other affected roads included in the contract for each day of non-compliance |  |  |
| **Average Traffic Speed** | Average traffic speed on road or road section is below the required threshold value | 10% of monthly lump sum, applied to the entire road for each step of 5 km/h below the threshold |  |  |
| **Road User Comfort** | *Corrugation amplitude (maximum*): The maximum amplitude measured anywhere in a on km section is above the threshold value. | 50% of the monthly lump sum for the length of road which does not comply |  |  |
|  | *Rut depth (maximum)*: the maximum rut depth measured anywhere in a one km section is above the threshold value | 50% of the monthly lump sum for the length of road which does not comply |  |  |
|  | *Surface degradations:* Either the maximum size or number exceed the threshold values anywhere in a one km section | 50% of the monthly lump sum for one km applied to each one-km section which does not comply |  |  |
| **Signage & Road Safety** | *Vertical Traffic Signaling:* One or more traffic signs is absent, destroyed, non-legible, incorrectly placed or non-functional | 25% of the monthly lump sum for one km, applied to each on-km section which does not comply. |  |  |
| **Vegetation** | *Vegetation height (maximum)*: The maximum height measured anywhere in an on-km section is above the threshold value | 25% of the monthly lump sum for one km, applied to each on-km section which does not comply. |  |  |
|  | *Vegetation (clearance above road):* The vertical clearance between the road surface and the lowest point of tree or other plan is less than the threshold value | 25% of the monthly lump sum for one km, applied to each on-km section which does not comply. |  |  |
| **Road Durability** | *Useable road surface width:* For a one-km section, to be measured in subsections of 50m each. The useable road width is determined for each subsection. If the useable road width in any of the sub-sections is below the threshold value minus the tolerance allowed, the one-km section does not comply | 10% of the monthly lump sum for one km applied to each one-km section which does not comply. |  |  |
|  | *Required longitudinal profile:* For a one-km section, if two or more of the twenty profiles show a height less than the height required in the longitudinal profile, minus the allowed tolerance, the one-km section does not comply | 10% of monthly lump sum for one km, applied each one-km road section, for each step of 3 cm below the threshold |  |  |
| **Drainage** | *Cleanliness and condition of drainage structures (lateral ditches)*: For a one-km section, to be determined for subsections of 50 m each. If unacceptable obstructions exist in more than one subsection, the one-km section does not comply | 50% of the monthly lump sum for one km, applied to each one-km section which does not comply |  |  |

Note: (i) The Unit Rates of payment reductions (“PRu) shown in the above table are applicable during the first 30 days of non-compliance.

(ii) If a non-compliance has not been remedied within thirty days, liquidated damages for periods beyond 30 days are calculated based on the following formula:

**PR = 2n PRu**

considering:

J = number of days of non-compliance, and n =  rounded up to full number (without decimals)

For paved roads, there are three types of Payment Reductions:

1. **Payment Reductions for non-compliance with Road User Service Comfort Measures:** For any road or road section as specified in Section II of this document (Bid Data Sheet), the Employer may reduce the monthly lump-sum payment by the percentage of non-complying kilometers as determined by the Project Manger each month. [Clause 2.1.14.1]. The payment will therefore be the basic lump-sum multiplied by the ratio of length of complying road to the total length of the network.

(ii) **Payment Reductions for non-compliance with road roughness criteria:** Calculated based on the provisions shown in section 2.5.4.2 (b) of the Technical Specifications. The amount of the reduction is to be deducted by the Employer from the monthly lump-sum payments due to the Contractor.

(ii) **Payment Reductions for non-compliance with pavement deflection criteria:** In case of non-compliance, the payment reductions are equivalent to the amount needed by the Employer to have the works carried out which are necessary to establish the conditions of compliance which the Contractor should have complied with according to the contract. However, the maximum amount of payment reduction applicable by the Employer for non-compliance with Service Level criteria on pavement deflection is equivalent to the performance guarantee provided by the Contractor for the entire contract.

2.10.2 Determination of Liquidated Damages

*[insert* ***section*** *on how to determine Liquidated Damages in case of non-compliance with performance criteria for Rehabilitation and Improvement Works. This should be done on a case by case basis, given that that the extent of rehabilitation and improvement works can be vastly different from one contract to another.]*

Proposed sample text for Section VI, Part C

**Specifications for Emergency Works**

**List of Contents**

Part C1 Specifications for Emergency Works

1. Definition of “Unforeseen Natural Phenomena”

2. Procedure for requesting Emergency Works

3. Remuneration of Emergency Works

4. Provision for Emergency Works

5. Obligations of Contractor during Emergencies and Emergency Works

6. Minor repairs made necessary by “Unforeseen Natural Phenomena”

1. Definition of “Unforeseen Natural Phenomena”

Emergency Works are designed to repair those damages to the roads under contract which are caused directly by unforeseen natural phenomena with imponderable consequences occurring either in the area of the roads or elsewhere, but with a direct impact on the roads. “Unforeseen Natural Phenomena” are defined as follows*: [indicate the type of phenomena and thresholds values]*

*[Note: “Unforeseen Natural Phenomena” are normally defined as (i) rainfalls and winds of an extraordinary intensity and/or duration, (ii) major landslides which have their origin outside the right-of-way of the road, (iii) floods during which water levels rise above a certain maximum, (iv) earthquakes above a certain intensity, etc. The definition of those phenomena and events is necessarily country-specific, and even specific for different areas within one country. They must be specified in such a way as to exclude “normal” damages, such as trees falling on the road, minor erosions of the road and embankments, and damages caused by traffic accidents; those must be remedied by the Contractor as a part of his normal obligations under the contract.]*

Without being limitative, the following is a list of damages requiring Emergency Works*:[Indicate list.]*

*[Note: Examples of how eligible damages can be defined are: (i) complete destruction of a culvert as a result of exceptional rainfall quantities, which lead to an interruption of road traffic, (ii) interruption of a road following washouts equivalent of more than 100 (one hundred) cubic meter of material on a road section of 500 meters length, (iii) submersion of the road along more than 100 meters, provided that the submersion is not the result of deficiencies in the drainage system or of insufficient maintenance of drainage structures, etc.]*

2. Procedure for Requesting Emergency Works

If damages clearly caused by “Unforeseen Natural Phenomena” result in a reduction of Service Levels below the normal threshold values specified in this contract, the Contractor may make a formal request to the Project Manager to carry out Emergency Works designed specifically to remedy those damages. If the Contractor decides to make a request for Emergency Works, he must (i) immediately inform the Project Manager of his intention to do so, by telephone, radio or other means, (ii) document the circumstances of the Force Majeure event and the damages caused, through photographs, video and other suitable means, (iii) prepare a written request, stating the type of works he intends to carry out, their exact location and the estimated quantities and costs, including photographic documentation. In any case, a request for Emergency Works must be made immediately after the Contractor gains knowledge of the existence of damages caused by “Unforeseen Natural Phenomena”.

The Project Manager, upon receipt of the request and not later than 24 hours thereafter, will evaluate the request made by the Contractor based on a site visit, and issue an order to carry out the Emergency Works. The order will specify the type of works, their estimated quantities, the remuneration to be paid to the Contractor, and the time allowed for their execution. The order may indicate a requirement for an engineering/geotechnical assessment of the options for the permanent repairs to the site.

3. Remuneration of Emergency Works

Emergency works are remunerated by the Employer on a lump sum for each work order established on the basis of estimated quantities, the unit prices being stated in the Bill of Quantities, and in accordance with the relevant clauses of the GC. The work items and the unit prices to be applied are specified in Section IV (Bidding Forms - Bills of Quantities) of this bidding document.

*[Note: The unit price table for Emergency Works must be provided in the relevant Bill of Quantities of the bidding document, and shall list (i) the types of works which are likely to occur under emergency and (ii) hypothetical quantities for those works. The bidders then give their prices as part of their bid. As an alternative the Employer can define the rates that will be used to recompense the Contractor. If this option is selected the unit prices are not subject to bidding and should be established during the preparation of the bidding document, by calculating the average prices of several recent contracts in areas presenting similar conditions as the roads under contract.]*

4. Provision for Emergency Works

The total contract amount will include a Lump Sum for provisional quantities of Emergency Works during the contract period, in accordance with the bidding data. The actual payments for emergency work will be based on the tendered rates.

*[Note: The Provisional Sum is a percentage of the sum of all other price components of the contract. The percentage may vary widely from one contract to another, depending on the particular conditions of the area in which the roads under contract are located. It is probably higher for mountain roads than for roads in flat areas, but there are many other factors which may play a role. As a rule of thumb, the provision may be estimated somewhere between 5 and 25 percent of the total contract amount.]*

5. Obligations of Contractor during Emergencies and Emergency Works

Given the nature of this contract and the fact that Emergency Works are remunerated separately, the Contractor will, during the execution of Emergency Works, continue to be responsible for assuring the normal Service Levels on all roads included in the contract. In particular, the Contractor will do everything reasonably possible in order to ensure the normal use of all the roads under contract, including the sections affected by emergencies.

If road traffic has been interrupted because of an emergency, the Contractor will take the measures necessary (i) to reopen the road to traffic in the shortest time possible, and (ii) maintain the road open during emergency works, without being entitled to a specific compensation for those measures. This is valid specifically for trees or other objects which may have fallen on the road, damage to access ramps to bridges, erosion of embankments, collapse of slopes, traffic accidents, flooding, etc.

6. Minor repairs made necessary by “Unforeseen Natural Phenomena”

If the works necessary to remedy damages caused by an “Unforeseen Natural Phenomena” are below certain threshold values, the Contractor will carry out those works as part of his normal obligations and without having the right to invoke the provision of the contract concerning emergencies and the remuneration of emergency works. In these cases, the consent of the Project Manager is not needed and the Contractor will simply carry out the works on his own initiative. He will nevertheless inform the Project Manager of the damages occurred and the remedial measures taken.

The threshold values for minor repairs are as shown in the table below*: [insert* ***table****]*

*[Note: Below is a sample table which may need to be adapted to the specific circumstances of the roads under contract]*

|  |  |  |
| --- | --- | --- |
| **Activity** | **Unit** | **Quantity per emergency event** |
| Slides of material onto road | M3 | 200 |
| Culverts | Number | 1 |
| Asphalt concrete | M3 | 20 |
| Base course | M3 | 50 |
| Concrete | M3 | 5 |
| Embankment | M3 | 200 |

1. The Bank offers two types of international public bidding documents (ICB): Request for Bids (RFB) that shall be used when the Borrower can specify in detail all the requirements, which allows firms to submit bids that meet the requirements established in the bidding document and where the evaluation criteria are normally expressed in monetary terms; and the Request for Proposals (RPF) to be used when the Borrower cannot clearly specify its requirements (in general, it is used for complex and innovative procurement), which allows firms to submit proposals that vary in the degree of compliance with the requirements established in the bidding document; in that case, the evaluation criteria usually include rated type criteria. [↑](#footnote-ref-2)
2. Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas [↑](#footnote-ref-3)
3. In such cases, the Bank must be satisfied with the functionality of said system, as provided in paragraph 2.11 of the Procurement Policies. [↑](#footnote-ref-4)
4. Information on how to present allegations of Prohibited Practices, the application of rules regarding investigation and sanctions process, and the agreement regulating the mutual recognition of sanctions among the IFI’s are available on the Bank's web site (www.iadb.org/integrity) [↑](#footnote-ref-5)
5. Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas [↑](#footnote-ref-6)
6. Control means the power to, directly or indirectly, direct or cause the direction of the management and policies of the companies or projects, whether through the ownership of voting shares, by contract or otherwise. It could include majority ownership of voting shares, other control mechanisms (such as “golden shares”, veto rights or shareholders’ agreements requesting special majorities) or, in the case of investment fund financing, the control exercised by a general partner or fund manager. Control will be determined in the context of each specific case. [↑](#footnote-ref-7)
7. A close relationship should be understood as being related up to the fourth degree of relationship by blood (consanguinity) or by adoption, or up to the second degree of relationship by marriage or domestic partnership (affinity). [↑](#footnote-ref-8)
8. Non-performance, as decided by the Employer, shall include all contracts where (a) non-performance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Non-performance shall not include contracts where Employers decision was overruled by the dispute resolution mechanism. Nonperformance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted. [↑](#footnote-ref-9)
9. This requirement also applies to contracts executed by the Bidder as JVCA member. [↑](#footnote-ref-10)
10. The Bidder shall provide accurate information on the related Bid Form about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five years. A consistent history of court/arbitral awards against the Bidder or any member of a joint venture may result in disqualifying the Bidder. [↑](#footnote-ref-11)
11. The Employer may use this information to seek further information or clarifications in carrying out its due diligence [↑](#footnote-ref-12)
12. Substantial completion shall be based on 80% or more works completed under the contract. [↑](#footnote-ref-13)
13. For contracts under which the Bidder participated as a joint venture member or sub-contractor, only the Bidder’s share, by value, shall be considered to meet this requirement [↑](#footnote-ref-14)
14. In the case of JVCA, the value of contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single contract has been met. Instead, each contract performed by each member shall satisfy the minimum value of a single contract as required for single entity. In determining whether the JVCA meets the requirement of total number of contracts, only the number of contracts completed by all members each of value equal or more than the minimum value required shall be aggregated. [↑](#footnote-ref-15)
15. Volume, number or rate of production of any key activity can be demonstrated in one or more contracts combined if executed during same time period.  [↑](#footnote-ref-16)
16. The minimum experience requirement for multiple contracts will be the sum of the minimum requirements for respective individual contracts, unless specified otherwise. [↑](#footnote-ref-17)
17. See Annex 1 in the Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas [↑](#footnote-ref-18)
18. If the most recent set of financial statements is for a period earlier than 12 months from the date of Bid, the reason for this should be justified. [↑](#footnote-ref-19)
19. If applicable [↑](#footnote-ref-20)
20. Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas [↑](#footnote-ref-21)
21. The sum of the two coefficients Ac and Bc should be 1 (one) in the formula for each currency. Normally, both coefficients will be the same in the formulae for all currencies, since coefficient A, for the nonadjustable portion of the payments, is a very approximate figure (usually 0.15) to take account of fixed cost elements or other nonadjustable components. The sum of the adjustments for each currency is added to the Contract Price. [↑](#footnote-ref-22)
22. Information on how to present allegations of Prohibited Practices, the application of rules regarding investigation and sanctions process, and the agreement regulating the mutual recognition of sanctions among the IFI’s are available on the Bank's web site (www.iadb.org/integrity) [↑](#footnote-ref-23)
23. Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas [↑](#footnote-ref-24)
24. *1 The Guarantor shall insert an amount representing the percentage of the Accepted Contract Amount specified in the Letter of Acceptance, less provisional sums, if any, and denominated either in the currency(cies) of the Contract or a freely convertible currency acceptable to the Beneficiary.* [↑](#footnote-ref-25)
25. *2 Insert the date twenty-eight days after the expected completion date. The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”* [↑](#footnote-ref-26)
26. *1 The Guarantor shall insert an amount representing the percentage of the Accepted Contract Amount specified in the Letter of Acceptance, less provisional sums, if any, and denominated either in the currency (cies) of the Contract or a freely convertible currency acceptable to the Beneficiary.* [↑](#footnote-ref-27)
27. *2 Insert the date twenty-eight days after the expected completion date. The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months] [one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”* [↑](#footnote-ref-28)
28. 1 *The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.* [↑](#footnote-ref-29)
29. 2 *Insert the expected expiration date of the Time for Completion. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”* [↑](#footnote-ref-30)
30. 1 *The Guarantor shall insert an amount representing the amount of the second half of the Retention Money or if the amount guaranteed under the Performance Guarantee when the Taking-Over Certificate is issued is less than half of the Retention Money, the difference between half of the Retention Money and the amount guaranteed under the Performance Security and denominated either in the currency(ies) of the second half of the Retention Money as specified in the Contract, or in a freely convertible currency acceptable to the Beneficiary.* [↑](#footnote-ref-31)
31. *2 Insert the same expiry date as set forth in the Performance Security, representing the date twenty-eight days after the completion date. The Employer should note that in the event of an extension of this date for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Beneficiary’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”* [↑](#footnote-ref-32)