STANDARD BIDDING DOCUMENTS

Procurement of Works

Smaller Contracts

Request for Bids (RFB) under International Competitive Bidding

Inter-American Development Bank

April  2022

Revisions

| Version | Modification | Reason |
| --- | --- | --- |
| October 2005 | First publication | First publication |
| August 2006 | Section I – Instruction to Bidder - Clause 3; Section V – General Condition of Contract – Clause 60 | Modification to the Policies for the Procurement of Goods and Works financed by the Inter-American Development Bank in the paragraph 1.14 (GN-2349-7) |
| 2011 | Section I Clause 3: Prohibited Practices; Clause 4: Eligible Bidders; Bidding Form; Section V Clause 60: Prohibited Practices. | Modification to the Policies for the Procurement of Goods and Works financed by the Inter-American Development Bank GN-2349-9. Modification of prohibited practices’ definitions and incorporation of cross debarment. |
| April 2019 | ITB, Forms and SCC | The instructions on conflict of interest are enhanced and aligned to the provisions of the other MDB. The terms “ITB Clause” and “ITB Sub-clause” are replaced with “ITB” for the terms “Clause” and “Sub-clause” to be used only in the Conditions of Contract. Instructions on correction of arithmetic errors in lump-sum bids and bids with BOQ separated. Use of bold font is reduced to avoid distraction while reading the ITB. Footnotes numbers restart in each section. The Section X is renamed “Contract Forms.” Provisions in the Letter of Bid and other parts of the bidding document added following advice of OII. Added detailed instructions for filling out the Bid Data Sheet |
| January 2020 | ITB, GCC and Forms | The revision is consequence of the approval by the Board of Executive Directors of Bank of the Procurement Policies GN-2349-15 on 2nd of July 2019, effective as of 1st of January 2020, which includes inter alia, Best Final Offer (BAFO), Most Advantageous Bid, Negotiations, Notification of Intention of Award, Standstill Period, Disclosure of Beneficial Ownership and Complaints. The term "Request for Bids" (RFB) is introduced to distinguish the document from the "Request for Proposals" (RFP) that may be available in the future. Prohibited Practices are updated. The term "bidding document" replaces the other ways of referring to the same: "Bidding Documents", "Bidding Document". Several ITBs are added as mandate by the Policies, including, interalia: 3.1, 26.1, 33, 36, 37, 38, 39, 40, 41, 42 and 45. Consequently, other Sections include the relevant adjustments and forms. As in the other MDB, ITB 33 is added to deal with bids frontally loaded. |
| November 2021 |  | Integration of language and requirements consistent with the Bank's new Environmental and Social Policy Framework (ESPF). |

Preface

Procurement under projects financed by the Inter-American Development Bank (IDB), is carried out in accordance with policies and procedures laid down in the   Policies for the Procurement of Goods and Works financed by the Inter-American Development Bank (hereinafter called Policies).

The Standard Bidding Document in this publication has been updated and prepared for use by Borrowers in the procurement of works for “smaller” contracts—valued at generally less than US$10 million—by international competitive bidding (ICB) using a Request for Bids (RFB). This document may also be adapted to national competitive bidding (NCB).  However, substantive changes to adapt to NCB are generally necessary in the Instructions to Bidders and the Special Conditions of Contract.

For complex works under US$10 million, such as marine works and water treatment plants, it may be preferable to use the Inter-American Development Bank’s Standard Bidding Document, Procurement of Works or Design & Build.

This SBD is consistent with the Policies for the Procurement of Goods and Works financed by the Inter-American Development Bank GN-2349-15 approved by the Board of Executive Directors of Bank on 2nd of July 2019,  effective as of 1st of January 2020. Procurement under loan operations approved under the previous Procurement Policies (where the Borrower has not subscribed the new Policies) shall use the previous version dated April 2019 of this SDB available on the Bank's website. Policies GN-2349-15 allows the use of the methods of Best Final Offer (BAFO) in the evaluation of bids or Negotiation (in the presence of an Independent Probity Assurance Authority agreed with the Bank), if so agreed with the Bank and if it is established in the BDS.

This version of the SBD includes provisions regarding the Bank’s new Environmental and Social Policy Framework . It also includes improved instructions to fill out the Bid Data Sheet and provisions to deal with conflict of interest; bids priced abnormally low; unbalanced or front-loaded bids, better assessment of variations and arithmetic errors in lump-sum bids and BOQ; and value engineering.

To obtain further information on procurement under Inter-American Development Bank-assisted projects, contact:

Operations Financial Management and Procurement Services Office

Inter-American Development Bank

1300 New York Ave., N.W., Washington D.C. 20577 U.S.A.

procurement@iadb.org

BIDDING DOCUMENT

Documents for Procurement of Works

Smaller Contracts

[Insert Name of the Works]

______________________________________________________________________

Issued on: [Insert Date]

RFB No: [Insert RFB number]

Employer: [Insert name of the Employer]

Country: [Insert name of country]

Table of Contents

Section I.  Instructions to Bidders	5

Section II.  Bid Data Sheet	41

Section III.  Eligible Countries	51

Section IV.  Bidding Forms	55

Letter of Bid	56

Qualification Information	60

Form ESHS- MSIP	63

Code of Conduct Standards	64

Bid Security (Bank Guarantee)	65

Bid Security (Bid Bond)	66

Bid Validity Declaration	68

Section V.  General Conditions of Contract	70

Section VI.  Special Conditions of Contract	103

Section VII.  Specifications & Performance Requirements	109

Section VIII.  Drawings	111

Section IX.  Bill of Quantities	113

Section X. Forms of Contract	115

Notification of Intention to Award	116

Beneficial Ownership Disclosure Form	120

Letter of Acceptance	123

Agreement	125

Performance Bank Guarantee	127

Performance Bond	129

Bank Guarantee for Advance Payment	131

Request for Bids	133

Introduction

This Standard Bidding Document is intended for ad-measurement (unit prices or unit rates in a bill of quantities) and lump sum types of Contract, which are the most common in Works contracting.  Lump sum contracts are used in particular for buildings and other forms of construction where the Works are well defined and are unlikely to change in quantity or specification, and where encountering difficult or unforeseen site conditions (for example, hidden foundation problems) is unlikely.  The main text refers to admeasurement contracts. Alternative instructions or texts are supplied for use with lump sum contracts.

Care should be taken to check the relevance of the provisions of the standard documents against the requirements of the specific Works to be procured.  The following directions should be observed when using the documents:

(a)	All the documents listed in the Table of Contents are normally required for the procurement of Works.  However, they should be adapted as necessary to the circumstances of the particular Project.

(b)	The Employer shall prepare the Bidding Data Sheet (Section II), Special Conditions of Contract (Section VI), and Sections VII, VIII, IX which deal with Specifications, Drawings, and Bill of Quantities (or List of Activities), respectively, and the Forms of Contract of Section X, before issuing this Bidding Document. The Employer should read and/or provide the information specified in the italicized notes inside brackets. In the few instances where the Bidder is requested to provide information, the note specifies it.  The footnotes and notes for the Employer are not part of the text; they should not be incorporated in the Bidding Document issued to the bidders.

(c)	Modifications to meet specific Project or Contract needs should be provided in the Bidding Data Sheet and the Special Conditions of Contract only, as amendments to the Instructions to Bidders and the General Conditions of Contract.

(d)	This Standard Bidding Document has been prepared to be used under a process that has not been used prequalification. However, they can also be used under prequalification, with relatively minor modifications. However, the documents do not address the bidder prequalification process per se. Details of the prequalification procedure used under Bank-financed contracts are provided in the Bank Standard Prequalification Documents, Procurement of Works issued by the Inter-American Development Bank.

# Section I.  Instructions to Bidders

This Section of the Bidding Document should provide the information necessary for bidders to prepare responsive bids, in accordance with the requirements of the Employer.  It should also give information on bid submission, opening and evaluation, and on the award of Contract.

Matters governing the performance of the Contractor, payments under the Contract, or matters affecting the risks, rights, and obligations of the parties under the Contract are not normally included in this Section, but rather under Section V, “General Conditions of Contract (GCC),” and/or Section VI, “Special Conditions of Contract (SCC)”. If duplication of a subject is inevitable in the different sections of the documents, care must be exercised to avoid contradictions between clauses dealing with the same matter.

Table of Instructions

A.  General	8

1.	Scope of Bid	8

2.	Source of Funds	8

3	Prohibited Practices  ………………………………………………    9

4.	Excluded Activies …………………………………………………… 15

5.	Eligible Bidders	15

6.	Qualifications of the Bidder	18

7.	One Bid per Bidder	20

8.	Cost of Bidding	20

9.	Site Visit	20

B.  Bidding Document	21

10.	Contents of Bidding Document	21

11. Clarification of Bidding Document	21

12.	Amendment of Bidding Document	21

C.  Preparation of Bids	22

13.	Language of Bid	22

14.	Documents Comprising the Bid	22

15.	Bid Prices	22

16.	Currencies of Bid and Payment	23

17.	Bid Validity	23

18.  Bid Security and Bid Validity Declaration	24

19.	Alternative Proposals by Bidders	25

20.	Format and Signing of Bid	26

D.  Submission of Bids	26

21.	Submission, Sealing and Marking of Bids	26

22.	Deadline for Submission of Bids	27

23.	Late Bids	27

24. Withdrawal, Substitution and Modification of Bids	27

E.  Bid Opening and Evaluation	28

25.	Bid Opening	28

26.	Confidentiality	29

27.	Clarification of Bids	29

28.	Determination of Responsiveness	29

29.	Correction of Errors	29

30.	Currency for Bid Evaluation	31

31.	Evaluation and Comparison of Bids	31

32.       Abnormally Low Bids	32

33.       Unbalanced or Front-Loaded Bids	32

34.       Best and Final Offer and Negotiations	33

35.	Domestic Preference	34

36.	Employer’s Right to Accept any Bid and to Reject any or all Bids	34

37.       Standstill Period	34

38.       Notification of Intention to Award	34

F.  Award of Contract	35

39.	Award Criteria	35

40.	Notification of Award	35

41.       Debriefing by the Employer	37

42.       Signing of Contract	37

43.	Performance Security	38

44.	Advance Payment and Security	38

45.	Technical Adjudicator	38

46.       Procurement Related Complaint	38

Instructions to Bidders (ITB)

A.  General

| 1. Scope of Bid | 1.1 The Employer as defined in “General Conditions of Contract” (GCC) and identified in Section II “Bidding Data Sheet” (BDS), invites bids for the construction of Works, as described in the BDS and Section VI, “Special Conditions of Contract” (SCC). The name and identification number of the Contract are provided in the BDS and the SCC. 1.2 The successful Bidder shall be expected to complete the Works by the Intended Completion Date specified in the BDS and SCC 1.1 (r). 1.3 Throughout this bidding document: (a) the term “in writing” means communicated in written form (e.g. by mail, e-mail, including, if specified in ITB 1.4, distributed or received through electronic-procurement system used by the Employer) with proof of receipt; (b) if the context so requires, “singular” means “plural” and vice versa; (c) “day” means calendar day; and (d) “ESHS” means environmental, social, health and safety (including labor, occupational and community health safety, disaster and climate change, Indigenous People, vulnerable groups, gender, and gender-based violence (SGBV) stakeholder engagement). e) SGBV” refers to any act that is perpetrated against a person’s will and is based on gender norms and unequal power relationships. It encompasses threats of violence, coercion, and harassment. It can be physical, emotional, psychological, or sexual in nature, and can take the form of a denial of resources or access to them. It includes sexual exploitation, abuse and harassment. It can affect persons at any age across the lifespan, and disproportionately affects women, girls, and people of diverse sexual orientations and gender identities. 1.4 If specified in the BDS, the Employer intents to use the electronic-procurement system indicated in the BDS to manage the aspects of this procurement process specified in the BDS. |
| --- | --- |
| 2. Source of Funds | 2.1 The Borrower, as defined in the BDS, intends to apply part of the funds of a loan from the Inter-American Development Bank (IDB) (hereinafter called “the Bank”), as defined in the BDS, in the amount as indicated in the BDS towards the cost of the Project, as defined in the BDS, to cover eligible expensive under the Contract for the Works. 2.2 Payments by the Inter-American Development Bank will be made only at the request of the Borrower and upon approval by the Bank in accordance with the terms and conditions of the financing agreement between the Borrower and the Bank (hereinafter called the “Loan Contract”) and will be subject in all respects to the terms and conditions of that Loan Contract. Except as the Bank may specifically otherwise agree, no party other than the Borrower shall derive any rights from the Loan Contract or have any rights to the loan proceeds. |
| 3. Prohibited Practices | The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, including members of its personnel, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, inter alia, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and representatives or agents, irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank all suspected acts of Prohibited Practices of which they have knowledge or become aware both, during the bidding process and throughout the negotiation or execution of a contract. Prohibited Practices are: (i) corrupt practices; (ii) fraudulent practices; (iii) coercive practices; (iv) collusive practices; (v) obstructive practices; and (vi) misappropriation of funds. The Bank has established mechanisms to report allegations of Prohibited Practices. Any allegation shall be submitted to the Bank’s Office of Institutional Integrity (OII) for the appropriate investigation. The Bank has adopted procedures to sanction those who have incurred in Prohibited Practices. The Bank also entered into an agreement with other International Financial Institutions (IFIs) to mutually recognize debarment decisions. For the purposes of this provision, the definitions of Prohibited Practices are as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (i) destroying, falsifying, altering or concealing of evidence material to an IDB Group investigation, or making false statements to investigators with the intent to impede an IDB Group investigation; (ii) threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to an IDB Group investigation or from pursuing the investigation, or (iii) acts intended to impede the exercise of the IDB Group’s contractual rights of audit or inspection provided for under ITB 3.1(f) below or access to information; and (vi) “misappropriation” is the use of IDB Group financing or resources for an improper or unauthorized purpose, committed either intentionally or through reckless disregard. If, the Bank determines that at any stage of the procurement or implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, inter alia, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires, (including their respective officers, employees and representatives or agents irrespective of whether the attribution is express or implied) engaged in a Prohibited Practice during the award or implementation of the contract, the Bank may: (i) not finance any proposal to award a contract for works, goods or services, and consulting services; (ii) suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has engaged in a Prohibited Practice; (iii) declare Misprocurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, inter alia, providing adequate notice to the Bank upon learning of the Prohibited Practice) within a time period which the Bank considers reasonable; (iv) issue the firm, entity or individual a reprimand in the form of a formal letter of censure for its behavior; (v) declare that a firm, entity, or individual is ineligible, either permanently or for a stated period of time, to participate and/or be awarded additional contracts financed with IDB Group resources; (vi) impose other sanctions that it deems to be appropriate, among others, the restitution of funds and of fines equivalent to the reimbursement for costs associated with investigations and proceedings contemplated in the Sanctions Procedures. Such other sanctions may be imposed in addition to or in lieu of the sanctions referred above (the “abovementioned” sanctions are reprimand and debarment/ineligibility); (vii) extend the sanctions imposed on any individual, entity or firm that, directly or indirectly, owns or controls a sanctioned entity, is owned or controlled by a sanctioned entity or is the object of common ownership or control with a sanctioned entity, as well as to officials, employees, affiliates or representatives or agents of a sanctioned entity who also own a sanctioned entity and / or exercise control over a sanctioned entity, even if it has not been concluded that those parties directly incurred in a Prohibited Practice; and/or (viii) refer the matter to appropriate law enforcement authorities. The provisions of ITB 3.1 (b) (i) and (ii) shall also be applicable when such parties have been temporarily suspended from eligibility to be awarded additional contracts pending a final outcome of a sanction proceeding, or otherwise. The imposition of any action to be taken by the Bank pursuant to the provisions referred to above may be made public. Pursuant to the Agreement for Mutual Enforcement of Debarment Decisions entered into with other IFIs, any firm, entity or individual bidding for or participating in a Bank-financed activity or acting as bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, concessionaires, personnel of the Borrower (including grant Beneficiaries), Executing Agencies or Contracting Agencies, (including their respective officers, employees, representatives and agents, irrespective of whether the attribution is expressed or implied) may be subject to a sanction. For purposes of this paragraph the term “sanction” shall mean any debarment, conditions on future contracting or any publicly-disclosed action taken in response to a violation of an IFI’s applicable framework for addressing allegations of Prohibited Practices. The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the submission of bids and contract performance as well as to have them audited by personnel appointed by the Bank. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its investigation. The Bank also requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires: (i) maintain all documents and records related to the Bank-financed activities for seven (7) years after completion of the work contemplated in the relevant contract; (ii) deliver any document necessary for the investigation of allegations of Prohibited Practices; and (iii) ensure that employees, representatives or agents of the applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers or concessionaires who have knowledge that the Bank financed the activities to respond to questions from Bank personnel or any properly designated investigator, agent, auditor or consultant relating to the investigation. If the applicant, bidder, supplier and its representative or agent, contractor, consultant, personnel, sub-contractor, sub-consultant, service provider or concessionaire fails to cooperate and/or comply with the Bank’s request, or otherwise obstructs the investigation, the Bank, discretionally, may take appropriate action against the applicant bidder, supplier and its agent or representative, contractor, consultant, personnel, sub-contractor, service provider or concessionaire. If the Borrower procures goods or services, works or consulting services directly from a specialized agency, all provisions regarding Prohibited Practices and to the correspondent sanctions shall apply in their entirety to applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, and concessionaires, (including their respective officers, employees, and representatives or agents, irrespective of whether the agency is express or implied), or to any other entities that signed contracts with such specialized agency to supply such goods, works, or non-consulting services in connection with the Bank-financed activities. The Bank will retain the right to require the Borrower to invoke remedies such as contract suspension or termination. Specialized agencies shall consult the Bank’s list of suspended or debarred firms and individuals. In the event a specialized agency signs a contract or purchase order with a firm or an individual suspended or debarred by the Bank, the Bank will not finance the related expenditures and will apply other remedies as appropriate. 3.2 By submitting bids bidders and proposers represent and warrant: that they have read and understood the Bank’s definition of Prohibited Practices and the applicable sanctions pursuant to the Sanctions Procedures; that they have not engaged in any Prohibited Practice as set forth herein during the selection, negotiation, adjudication or execution of this contract; that they have not misrepresented or concealed any material facts during the procurement or contract negotiation processes or during the performance of the contract; that neither they nor their representatives or agents, sub-contractors, sub-consultants, directors, key personnel or principal shareholders have been declared ineligible to be awarded a contract by the Bank that all commissions, representative or agents’ fees, facilitating payments or revenue-sharing agreements related to the Bank-financed activities have been disclosed; and that they acknowledge that the breach of any of these representations may constitute a basis for the adoption by the Bank of one or more of the measures set forth in ITB 3.1 (b). |
| 4. Excluded Activities 5. Eligible Bidders | 4.1 The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, inter alia, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall will not knowingly engage, in directly, or indirectly through Financial Intermediaries, activities involved in the production, trade, or use of the products and , substances or the activities listed in the Annex 1 of the IDB Environmental and Social Policy Framework the IDBs Environmental and Social Exclusion List. Additional exclusions may apply. If, the Bank determines that at any stage of the implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, inter alia, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires used IDB resources to engaged in an Excluded Activity during the implementation of the contract, the Bank may: Suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has used IDB resources to engage in an Excluded Activity. Declare Mis-procurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, inter alia, providing adequate notice to the Bank upon learning of the Excluded Activity) within a time period which the Bank considers reasonable refer the matter to appropriate law enforcement authorities The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the contract performance as well as to have them audited by personnel appointed by the Bank. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its monitoring and supervision. 5.1 A Bidder, and all parties constituting the Bidder, shall be a national from member countries of the Bank. Bidders from other countries shall be disqualified from participating in contracts intended to be financed in whole or in part from Bank loans. Section III, “Eligible Countries” of this document establishes the Bank’s member countries, as well as the criteria to determine the nationality of the Bidders and the country of origin of goods and services. The Bidders with the nationality of a Bank’s member country and the goods to be supplied under the Contract are not eligible: if as a matter of law or official regulation, the Borrower’s country prohibits commercial relations with that country, provided that the Bank is satisfied that such exclusion does not preclude effective competition for the supply of goods and works required; or by an act of compliance with a decision of the United nations Security Council taken under Chapter VII of the Charter of the United Nations, the Borrower’s Country prohibits any imports of goods from that country or any payments to persons or entities in that country. 5.2 A Bidder, included in all cases, the directors, key personnel, principal shareholders, proposed personnel and agents should not have conflicts of interest unless the conflict has been resolved in a manner acceptable to the Bank. A Bidder may be considered to have a conflict of interest for the purpose of this Bidding process, if the Bidder: directly or indirectly controls another Bidder, is controlled directly or indirectly by another Bidder, or is controlled together with another Bidder by a natural or legal entity in common; or receives or has received any direct or indirect subsidy from another Bidder for the purpose of this bidding process; or has the same legal representative as another Bidder for the purpose of this bidding process; or has a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the Bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or or any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the works that are the subject of the Bid; or or any of its affiliates has been hired (or is proposed to be hired) by the Employer or Borrower as Project Manager for the Contract implementation; would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS in reference to ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm; has a close family or financial relationship or past or future employment with a professional staff of the Borrower (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the bidding document or specifications of the contract, and/or the Bid evaluation process of such contract; or (ii) would be involved in the implementation or supervision of such contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to the Bank throughout the procurement process and execution of the contract. 5.3 5.4 A firm that is a Bidder (either individually or as member of a Joint Venture, Consortium or Association (“JVCA”)) shall not participate in more than one Bid, except for permitted alternative Bids. This includes participation as a Subcontractor in other Bids. Such participation shall result in the disqualification of all Bids in which the firm is involved. A firm that is not a Bidder or a JVCA member may participate as a subcontractor in more than one Bid. Unless specified in the BDS, there is no limit on the number of members in a JVCA. 5.5 Government-owned enterprises in the Employer’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) are not a dependent agency of the Borrower. 5.6 A Bidder shall not be under suspension from bidding by the Employer as a result of non-compliance with a Bid-Securing Declaration. 5.7 Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. |
| 6. Qualifications of the Bidder | 6.1 All bidders shall provide in Section IV, “Bidding Forms,” a preliminary description of the proposed work method and schedule, including drawings and charts, as necessary. 6.2 In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders shall be considered for award of Contract. These qualified bidders should submit with their bids any information updating their original prequalification applications or, alternatively, confirm in their bids that the originally submitted prequalification information remains essentially correct as of the date of bid submission. The update or confirmation should be provided in Section IV, “Bidding Forms. ” 6.3 If the Employer has not undertaken prequalification of potential bidders, all bidders shall include the following information and documents with their bids in Section IV, “Bidding Forms” unless otherwise stated in the BDS: (a) copies of original documents defining the constitution or incorporation, and principal place of business of the Bidder; written power of attorney of the signatory of the Bid to commit the Bidder; (b) total monetary value of construction works performed for each of the last five (5) years; (c) experience in works of a similar nature and size for each of the last five (5) years, and details of work under way or contractually committed; and clients who may be contacted for further information on those contracts; (d) major items of construction equipment proposed to carry out the Contract; (e) qualifications and experience of key site management and technical personnel proposed for the Contract; (f) reports on the financial standing of the Bidder, such as profit and loss statements and auditor’s reports for the past five (5) years; (g) evidence of adequacy of working capital for this Contract (access to line(s) of credit and availability of other financial resources); (h) authorization to seek references from the Bidder’s bankers; (i) information regarding any litigation, current or during the last five (5) years, in which the Bidder was/is involved, the parties concerned, and the disputed amounts and awards; and (j) proposals for subcontracting components of the Works amounting to more than ten (10) percent of the Contract Price. The ceiling for subcontractor's participation is stated in the BDS. 6..4 Bids submitted by a Joint venture, Consortium or Association (JVCA) of two or more firms as partners shall comply with the following requirements, unless otherwise stated in the BDS: (a) the Bid shall include all the information listed in ITB 6.3 above for each JVCA partner; (b) the Bid shall be signed so as to be legally binding on all partners; (c) all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms; (d) one of the partners shall be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the JVCA; (e) the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge; and (f) a copy of the JVCA Agreement entered into by the partners shall be submitted with the bid; or a Letter of Intent to execute a JVCA agreement in the event of a successful bid shall be signed by all partners and submitted with the bid, together with a copy of the proposed Agreement. The Letter or The Agreement shall specify the participation share (as a percentage) of each member. 6.5 To qualify for award of the Contract, bidders shall meet the following minimum qualifying criteria (a) an average annual billing of construction work over the period specified in the BDS of at least the multiple indicated in the BDS (b) experience as prime contractor in the construction of at least the number of works of a nature and complexity equivalent to the Works over the period specified in the BDS (to comply with this requirement, works cited should be at least seventy (70) percent complete); (c) show that it can ensure the timely availability (own, lease, hire, etc.) of the essential equipment listed in the BDS; (d) hire a Contract Manager with five years’ experience in works of an equivalent nature and volume, including no less than three years as Manager; and (e) liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than the amount specified in the BDS. A consistent history of litigation or arbitration awards against the Applicant or any partner of a JVCA may result in disqualification. 6.6 The figures for each of the partners of a JVCA shall be added together to determine the Bidder’s compliance with the minimum qualifying criteria of ITB 6.5 (a) and (e); however, for a JVCA to qualify, each of its partners must meet at least twenty five (25) percent of minimum criteria of ITB 6.5 (a), (b), and (e) for an individual Bidder, and the partner in charge at least forty (40) percent of those minimum criteria. Failure to comply with this requirement shall result in rejection of the JVCA’s Bid. 6.7 Subcontractors’ experiences and resources shall not be taken into account in determining the Bidder’s compliance with the qualifying criteria, unless otherwise stated in the BDS. |
| 7. One Bid per Bidder | 7.1 Each Bidder shall submit only one Bid, either individually or as a partner in a JVCA. A Bidder who submits or participates in more than one Bid (other than as a subcontractor or in cases of alternatives that have been permitted or requested) shall cause all the proposals with the Bidder’s participation to be rejected. |
| 8. Cost of Bidding | 8.1 The Bidder shall bear all costs associated with the preparation and submission of his Bid, and the Employer shall in no case be responsible or liable for those costs. |
| 9. Site Visit | 9.1 The Bidder, at the Bidder’s own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense. |

B.  Bidding Document

| 10. Contents of Bidding Document | 10.1 The bidding document comprises the documents listed below, and addenda issued in accordance with ITB 12: Section I. Instructions to Bidders (ITB) Section II. Bid Data Sheet (BDS) Section III. Eligible Countries Section IV. Bidding Forms Section V. General Conditions of Contract (GCC) Section VI. Special Conditions of Contract (SCC) Section VII. Specifications & Performance Requirement Section VIII. Drawings Section IX. Bill of Quantities Section X. Contract Forms |
| --- | --- |
| 11. Clarification of Bidding Document | 11.1 A prospective Bidder requiring any clarification of the bidding document may notify the Employer in writing at the Employer’s address indicated in the BDS. The Employer shall respond to any request for clarification received earlier than 14 days prior to the deadline for submission of bids. Copies of the Employer’s response shall be forwarded to all purchasers of the bidding document, including a description of the inquiry, but without identifying its source. |
| 12. Amendment of Bidding Document | 12.1 Before the deadline for submission of bids, the Employer may modify the bidding document by issuing addenda. 12.2 Any addendum thus issued shall be part of the bidding document and shall be communicated in writing to all prospective bidders that obtained the bidding document. Prospective bidders shall acknowledge receipt of each addendum in writing to the Employer. 12.3 To give prospective bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer shall extend, as necessary, the deadline for submission of bids, in accordance with ITB 22.2 below. |

C.  Preparation of Bids

| 13. Language of Bid | 13.1 All documents relating to the Bid shall be in the language specified in the BDS. |
| --- | --- |
| 14. Documents Comprising the Bid | 14.1 The Bid submitted by the Bidder shall comprise the following: (a) Letter of Bid: in the format indicated in Section IV, “Bidding Forms”; (b) Bid Security, or Bid Validity Declaration, in accordance with ITB 18, if required; (c) Bill of Quantities or Activity Schedule: as specified in ITB 15; (d) Qualifications: Information Form and Documents; (e) Alternative offers where invited; and (f) any other documents required to be completed and submitted by bidders, as specified in the BDS. |
| 15. Bid Prices | 15.1 The Contract shall be for the whole Works, as described in ITB 1.1, based on the priced Bill of Quantities submitted by the Bidder. 15.2 The Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities. Items for which no rate or price is entered by the Bidder shall not be paid for by the Employer when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities. Corrections, if any, shall be made by crossing out, initialing, dating and rewriting. 15.3 All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of bids, shall be included in the rates, the unit prices, and total Bid price submitted by the Bidder. 15.4 The rates and unit prices quoted by the Bidder shall be subject to adjustment during the performance of the Contract if provided for in the BDS and SCC and the provisions of Clause 47 of the General Conditions of Contract. The Bidder shall submit with the Bid all the information required under the Special Conditions of Contract and GCC Clause 47. |
| 16. Currencies of Bid and Payment | 16.1 The unit rates and prices shall be quoted by the Bidder entirely in the currency of the Employer’s country as specified in the BDS Foreign currency requirements shall be indicated as percentages of the Bid price (excluding provisional sums) and shall be payable at the option of the Bidder in up to three foreign currencies. 16.2 The rates of exchange to be used by the Bidder in arriving at the local currency equivalent and the percentages mentioned in para. 16.1 above shall be the selling rates for similar transactions established by the source specified in the BDS prevailing on the date 28 days prior to the latest deadline for submission of bids. These exchange rates shall apply for all payments so that no exchange risk shall be borne by the Bidder. If the Bidder uses other rates of exchange, the provisions of ITB 30.1 shall apply; in any case, payments shall be computed using the rates quoted in the Bid. 16.3 Bidders shall indicate details of their expected foreign currency requirements in the Bid. 16.4 Bidders may be required by the Employer to clarify their foreign currency requirements and to substantiate that the amounts included in the rates and prices, if required in the BDS, are reasonable and responsive to ITB 16.1. |
| 17. Bid Validity | 17.1 Bids shall remain valid for the period specified in the BDS. 17.2 In exceptional circumstances, the Employer may request that the bidders extend the period of validity for a specified additional period. The request and the bidders’ responses shall be made in writing. If a Bid Security is requested in accordance with ITB 18, it shall be extended up to 28 days after the deadline of the extended bid validity period. A Bidder may refuse the request without forfeiting the Bid Security or execution of its Bid Validity Declaration. A Bidder agreeing to the request shall not be required or permitted to modify its Bid, except as provided in ITB 18. 17.3 In the case of contracts in which the Contract Price is fixed (not subject to price adjustment), if the period of bid validity is extended beyond 56 days, the amounts payable in local and foreign currency to the Bidder selected for award, shall be adjusted as specified in the request for extension. Bid evaluation shall be based on the Bid Price without taking the above correction into consideration. |
| 18. Bid Security and Bid Validity Declaration | 18.1 If required in the BDS, the Bidder shall furnish as part of its Bid, a Bid Security or a Bid Validity Declaration in original form as specified in the BDS. 18.2 The Bid Security shall be in the amount specified in BDS and denominated in the currency of the Employer’s country or the currency of the Bid or in another freely convertible currency, and shall: at the bidder’s option, be in the form of either a letter of credit, or a bank guarantee from a banking institution, or a bond or surety issued by an insurance or bonding institution; be issued by a reputable institution selected by the bidder and located in any country. If the institution issuing the bond or surety is located outside the Employer’s Country, it shall have a correspondent financial institution located in the Employer’s Country to make it enforceable. be substantially in accordance with one of the forms of Bid Security included in Section IV “Bidding Forms,” or other form approved by the Employer prior to bid submission; be payable promptly upon written demand by the Employer in case the conditions listed in ITB 18.5 are invoked; be submitted in its original form; copies shall not be accepted; remain valid for a period of 28 days beyond the validity period of the bids, as extended, if applicable, in accordance with ITB 16.2. 18.3 If a Bid Security or a Bid Validity Declaration is required in accordance with ITB 18.1, any bid not accompanied by a substantially responsive Bid Security or Bid Validity Declaration in accordance with ITB 18.1, shall be rejected by the Employer as non-responsive. 18.4 The Bid Security or the Bid Validity Declaration of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the performance security. 18.5 The Bid Security may be forfeited, or the Bid Validity Declaration executed: if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Bid Submission Sheet, except as provided in ITB 17.2; or if the Bidder does not accept the correction of its Bid Price pursuant to ITB Sub-Clause 28. if the successful Bidder fails within the specified time to: sign the Contract; or furnish the required performance security. 18.6 The Bid Security or Bid Validity Declaration of a JVCA must be in the name of the JVCA that submits the bid. If the JVCA has not been legally constituted at the time of bidding, the Bid Security or Bid Validity Declaration shall be in the names of all future partners as named in the letter of intent. |
| 19. Alternative Proposals by Bidders | 19.1 Alternatives shall not be considered, unless specifically allowed in the BDS. If so allowed, ITB 19.1 and 19.2 shall govern, and BDS shall specify which of the following options shall be allowed: (a) Option One. A bidder may submit alternative bids with the base bid and the Employer shall only consider the alternative bids offered by the Bidder whose bid for the base case was determined to be the Most Advantageous Bid, or (b) Option Two. A bidder may submit an alternative bid with or without a bid for the base case. All bids received, for the base case, as well as alternative bids meeting the technical specifications and performance requirements pursuant to Section VII, shall be evaluated on their own merits. 19.2 Alternative bids shall provide all information necessary for a complete evaluation of the alternative by the Employer, including design calculations, technical specifications, breakdown of prices, proposed construction methods and other relevant details. |
| 20. Format and Signing of Bid | 20.1 The Bidder shall prepare one original of the documents comprising the Bid as described in ITB 14, bound with the volume containing the Form of Bid, and clearly marked “ORIGINAL.” In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly marked as “COPIES.” In the event of discrepancy between them, the original shall prevail. 20.2 The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Bidder, pursuant to ITB 6.3 (a). The person or persons signing the Bid shall initial all pages of the Bid where entries or amendments have been made. 20.3 The Bid shall contain no alterations or additions, except those to comply with instructions issued by the Employer, or as necessary to correct errors made by the Bidder, in which case such corrections shall be initialed by the person or persons signing the Bid. 20.4 The Bidder shall furnish information as described in the Form of Bid on commissions or gratuities, if any, paid or to be paid to agents relating to this Bid, and to contract execution if the Bidder is awarded the contract. |

D.  Submission of Bids

| 21. Submission, Sealing and Marking of Bids | 21.1 Bidders may always submit their bids by mail or by hand. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Bidders submitting bids electronically shall follow the procedures specified in the BDS. In the case of Bids submitted by mail or by hand the Bidder shall seal the original and all copies of the Bid in two inner envelopes, duly marking them as “ORIGINAL” and “COPIES”, respectively, and shall seal the two inner envelopes into an outer envelope 21.2 The inner and outer envelopes shall (a) be addressed to the Employer at the address provided in the BDS; (b) bear the name and identification number of the Contract as defined in the BDS and SCC; and (c) provide a warning not to open before the specified time and date for Bid opening as defined in the BDS. 21.3 In addition to the identification required in ITB 21.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to ITB 23. 21.4 If the outer envelope is not sealed and marked as above, the Employer shall assume no responsibility for the misplacement or premature opening of the Bid. |
| --- | --- |
| 22. Deadline for Submission of Bids | 22.1 Bids shall be delivered to the Employer at the address specified in ITB 21.2 (a) no later than the time and date specified in the BDS. 22.2 The Employer may extend the deadline for submission of bids by issuing an amendment in accordance with ITB 12, in which case all rights and obligations of the Employer and the bidders previously subject to the original deadline shall then be subject to the new deadline. |
| 23. Late Bids | 23.1 Any Bid received by the Employer after the deadline prescribed in ITB 22 shall be returned unopened to the Bidder. |
| 24. Withdrawal, Substitution and Modification of Bids | 24.1 Bidders may withdraw, substitute or modify their Bids by giving notice in writing before the deadline prescribed in ITB 22. 24.2 Each Bidder’s withdrawal, substitution or modification notice shall be prepared, sealed, marked, and delivered in accordance with ITB 20 and 21, with the outer and inner envelopes additionally marked “Withdrawal”, Substitution”, or “Modification” as appropriate. 24.3 Notices for withdrawal, substitution or modification of bids shall be delivered to the Employer at the address specified in ITB 21.2 (a) no later than the time and date specified in ITB 22.1 of the BDS. 24.4 Withdrawal of a Bid between the deadline for submission of bids and the expiration of the period of Bid validity specified in the Bidding Data or as extended pursuant to ITB 17.2 may result in the forfeiture of the Bid Security or execution of the Bid Validity Declaration pursuant to ITB 18. 24.5 Bidders may only offer discounts to, or otherwise modify the prices of their bids, by submitting Bid modifications in accordance with this instruction or including them in the initial Bid |

E.  Bid Opening and Evaluation

| 25. Bid Opening | 25.1 The Employer shall open the bids in public, and the withdrawal, substitution and modification notices made pursuant to ITB 24, in the presence of the bidders’ representatives who choose to attend at the time, date and in the place specified in the BDS. Any specific opening procedures required if electronic bidding is permitted in accordance with ITB 21.1, shall be as specified in the BDS. 25.2 Envelopes marked “WITHDRAWAL” shall be opened and read out first. Bids for which an acceptable notice of withdrawal has been submitted pursuant to ITB 24 shall not be opened. 25.3 The bidders’ names, the Bid prices, the total amount of each Bid and of any alternative Bid (if alternatives have been requested or permitted), any discounts, Bid withdrawals, substitutions, or modifications notices, the presence or absence of Bid Security or Bid Validity Declaration, if required, and such other details as the Employer may consider appropriate, shall be read aloud (and posted online when electronic bidding is used) by the Employer at the opening, and recorded when opened. No bid or notice shall be rejected at bid opening except for the late bids and notices pursuant to ITB 23. Substitution Bids and modifications submitted pursuant to ITB 24 that are not opened and read out at bid opening shall not be considered for further evaluation regardless of the circumstances. Late, withdrawn and substituted bids and notices shall be returned un-opened to bidders 25.4 The Employer shall prepare Minutes of the Bid Opening, including the record of readout bids and the information disclosed to those present, in accordance with ITB 25.3and promptly send copy of such minutes to all bidders who submitted bids in time. |
| --- | --- |
| 26. Confidentiality | 26.1 Information relating to the Examination, Clarification, Evaluation, and Comparison of Bids and Recommendations for the Award of a contract shall not be disclosed to bidders or any other persons not officially concerned with such process until the Notification of Intention to Award the Contract is transmitted to all Bidders in accordance with ITB 38.1. Any effort by a Bidder to influence the Employer’s processing of bids or award decisions may result in the rejection of its Bid. Notwithstanding the above, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it should do so in writing. |
| 27. Clarification of Bids | 27.1 To assist in the examination, evaluation, and comparison of Bids, the Employer may, at the Employer’s discretion, ask any Bidder for clarification of the Bidder’s Bid, including breakdowns of unit rates. The request for clarification and the response shall be in writing, but no change in the price or substance of the Bid shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Bids in accordance with ITB 29. |
| 28. Determination of Responsiveness | 28.1 Prior to the detailed evaluation of Bids, the Employer shall determine whether each Bid (a) meets the eligibility criteria defined in ITB 5; (b) has been properly signed; (c) is accompanied by the Bid Security or the Bid Validity Declaration, if required; and (d) is substantially responsive to the requirements of the bidding document. 28.2 A substantially responsive Bid is one which conforms to all the terms, conditions, and specifications of the bidding document, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the bidding document, the Employer’s rights or the Bidder’s obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other bidders presenting substantially responsive bids. 28.3 If a Bid is not substantially responsive, it shall be rejected by the Employer and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation. |
| 29. Correction of Errors | 29.1 Bids determined to be substantially responsive shall be checked by the Employer for any arithmetic errors. In admeasurement contracts, errors shall be corrected by the Employer as follows: where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted shall govern, unless in the opinion of the Employer there is an obviously gross misplacement of the decimal point in the unit rate, in which case the line item total as quoted shall govern, and the unit rate shall be corrected; if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail, and the total shall be corrected; and if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. 29.2 In lump-sum contracts, the evaluation of the Financial part of each Bid, the Employer shall correct the arithmetic errors in the following manner: (a) List of Sub-Activity with prices: if there are errors between the total of quantities in the column for Sub-Activity price and the amount shown in the total for the Sub-activity, the first one shall prevail and consequently, the latter corrected; (b) List of Activity with prices: if there are errors between the total of the quantities shown in the price column for the Activity Price and the amount shown in the total price of the activities, the first one shall prevail and the latter corrected as a result; and when there is an error between the total of the quantities in the List of Sub-activity with prices and the corresponding amount in the Schedule of Activities with prices, the first one shall prevail and the second shall be corrected as a result; and (c) Global Summary: in case of errors between the total price of the activities in the calendar with prices and the amount indicated in the Global Summary, the first shall prevail and the latter corrected as a result. 29.3 The amount stated in the Bid shall be adjusted by the Employer in accordance with the above procedure for the correction of errors and, with the concurrence of the Bidder, shall be considered as binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid shall be rejected, and the Bid Security may be forfeited or the Bid - Validity Declaration executed in accordance with ITB 18.5 (b). |
| 30. Currency for Bid Evaluation | 30.1 Bids shall be evaluated as quoted in the currency of the Employer’s Country in accordance with ITB 16.1, unless a Bidder has used different exchange rates than those prescribed in ITB 16.2, in which case the Bid shall be first converted into the amounts payable in different currencies using the rates quoted in the Bid and then reconverted to the currency of the Employer’s country using the exchange rates prescribed in ITB 16.2. |
| 31. Evaluation and Comparison of Bids | 31.1 The Employer shall evaluate and compare only the bids determined to be substantially responsive in accordance with ITB 28. 31.2 In evaluating the bids, the Employer shall determine for each Bid the evaluated Bid price by adjusting the Bid price as follows: (a) making any correction for errors pursuant to ITB 29; (b) excluding provisional sums and the provision, if any, for contingencies in the Bill of Quantities, but including Daywork, where priced competitively; (c) making an appropriate adjustment for any other acceptable variations, deviations, or alternative offers submitted in accordance with ITB 19; (d) making appropriate adjustments to reflect discounts or other price modifications offered in accordance with ITB 24.5; and (e) using BAFO if so specified in BDS in reference to ITB 34.2. 31.3 The Employer reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the bidding document or otherwise result in unsolicited benefits for the Employer shall not be taken into account in Bid evaluation. 31.4 The estimated effect of any price adjustment conditions under GCC Clause 47, during the period of implementation of the Contract, shall not be taken into account in Bid evaluation. 31.5 An abnormally low bid is one where the Bid price, in combination with other constituent elements of the Bid, appears unreasonably low to the extent that the Bid price raises material concerns as to the capability of the Bidder to perform the Contract for the offered Bid price. 31.6 In the event of identification of a potentially abnormally low Bid, the Employer shall seek written clarifications from the Bidder, including detailed price analyses of its Bid price in relation to the subject matter of the contract, scope, proposed methodology, schedule, allocation of risks and responsibilities and any other requirements of the bidding document. 31.7 After evaluation of the price analyses, in the event that the Employer determines that the Bidder has failed to demonstrate its capability to perform the Contract for the offered Bid Price, the Employer shall reject the Bid. 31.8 |
| 32. Abnormally Low Bids | 32.1 An Abnormally Low Bid is one where the Bid price, in combination with other constituent elements of the Bid, appears unreasonably low to the extent that the Bid price raises material concerns as to the capability of the Bidder to perform the Contract for the offered Bid price. 32.2 In the event of identification of a potentially Abnormally Low Bid, the Employer shall seek written clarifications from the Bidder, including detailed price analyses of its Bid price in relation to the subject matter of the contract, scope, proposed methodology, schedule, allocation of risks and responsibilities and any other requirements of the bidding document. 32.3 After evaluation of the price analyses, in the event that the Employer determines that the Bidder has failed to demonstrate its capability to perform the Contract for the offered Bid Price, the Employer shall reject the Bid. |
| 33. Unbalanced or Front-Loaded Bids | 33.1 If the Bid for an admeasurement contract, which results in the lowest evaluated cost, in the Employer’s opinion, seriously unbalanced or front loaded the Employer may require the Bidder to provide written clarifications. Clarifications may include detailed price analyses to demonstrate the consistency of the Bid prices with the scope of works, proposed methodology, schedule and any other requirements of the bidding document. 33.2 After the evaluation of the information and detailed price analyses presented by the Bidder, the Employer may as appropriate: accept the Bid; or require that the total amount of the Performance Security be increased at the expense of the Bidder to a level not exceeding 20% of the Contract Price; or reject the Bid. |
| 34. Best and Final Offer and Negotiations | 34.1 If so specified in the BDS the Employer will use the Best and Final Offer method, the Bidders who submitted bids substantially responsive to the requirements will be invited to present their Best and Final Offer in accordance with ITB 34.3 to ITB 34.6 reducing prices, clarifying or modifying the bid or providing additional information, as appropriate. 34.2 If so specified in the BDS the Employer will use Negotiations after evaluation of bids and before final award of Contract, the Bidder who submitted the Most Advantageous Bid will be invited to Negotiations in accordance with ITB 39.2 and following instructions. 34.3 Bidders are not required to submit a Best and Final Offer. There shall be no Negotiations after Best and Final Offer. 34.4 To observe and report on the application of the Best and Final Offer, the Employer may, and in the case of Negotiations shall, appoint the Independent Probity Assurance Authority indicated in the BDS. 34.5 The Employer shall specify in the BDS a new deadline and details for the submission of the Best and Final Offer or to initiate Negotiations. Instructions in ITB 21 to ITB 27 shall apply to the presentation, opening and clarifications of the Best and Final Offer of the Bidders. 34.6 On receipt of the Best and Final Offer from each Bidder, the Employer shall proceed with the evaluation and comparison of the bids again in accordance with ITB 28 to ITB 33 and then shall proceed with ITB 34 and following instructions. |
| 35. Domestic Preference | 35.1 A margin of preference shall not apply to compare the bids of national and foreign bidders. |
| 36. Employer’s Right to Accept any Bid and to Reject any or all Bids | 36.1 The Employer reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Employer’s action. |
| 37. Standstill Period | 37.1 The Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITB 41. The Standstill Period commences when the Employer has transmitted to each Bidder the Notification of Intention to Award the Contract. Where only one Bid is submitted, or if this contract is in response to an emergency situation recognized by the Bank, the Standstill Period shall not apply. |
| 38. Notification of Intention to Award | 38.1 The Employer shall send to each Bidder the Notification of Intention to Award the Contract to the successful Bidder. The Notification of Intention to Award shall contain, at a minimum, the following information: the name and address of the Bidder submitting the successful Bid; the Contract price of the successful Bid; the names of all Bidders who submitted Bids, and their Bid prices as readout, and as evaluated; a statement of the reason(s) the Bid (of the unsuccessful Bidder to whom the notification is addressed) was unsuccessful, unless the price information in c) above already reveals the reason; if the method of Best and Final Offer was used in the evaluation of bids; the expiry date of the Standstill Period; and instructions on how to request a debriefing and/or submit a complaint during the standstill period. |

F.  Award of Contract

| 39. Award Criteria | 39.1 Subject to ITB 36, the Employer shall award the Contract to the Bidder offering the Most Advantageous Bid. The Most Advantageous Bid is the Bid of the Bidder that meets the qualification criteria and whose Bid has been determined to be: substantially responsive to the bidding document; and the lowest evaluated cost. 39.2 If the Employer has not used the Best and Final Offer method in the Bid evaluation and if in the BDS in reference to ITB 34.2 it is specified that the Employer will use Negotiations with the Bidder with the Most Advantageous Bid, the selected Bidder shall be invited to Negotiations before the final adjudication of the Contract. The Negotiations will be performed in the presence of the Independent Probity Assurance Authority established in the BDS in reference to ITB 34.4. Negotiations may include terms and conditions, price or social, environmental, innovative and cybersecurity aspects, provided that the minimum requirements of the bid are not modified. 39.3 Once the Employer has determined the Bidder with the Most Advantageous Bid, the Employer shall promptly notify the selected Bidder the terms to initiate Negotiations in accordance with BDS in reference to ITB 34.5. 39.4 The Employer will first negotiate with the Bidder that has submitted the Most Advantageous Bid. If the result is not satisfactory or an agreement is not reached, the Employer will notify the Bidder that the Negotiations concluded without agreement and may then notify the Bidder with the following Most Advantageous Bid on the list, and so on until a satisfactory result is achieved. |
| --- | --- |
| 40. Notification of Award | 40.1 Prior to the expiration of the Bid Validity Period and upon expiry of the Standstill Period or any extension thereof, and upon satisfactorily addressing any complaint that has been filed within the Standstill Period, the Employer shall notify the successful Bidder, in writing, that its Bid has been accepted. The notification of award (hereinafter and in the Contract Forms called the “Letter of Acceptance”) shall specify the sum that the Employer will pay the Supplier in consideration of the execution of the Contract (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”). 40.2 Within ten (10) Business Days after the date of transmission of the Letter of Acceptance, the Employer shall publish the Contract Award Notice which shall contain, at a minimum, the following information: name and address of the Employer; name and reference number of the contract being awarded, and the selection method used; names of all Bidders that submitted Bids, and their Bid prices as read out at Bid opening, and as evaluated; names of all Bidders whose Bids were rejected either as nonresponsive or as not meeting qualification criteria, or were not evaluated, with the reasons therefor; the name of the successful Bidder, the final total contract price, the contract duration and a summary of its scope; if Negotiations were used in the final award; and successful Bidder’s Beneficial Ownership Disclosure Form, if specified in BDS in reference to ITB 42.1. 40.3 The Contract Award Notice shall be published on the Employer’s website with free access if available, or in at least one newspaper of national circulation in the Employer’s Country, or in the official gazette. The Employer shall also publish the contract award notice in UNDB online. 40.4 Until a formal Contract is prepared and executed, the Letter of Acceptance shall constitute a binding Contract. |
| 41. Debriefing by the Employer | 41.1 On receipt of the Employer’s Notification of Intention to Award referred to in ITB 38.1, an unsuccessful Bidder has three (3) Business Days to make a written request to the Employer for a debriefing on the reasons why its Bid was not selected. The Employer shall provide a debriefing to all unsuccessful Bidders whose request is received within this deadline. 41.2 Where a request for debriefing is received within the deadline, the Employer shall provide a debriefing within five (5) Business Days, unless the Employer decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Employer shall promptly inform, by the quickest means available, all Bidders of the extended standstill period. 41.3 Where a request for debriefing is received by the Employer later than the three (3)-Business Day deadline, the Employer should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of Public Notice of Award of contract. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period. 41.4 Debriefing of unsuccessful Bidders may be done in writing or through an information meeting, or both, at the option of the Employer. The Bidders shall bear their own costs of attending such a meeting. |
| 42. Signing of Contract | 42.1 The Employer shall send to the successful Bidder the Letter of Acceptance including the Contract Agreement, and, if specified in the BDS, a request to submit the Beneficial Ownership Disclosure Form providing additional information on its beneficial ownership. The Beneficial Ownership Disclosure Form, if so requested, shall be submitted within eight (8) Business Days of receiving this request. 42.2 The successful Bidder shall sign, date and return to the Employer, the Contract Agreement within twenty-one (21) days of its receipt. |
| 43. Performance Security | 43.1 Within twenty-eight (21) days of the receipt of Letter of Acceptance from the Employer, the successful Bidder, if required, shall furnish the Performance Security using for that purpose the Performance Security Form included in Section IX, Contract Forms, or another Form acceptable to the Employer. If the Performance Security furnished by the successful Bidder is in the form of a bond, it shall be issued by a bonding or insurance company that has been determined by the successful Bidder to be acceptable to the Employer. A foreign financial institution providing a bond shall have a correspondent financial institution located in the Employer’s Country, unless the Employer has agreed in writing that a correspondent financial institution is not required. 43.2 Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the Bid Security. In that event the Employer may award the Contract to the Bidder offering the next Most Advantageous Bid. |
| 44. Advance Payment and Security | 44.1 The Employer shall provide an Advance Payment on the Contract Price as stipulated in the GCC, subject to a maximum amount, as stated in the BDS. The Advance Payment shall be guaranteed by a Security. Section X “Contract Forms” provides a Bank Guarantee for Advance Payment form. |
| 45. Technical Adjudicator | 45.1 The Employer proposes the person named in the BDS to be appointed as Technical Adjudicator under the Contract, at an hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in the Bid. If, in the Letter of Acceptance, the Employer has not agreed on the appointment of the Technical Adjudicator, the Technical Adjudicator shall be appointed by the Appointing Authority designated in the BDS and the SCC at the request of either party. |
| 46. Procurement Related Complaint | 46.1 The procedures for making a Procurement-related Complaint are as specified in the BDS. |

# Section II.  Bid Data Sheet

| A. General |
| --- |
| ITB 1.1 | The Employer is [insert name of the Employer] The Works are [Insert brief description of the Works] The name and identification of the contract are [insert name and identification number of the contract] |
| ITB 1.2 | The Intended Completion Date is [insert date] |
| ITB 1.4 Electronic – Procurement System | The Employer [insert "shall use a" or "shall not use any" ] electronic-procurement system to manage this RFB: [If an e-procurement system is used, insert name of the e-system and url address or link; if not used delete this and the next text] The electronic-procurement system shall be used to manage the following aspects of the procurement process: [list the aspects here and modify the relevant parts of the BDS accordingly e.g., issuing Bidding document, issuing amendments to the bidding document, submissions of Bids, opening of Bids] |
| ITB 2.1 | The Borrower is: ______ [insert name of Borrower]. |
| ITB 2.1 | The expression “Bank” used in this document includes the Inter-American Development Bank and the funds it administers. Requirements of IDB and any other fund administered by the IDB are identical; except in the case of eligibility where membership is different (See Section III, “Eligible Countries”). The expression “loans” include the financing instruments and methods, the technical cooperation (TC) and the financing of operations. The expression “Loan Contract” includes all the legal instruments under which the Bank operations are formalized The Bank’s loan is: _______ [insert name or identification of the loan] Number: ______ [insert # of the loan] Date: _________[Insert date of approval] |
| ITB 2.1 | The Project is [insert name and summary description of the Project financed by the Inter-American Development Bank loan]. |
| ITB 4.3 | The Bank's website (www.iadb.org/integridad) provides information on companies and sanctioned persons. |
| ITB 5.4 | [Delete if not applicable] Maximum number of members in a JVCA shall be: [insert a number] _______________ |
| ITB 6.3 | The information required from bidders in ITB 6.3 is modified as follows: [list any additions or deletions to list in ITB 6.3; otherwise list “none”]. |
| ITB 6.3 (j) | The ceiling for sub contractor's participation is: [Insert the percentage] |
| ITB 6.4 | The qualification data required from JVCA in ITB 6.4 are modified as follows: [list any additions or deletions to list in ITB 6.4; otherwise list “none”]. |
| ITB 6.5 | The qualification criteria for Bidders in ITB 6.5 are modified as follows: _______ [list any additions or deletions to list in ITB 6.5; otherwise insert “none”]. |
| ITB 6.5 (a) | The multiple is: _________ [insert multiple; usually two] The period is: __________ [insert number of years; usually 5 years] |
| ITB 6.5 (b) | The number is: _________ [insert number; usually two] The period is: __________ [insert number of years; usually 5 years] |
| ITB 6.5 (c) | The essential equipment to be made available for the Contract by the successful Bidder shall be: ______ [insert equipment list]. |
| ITB 6.5 (e) | The minimum amount of liquid assets and/or credit facilities net of other contractual commitments of the successful Bidder shall be [insert figure], expressed in [insert name of international trading currency]. |
| ITB 6.7 | Subcontractors’ experience and resources _______ [insert “shall” or” shall not”] be taken into account. |
| B. Bidding Document |
| ITB 11.1 | For Clarification of Bid purposes only, the Employer’s address is: [insert the corresponding information as required below. This address may be the same as or different from that specified under provision ITB 21.2 (a) for Bid submission] Attention: ______ [insert full name of person, if applicable] Address: _______ [insert street address and number] Floor/ Room number: ________ [insert floor and room number, if applicable] City: ________ [insert name of city or town] ZIP Code: ______ [insert postal (ZIP) code, if applicable] Country: _______ [insert name of country] Telephone: _____ [insert telephone number, including country and city codes] Electronic mail address: ________ [insert email address, if applicable] [Note: Requests for clarification sent via email must be sent on a company's letterhead, signed and stamped by the company's legal representative and preferably in pdf format.] |
| C. Preparation of Bids |
| ITB 13.1 | The language of all documents relating to the bid is: _______ [insert English, French, Portuguese or Spanish] |
| ITB 14.1 (f) | The Bidder shall submit the following additional documents in its Bid: [list any additional document not already listed in ITB 14.1 that must be submitted with the Bid. The list of additional documents should include the following:] Code of Conduct (ESHS) The Bidder shall submit its Code of Conduct that will apply to and be properly communicated to the Contractor’s employees and subcontractor’s employees to ensure compliance with its Environmental, Social, Health and Safety (ESHS) obligations under the contract. In addition, the Bidder shall detail how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, how it will be communicated to personnel, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches. The Contractor and its subcontractors shall be required to implement the agreed Code of Conduct. Management Strategies and Implementation Plans (MSIP) to manage the (ESHS) risks The Bidder shall submit Management Strategies and Implementation Plans (MSIP) to manage the following key Environmental, Social, Health and Safety (ESHS) risks and impacts. that are collectively referred to as the Contractor’s Environmental and Social Management Plan (C-ESMP) and are to be developed according to the Project’s Environmental and Social Assessment (ESA), the Project Specific Environmental and Social Framework (ESF), and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan (ESAP). etc. |
| ITB 15.4 | The rates and prices [specify “shall” or “shall not”] _______ be subject to price adjustment in accordance with GCC Clause 47. [Price adjustment is mandatory when the expected completion time exceeds 18 months] |
| ITB 16.1 | The currency of the Employer’s country is: _____ [Name of the currency]. |
| ITB 16.2 | The source for establishing the rates of exchange shall be [insert name,]. |
| ITB 16.4 | Bidders [insert “are” or “are not”] _______ required to clarify their foreign currency requirements and to substantiate that the amounts included in the rates and prices are reasonable and responsive to ITB 16.1. |
| ITB 17.1 | The Bid shall be valid for [insert a number of days as a multiple of seven counted from the expiration of the deadline for submission of bids] ____ days counted from the date of submission of bids. |
| ITB 18.1 | [Select one of the following options] No Bid Security is required. OR Bid shall include a Bid Security issued by a bank or a by a surety using the form for bid security (bank guarantee or bid bond) included in Section IV, “Bidding Forms.” The Bid Security shall be [insert amount in local currency should be the same as provided in the Invitation to Bid] or an equivalent amount in a freely convertible currency. OR Bid shall include a Bid Validity Declaration using the form included in Section IV, "Bidding Forms” |
| ITB 18.2 | The Bid Security amount is: _____ [insert amount. It should not exceed 3 percent of the estimated value of the Works. For reasons of confidentiality, a fixed sum should be specified, in preference to a percentage of the Bid price.] |
| ITB 19.1 | Alternative Bids [insert “shall be” or “shall not be”] ________ considered. [If alternatives shall be considered insert “the Employer shall only consider (insert “Option One” or” Option Two”)]. |
| ITB 20.1 | The number of copies of the Bid to be submitted shall be [insert number of copies] ______ copies |
| D. Submission of Bids |
| ITB 21.1 | Bidders may submit their bids electronically: [insert “Yes” or “No”; if yes insert description of the procedures]_____. |
| ITB 21.2 (a) | For Bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 10.1 for clarifications] Attention: _____ [insert full name of person, if applicable] Street Address:______ [insert street address and number] Floor/Room number: _______ [insert floor and room number, if applicable] City: _______ [insert name of city or town] ZIP Code: ________ [insert postal (ZIP) code, if applicable] Country: _________ [insert name of country] |
| ITB 21.2 (b) | Name and Identification number of the contract as given in ITB 1.1 above. |
| ITB 21.2 (c) | The warning should read “DO NOT OPEN BEFORE ______ [insert date and time]” |
| ITB 22.1 | The deadline for Bid submission (and withdrawals, substitutions or modifications) is: Date: ______ [insert day, month, and year, e.g. 19 December 2017] Time: _____ [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.] |
| E. Bid Opening and Evaluation |
| ITB 25.1 | The Bid opening (and reading of notices of withdrawals, substitutions or modifications of bids) shall take place at the following location and time: Street Address: ______ [insert street address and number] Floor/Room number: ______ [insert floor and room number, if applicable] City: _______ [insert name of city or town] Country: ______ [insert name of country] Date: ________ [insert day, month, and year, i.e. 19 December 2019] Time: ______ [insert time, and identify if a.m. or p.m., e.g. 10:30 a.m.] [insert time, and identify if a.m. or p.m. i.e. 10:30 a.m.] [Date and time should be the same as those given for the deadline for submission of Bids in ITB 22.1)] |
| ITB 34.1 BAFO | [Delete if not applicable] The evaluation will use the Best and Final Offer (BAFO) method. |
| ITB 34.2 Negotiations | [Delete if not applicable or if BDS in reference to ITB 34.1 specifies that BAFO is used] The final award will use Negotiations. |
| ITB 34.4 Independent Probity Assurance Authority | [Delete if not applicable,] If Negotiations are used, the Independent Probity Assurance Authority shall be: [indicate: name and address]. |
| ITB 34.5 Address for submission of BAFO | [Delete if not applicable] For the purpose of presenting the BAFO, the Employer's address is: [This address may be the same as in relation to the provision of ITB 8.1 for clarification or a different one] Attention: [insert full name of person, if applicable] Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City:] [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: :[insert name of country] |
| ITB 34.5 Deadline for submission of BAFO | [Delete if not applicable] The deadline for the presentation of the Best and Final Offer is: Date: [insert day, month, and year, e.g. 19 December, 2019] Time: [insert time, and identify if a.m. or p.m. e.g. 10:30 a.m.] [Date and time should be the same as those given for the deadline for submission of Bids (ITB 23)] [Note: The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their Bids electronically. Otherwise omit.] Bidders [insert “shall” or “shall not”] have the option of submitting their BAFO Bids electronically. The electronic Bid opening procedures shall be: [insert a description of the electronic Bid opening procedures] |
| ITB 34.5 Address for Negotiations and submission of Negotiated Bid | [Delete if not applicable] For the purpose of starting Negotiations and presenting the negotiated bid, the Employer's address is: [This address may be the same as in relation to the provision of ITB 7.1 for clarification or a different one] Attention: [insert full name of person, if applicable] Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City:] [insert name of city or town] ZIP Code: [insert postal (ZIP) code, if applicable] Country: :[insert name of country] |
| ITB 34.5 Deadline for submission of Negotiated Bid | [Delete if not applicable] The deadline for the presentation of the negotiated Bid will be defined in a Notification of the Employer certified by the Probity Authority. [The time allowed to present the negotiated bid will be determined by giving due consideration to the particular circumstances of the Project and the magnitude and complexity of the purchase. The period allowed must be at least five business days from the end of the negotiations] [The following provision will be included and the corresponding information required will be indicated only if Bidders have the option to submit the Negotiated Offer electronically. Delete if not applicable]. Selected Bidder [insert “shall” or “shall not”] have the option of submitting its negotiated Bid electronically. The procedures for submitting the negotiated bid electronically will be the following: [describe the procedures for submitting bids electronically] ________________ |
| F. Award of Contract |
| ITB 42.1 Beneficial Ownership | The selected Bidder ["shall" or "shall not"] submit the Form of Disclosure of Beneficial Ownership. |
| ITB 43.1 Performance Guarantee | The Standard Form of Performance Security acceptable to the Employer shall be [insert “a Bank Guarantee” or “a Performance Bond”]. [A Bank Guarantee shall be unconditional (on demand) (see Section X: Contract Forms). An amount of 5 to 10 percent of the Contract Price is commonly specified for Performance Bank Guarantees. A Performance Bond is an undertaking by a bonding or insurance company (surety) to complete the construction in the event of default by the Contractor, or to pay the amount of the Bond to the Employer. An amount of 30 percent of the Contract Price is commonly used internationally for this type of security (see Section X, “Contract Forms”)] |
| ITB 44.1 Advance Payment | The Advance Payment shall be limited to _____ [insert percentage] percent of the Contract Price. [Normally 10 to 30 percent of the Contract Price. The amount shall be adequate to minimize the needs of the Contractor to borrow for the Contract, notably in foreign currency(ies).] |
| ITB 45.1 Technical Adjudicator | The Technical Adjudicator proposed by the Employer is: ______ [insert name and address]. The hourly fee for this proposed Technical Adjudicator shall be [insert amount and currency]. The biographical data of the proposed Technical Adjudicator is as follows: [provide relevant information, such as education, experience, age, nationality, and present position; attach additional pages as necessary]. The Appointing Authority is: _______ [insert complete legal name and address] |
| ITB 46 Procurement-Related Complaints | The procedures for making a Procurement-related Complaint are detailed in the Procurement Policies for Goods and Works financed by the Inter-American Development Bank GN-2349-15. If a Bidder wishes to make a Procurement-related Complaint, the Bidder should submit its complaint following these procedures, in writing (by the quickest means available, that is email), to: For the attention: [insert full name of person receiving complaints] Title/position: [insert title/position] Employer: [insert name of Employer] Email address: [insert email address] |

# Section III.  Eligible Countries

Eligibility for the Provision of Goods, Works and Services in Bank-Financed Procurement

Note: In these documents, references to Bank include both, the IDB, Bid Lab, as well as any fund administered by the Bank

Next,  2 options of number 1) are shown, for the User to choose the one that is appropriate, according to the source of financing.  This source may be the Inter-American Development Bank (IDB), the Bid Lab  or, occasionally, contracts can be financed by special funds that could include different criteria for eligibility to a particular group of member countries. When the last option is selected, the eligibility criteria should be mentioned therein:

------------------------------------------------

1) List of Member Countries and Territories when the Inter-American Development Bank is financing:

Argentina, Austria, Bahamas, Barbados, Belgium, Belize, Bolivia, Brazil, Canada, Colombia, Costa Rica, Chile, Croatia,  Denmark, Dominican Republic, Ecuador, El Salvador, Finland, France, Germany, Guatemala, Guyana, Haiti, Honduras, Israel, Italy, Jamaica, Japan, Mexico, Netherlands, Nicaragua, Norway, Panama, Paraguay, People’s Republic of China, Peru, Portugal, Republic of Korea, Slovenia, Spain, Suriname, Sweden, Switzerland, Trinidad & Tobago, United Kingdom, United States, Uruguay and Venezuela.

Eligible Territories

      - Guadeloupe, French Guiana, Martinique, Reunion – as Departments of France

      - U.S. Virgin Islands, Puerto Rico, Guam – as Territories of the USA

      - Aruba – as a constituent country of the Kingdom of the Netherlands; and Bonaire, Curacao, Saint Marten, Saba, St Eustatius – as Departments of the Kingdom of the Netherlands

      - Hong Kong – as a Special Administrative Region of the People’s Republic of China

----------------------------------------------

1) List of Countries when a Fund administered by the Bank is financing

(Include the list of countries)]

-------------------------------------------------

2) Nationality and origin of Goods and Services Criteria

These policy provisions make it necessary to establish criteria to determine: a) the nationality of the firms and individuals eligible to bid or participate in a bank-financed contract and b) the country of origin of goods, and services.  For these determinations, the following criteria shall be used:

A) Nationality.

a) An individual is considered to be a national of a member country of the Bank if he or she meets either of the following requirements:

- is a citizen of a member country; or

- has established his/her domicile in a member country as a “bona fide” resident and is legally entitled to work in the country of domicile.

b) A firm is considered to have the nationality of a member country if it meets the two following requirements:

- is legally constituted or incorporated under the laws of a member country of the Bank; and

- more than fifty percent (50%) of the firm’s capital is owned by individuals or firms from member countries of the Bank.

All members of a JVCA and all subcontractors must meet the nationality criteria set forth above.

B) Origin of Goods.

Goods have their origin in a member country of the Bank if they have been mined, grown, harvested, or produced in a member country of the Bank.  A good has been produced when through manufacture, processing or assembly another commercially recognized article results that differs substantially in its basic characteristics, function or purpose of utility from its parts or components.

For a good consisting of several individual components that need to be interconnected (either by the supplier, the Employer or by a third party) to make the good operative and regardless of the complexity of the interconnection, the Bank considers that such good is eligible for financing if the assembly of the components took place in a member country, regardless of the origin of the components.  When the good is a set of several individual goods that are normally packaged and sold commercially as a single unit, the good is considered to originate in the country where the set was packaged and shipped to the Employer.

For purpose of origin, goods labeled “made in the European Union” shall be eligible without the need to identify the corresponding specific country of the European Union.

The origin of materials, parts or components of the goods or the nationality of the firm that produces, assembles, distributes or sells the goods, does not determine the origin of the goods.

C) Origin of Services.

The country of origin of services is that of the individual or firm providing the services as determined under the nationality criteria set forth above.  These criteria apply to services ancillary to the supply of goods (such as transportation, insurance, erection, assembly, etc.), to construction services and to consulting services.

# Section IV.  Bidding Forms

Table of Bidding Forms

Letter of Bid	54

Qualification Information	58

Form ESHS- MSIP	61

Code of Conduct Standards	62

Bid Security (Bank Guarantee)	63

Bid Security (Bid Bond)	64

Bid Validity Declaration	66

## Letter of Bid

[The Bidder shall fill in and submit this form with the Bid.  If the Bidder objects to the Technical Adjudicator proposed by the Employer in the bidding document, it should so state in its Bid, and present an alternative candidate, together with the candidate’s daily fees and biographical data, in accordance with ITB 45

In respect to the statement on commissions, bonuses or fees, services it may be for example, payments to, or through, individuals or entities that are authorized to act on behalf of the Bidder to advance the interests of the Bidder in relation to this process of bidding or execution of the Contract]

Note: All italicized text is to help Bidders in preparing this form.

[date]

RFB Identification No and Title of Contract: [insert identification number and title of the Contract]

To: [name and address of Employer]

- Conformity: Having examined the bidding document, including addenda [insert list], we offer to execute the [name and identification number of Contract] in accordance with the GCC accompanying this Bid for the Contract Price of [insert amount in numbers], [insert amount in words] [insert name of currency].

- Total price: The Contract shall be paid in the following currencies:

| Currency | Percentage payable in currency | Rate of exchange: [insert number of local currency units per unit of foreign currency] | Inputs for which foreign currency is required |
| --- | --- | --- | --- |
| (a) (b) (c) (d) |  |  |  |

- Advance Payment: The advance payment required is:

| Amount | Currency |
| --- | --- |
| (a) (b) (c) (d) |  |

- Technical Adjudicator: We accept the appointment of [insert name proposed in Bid Data Sheet] as the Technical Adjudicator.

[or]

We do not accept the appointment of [insert name proposed in Bid Data Sheet] as the Technical Adjudicator and propose instead that [insert name] be appointed as Technical Adjudicator, whose daily fees and biographical data are attached.

- Binding Contract: This Bid and your written acceptance of it shall constitute a binding Contract between us. We understand that the Employer is not bound to accept the Most Advantageous Bid or any Bid you receive.

- Bid Validity: We hereby confirm that this Bid complies with the Bid validity and, if required, Bid Security or Bid Validity Declaration as required by the bidding document and specified in the BDS.

- Bid Validity and Bid Security: Our Bid shall be valid for a period specified in the bidding document, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- Eligibility: We meet the eligibility requirements and have no conflict of interest in accordance with ITB 5; and in case of detecting that any of the named parties are in any conflict of interest, we will notify this circumstance in writing to the Employer, either during the selection process, the negotiations or the execution of the Contract. In the event that the works contract includes the supply of goods and related services, we undertake that these goods and related services originate in member countries of the Bank.

In addition, we, including any subcontractor or supplier for any component of the contract, have no conflict of interest, in accordance with the provisions of ITB 5.2; and in case of detecting that any of those named are in any conflict of interest, we will notify this circumstance in writing to the Employer, either during the selection process and the negotiations or the execution of the Contract;

- Suspension and Debarment: We, our subcontractors and suppliers for any component of the contract (including, in all cases, the respective directors, officers, principal shareholders, proposed key personnel and agents), we have not been directors, officers or principal shareholders and agents of a company or entity:

- that has been declared ineligible by the Bank, or has been declared ineligible by the IDB in in accordance with the Agreement for Mutual Enforcement of Debarment Decisions between the IDB and other development banks;

- that has been declared ineligible under the laws or official regulations of the Employer's country,

- that has been declared ineligible pursuant to a decision of the United Nations Security Council, and

- that has incurred in any Prohibited Practice ;

- State-owned enterprise or institution: [select the appropriate option and delete the other] [We are not a state-owned enterprise or institution] / [We are a state-owned enterprise or institution but meet the requirements of ITB 5.5]

- Cooperation: We will use our best efforts to assist the Bank in any investigation;

- Commissions, gratuities and fees: We have paid, or will pay the following commissions, gratuities, or fees with respect to the Bidding process or execution of the Contract: [insert complete name of each Recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity]

| Name of Recipient | Address | Purpose of the commission or gratuity | Amount |
| --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- Binding Contract: We understand that this Bid, together with your written acceptance thereof included in your Letter of Acceptance, shall constitute a binding contract between us, until a formal contract is prepared and executed;

- Not Bound to Accept: We understand that the Purchaser is not bound to accept the Most Advantageous Bid or any other Bid that you may receive;

- Best Final Offer or Negotiations: We understand that if the Employer use the Best Final Offer method (in the evaluation of Bids or Negotiations (in the presence of an Indepencdent Probity Assurance Authority agreed with the Bank) in the final adjudication, if so specified in BDS in reference to ITB 34, there will be an Independent Probity Assurance Authority hired by the Employer to observe and report on this process.

- Prohibited Practices: We, and our subcontractors or suppliers for any component of the contract (including, in all cases, the respective directors, officers, principal shareholders, proposed key personnel and agents) have read and understood the definitions of Prohibited Practices of the Bank and the sanctions applicable to acts as described in this document and we are obliged to observe the relevant norms. In addition, we commit ourselves that within the selection process (and in case of being awarded, in the execution) of the contract, to observe the laws on fraud and corruption, including bribery, applicable in the country of the Employer.

In addition, we, and our subcontractors or suppliers for any component of the contract (including, in all cases, the respective directors, officers, principal shareholders, proposed key personnel and agents) acknowledge that failure to comply with any of these statements is the basis for the imposition by the Bank of one or more of the measures described in ITB 3.1.

Our company, its parent company, its affiliates or subsidiaries, subcontractors or suppliers for any part of the contract (including, in all cases, directors, officers, principal shareholders, proposed key personnel and agents):

- We have not been declared ineligible by the Bank, or by any other International Financial Institution (IFI) with which the Bank has signed an agreement for the reciprocal recognition of sanctions, so that we may be awarded contracts financed by any of them; and

- We have not engaged in any Prohibited Practice or Fraud and Corruption and have taken the necessary measures to ensure that no person acting for us or on our behalf participates in fraud and corruption or prohibited practices.

- Excluded Activities: We, and our subcontractors or suppliers for any component of the contract have read and understood the definitions of the Excluded Activities contained in Annex I “IDB Environmental and Social Exclusion List” to the Bank’s Environmental and Social Policy Framework (ESPF), and will under the terms of the awarded contract not knowingly engage directly or indirectly in the production, trade or use of the products, substance or participate in the activities listed in said list.

- Disclosure of Beneficial Ownership Form: (Applies in the event that the Bidder must provide the Form). We understand that in the event that our Bid is accepted we will be providing the required information on the Beneficial Ownership Disclosure Form or, where appropriate, we will indicate the reasons why it is not possible to provide the required information. We state herewith the authorization for the Borrower to publish as part of the Contract Award Notification the Beneficial Ownership Disclosure Form.

Authorized Signature:

Name and Title of Signatory:

Name of Bidder:

Address:

## Qualification Information

[The information to be filled in by bidders in the following pages shall be used for purposes of qualification or for verification of prequalification as provided for in ITB 6.  This information shall not be incorporated in the Contract.  Attach additional pages as necessary. If used for prequalification verification, the Bidder should fill in updated information only.]

| 1. Firms or Members of JVCA | 1.1 Incorporation, constitution or legal status of Bidder: [attach copy of document or letter of intent] Place of constitution or incorporation: [insert] Principal place of business: [insert] Power of attorney of signatory of Bid: [attach] 1.2 Annual amounts of construction works performed during the last [insert number pursuant to BDS 5.5(a)] years [insert amounts in the national currency equivalent] 1.3 Experience in works of a similar nature and size is in [insert number of works and information specified in ITB 6.3(c)] [The amounts should be indicated in the same currency used for Item 1.2 above. Also list details of work under way or committed, including expected completion date(s).] |
| --- | --- |

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract (national currency equivalent) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

|  | 1.4 The major items of Contractor’s Equipment proposed for carrying out the Works are: [List all information requested below in accordance with ITB 6.3 (d).] |
| --- | --- |

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

|  | 1.5 The qualifications and experience of key personnel proposed are attached. [Attach biographical data in accordance with ITB 6.3 (e). See also GCC Sub-Clause 9.1 and SCC Sub-Clause 9.1. Include the list of such staff in the following table] |
| --- | --- |

| Position | Name | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- |
| (a) (b) |  |  |  |

|  | 1.6 The financial reports for the last 5 years: balance sheets, profit and loss statements, auditors’ reports, etc., that are attached in accordance with ITB 6.3(f) are: [List below and attach copies.] 1.7 The evidence of access to financial resources in accordance with ITB 6.3(g) is: [List below and attach copies of support documents.] 1.8 Authorization with name, address, telephone, and facsimile numbers of banks that may provide references if contacted by the Employer is attached in accordance with ITB 6.3(h). [Attach authorization] 1.9 The information on current litigation(s) in which the Bidder is involved is attached in accordance with ITB 6.3(i). [insert information in the following table]. 1.10 Declare works contracts that have been suspended or terminated by an Employer for reasons related to non-compliance with any environmental, social, health or safety requirements (including exploitation and sexual abuse and gender-based violence (SVBG)) in the last five years. |
| --- | --- |

| Other part(y)(ies) | Cause of dispute and amount involved | Amount of award and awardee |
| --- | --- | --- |
| (a) (b) |  |  |
| Sections of the Works | Value of subcontract | Subcontractor (name and address) | Experience in similar work |
| (a) (b) |  |  |  |

|  | 1.11 The proposed subcontracts and firms involved in accordance with ITB 6.3(j) are: [Insert information in the table above. Also see GCC Clause 7 and SCC 7] |
| --- | --- |

|  | 1.12 Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding document. |
| --- | --- |
| 2. Joint Venture, Consortium or Association (JVCA) | 2.1 The information listed in 1.1 - 1.10 above shall be provided for each partner of the JVCA. |
|  | 2.2 The information in 1.11 above shall be provided for the JVCA. |
|  | 2.3 Attach the power of attorney of the signatory(ies) of the Bid authorizing signature of the Bid on behalf of the JVCA. |
|  | 2.4 Attach the Agreement among all partners of the JVCA (and which is legally binding on all partners), which shows that: (a) all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms; (b) one of the partners shall be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the JVCA; and (c) the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge. |
| 3. Additional Requirements | 3.1 Bidders should provide any additional information required in the BDS. |

## Form ESHS- MSIP

Environmental, Social, Safety and Health Management

Strategies and Implementation Plans

[Note to the Employer:  modify the text as appropriate for the Project]

[The Bidder shall submit for approval, and subsequently implement the Management Strategies and Implementation Plans (MSIP) to manage the key Environmental, Social, Health and Safety (ESHS) risks and impacts, including risks related to labor, occupational and community health and safety, disaster and climate change, indigenous peoples, vulnerable groups, gender, sexual and gender-based violence (SGBV) and stakeholder engagement, that are collectively referred to as the Contractor’s Environmental and Social Management Plan (C-ESMP). The MSIPs are to be developed according to the Project’s Environmental and Social Assessment (ESA), Project-specifc Environmental and Social Framework (ESF) and Environmental and Social Management Plan (ESMP) and the respective IDB Environmental and Social Action Plan (ESAP.. ]

In preparing these strategies and plans, the Bidder shall take into account the contract ESHS stipulations, including the ones described in more details in Section VII, “Specifications & Performance Requirements.”

## Code of Conduct Standards

Environmental, Social, Health and Safety

[Note to the Employer:  modify the text to refer to the appropriate documents]

The Bidder shall submit the Code of Conduct  defining rules of behavior for all workers related to prevention and management measures for environmental, labor, and social risks of the Project, including health and safety risks, sexual and gender-based violence, discrimination, and sexual abuse and exploitation of children and other individuals or vulnerable groups that will apply to the Contractor’s employees and  subcontractors' employees. The standards of conduct shall guarantee compliance with ESHS contract provisions, including those described in more details in Section VII, “Specifications & Performance Requirements.”

The Code of Conduct should be written in plain language, in a manner that is clear, understandable and accessible, will be provided and properly communicated to all workers and should, where possible, be signed by each worker to indicate that they have:

•	received a copy of the code;

•	had the code explained to them;

•	acknowledged that adherence to this Code of Conduct is a condition of employment; and

•	understood that violations of the Code can result in serious consequences, up to and including dismissal, or referral to legal authorities.

A copy of the Code shall be displayed throughout project implementation in a location easily accessible to the workers, community and project affected person. It shall be provided in languages comprehensible to the local community, Contractor’s Personnel, Employer’s Personnel, and affected persons.

## Bid Security (Bank Guarantee)

[If required, the Bank/Bidder shall fill in this Bank Guarantee form in accordance with the instructions indicated in brackets.]

[insert bank’s name, and address of issuing branch or office]

Beneficiary:	 [insert name and address of Employer]

Date:	[insert date]

BID GUARANTEE No.:	[insert number]

We have been informed that [insert name of the Bidder; if a JVCA, list complete legal names of partners] (hereinafter called "the Bidder") has submitted to you its bid dated [insert date]  (hereinafter called "the Bid") for the execution of [insert name of Contract] under Request for Bids No. [insert RFB number] (“the RFB”).

Furthermore, we understand that, according to your conditions, Bids must be supported by a Bid Guarantee.

At the request of the Bidder, we [insert name of bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [insert amount in figures expressed in the currency of the Employer’s Country or the equivalent amount in an international freely convertible currency]  ([insert amount in words]) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a) 	has withdrawn its Bid during the period of bid validity specified by the Bidder in the Form of Bid; or

(b) 	does not accept the correction of errors in accordance with the Instructions to Bidders (hereinafter “the ITB”) of the bidding document; or

(c) 	having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Form, if required, or (ii) fails or refuses to furnish the Performance Security, in accordance with the ITB.

This Guarantee shall expire:  (a) if the Bidder is the successful bidder, upon our receipt of copies of the Contract signed by the Bidder and of the Performance Security issued to you by the Bidder; or (b) if the Bidder is not the successful bidder, upon the earlier of (i) our receipt of a copy of your notification to the Bidder that the Bidder was unsuccessful, or (ii) twenty-eight days after the expiration of the Bidder’s Bid.

Consequently, any demand for payment under this Guarantee must be received by us at the office on or before that date.  This Guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

_____________________________

[signature(s) of authorized representative(s) ]

## Bid Security (Bid Bond)

[If required, the Surety/Bidder shall fill in this Bid Bond Form in accordance with the instructions indicated in brackets.]

BOND NO. [insert Bond number]

BY THIS BOND [insert name of Bidder; if JVCA, insert complete legal names of partners] as Principal (hereinafter called “the Principal”), and [insert name, legal title, and address of Surety], authorized to transact business in [insert name of country of Employer], as Surety (hereinafter called “the Surety”), are held and firmly bound unto [insert name of Employer] as Obligee (hereinafter called “the Employer”) in the sum of [insert amount in figures expressed in the currency of the Employer’s Country or the equivalent amount in an international freely convertible currency] [insert amount in words], for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted a written Bid to the Employer dated the [number] day of [month], [year], for the construction of [insert name of Contract] (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

- withdraws its Bid during the period of bid validity specified in the Form of Bid; or

- refuses to accept the correction of its Bid Price, pursuant to ITB Sub-Clause 28.2; or

- having been notified of the acceptance of its Bid by the Employer during the period of Bid validity;

- fails or refuses to execute the Agreement in accordance with the Instructions to Bidders, if required; or

- fails or refuses to furnish the Performance Security in accordance with the Instructions to Bidders;

then the Surety undertakes to immediately pay to the Employer up to the above amount  upon receipt of the Employer’s first written demand, without the Employer having to substantiate its demand, provided that in its demand the Employer shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation shall remain in full force and affect up to and including the date 28 days after the date of expiration of the Bid validity as stated in the Invitation to Bid or extended by the Employer at any time prior to this date, notice of which extension(s) to the Surety being hereby waived.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this [insert number] day of [month], [year]

Principal: _______________________	Surety: ______________________________

Corporate Seal (where appropriate)

_______________________________	____________________________________

[insert signature(s) of authorized	[insert signature(s) of authorized representative(s)]	representative(s)]

_______________________________	____________________________________

[insert printed name and title]	[insert printed name and title]

## Bid Validity Declaration

[If required, the Bidder shall fill in this form in accordance with the instructions indicated in brackets.]

Date: [insert date]

Name of contract: [insert name]

Contract Identification No: [insert number]

RFB No.: [insert number]

To: ____________________________

We, the undersigned, declare that:

1.	We understand that, according to your conditions, bids must be supported by a bid validity declaration.

2.	We accept that we shall be suspended from being eligible for bidding in any contract with the Employer for the period of time of [insert time period] starting on [insert start date], if we are in breach of our obligation(s) under the bid conditions, because we:

(a) 	have withdrawn our Bid during the period of bid validity specified by us in the Bid Submission Sheet; or

(b) 	do not accept the correction of errors in accordance with the Instructions to Bidders (hereinafter “the ITB”) of the bidding document; or

(c) 	having been notified of the acceptance of our Bid by the Employer  during the period of bid validity, (i) fail or refuse to execute the Contract Form, if required, or (ii) fail or refuse to furnish the performance security, in accordance with the ITB.

3.	We understand this bid validity shall expire if we are not the successful bidder, upon the earlier of (i) our receipt of your notification informing us that we are not the successful bidder; or (ii) twenty-eight days after the expiration of our bid.

4.	We understand that if we are a JVCA, the Bid Validity Declaration must be in the name of the JVCA that submits the bid. If the JVCA has not been legally constituted at the time of bidding, the Bid Validity Declaration shall be in the names of all future partners as named in the letter of intent.

Signed [insert signature(s) of authorized representative] In the Capacity of [insert title]

Name [insert printed or typed name]

Duly authorized to sign the bid for and on behalf of [insert authorizing entity]

Dated on [insert day] day of [insert month], [insert year]

# Section V.  General Conditions of Contract

The General Conditions of Contract (GCC), read in conjunction with the Special Conditions of Contract (SCC) and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties.

The form of General Conditions of Contract that follows has been developed on the basis of considerable international experience in the drafting and management of contracts, bearing in mind a trend in the construction industry towards simpler, more straightforward language.

The form can be used directly for smaller admeasurement contracts and, with the modifications noted in the footnotes, it can be adapted for lump sum contracts.

The use of standard General Conditions of Contract (GCC) for building and civil works in a country shall promote comprehensiveness of coverage, general acceptability of its provisions, savings in cost and time in Bid preparation and review, and the development of a solid background of legal case histories.

Table of Clauses

A.  General	63

1.	Definitions	63

2.	Interpretation	65

3.	Language and Law	66

4.	Project Manager’s Decisions	66

5.	Delegation	66

6.	Communications	66

7.	Subcontracting	66

8.	Other Contractors	66

9.	Personnel	66

10.	Employer’s and Contractor’s Risks	67

11.	Employer’s Risks	67

12.	Contractor’s Risks	68

13.	Insurance	68

14.	Site Investigation Reports	68

15.	Queries about the Special Conditions of Contract	69

16.	Contractor to Construct the Works	69

17.	The Works to Be Completed by the Intended Completion Date	69

18.	Approval by the Project Manager	69

19.	Safety	69

20.	Discoveries	69

21.	Possession of the Site	69

22.	Access to the Site	70

23.	Instructions, Inspections and Audits	70

24.	Disputes	70

25.	Procedure for Disputes	70

26.	Replacement of Technical Adjudicator	70

B.  Time Control	71

27.	Program	71

28.	Extension of the Intended Completion Date	71

29.	Acceleration	72

30.	Delays Ordered by the Project Manager	72

31.	Management Meetings	72

32.	Early Warning	72

C.  Quality Control	73

33.	Identifying Defects	73

34.	Tests	73

35.	Correction of Defects	73

36.	Uncorrected Defects	73

D.  Cost Control	73

37.	Bill of Quantities	73

38.	Changes in the Quantities	74

39.	Variations	74

40.	Payments for Variations	74

41.	Cash Flow Forecasts	75

42.	Payment Certificates	75

43.	Payments	75

44.	Compensation Events	76

45.	Tax	77

46.	Currencies	77

47.	Price Adjustment	78

48.	Retention	78

49.	Liquidated Damages	79

50.	Bonus	79

51.	Advance Payment	79

52.	Securities	80

53.	Daywork	80

54.	Cost of Repairs	80

E.  Finishing the Contract	80

55.	Completion	80

56.	Taking Over	80

57.	Final Account	81

58.	Operating and Maintenance Manuals	81

59.	Termination	81

60     Prohibited Practices ………………	82

61.	Payment upon Termination	91

62.	Property	91

63.	Release from Performance	92

64.	Payment’s Suspension of Bank Loan	92

65.    Eligibility	92

General Conditions of Contract

A.  General

| 1. Definitions | 1.1 Boldface type is used to identify defined terms. The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in GCC Clauses 24 and 25 hereunder. Bill of Quantities means the priced and completed Bill of Quantities forming part of the Bid. Compensation Events are those defined in GCC Clause 44 hereunder. The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with GCC Sub-Clause 55.1. The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in GCC Clause 2.3 below. The Contractor is a person or corporate body whose Bid to carry out the Works has been accepted by the Employer. The Contractor’s Bid is the completed bidding document submitted by the Contractor to the Employer. The Contract Price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract. Days are calendar days; months are calendar months. Dayworks are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant. A Defect is any part of the Works not completed in accordance with the Contract. The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor. The Defects Liability Period is the period named in the SCC Sub-Clause 35.1 and calculated from the Completion Date. Drawings include calculations and other information provided or approved by the Project Manager for the execution of the Contract. The Employer is the party who employs the Contractor to carry out the Works, as specified in the SCC. Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the SCC. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. The Project Manager is the person named in the SCC (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. SCC means Special Conditions of Contract The Site is the area defined as such in the SCC. Site Investigation Reports are those that were included in the bidding document and are factual and interpretative reports about the surface and subsurface conditions at the Site. Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. The Start Date is given in the SCC. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. A Variation is an instruction given by the Project Manager which varies the Works. The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the SCC. ESHS are the environmental, social, health and safety obligations as stated in the Contractor’s Bid as accepted by the Employer that the Contractor shall implement in the execution of the Works as well any national requirements on these topics, and should they not exist, as they are contained in the Inter-American Development Bank policy and implementation guidelines and the Specification. |
| --- | --- |
| 2. Interpretation | 2.1 In interpreting these GCC, singular also means plural, male also means female, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager shall provide instructions clarifying queries about these GCC. 2.2 If sectional completion is specified in the SCC, references in the GCC to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). 2.3 The documents forming the Contract shall be interpreted in the following order of priority: Agreement, Letter of Acceptance, Contractor’s Bid (the last if BAFO or Negotiations were used), Special Conditions of Contract, General Conditions of Contract, Specifications, Drawings, Bill of Quantities, (the last if BAFO or Negotiations were used) and any other document listed in the SCC as forming part of the Contract. |
| 3. Language and Law | 3.1 The language of the Contract and the law governing the Contract are stated in the SCC. |
| 4. Project Manager’s Decisions | 4.1 Except where otherwise specifically stated, the Project Manager shall decide contractual matters between the Employer and the Contractor in the role representing the Employer. |
| 5. Delegation | 5.1 The Project Manager may delegate any of his duties and responsibilities to other people, except to the Technical Adjudicator, after notifying the Contractor, and may cancel any delegation after notifying the Contractor. |
| 6. Communications | 6.1 Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| 7. Subcontracting | 7.1 The Contractor may subcontract with the approval of the Project Manager but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations. |
| 8. Other Contractors | 8.1 The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the SCC. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors and shall notify the Contractor of any such modification. |
| 9. Personnel | 9.1 The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the SCC, to carry out the functions stated in the Schedule or other personnel approved by the Project Manager. The Project Manager shall approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. 9.2 If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract. Reasons for dismissing a person include behavior that disregards the ESHS Code of Conduct (such as the spread of contagious diseases, sexual harassment, gender-based violence (GBV)), illegal or criminal activities). |
| 10. Employer’s and Contractor’s Risks | 10.1 The Employer carries the risks which this Contract states are the Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| 11. Employer’s Risks | 11.1 From the Start Date until the Defects Correction Certificate has been issued, the following are the Employer’s risks: (a) The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to (i) use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works or (ii) negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor. (b) The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed. 11.2 From the Completion Date until the Defects Correction Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to (a) a Defect which existed on the Completion Date, (b) an event occurring before the Completion Date, which was not itself an Employer’s risk, or (c) the activities of the Contractor on the Site after the Completion Date. |
| 12. Contractor’s Risks | 12.1 From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks are Contractor’s risks. 12.2 Contractor’s risks are when there is a breach of the environmental, social (including sexual exploitation and abuse (SEA) and gender-based violence (GBV) and health and safety (ESHS) obligations established by the applicable law and/or the applicable Contract provisions. |
| 13. Insurance | 13.1 The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the SCC for the following events which are due to the Contractor’s risks: (a) loss of or damage to the Works, Plant, and Materials; (b) loss of or damage to Equipment; (c) loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and (d) personal injury or death. 13.2 Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. 13.3 If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. 13.4 Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. 13.5 Both parties shall comply with any conditions of the insurance policies. |
| 14. Site Investigation Reports | 14.1 The Contractor, in preparing the Bid, shall rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder. |
| 15. Queries about the Special Conditions of Contract | 15.1 The Project Manager shall clarify queries on the SCC. |
| 16. Contractor to Construct the Works | 16.1 The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. 16.2 The Contractor shall not carry out any Works, including mobilization and/or pre-construction activities (e.g. limited clearance for haul roads, site accesses and work site establishment, geotechnical investigations or investigations to select ancillary features such as quarries and borrow pits), unless the Project Manager is satisfied that appropriate measures are in place to address ESHS risks and impacts including labor, occupational and community health and safety, disaster and climate change, Indigenous Peoples, vulnerable groups, gender, and sexual and gender-based violence (SGBV) and stakeholder engagement. . At a minimum, the Contractor shall apply the Management Strategies and Implementation Plans and Code of Conduct, submitted as part of the Bid and agreed as part of the Contract. At a minimum, the Contractor shall apply the Management Strategies and Implementation Plans and Code of Conduct, submitted as part of the Bid and agreed as part of the Contract. These Management Strategies and Implementation Plans collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP) that the Contractor shall submit, on a continuing basis, for the Engineer’s No-objection, to manage the ESHS risks and impacts of the ongoing Works. . The C-ESMP will include an Occupational Health and Safety Plan that shall be approved prior to the commencement of construction activities (e.g. excavation, earth works, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). The approved C-ESMP shall be reviewed, periodically, and updated in a timely manner, as required, by the Contractor to ensure that it contains measures appropriate to the Works activities to be undertaken and the ESHS risks identified. The updated C-ESMP shall be subject to prior approval by the Project Manager. |
| 17. The Works to Be Completed by the Intended Completion Date | 17.1 The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| 18. Approval by the Project Manager | 18.1 The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, who is to approve them if they comply with the Specifications and Drawings. 18.2 The Contractor shall be responsible for design of Temporary Works. 18.3 The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. 18.4 The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required. 18.5 All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before their use. |
| 19. Safety | 19.1 The Contractor shall be responsible for all obligations concerning the environment, social, health and safety of all activities at the Site, according to the regulations in the Country of the Employer, and should there be none, according to stipulations of the contract conditions and the Specifications. |
| 20. Discoveries | 20.1 Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| 21. Possession of the Site | 21.1 The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the SCC, the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event. |
| 22. Access to the Site | 22.1 The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |
| 23. Instructions, Inspections and Audits | 23.1 The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located. 23.2 The Contractor shall permit the Bank to inspect their accounts, records and other documents relating to the submission of bids and contract performance and to have them audited by persons appointed by the Bank. The Contractor shall maintain all documents and records related to the Bank-financed project for seven (7) years after completion of the work. The Contractor shall deliver any document necessary for the investigation of allegations of prohibited practices and require to employees or agents with knowledge of the Bank-financed project to respond to questions from the Bank. |
| 24. Disputes | 24.1 If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Technical Adjudicator within 14 days of the notification of the Project Manager’s decision. |
| 25. Procedure for Disputes | 25.1 The Technical Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute. 25.2 The Technical Adjudicator shall be paid by the hour at the rate specified in the BDS and SCC, together with reimbursable expenses of the types specified in the SCC, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Technical Adjudicator. Either party may refer a decision of the Technical Adjudicator to an Arbitrator within 28 days of the Technical Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Technical Adjudicator’s decision shall be final and binding. 25.3 The arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place specified in the SCC. |
| 26. Replacement of Technical Adjudicator | 26.1 Should the Technical Adjudicator resign or die, or should the Employer and the Contractor agree that the Technical Adjudicator is not functioning in accordance with the provisions of the Contract, a new Technical Adjudicator shall be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within 30 days, the Technical Adjudicator shall be designated by the Appointing Authority designated in the SCC at the request of either party, within 14 days of receipt of such request. |

B.  Time Control

| 27. Program | 27.1 Within the time stated in the SCC, after the date of the Letter of Acceptance, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. 27.2 An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. 27.3 The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the SCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the SCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted. 27.4 The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| --- | --- |
| 28. Extension of the Intended Completion Date | 28.1 The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. 28.2 The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |
| 29. Acceleration | 29.1 When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager shall obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date shall be adjusted accordingly and confirmed by both the Employer and the Contractor. 29.2 If the Contractor’s priced proposals for an acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation. |
| 30. Delays Ordered by the Project Manager | 30.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| 31. Management Meetings | 31.1 Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure. 31.2 The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| 32. Early Warning | 32.1 The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price, or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. 32.2 The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |

C.  Quality Control

| 33. Identifying Defects | 33.1 The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |
| --- | --- |
| 34. Tests | 34.1 If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| 35. Correction of Defects | 35.1 The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the SCC. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. 35.2 Every time notice of a Defect is given the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| 36. Uncorrected Defects | 36.1 If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager shall assess the cost of having the Defect corrected, and the Contractor shall pay this amount. |

D.  Cost Control

| 37. Bill of Quantities | 37.1 The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. 37.2 The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item. |
| --- | --- |
| 38. Changes in the Quantities | 38.1 If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change. 38.2 The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer. 38.3 If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. |
| 39. Variations | 39.1 All Variations shall be included in updated Programs produced by the Contractor. |
| 40. Payments for Variations and Value Engineering | 40.1 The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven (7) days of the request or within any longer period stated by the Project Manager, before the Variation is ordered. 40.2 If the work in the Variation corresponds with an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 38.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. 40.3 If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. 40.4 If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given, and the Variation shall be treated as a Compensation Event. 40.5 The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. 40.6 Value Engineering: The Contractor may prepare, at its own cost, a value engineering proposal at any time during the performance of the contract. The value engineering proposal shall, at a minimum, include the following; (a) the proposed change(s), and a description of the difference to the existing contract requirements; (b) a full cost/benefit analysis of the proposed change(s) including a description and estimate of costs (including life cycle costs) the Employer may incur in implementing the value engineering proposal; and (c) a description of any effect (s) of the change on performance/functionality. The Employer may accept the value engineering proposal if the proposal demonstrates benefits that: (a) accelerate the contract completion period; or (b) reduce the Contract Price or the life cycle costs to the Employer; or (c) improve the quality, efficiency, safety or sustainability of the Facilities; or (d) yield any other benefits to the Employer, (e) without compromising the functionality of the Works. If the value engineering proposal is approved by the Employer and results in: (i) a reduction of the Contract Price; the amount to be paid to the Contractor shall be the percentage specified in the PCC of the reduction in the Contract Price; or (ii) an increase in the Contract Price; but results in a reduction in life cycle costs due to any benefit described in (a) to (d) above, the amount to be paid to the Contractor shall be the full increase in the Contract Price |
| 41. Cash Flow Forecasts | 41.1 When the Program is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. The cash flow forecast shall include different currencies, as defined in the Contract, converted as necessary using the Contract exchange rates. |
| 42. Payment Certificates | 42.1 The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously. 42.2 The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor. 42.3 The value of work executed shall be determined by the Project Manager. 42.4 The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantities that have been completed. 42.5 The value of work executed shall include the valuation of Variations and Compensation Events. 42.6 The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. 42.7 If the Contractor was, or is, failing to perform any ESHS obligations or work under the Contract, the value of this work or obligation, as determined by the Project Manager, may be withheld until the work or obligation has been performed, and/or the cost of rectification or replacement, as determined by the Project Manager, may be withheld until rectification or replacement has been completed. Failure to perform includes, but is not limited to the following: failure to comply with any ESHS obligations or work described in the Works’ Requirements which may include: working outside site boundaries, excessive dust, failure to keep public roads in a safe usable condition, damage to offsite vegetation, pollution of water courses from oils or sedimentation, contamination of land e.g. from oils, human waste, damage to archeology or cultural heritage features, air pollution as a result of unauthorized and/or inefficient combustion; failure to regularly review C-ESMP and/or update it in a timely manner to address emerging ESHS issues, or anticipated risks or impacts; failure to implement the C-ESMP e.g. failure to provide required training or sensitization; failure to have appropriate consents/permits prior to undertaking Works or related activities; failure to implement remediation as instructed by the Project Manager within the specified timeframe (e.g. remediation addressing non-compliance/s). |
| 43. Payments | 43.1 Payments shall be adjusted for deductions for advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made. 43.2 If an amount certified is increased in a later certificate or as a result of an award by the Technical Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. 43.3 Unless otherwise stated, all payments and deductions shall be paid or charged in the proportions of currencies comprising the Contract Price. 43.4 Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |
| 44. Compensation Events | 44.1 The following shall be Compensation Events: (a) The Employer does not give access to a part of the Site by the Site Possession Date pursuant to GCC Sub-Clause 21.1. (b) The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. (c) The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. (d) The Project Manager instructs the Contractor to uncover work done, or to carry out additional tests upon work, which is then found to have no Defects. (e) The Project Manager unreasonably does not approve a subcontract to be let. (f) Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site. (g) The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons. (h) Other contractors, public authorities, utilities, or the Employer do not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor. (i) The advance payment is delayed. (j) The effects on the Contractor of any of the Employer’s Risks. (k) The Project Manager unreasonably delays issuing a Certificate of Completion. 44.2 If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. 44.3 As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager shall assume that the Contractor shall react competently and promptly to the event. 44.4 The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| 45. Tax | 45.1 The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of bids for the Contract and the date of the last Completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of GCC Clause 47. |
| 46. Currencies | 46.1 Where payments are made in currencies other than the currency of the Employer’s country specified in the SCC, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Bid. |
| 47. Price Adjustment | 47.1 Prices shall be adjusted for fluctuations in the cost of inputs only if provided for in the SCC. If so provided, the amounts certified in each payment certificate, before deducting for Advance Payment, shall be adjusted by applying the respective price adjustment factor to the payment amounts due in each currency. A separate formula of the type indicated below applies to each Contract currency: Pc = Ac + Bc (Imc/Ioc) where: Pc is the adjustment factor for the portion of the Contract Price payable in a specific currency “c.” Ac and Bc are coefficients specified in the SCC, representing the nonadjustable and adjustable portions, respectively, of the Contract Price payable in that specific currency “c;” and Imc is the index prevailing at the end of the month being invoiced and Ioc is the index prevailing 28 days before Bid opening for inputs payable; both in the specific currency “c.” 47.2 If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected, and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs. |
| 48. Retention | 48.1 The Employer shall retain from each payment due to the Contractor the proportion stated in the SCC until Completion of the whole of the Works. 48.2 On completion of the whole of the Works and the Project Manager certification of completion of the works according to GCC Sub-Clause 55.1, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. 48.3 On completion of the whole Works and the Project Manager certification of completion of the works according to GCC Sub-Clause 55.1, the Contractor may substitute retention money with an “on demand” Bank guarantee. |
| 49. Liquidated Damages | 49.1 The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the SCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. 49.2 If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC Sub-Clause 43.1. |
| 50. Bonus | 50.1 The Contractor shall be paid a Bonus calculated at the rate per calendar day stated in the SCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Project Manager shall certify that the Works are complete, although they may not be due to be complete. |
| 51. Advance Payment | The Employer shall make advance payment to the Contractor of the amounts stated in the SCC by the date stated in the SCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest shall not be charged on the advance payment. The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages. |
| 52. Securities | 52.1 The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount specified in the SCC, by a bank or surety acceptable to the Employer, and denominated in the types and proportions of the currencies in which the Contract Price is payable. The Performance Security shall be valid until a date 28 days later than the date of issue of the Certificate of Completion in the case of a Bank Guarantee, and until one year later than the date of issue of the Completion Certificate in the case of a Performance Bond. |
| 53. Daywork | 53.1 If applicable, the Daywork rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. 53.2 All work to be paid for as Daywork shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two days of the work being done. 53.3 The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| 54. Cost of Repairs | 54.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |

E.  Finishing the Contract

| 55. Completion | 55.1 The Contractor shall request the Project Manager to issue a certificate of Completion of the Works, and the Project Manager shall do so upon deciding that the work is completed. |
| --- | --- |
| 56. Taking Over | 56.1 The Employer shall take over the Site and the Works within seven (7) days of the Project Manager’s issuing a certificate of Completion. |
| 57. Final Account | 57.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| 58. Operating and Maintenance Manuals | 58.1 If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the SCC. 58.2 If the Contractor does not supply the Drawings and/or manuals by the dates stated in the SCC, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the SCC from payments due to the Contractor. |
| 59. Termination | 59.1 The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. 59.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following: (a) the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager; (b) the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days; (c) the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; (d) a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate; (e) the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; (f) the Contractor does not maintain a Security, which is required; (g) the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the SCC; (h) if Contractor, in the judgment of the Employer has engaged in Fraud and Corruption or Prohibited Practices in competing for or in executing the Contract, as established in the Policies of the Inter-American Development Bank, indicated in Clause 60.1 of these GCC; and (i) if the Contractor substantially prevents the exercise of the Bank's rights to perform audits, notwithstanding the provisions of Subclause 60.1 (f). of this Contract. 59.3 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC Sub-Clause 59.2 above, the Project Manager shall decide whether the breach is fundamental or not. 59.4 Notwithstanding the above, the Employer may terminate the Contract for convenience at any time. 59.5 If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| 60.Prohibited Practices | 60.1 The Bank requires that all Borrowers (including grant beneficiaries), Executing Agencies and Contracting Agencies, including members of its personnel, as well as all firms, entities and individuals participating in a Bank-financed activity acting as, inter alia, bidders, proposers, suppliers, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires (including their respective officers, employees and representatives or agents, irrespective of whether the agency is express or implied), adhere to the highest ethical standards, and report to the Bank all suspected acts of Prohibited Practices of which they have knowledge or become aware both, during the bidding process and throughout the negotiation or execution of a contract. Prohibited Practices are: (i) corrupt practices; (ii) fraudulent practices; (iii) coercive practices; (iv) collusive practices; (v) obstructive practices; and (vi) misappropriation of funds. The Bank has established mechanisms to report allegations of Prohibited Practices. Any allegation shall be submitted to the Bank’s Office of Institutional Integrity (OII) for the appropriate investigation. The Bank has adopted procedures to sanction those who have incurred in Prohibited Practices. The Bank also entered into an agreement with other International Financial Institutions (IFIs) to mutually recognize debarment decisions. For the purposes of this provision, the definitions of Prohibited Practices are as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (i) destroying, falsifying, altering or concealing of evidence material to an IDB Group investigation, or making false statements to investigators with the intent to impede an IDB Group investigation; (ii) threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to an IDB Group investigation or from pursuing the investigation, or (iii) acts intended to impede the exercise of the IDB Group’s contractual rights of audit or inspection provided for under Subclause 60.1(f) below or access to information; and (vi) “misappropriation” is the use of IDB Group financing or resources for an improper or unauthorized purpose, committed either intentionally or through reckless disregard. If, the Bank determines that at any stage of the procurement or implementation of a contract the Borrower (including beneficiaries of grants), Executing Agencies, Contracting Agencies, any firm, entity or individual participating in a Bank-financed activity as, inter alia, bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, goods or service providers, concessionaires, (including their respective officers, employees and representatives or agents irrespective of whether the attribution is express or implied) engaged in a Prohibited Practice during the award or implementation of the contract, the Bank may: (i) not finance any proposal to award a contract for works, goods or services, and consulting services; (ii) suspend disbursement of the operation if it is determined at any stage that an employee, agent or representative of the Borrower, Executing Agency or Employer has engaged in a Prohibited Practice; (iii) declare Misprocurement and cancel, and/or accelerate repayment of the portion of a loan or grant earmarked for a contract, when there is evidence that the representative of the Borrower, or Beneficiary of a grant, has not taken the adequate remedial measures (including, inter alia, providing adequate notice to the Bank upon learning of the Prohibited Practice) within a time period which the Bank considers reasonable; (iv) issue the firm, entity or individual a reprimand in the form of a formal letter of censure for its behavior; (v) declare that a firm, entity, or individual is ineligible, either permanently or for a stated period of time, to participate and/or be awarded additional contracts financed with IDB Group resources; (vi) impose other sanctions that it deems to be appropriate, among others, the restitution of funds and of fines equivalent to the reimbursement for costs associated with investigations and proceedings contemplated in the Sanctions Procedures. Such other sanctions may be imposed in addition to or in lieu of the sanctions referred above (the “abovementioned” sanctions are reprimand and debarment/ineligibility); (vii) extend the sanctions imposed on any individual, entity or firm that, directly or indirectly, owns or controls a sanctioned entity, is owned or controlled by a sanctioned entity or is the object of common ownership or control with a sanctioned entity, as well as to officials, employees, affiliates or representatives or agents of a sanctioned entity who also own a sanctioned entity and / or exercise control over a sanctioned entity, even if it has not been concluded that those parties directly incurred in a Prohibited Practice; and/or (viii) refer the matter to appropriate law enforcement authorities. The provisions of Subclause 60.1 (b) (i) and (ii) shall also be applicable when such parties have been temporarily suspended from eligibility to be awarded additional contracts pending a final outcome of a sanction proceeding, or otherwise. The imposition of any action to be taken by the Bank pursuant to the provisions referred to above may be made public. Pursuant to the Agreement for Mutual Enforcement of Debarment Decisions entered into with other IFIs, any firm, entity or individual bidding for or participating in a Bank-financed activity or acting as bidders, proposers, suppliers, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, concessionaires, personnel of the Borrower (including grant Beneficiaries), Executing Agencies or Contracting Agencies, (including their respective officers, employees, representatives and agents, irrespective of whether the attribution is expressed or implied) may be subject to a sanction. For purposes of this paragraph the term “sanction” shall mean any debarment, conditions on future contracting or any publicly-disclosed action taken in response to a violation of an IFI’s applicable framework for addressing allegations of Prohibited Practices. The Bank requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, officers or employees, sub-contractors, service providers and concessionaires permit the Bank to inspect accounts, records and other documents relating to the submission of bids and contract performance as well as to have them audited by personnel appointed by the Bank. Applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, sub-contractors, sub-consultants, service providers and concessionaires shall fully assist the Bank with its investigation. The Bank also requires that all applicants, bidders, proposers, suppliers, and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers and concessionaires: (i) maintain all documents and records related to the Bank-financed activities for seven (7) years after completion of the work contemplated in the relevant contract; (ii) deliver any document necessary for the investigation of allegations of Prohibited Practices; and (iii) ensure that employees, representatives or agents of the applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers or concessionaires who have knowledge that the Bank financed the activities to respond to questions from Bank personnel or any properly designated investigator, agent, auditor or consultant relating to the investigation. If the applicant, bidder, supplier and its representative or agent, contractor, consultant, personnel, sub-contractor, sub-consultant, service provider or concessionaire fails to cooperate and/or comply with the Bank’s request, or otherwise obstructs the investigation, the Bank, discretionally, may take appropriate action against the applicant bidder, supplier and its agent or representative, contractor, consultant, personnel, sub-contractor, service provider or concessionaire. If the Borrower procures goods or services, works or consulting services directly from a specialized agency, all provisions regarding Prohibited Practices and to the correspondent sanctions shall apply in their entirety to applicants, bidders, proposers, suppliers and their representatives or agents, contractors, consultants, personnel, sub-contractors, sub-consultants, service providers, and concessionaires, (including their respective officers, employees, and representatives or agents, irrespective of whether the agency is express or implied), or to any other entities that signed contracts with such specialized agency to supply such goods, works, or non-consulting services in connection with the Bank-financed activities. The Bank will retain the right to require the Borrower to invoke remedies such as contract suspension or termination. Specialized agencies shall consult the Bank’s list of suspended or debarred firms and individuals. In the event a specialized agency signs a contract or purchase order with a firm or an individual suspended or debarred by the Bank, the Bank will not finance the related expenditures and will apply other remedies as appropriate. 60.2 The Contractor represents and warrants: that has read and understood the Bank’s definition of Prohibited Practices and the applicable sanctions pursuant to the Sanctions Procedures; that they have not engaged in any Prohibited Practice as set forth herein during the selection, negotiation, adjudication or execution of this contract; that has not misrepresented or concealed any material facts during the procurement or contract negotiation processes or during the performance of the contract; that neither they nor their representatives or agents, sub-contractors, sub-consultants, directors, key personnel or principal shareholders have been declared ineligible to be awarded a contract by the Bank that all commissions, representative or agents’ fees, facilitating payments or revenue-sharing agreements related to the Bank-financed activities have been disclosed; and that they acknowledge that the breach of any of these representations may constitute a basis for the adoption by the Bank of one or more of the measures set forth in Subclause 60.1 (b). |
| 61. Payment upon Termination | 61.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the SCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. 61.2 If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| 62. Property | All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |
| 63. Release from Performance | 63.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |
| 64. Payment’s Suspension of Bank Loan | 64.1 In the event that the Bank suspends the Loan or Credit to the Employer, from which part of the payments to the Contractor are being made: (a) The Employer is obligated to notify the Contractor of such suspension within 7 days of having received the Bank’s suspension notice. (b) If the Contractor has not received sums due it within the 28 days for payment provided for in Sub-Clause 43.1, the Contractor may immediately issue a 14-day termination notice. |
| 65. Eligibility | 65.1 The Contractor and its Subcontractors shall have the nationality of a Bank’s member country. A Contractor or Subcontractor shall be deemed to have the nationality of a country if it complies with the following requirements: An individual is considered to be a national of a member country of the Bank if he or she meets either of the following requirements: is a citizen of a member country; or has established his/her domicile in a member country as a “bona fide” resident and is legally entitled to work in the country of domicile. A firm is considered to have the nationality of a member country if it meets the two following requirements: is legally constituted or incorporated under the laws of a member country of the Bank; and more than fifty percent (50%) of the firm’s capital is owned by individuals or firms from member countries of the Bank. 65.2 All members of a JVCA and all subcontractors must meet the nationality criteria set forth above. 65.3 All the Goods and Related Services to be supplied under the Contract and financed by the Bank shall have their origin in any Bank’s member country. Goods have their origin in a member country of the Bank if they have been mined, grown, harvested, or produced in a member country of the Bank. A good has been produced when through manufacture, processing or assembly another commercially recognized article results that differs substantially in its basic characteristics, function or purpose of utility from its parts or components. |

# Section VI.  Special Conditions of Contract

[Except where otherwise indicated, all SCC should be filled in by the Employer prior to issuance of the bidding document.  Schedules and reports to be provided by the Employer should be annexed.]

| A. General |
| --- |
| GCC 1.1 (m) | The Defects Liability Period is [insert period of time calculated from the Completion Date] |
| GCC 1.1 (o) | The Employer is [insert name, address, and name of authorized representative]. |
| GCC 1.1 (r) | The Intended Completion Date for the whole of the Works shall be [insert date] [If different dates are specified for completion of the Works by section (“sectional completion” or milestones), these dates should be listed here] |
| GCC 1.1 (u) | The Project Manager is [insert name and address of Project Manager ]. |
| GCC 1.1 (w) | The Site is located at [insert address of Site ] and is defined in drawings No. [insert numbers] |
| GCC 1.1 (z) | The Start Date shall be [insert date]. |
| GCC 1.1 (dd) | The Works consist of [insert brief summary, including relationship to other contracts under the Project]. |
| GCC 2.2 | Sectional Completions with different completion date to the completion date for the whole works are: [insert nature and dates, if appropriate] |
| GCC 2.3 | The following documents also form part of the Contract: [list documents] |
| GCC 3.1 | The language of the contract is [select a language: English, French, Portuguese or Spanish]. The law that applies to the Contract is the law of [insert name of Country]. |
| GCC 8.1 | Schedule of other contractors: [insert Schedule of Other Contractors, if appropriate] |
| GCC 9.1 | Key Personnel: [insert Schedule of Key Personnel] |
| GCC 13.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: [insert amounts]. (b) For loss or damage to Equipment: [insert amounts]. (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract [insert amounts]. (d) for personal injury or death: of the Contractor’s employees: [amount]. of other people: [amount]. |
| GCC 14.1 | Site Investigation Reports are: [list Site Investigation Reports] |
| GCC 21.1 | The Site Possession Date(s) shall be: [insert location(s) and date(s)] |
| GCC 25.2 | Fees and types of reimbursable expenses to be paid to the Technical Adjudicator: [insert hourly fees and reimbursable expenses]. |
| GCC 25.3 | [For smaller contracts, the institution is usually from the Employer’s country. For larger contracts, and contracts that are likely to be awarded to foreign contractors, it is recommended that the arbitration procedure of an international institution be used] Institution whose arbitration procedures shall be used: [insert name of the institution] [For larger contracts and contracts with foreign contractors, it is recommended that one institution be selected among those listed below; insert the corresponding wording] “United Nations Commission on International Trade Law (UNCITRAL) Arbitration Rules: Sub-Clause 25.3—Any dispute, controversy, or claim arising out of or relating to this Contract, or breach, termination, or invalidity thereof, shall be settled by arbitration in accordance with the UNCITRAL Arbitration Rules as at present in force.” or “Rules of Conciliation and Arbitration of the International Chamber of Commerce (ICC): Sub-Clause 25.3—All disputes arising in connection with the present Contract shall be finally settled under the Rules of Conciliation and Arbitration of the International Chamber of Commerce by one or more arbitrators appointed in accordance with said Rules.” or “Rules of Arbitration Institute of the Stockholm Chamber of Commerce: Sub-Clause 25.3—Any dispute, controversy, or claim arising out of or in connection with this Contract, or the breach, termination, or invalidity thereof, shall be settled by arbitration in accordance with the Rules of the Arbitration Institute of the Stockholm Chamber of Commerce.” or “Rules of the London court of International Arbitration: Sub-Clause 25.3—Any dispute arising out of or in connection with this Contract, including any question regarding its existence, validity, or termination shall be referred to and finally resolved by arbitration under the Rules of the London Court of International Arbitration, which rules are deemed to be incorporated by reference to this clause.” The place of arbitration shall be: [Insert city and country] |
| GCC 26.1 | Appointing Authority for the Technical Adjudicator: [insert name of Authority]. |
| B. Time Control |
| GCC 27.1 | The Contractor shall submit for approval by the Project Manager a Program for the Works within [number] days from the date of the Letter of Acceptance. |
| GCC 27.2 | ESHS Reporting Inserted at the end of GCC 26.2: “The Contractor shall also provide immediate notification to the Project Manager of incidents in at least the following categories. Full details of such incidents shall be provided to the Project Manager within the timeframe agreed with the Project Manager: confirmed or likely violation of any law or international agreement; any fatality or serious (lost time) injury; significant adverse effects or damage to private property (e.g. vehicle accident, damage from fly rock, working beyond the boundary) major pollution of drinking water aquifer or damage or destruction of rare or endangered habitat (including protected areas) or species; any allegation of SGBV” refers to any act that is perpetrated against a person’s will and is based on gender norms and unequal power relationships. It encompasses threats of violence, coercion, and harassment. It can be physical, emotional, psychological, or sexual in nature, and can take the form of a denial of resources or access to them, It can affect persons at any age across the lifespan, and disproportionately affects women, girls, and people of diverse sexual orientations and gender identities. significant leak of hazardous material or pollution of water ways. |
| GCC 27.3 | The period between Program updates is [insert number] days. The amount to be withheld for late submission of an updated Program is [insert amount]. |
| C. Quality Control |
| GCC 35.1 | The Defects Liability Period is: [insert number] days. [The Defects Liability Period is usually limited to 12 months, but could be less in very simple cases] |
| D. Cost Control |
| GCC 39.1 | At the end of 39.1 add after the first sentence: “The Contractor shall also provide information of any ESHS risks and impacts of the Variation.” |
| GCC 40.6 | If the Employer approves the value-engineering proposal the amount to be paid to the Contractor shall be ___% (insert appropriate percentage. The percentage is normally up to 50%) of the reduction in the Contract Price. |
| GCC 40.7 New (to be used only in contracts based on Bill of Quantities) | “40.7 If the work in the Variation corresponds to an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 37.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work.” |
| GCC 46.1 | The currency of the Employer’s country is: [insert name of currency of the Employer’s country]. |
| GCC 47.1 | The Contract [insert “is” or “is not”] subject to price adjustment in accordance with GCC Clause 47, and the following information regarding coefficients [specify “does” or “does not”] apply. [Price adjustment is mandatory for contracts which provide for time of completion exceeding 18 months] The coefficients for adjustment of prices are: (a) For currency [insert name of currency]: (i) [insert percentage] percent nonadjustable element (coefficient A). (ii) [insert percentage] percent adjustable element (coefficient B). (b) For currency [insert name of currency]: (i) [insert percentage] percent nonadjustable element (coefficient A). (ii) [insert percentage] percent adjustable element (coefficient B). The Index I for local currency shall be [insert index]. The Index I for the specified international currency shall be [insert index]. [These proxy indices shall be proposed by the Contractor, subject to acceptance by the Employer] The Index I for currencies other than the local currency and the specified international currency shall be [insert index]. [These proxy indices shall be proposed by the Contractor, subject to acceptance by the Employer.] |
| GCC 48.1 | The proportion of payments retained is: [insert percentage] [The retention amount is usually close to 5 percent and in no case exceeds 10 percent.] |
| GCC 49.1 | The liquidated damages for the whole of the Works are [insert percentage of the final Contract Price] per day. The maximum amount of liquidated damages for the whole of the Works is [insert percentage] of the final Contract Price. [Usually liquidated damages are set between 0.05 percent and 0.10 percent per day, and the total amount is not to exceed between 5 percent and 10 percent of the Contract Price. If Sectional Completion and Damages per Section have been agreed, the latter should be specified here] |
| GCC 50.1 | The Bonus for the whole of the Works is [insert percentage of final Contract Price] per day. The maximum amount of Bonus for the whole of the Works is [insert percentage] of the final Contract Price. [If early completion would provide benefits to the Employer, this clause should remain; otherwise delete. The Bonus is usually numerically equal to the liquidated damages.] |
| GCC 51.1 | The Advance Payments shall be: [insert amount(s)] and shall be paid to the Contractor no later than [insert date(s)]. |
| GCC 52.1 | The Performance Security amount is [insert amount(s) denominated in the types and proportions of the currencies in which the Contract Price is payable, or in a freely convertible currency acceptable to the Employer] (a) Bank Guarantee: [insert percentage and amount(s) ]. (b) Performance Bond: [insert percentage and amount(s) ]. [A Bank Guarantee shall be unconditional (on demand) (see Section X. Contract Forms). An amount of 5 to 10 percent of the Contract Price is commonly specified for Performance Bank Guarantees. A Performance Bond is an undertaking by a bonding or insurance company (surety) to complete the construction in the event of default by the Contractor, or to pay the amount of the Bond to the Employer. An amount of 30 percent of the Contract Price is commonly used internationally for this type of security (see Section X. Contract Forms).] |
| E. Finishing the Contract |
| GCC 58.1 | The date by which operating, and maintenance manuals are required is [insert date]. The date by which “as built” drawings are required is [insert date]. |
| GCC 58.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required in GCC 58.1 is [insert amount in local currency]. |
| GCC 59.2 (g) | The maximum number of days is: [insert number; consistent with clause 41.1 on liquidated damages]. |
| GCC 61.1 | The percentage to apply to the value of the work not completed is [insert percentage]. |

# Section VII.  Specifications & Performance Requirements

A set of precise and clear Specifications is a prerequisite for bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their bids.  In the context of international competitive bidding, the Specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured.  Only if this is done shall the objectives of economy, efficiency, and fairness in procurement be realized, responsiveness of bids be ensured, and the subsequent task of Bid evaluation facilitated.  The Specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

Samples of Specifications from previous similar projects in the same country are useful in to prepare Specifications.  The Bank encourages the use of metric units.  Most Specifications are normally written specially by the Employer or Project Manager to suit the Contract Works in hand.  There is no standard set of Specifications for universal application in all sectors in all countries, but there are established principles and practices, which are reflected in these documents.

There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract.  Deletions or addendums should then adapt the General Specifications to apply them to the particular Works.

Care must be taken in drafting Specifications to ensure that they are not restrictive.  In the Specifications of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible.  Where other particular standards are used, whether national standards of the Borrower’s country or other standards, the Specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, shall also be acceptable. To that effect, the following sample clause may be inserted in the Special Conditions or Specifications.

“Equivalency of Standards and Codes”

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract.  Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified shall be accepted subject to the Project Manager’s prior review and written consent.  Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the Project Manager at least 28 days prior to the date when the Contractor desires the Project Manager’s consent.  In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.”

These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the bidding document.  They should not be included in the final documents.

# Section VIII.  Drawings

Insert here a list of Drawings.  The Drawings, including site plans, should be attached to this section or annexed in a separate folder.

# Section IX.  Bill of Quantities

Objectives

The objectives of the Bill of Quantities are:

(a)	to provide sufficient information on the quantities of Works to be performed to enable bids to be prepared efficiently and accurately; and

(b)	when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic valuation of Works executed.

In order to attain these objectives, Works should be itemized in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost.  Consistent with these requirements, the layout and contents of the Bill of Quantities should be as simple and brief as possible.

Daywork Schedule

A Daywork Schedule should be included only if the probability of unforeseen work, outside the items included in the Bill of Quantities, is high.  To facilitate checking by the Employer of the realism of rates quoted by the bidders, the Daywork Schedule should normally comprise the following:

(a)	A list of the various classes of labor, materials, and Constructional Plant for which basic daywork rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the Contractor shall be paid for work executed on a daywork basis.

(b)	Nominal quantities for each item of daywork, to be priced by each Bidder at daywork rates as Bid.  The rate to be entered by the Bidder against each basic daywork item should include the Contractor’s profit, overheads, supervision, and other charges.

Provisional Sums

A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities.  Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary priced Bill of Quantities.  The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises.  Where such provisional sums or contingency allowances are used, the Special Conditions of Contract should state the manner in which they shall be used, and under whose authority (usually the Project Manager’s).

The estimated cost of specialized work to be carried out, or of special goods to be supplied, by other contractors (refer to GCC Clause 8) should be indicated in the relevant part of the Bill of Quantities as a particular provisional sum with an appropriate brief description.  A separate procurement procedure is normally carried out by the Employer to select such specialized contractors.  To provide an element of competition among the bidders in respect of any facilities, amenities, attendance, etc., to be provided by the successful Bidder as prime Contractor for the use and convenience of the specialist contractors, each related provisional sum should be followed by an item in the Bill of Quantities inviting the Bidder to quote a sum for such amenities, facilities, attendance, etc.

These Notes for Preparing a Bill of Quantities are intended only as information for the Employer or the person drafting the bidding document.  They should not be included in the final documents.

# Section X. Forms of Contract

Samples of acceptable forms of Bid, Performance, and Advance Payment Securities are provided in this Section X.  Bidders shall not complete the Performance and Advance Payment Security forms at this stage of the procurement process.  Only the successful Bidder shall be required to provide these two securities.

## Notification of Intention to Award

[This Notification of Intention to Award shall be sent to each Bidder that submitted a Bid.]

[Send this Notification to the Bidder’s Authorized Representative named in the Bidder Information Form]

For the attention of Bidder’s Authorized Representative

Name: [insert Authorized Representative’s name]

Address: [insert Authorized Representative’s Address]

Telephone number: [insert Authorized Representative’s telephone number]

Email Address: [insert Authorized Representative’s email address]

[IMPORTANT: insert the date that this Notification is transmitted to Bidders. The Notification must be sent to all Bidders simultaneously. This means on the same date and as close to the same time as possible.]

DATE OF TRANSMISSION: This Notification is sent by: [email] on [date] (local time)

Notification of Intention to Award

Employer: [insert the name of the Employer]

Project: [insert name of project]

Contract title: [insert the name of the contract]

Country: [insert country where RFB is issued]

Loan No. [insert reference number for loan]

RFB No: [insert RFB reference number from Procurement Plan]

This Notification of Intention to Award (Notification) notifies you of our decision to award the above contract. The transmission of this Notification begins the Standstill Period. During the Standstill Period, you may:

- request a debriefing in relation to the evaluation of your Bid, and/or

- submit a Procurement-related Complaint in relation to the decision to award the contract.

- The successful Bidder

| Name: | [insert name of successful Bidder] |
| --- | --- |
| Address: | [insert address of the successful Bidder] |
| Contract price: | [insert contract price of the successful Bid] |

- Other Bidders [INSTRUCTIONS: insert names of all Bidders that submitted a Bid. If the Bid’s price was evaluated include the evaluated price as well as the Bid price as read out.]

| Name of Bidder | Bid price | Evaluated Bid price (if applicable) |
| --- | --- | --- |
| [insert name] | [insert Bid price] | [insert evaluated price] |
| [insert name] | [insert Bid price] | [insert evaluated price] |
| [insert name] | [insert Bid price] | [insert evaluated price] |
| [insert name] | [insert Bid price] | [insert evaluated price] |
| [insert name] | [insert Bid price] | [insert evaluated price] |

- Reason/s why your Bid was unsuccessful

[INSTRUCTIONS: State the reason/s why this Bidder’s Bid was unsuccessful. Do NOT include: (a) a point by point comparison with another Bidder’s Bid or (b) information that is marked confidential by the Bidder in its Bid.]

- Best and Final Offer or Negotiations

Pursuant to ITB 34.1, in the evaluation of bids or pursuant to ITB 34.2 in the final award of this Contract, the following method was used: ( Best and Final Offer ( Negotiations ( Neither method [Delete if not applicable] The name of the Independent Probity Assurance Authority is: [insert the name of the Authority]

- How to request a debriefing

DEADLINE: The deadline to request a debriefing expires at midnight on [insert date] (local time). You may request a debriefing in relation to the results of the evaluation of your Bid. If you decide to request a debriefing your written request must be made within three (3) Business Days of receipt of this Notification of Intention to Award. Provide the contract name, reference number, name of the Bidder, contact details; and address the request for debriefing as follows: Attention: [insert full name of person, if applicable] Title/position: [insert title/position] Agency: [insert name of Employer] Email address: [insert email address] If your request for a debriefing is received within the 3 Business Days deadline, we will provide the debriefing within five (5) Business Days of receipt of your request. If we are unable to provide the debriefing within this period, the Standstill Period shall be extended by five (5) Business Days after the date that the debriefing is provided. If this happens, we will notify you and confirm the date that the extended Standstill Period will end. The debriefing may be in writing, by phone, video conference call or in person. We shall promptly advise you in writing how the debriefing will take place and confirm the date and time. If the deadline to request a debriefing has expired, you may still request a debriefing. In this case, we will provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract Award Notice.

- How to make a complaint

Period: Procurement-related Complaint challenging the decision to award shall be submitted by midnight, [insert date] (local time). Provide the contract name, reference number, name of the Bidder, contact details; and address the Procurement-related Complaint as follows: Attention: [insert full name of person, if applicable] Title/position: [insert title/position] Agency: [insert name of Employer] Email address: [insert email address] At this point in the procurement process, you may submit a Procurement-related Complaint challenging the decision to award the contract. You do not need to have requested, or received, a debriefing before making this complaint. Your complaint must be submitted within the Standstill Period and received by us before the Standstill Period ends. In summary, there are four essential requirements: You must be an ‘interested party’. In this case, that means a Bidder who submitted a Bid in this bidding process, and is the recipient of a Notification of Intention to Award. The complaint can only challenge the decision to award the contract. You must submit the complaint within the period stated above. You must include, in your complaint, all of the information pursuant to paragraphs 2.77 to 2.81 of the Bank´s Procurement Policies and Appendices 1 and 3.

- Standstill Period

DEADLINE: The Standstill Period is due to end at midnight on [insert date] (local time). The Standstill Period lasts ten (10) Business Days after the date of transmission of this Notification of Intention to Award. The Standstill Period may be extended as stated in Section 5 above.

If you have any questions regarding this Notification, please do not hesitate to contact us.

On behalf of the Employer:

Signature:	______________________________________________

Name:	______________________________________________

Title/position:	______________________________________________

Telephone:	______________________________________________

E-mail: ______________________________________________

## Beneficial Ownership Disclosure Form

RFB No.: [insert number of RFB process]

Request for Bid No.: [insert identification]

To: [insert complete name of Employer]

In response to your request in the Letter of Acceptance dated [insert date of letter of Acceptance] to furnish additional information on beneficial ownership: [select one option as applicable and delete the options that are not applicable]

(i) we hereby provide the following beneficial ownership information.

Details of beneficial ownership

| Identity of Beneficial Owner | Directly or indirectly holding 25% or more of the shares (Yes / No) | Directly or indirectly holding 25 % or more of the Voting Rights (Yes / No) | Directly or indirectly having the right to appoint a majority of the board of the directors or an equivalent governing body of the Bidder (Yes / No) |
| --- | --- | --- | --- |
| [include full name (last, middle, first), nationality, country of residence] |  |  |  |

OR

(ii) We declare that there is no Beneficial Owner meeting one or more of the following conditions:

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder

OR

(iii) We declare that we are unable to identify any Beneficial Owner meeting one or more of the following conditions. [If this option is selected, the Bidder shall provide explanation on why it is unable to identify any Beneficial Owner]

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder]”

Name of the Bidder: *[insert complete name of the Bidder]_________

Name of the person duly authorized to sign the Bid on behalf of the Bidder: **[insert complete name of person duly authorized to sign the Bid]___________

Title of the person signing the Bid: [insert complete title of the person signing the Bid]______

Signature of the person named above: [insert signature of person whose name and capacity are shown above]_____

Date signed [insert date of signing] day of [insert month], [insert year]_____

* In the case of the Bid submitted by a Joint Venture specify the name of the Joint Venture as Bidder. In the event that the Bidder is a joint venture, each reference to “Bidder” in the Beneficial Ownership Disclosure Form (including this Introduction thereto) shall be read to refer to the joint venture member.

** Person signing the Bid shall have the power of attorney given by the Bidder. The power of attorney shall be attached with the Bid Schedules.
*** It is understood that any false or equivocal information that has been provided in relation to this requirement may result in actions or penalties by the Bank in accordance with its rules and policies.

## Letter of Acceptance

[letterhead paper of the Employer]

[The Letter of Acceptance shall be the basis for formation of the Contract as described in ITB 39 and 42.  This Standard Form of Letter of Acceptance shall be filled in and sent to the successful Bidder only after evaluation of bids has been completed, subject to any review by the Bank required under the Loan Agreement.]

[insert date]

Identification No and Title of Contract: [insert identification number and title of the Contract]

To:  [insert name and address of the selected Contractor]

This is to notify you that your Bid dated [insert date] for execution of the [insert name of the Contract and identification number, as given in the SCC] for the Contract Price of the equivalent of [insert amount in numbers and words] [insert name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

[insert one of the following (a) or (b) options]

(a)	We accept that [insert name proposed by bidder] be appointed as the Technical Adjudicator.

(b)	We do not accept that [insert name proposed by bidder] be appointed as Technical Adjudicator, and by sending a copy of this Letter of Acceptance to [insert name of the Appointing Authority], we are hereby requesting [insert name], the Appointing Authority, to appoint the Technical Adjudicator in accordance with ITB 44.1.

You are hereby instructed to (a) proceed with the execution of the said Works in accordance with the Contract Documents, (b) sign and return the attached Contract Documents, and (c) forward the performance security pursuant to ITB 42.1, i.e., within 21 days after receipt of this Letter of Acceptance, and pursuant to GCC Sub-Clause 52.1; and (d) additional information on Beneficial Ownership in accordance with BDS in reference to ITB 41.1, within the next 8 (eight) business days using the Beneficial Ownership Disclosure Form of Section X. Contract Forms.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Agreement

## Agreement

[The Agreement shall incorporate any corrections or modifications to the Bid resulting from corrections of errors (ITB 28), price adjustment during the evaluation process (ITB 16.3, selection of an alternative offer (ITB 18), acceptable deviations (ITB 27), BAFO or the outcome of the Negotiations (if any, pursuant to ITB 33) or any other mutually-agreeable changes allowed for in the Conditions of Contract, such as changes in key personnel, subcontractors, scheduling, and the like.]

This Agreement made the [insert day] day of [insert month], [insert year] between [insert name and address of Employer] (hereinafter called “the Employer”) and [insert name and address of Contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the Employer is desirous that the Contractor execute [insert name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein.

Now this Agreement witnessed as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

In Witness whereof the parties thereto have signed this Agreement to be executed the day and year first before written.

The Common Seal of [Witness entity]

was hereunto affixed in the presence of:

Signed, Sealed, and Delivered by the said

in the presence of:

Binding Signature of Employer [signature of an authorized representative of the Employer]

Binding Signature of Contractor [signature of an authorized representative of the Contractor]

## Performance Bank Guarantee

(Unconditional)

[The bank/successful Bidder providing the Guarantee shall fill in this form in accordance with the instructions indicated in brackets, if the Employer requires this type of security.]

[insert bank’s name, and address of issuing branch or office]

Beneficiary:	[insert name and address of Employer]

Date:	[insert date]

PERFORMANCE GUARANTEE No.:	[insert Performance Guarantee number]

We have been informed that [insert name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. [insert reference number of the Contract] dated with you, for the execution of [insert name of Contract and brief description of Works] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Contractor, we [insert name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [insert amount in figures] ([insert amount in words]), such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation(s) under the Contract, without your needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall expire no later than twenty-eight days from the date of issuance of the Taking-Over Certificate, calculated based on a copy of such Certificate which shall be provided to us, or on the [insert number day of [insert month], [insert year], whichever occurs first.   Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No.758, except that subparagraph (ii) of Sub-article 20(a) is hereby excluded.

_____________________ 
[signature(s) of an authorized representative(s) of the Bank]

## Performance Bond

[The Surety/successful Bidder providing the Bond shall fill in this form in accordance with the instructions indicated in brackets, if the Employer requires this type of security]

By this Bond, [insert name and address of Contractor] as Principal (hereinafter called “the Contractor”) and [insert name, legal title, and address of surety, bonding company, or insurance company] as Surety (hereinafter called “the Surety”), are held and firmly bound unto [insert name and address of Employer] as Obligee (hereinafter called “the Employer”) in the amount of [insert amount of Bond] [insert amount of Bond in words], for the payment of which sum well and truly to be made in the types and proportions of currencies in which the Contract Price is payable, the Contractor and the Surety bind themselves, their heirs, executors, administrators, successors, and assigns, jointly and severally, firmly by these presents.

Whereas the Contractor has entered into a Contract with the Employer dated the [insert number] day of [insert month], [insert year] for [insert name of Contract] in accordance with the documents, plans, specifications, and amendments thereto, which to the extent herein provided for, are by reference made part hereof and are hereinafter referred to as the Contract.

Now, therefore, the Condition of this Obligation is such that, if the Contractor shall promptly and faithfully perform the said Contract (including any amendments thereto), then this obligation shall be null and void; otherwise it shall remain in full force and effect.  Whenever the Contractor shall be, and declared by the Employer to be, in default under the Contract, the Employer having performed the Employer’s obligations thereunder, the Surety may promptly remedy the default, or shall promptly:

(1)	complete the Contract in accordance with its terms and conditions; or

(2)	obtain a Bid or bids from qualified bidders for submission to the Employer for completing the Contract in accordance with its terms and conditions, and upon determination by the Employer and the Surety of the lowest responsive bidder, arrange for a Contract between such Bidder and Employer and make available as work progresses (even though there should be a default or a succession of defaults under the Contract or Contracts of completion arranged under this paragraph) sufficient funds to pay the cost of completion less the balance of the Contract Price; but not exceeding, including other costs and damages for which the Surety may be liable hereunder, the amount set forth in the first paragraph hereof.  The term “Balance of the Contract Price,” as used in this paragraph, shall mean the total amount payable by the Employer to the Contractor under the Contract, less the amount properly paid by the Employer to the Contractor; or

(3)	pay the Employer the amount required by the Employer to complete the Contract in accordance with its terms and conditions up to a total not exceeding the amount of this Bond.

The Surety shall not be liable for a greater sum than the specified penalty of this Bond.

Any suit under this Bond must be instituted before the expiration of one year from the date of issuance of the Certificate of Completion.

No right of action shall accrue on this Bond to or for the use of any person or corporation other than the Employer named herein or the heirs, executors, administrators, successors, and assigns of the Employer.

In testimony whereof, the Contractor has hereunto set its hand and affixed its seal, and the Surety has caused these presents to be sealed with its corporate seal duly attested by the signature of its legal representative, this [insert day] day of [insert month], [insert year].

Signed by [insert signature(s) of authorized representative(s) ]

on behalf of [name of Contractor] in the capacity of  [insert title(s)]

In the presence of [insert name and signature of witness]

Date [insert date]

Signed by [insert signature(s) of authorized representative(s) of Surety]

on behalf of [name of Surety] in the capacity of [insert title(s)]

In the presence of [insert name and signature of witness]

Date [insert date]

## Bank Guarantee for Advance Payment

The bank/successful bidder providing the Guarantee shall fill in this form in accordance with the instructions indicated in brackets, if an Advance Payment is to be provided under the Contract

[insert Bank’s name, and address of issuing branch or office]

Beneficiary:	 [insert name and address of Employer]

Date:	[insert date]

ADVANCE PAYMENT GUARANTEE No.: [insert number]

We have been informed that [insert name of Contractor] (hereinafter called "the Contractor") has entered into Contract No. [insert reference number of the contract] dated [insert date] with you, for the execution of [insert name of contract and brief description of Works] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, an advance payment is to be made against an advance payment guarantee in the sum or sums indicated below.

At the request of the Contractor, we [insert name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of [insert amount in figures] ([insert amount in words]) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Contractor is in breach of its obligation under the Contract because the Contractor used the Advance Payment for purposes other than the costs of mobilization in respect of the Works.

It is a condition for any claim and payment under this guarantee to be made that the Advance Payment referred to above must have been received by the Contractor on its account number [insert account number] at [insert name and address of Bank].

The maximum amount of this guarantee shall be progressively reduced by the amount of the Advance Payment repaid by the Contractor as indicated in copies of interim statements or payment certificates which shall be presented to us.  This guarantee shall expire, at the latest, upon our receipt of a copy of the Interim Payment Certificate indicating that eighty (80) percent of the Contract Price has been certified for payment, or on the [insert number] day of [insert month], [insert year], whichever is earlier.  Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

_____________________ 
[insert signature(s) of authorized representative(s) of bank]

## Request for Bids

[The invitation for Bids and the publicity of the Request for Bids (see para. 2.6 and 2.7 of the Policies for the Procurement of Goods and Works financed by the IDB) shall be issued as:

(a)	an advertisement in at least one newspaper of general circulation in the Borrower’s country and in the official gazette (if it is available online), or in an electronic portal with free access if it is possible, where the country advertises all its business opportunities, and

(b)	an advertisement in United Nations Development Business on-line, the Internet site of the Bank, and/or in well-known technical magazines (the latter being mandatory if specified in the Loan or Credit Agreement)

[Advertising inquiries about the U.N. Development Business publication can be directed at: Development Business, Telephone:  1-212-963-1516; Facsimile:  1-212-963-1381; Internet: www.devbusiness.com ]

The RFB provides information that enables potential bidders to decide whether to participate in the bidding process.  The RFB shall specify any important bid evaluation criteria (for example, the application of a margin of preference in bid evaluation) and qualification requirements (for example, a requirement for a minimum level of experience in carrying out works of a similar type(s) and size to those for which the IFB is issued).

The IFB shall not be incorporated into the bidding document. However, the information included in the IFB shall conform to the bidding document and in particular to the information in the Bidding Data Sheet.

SAMPLE FORMAT FOR INVITATION FOR BIDS

Request for Bids (RFB)

[ insert name of Country]

[ insert name of Project]

[ insert loan / credit number]

[ insert RFB title and Number]

1.	This RFB follows the General Procurement Notice for this Project that appeared in Development Business, issue no. [insert number] of [insert date].1

2.	The [insert name of Borrower] [insert “has received/has applied for/intends to apply for”] a loan from the Inter-American Development Bank toward the cost of [insert name of Project], and it intends to apply part of the proceeds of this loan to payments under the Contract for [insert name and number of Contract].2

3.	The [insert complete name of Employer] now invites sealed bids from eligible and qualified bidders for [insert brief description of the Works to be procured].3 The delivery/construction period is [insert number of days/months/years or dates].

4.	The RFB will be conducted through the International Competitive Bidding (ICB) procedures specified in the Inter-American Development Bank’s Policies for the Procurement of Goods and Works financed by the Inter-American Development Bank GN-2349-15 approved by the Board of Executive Directors of the Bank on 2nd of July 2019 and effective 1st of January 2020, and is open to all bidders from Eligible Source Countries as defined in the bidding document.4

5.	Interested eligible bidders may obtain further information from [insert complete legal name of Employer; insert name and e-mail of officer in charge] and inspect the bidding document at the address given below [state address at end of this invitation] from [insert office hours].5 .

6.	Qualifications requirements include: [insert key technical, financial, legal and other requirements]. A margin of preference for national contractors/JVCAs shall not be applied.   [Delete these paragraphs or delete either one  that  does not apply: “The Employer will use the Best and Final Offer method in the evaluation of bids” or “The Employer will use Negotiations in the final award of the contract”.]

7.	A complete set of the bidding document in [insert name of language(s)] may be purchased by interested bidders on the submission of a written Application to the address below and upon payment of a non-refundable fee6 [insert amount in local currency] or in [insert amount in specified convertible currency].  The method of payment will be [insert method of payment].7 The bidding document will be sent by [insert delivery procedure].8

8.	Bids must be delivered to the address below at or before [insert time and date]. Electronic bidding [insert “shall” or “shall not”] be permitted. Late bids will be rejected.  Bids will be opened physically [insert “and electronically” if electronic bidding is permitted] in the presence of the bidders’ representatives who choose to attend in person or on-line at the address below at [insert time and date].

9	All bids [insert “shall” or “shall not”] be accompanied by a [insert “Bid Security” or “Bid Validity Declaration”, as appropriate and if required] of [insert amount in local currency or an equivalent amount in a freely convertible currency, or a minimum percentage of bid price in case of a Bid Security]9.

10.	The address(es) referred to above is(are): [insert detailed address(es) including complete  legal name of the Employer, Office designation (room number) , name of Officer, Street address, City (code), Country; insert electronic address if electronic bidding is permitted; insert different addresses if addresses for purchase of bidding document,  bid submission and bid opening are different]10

____________________

1. 	Day, month, year; for example, 19 December 2017.

2.	[Insert if applicable: “This contract will be jointly financed by [insert name of cofinancing agency].  Bidding will be governed by the Bank’s eligibility rules and procedures.”]

3. 	A brief description of the type(s) of Works should be provided, including quantities, location of Project, and other information necessary to enable potential bidders to decide whether or not to respond to the Invitation.

4. 	Occasionally, contracts may be financed out of special funds that would further restrict eligibility to a particular group of member countries.  When this is the case, it should be mentioned in this paragraph.

5.	For example, 9.00 AM to 5.00 PM.

6. 	The fee should defray the printing and mailing/shipping costs); it should not deter competition.

7. 	For example, cashier’s check, direct deposit to specified account number.

8. 	The delivery procedure is usually by airmail for overseas delivery and surface mail or courier for local delivery, or by electronic means if electronic bidding is permitted. If urgency or security dictates, courier services may be required for overseas delivery.

9.	The amount of Bid Security should be stated as a fixed amount or as a minimum percentage of the Bid Price.  Alternatively, if a Bid Security or a Bid Validity Declaration is not required (often the case in supply contracts), the paragraph should so state.

10.	If the addresses for bid opening, inspection and issuing of the documents, and reception of bids are not the same, each address should be specified at the end of paragraph 10 and be numbered, i.e. (1), (2), (3). Therefore, the text in the paragraph should refer to addresses (1), (2), etc.  Only one address should be specified for the reception of the bids, which should be located as close as possible to the address where bids will be opened, to reduce the time between the deadline for bid submission and the time for bid opening

# Footnotes

The expression “Bank” used in this document includes the Inter-American Development Bank and the funds it administers. Requirements of IDB and any other fund administered by the IDB are identical; except in the case of eligibility where membership is different (See Eligible Countries Section). The expression “loans” include the financing instruments and methods, the technical cooperation (TC) and the financing of operations. The expression “Loan Contract” includes all the legal instruments under which the Bank operations are formalized.

The Bank has two types of international public bidding documents (LPI): Request for Bids (RFB) that shall be used when the Borrower can specify in detail all the requirements, which allows firms to submit bids that meet the requirements established in the bidding document and where the evaluation criteria are normally expressed in monetary terms; and the Request for Proposals (RPF) to be used when the Borrower cannot clearly specify its requirements (in general, it is used for complex and innovative procurement), which allows firms to submit proposals that vary in the degree of compliance with the requirements established in the bidding document; in that case, the evaluation criteria usually include rated type criteria.

Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas

Lump sum contracts should be used for Works that can be defined in their full physical and qualitative characteristics before bids are called, or where the risks of substantial design variations are minimal—usually construction of buildings, pipe laying, power transmission towers, and series of small structures, such as bus shelters or school ablution units.  In lump sum contracts, the concept of priced “activity schedules” enable payments to be made as “activities” or “sub-activities” are completed.  Payments can also be made on the basis of percentage completion of each activity.

See Section V, “General Conditions of Contract”, Clause 1. Definitions.

In such cases, the Bank must be satisfied with the functionality of said system, as provided in paragraph 3.21 of the Procurement Policies GN-2349-15.

Information on how to present allegations of Prohibited Practices, the application of rules regarding investigation and sanctions process, and the agreement regulating the mutual recognition of sanctions among the IFI’s are available on the Bank's web site (www.iadb.org/integrity)

See Annex 1 - Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas

Control means the power to, directly or indirectly, direct or cause the direction of the management and policies of the companies or projects, whether through the ownership of voting shares, by contract or otherwise. It could include majority ownership of voting shares, other control mechanisms (such as “golden shares”, veto rights or shareholders’ agreements requesting special majorities) or, in the case of investment fund financing, the control exercised by a general partner or fund manager. Control will be determined in the context of each specific case.

A close relationship should be understood as being related up to the fourth degree of relationship by blood (consanguinity) or by adoption, or up to the second degree of relationship by marriage or domestic partnership (affinity).

Usually the equivalent of the estimated payments flows over 4-6 months at the average (straight line distribution) construction rate.  The actual period of reference shall depend on the speed with which the Employer shall pay the Contractor’s monthly certificates.

For the avoidance of doubt, where the bidding includes lots, "Bid" means bid for each lot.

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule”.

It may be necessary to extend the deadline for submission of bids if the Employer’s response results in substantial changes to the bidding document. See ITB Clause 11 below.

It is therefore important that the Employer maintain a complete and accurate list of recipients of the bidding document and their addresses.

In lump sum contracts, delete “priced Bill of Quantities” and replace with “priced Activity Schedule.”

In lump sum contracts, delete “priced Bill of Quantities” and replace with “priced Activity Schedule.”

In lump sum contracts, delete “described in the Bill of Quantities” and replace with “described in the drawings and specifications and listed in the Activity Schedule.”

In lump sum contracts, delete “rates, unit prices, and.”

In lump sum contracts, delete “rates and unit prices” and replace with “lump sum price.”

In lump sum contracts, delete “unit rates and prices” and replace with “lump sum price.”

Provisional sums are monetary sums specified by the Employer in the Bill of Quantities, to be used at his discretion for nominated subcontractors and other specified purposes.

For lump sum contracts, delete “rates and prices” and replace with “Lump Sum.”

The period is a realistic time, usually not less than 35 days nor more than 105, allowing for bid evaluation, clarifications, and the  Bank’s “no objection” (where awards of Contract are subject to prior review).

The receiving address should be an office that is staffed during normal working hours by personnel authorized to certify time and date of receipt and assure safekeeping until Bid opening.  A post office address is not satisfactory.  The address must be the same as the receiving address described in the Invitation for Bids.

A copy of the minutes should be sent by the Employer to the Inter-American Development Bank together with the Bid evaluation report, for contracts subject to prior review.

In lump sum contracts, delete “unit rates” and replace with “the prices in the Activity Schedule.”

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule.”

Daywork is work carried out following instructions of the Project Manager and paid for on the basis of time spent by workers, and the use of materials and the Contractor’s equipment, at the rates quoted in the Bid.  For Daywork to be priced competitively for Bid evaluation purposes, the Employer must list tentative quantities for individual items to be costed against Daywork (e.g., a specific number of tractor driver staff-days, or a specific tonnage of Portland cement), to be multiplied by the bidders’ quoted rates and included in the total Bid price.

If the bidding document includes two or more lots, add ITB 30.5:  “In the case of several lots, pursuant to ITB Sub-Clause 30.2 (d), the Employer shall determine the application of discounts so as to minimize the combined cost of all the lots”

Employers shall not reject bids or annul bidding processes, except as permitted in the Policies for the Procurement of Goods and Works financed by the Bank.

This section should be filled out by the Employer before issuance of the bidding document.

Delete if prequalification has been conducted.

Delete if prequalification has been conducted.

See Annex 1 in the Environmental and Social Policy Framework GN-2965-23: https://www.iadb.org/en/mpas

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule.”

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace GCC Sub-Clauses 37.1 and 37.2, as follows:

37.1	The Contractor shall provide updated Activity Schedules within 14 days of being instructed to by the Project Manager.  The activities on the Activity Schedule shall be coordinated with the activities on the Program.

37.2	The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately.

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace entire GCC Clause 38 with new GCC Sub-Clause 38.1, as follows:

38.1	The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion.  Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule.

In lump sum contracts, add “and Activity Schedules” after “Programs.”

In lump sum contracts, delete this paragraph.

In lump sum contracts, add “or Activity Schedule” after “Program.”

In lump sum contracts, replace this paragraph with the following:  “The value of work executed shall comprise the value of completed activities in the Activity Schedule.”

The sum of the two coefficients Ac and Bc should be 1 (one) in the formula for each currency.  Normally, both coefficients shall be the same in the formulae for all currencies, since coefficient A, for the nonadjustable portion of the payments, is a very approximate figure (usually 0.15) to take account of fixed cost elements or other nonadjustable components.  The sum of the adjustments for each currency are added to the Contract Price.

Information on how to present allegations of Prohibited Practices, the application of rules regarding investigation and sanctions process, and the agreement regulating the mutual recognition of sanctions among the IFI’s are available on the Bank's web site (www.iadb.org/integrity)

In lump sum contracts, the “Bill of Quantities” is prepared for information; it is not contractual. The contractual document prepared by the Bidder shall be a “Schedule of Activities.”

Delete “of the equivalent” if the Contract Price is expressed wholly in one currency.

Delete “corrected and” or “and modified” if not applicable.  See Notes on Standard Form of Agreement, next page.

To be used only if the Contractor disagrees in the Bid with the Technical Adjudicator proposed by the Employer in the Instructions to Bidders and has accordingly offered another candidate.

To be used only if the Contractor disagrees in the Bid with the Technical Adjudicator proposed by the Employer in the ITB, has accordingly offered another candidate, and the Employer does not accept the counterproposal.

The Guarantor (bank) shall insert an amount representing the percentage of the Contract Price specified in the Contract and denominated either in the currency(ies) of the Contract or a freely convertible currency acceptable to the Employer.

Insert the date twenty-eight days after the expected Completion date. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this Guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the Guarantee. In preparing this Guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “The Guarantor agrees to a one-time extension of this Guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the Guarantee.”

An amount is to be inserted by the Surety, representing the percentage of the Contract Price specified in the Contract Data, and denominated either in the currency(ies) of the Contract or in a freely convertible currency of type and amount acceptable to the Employer.

Date of Letter of Acceptance or Agreement.

The Guarantor shall insert an amount representing the amount of the Advance Payment and denominated either in the currency(ies) of the Advance Payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.

Insert the expected expiration date of the Time for Completion.  The Employer should note that in the event of an extension of the Time for Completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor.  Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph:  “ We agree to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to us before the expiry of the guarantee.”

# Text boxes

INSTRUCTIONS TO BIDDERS: DELETE THIS BOX ONCE YOU HAVE COMPLETED THE FORM

This Beneficial Ownership Disclosure Form (“Form”) is to be completed by the successful Bidder.  In case of joint venture, the Bidder must submit a separate Form for each member.  The beneficial ownership information to be submitted in this Form shall be current as of the date of its submission.

For the purposes of this Form, a Beneficial Owner of a Bidder is any natural person who ultimately owns or controls the Bidder by meeting one or more of the following conditions:

- directly or indirectly holding 25% or more of the shares

- directly or indirectly holding 25% or more of the voting rights

- directly or indirectly having the right to appoint a majority of the board of directors or equivalent governing body of the Bidder