## PROCUREMENT-PLAN
Procurement Plan
Approval Number | 4978/OC-BH
Operation Number | BH-L1048
Country | BAHAMAS
Coverage Plan | 14 Oct 2026 - 14 Jun 2027
Executing Agency | BH-MOET - MINISTRY OF ENERGY AND TRANSPORT
Goods and Services Total | 7929709.55
Works Total | 20437065.6
Consulting Services Total | 6563082.22
External Audit | 0
Version | 2026-15
Process Id | Procurement Process Name | Description | Estimated Amount (USD) | Procurement Type | Procurement Method | Supervision Method | Process Status | Lots | Initial Process Estimated Date | Signed Contract Estimated Date | Bidder/Proponent Name | Nationality | Contract Status | Start Date Contract | End Date Contract | Contract Amount USD
BH-L1048-P00001 | Program Coordinator - 2021 | Program Coordinator - 2021 | 123113 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00002 | Development of Solar PV Systems in MICAL (Mayaguana, Inagua, Crooked Island, Inagua, Long Cay) | Mayaguana, Inagua, Crooked Island, Inagua, Long Cay | 28000000 | Works | International Competitive Bidding | Ex-ante | Unsuccessful Process | 0 | 2025-05-19 04:00 | 2025-09-30 04:00:00 | [5 empty] | 0
BH-L1048-P00003 | Development of Solar PV Systems in Crooked Island | Development of Solar PV Systems in Crooked Island | 3900000 | Works | International Competitive Bidding | Ex-ante | Cancelled | 0 | 2025-04-18 | 2025-08-16 00:00:00 | [5 empty] | 0
BH-L1048-P00004 | Support to the Governement of The Bahamas with the Diagnosis, Proposed Action Plan, and Implementation of Institutional, Regulatory and Governance Reforms of the Country''s Energy Sector. | (Energy Policy and Regulatory Advisory Firm) | 300000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Unsuccessful Process | 0 | 2023-10-23 | 2024-02-09 00:00:00 | [5 empty] | 0
BH-L1048-P00005 | Development of a Third-Party Access Code for the T&D Networks in The Bahamas (Competition Gidelines) | Development of a Third-Party Access Code for the T&D Networks in The Bahamas (Competition Gidelines) | 250000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Contract under execution | 0 | 2023-04-17 | 2023-08-08 00:00:00 | MRC Consultants and Transaction Advisers / Nicholson y Cano Abogados legal firm | Spain | Finished | 2025-05-17 | 2025-11-01 | 162460
BH-L1048-P00006 | Support to the Government of The Bahamas In the Development of an Integrated Resource and Resilience Plan | Support to the Government of The Bahamas In the Development of an Integrated Resource and Resilience Plan | 494100 | Consulting Firms | Single-Source Selection of Firms (SSS) | Ex-ante | Procurement complete | 0 | 2023-05-31 | 2023-03-16 00:00:00 | [5 empty] | 0
BH-L1048-P00007 | Project Manager-2022 | Project Manager-2022 | 70000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2022-05-30 | 2022-05-30 00:00:00 | [5 empty] | 0
BH-L1048-P00008 | Administrative Assistant - 2021 | Administrative Assistant - 2021 | 38000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-15 | 2021-04-05 00:00:00 | [5 empty] | 0
BH-L1048-P00009 | Financial Specialist - 2022 | Financial Specialist - 2022 | 55000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2022-05-02 | 2022-05-02 00:00:00 | [5 empty] | 0
BH-L1048-P00010 | Procurement Specialist - 2022 | Procurement Specialist - 2022 | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2022-05-02 | 2022-05-02 00:00:00 | [5 empty] | 0
BH-L1048-P00011 | Monitoring Assistant - 2022 | Monitoring Assistant - 2022 | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2022-05-02 | 2022-05-02 00:00:00 | [5 empty] | 0
BH-L1048-P00012 | Transmission and Distribution Electrical Engineer Consultant - 2022 | 6 months contract - part-time individual consultant | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2022-05-30 | 2022-05-30 00:00:00 | [5 empty] | 0
BH-L1048-P00013 | Program Coordinator - 2022 | Program Coordinator - 2022 | 30778.23 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-12-21 | 2022-01-04 00:00:00 | [5 empty] | 0
BH-L1048-P00014 | Financial Specialist - 2021-2022 | Financial Specialist - 2021-2022 | 13465.5 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-11-16 | 2021-11-17 00:00:00 | [5 empty] | 0
BH-L1048-P00015 | Electrical Engineer - 2022 | Electrical Engineer - 2022 | 22990.25 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-12-21 | 2022-01-04 00:00:00 | [5 empty] | 0
BH-L1048-P00016 | Monitoring Assistant - 2022 | Monitoring Assistant - 2022 | 19705.74 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00017 | Electrical Engineer - 2022 | Electrical Engineer - 2022 | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00018 | Solar Rooftop PV projects installations in New Providence - EPC - Phase I | Solar Rooftop PV projects installations in New Providence - EPC - Phase I - Three (3) Lots - CV Bethel Sr. High School; Doris Johnson Sr. High School; Princess Margaret Hospital | 943329.64 | Works | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2021-04-27 | 2021-05-17 00:00:00 | [5 empty] | 0
BH-L1048-P00019 | Energy Electrical Engineer - 2022 | Energy Electrical Engineer - 2022 | 108000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00020 | Administrative Assistant - 2022 | Administrative Assistant - 2022 | 38000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-15 | 2021-04-05 00:00:00 | [5 empty] | 0
BH-L1048-P00021 | Survey Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | Survey Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | 61600 | Non-Consulting Services | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2023-02-02 | 2023-02-27 00:00:00 | [5 empty] | 0
BH-L1048-P00022 | Survey Studies in Acklins (Spring Point and Salina Point) | Survey Studies in Acklins (Spring Point and Salina Point) | 61050 | Non-Consulting Services | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2022-12-20 | 2022-12-29 00:00:00 | [5 empty] | 0
BH-L1048-P00023 | Survey Studies in Inagua and Mayaguana | Survey Studies in Inagua and Mayaguana | 92263.5 | Non-Consulting Services | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2022-12-21 | 2023-01-14 00:00:00 | [5 empty] | 0
BH-L1048-P00024 | Survey Studies in Crookled Island and Long Cay | Survey Studies in Crookled Island and Long Cay | 61606.05 | Non-Consulting Services | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2023-01-19 | 2023-01-30 00:00:00 | [5 empty] | 0
BH-L1048-P00025 | Engineering Design for Utilities Scale Storage (MICAL) | Engineering Design for Utilities Scale Storage (MICAL) | 98500 | Consulting Firms | Single-Source Selection of Firms (SSS) | Ex-ante | Procurement complete | 0 | 2023-02-15 | 2023-07-21 00:00:00 | [5 empty] | 0
BH-L1048-P00026 | Supervision - Solar PV and Hybrid (storage) Projects Installed in the FI | Supervision - Solar PV and Hybrid (storage) Projects Installed in the FI | 1100000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Process ongoing | 0 | 2025-08-15 04:00 | 2026-03-31 04:00:00 | [5 empty] | 0
BH-L1048-P00027 | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Transformer purchase | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Transformer purchase | 450000 | Goods | International Competitive Bidding | Ex-ante | Unsuccessful Process | 0 | 2023-10-02 | 2023-11-03 00:00:00 | [5 empty] | 0
BH-L1048-P00028 | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Cabling/Commodities | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Cabling/Commodities | 2100000 | Goods | International Competitive Bidding | Ex-ante | Evaluation of Bids/Proposals | 0 | 2023-09-29 | 2024-01-05 00:00:00 | [5 empty] | 0
BH-L1048-P00029 | Works - T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Trenching Leisure Lee and Government Complex | Works - T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Trenching Leisure Lee and Government Complex | 300000 | Works | National Competitive Bidding | Ex-ante | Expected | 0 | 2027-02-01 05:00 | 2027-06-30 04:00:00 | [5 empty] | 0
BH-L1048-P00030 | Phase II: C.H Reeves Junior High School | Phase II: C.H Reeves Junior High School | 121000 | Works | National Competitive Bidding | Ex-ante | Contract under execution | 0 | 2023-06-09 | 2023-09-18 00:00:00 | [5 empty] | 0
BH-L1048-P00031 | Phase II: Carmichael Road Post Office and Public Library | Phase II: Carmichael Road Post Office and Public Library | 102000 | Works | National Competitive Bidding | Ex-ante | Contract under execution | 0 | 2023-07-22 | 2023-09-15 00:00:00 | [5 empty] | 0
BH-L1048-P00032 | Phase II: Elizabeth Estates Post Office, Public Library, and Clinic | Phase II: Elizabeth Estates Post Office, Public Library, and Clinic | 125000 | Works | National Competitive Bidding | Ex-ante | Procurement complete | 0 | 2023-07-22 | 2023-09-15 00:00:00 | [5 empty] | 0
BH-L1048-P00033 | Phase II: Ministry of Education | Phase II: Ministry of Education | 573240 | Works | National Competitive Bidding | Ex-ante | Cancelled | 0 | 2024-11-05 | 2025-02-15 00:00:00 | [5 empty] | 0
BH-L1048-P00034 | Phase II: UB Clean Energy | Phase II: UB Clean Energy | 900000 | Works | National Competitive Bidding | Ex-ante | Evaluation of Bids/Proposals | 0 | 2023-07-17 | 2023-10-24 00:00:00 | [5 empty] | 0
BH-L1048-P00035 | Completion of the Transmission and Distribution Network from Marsh Harbour to Coopers Town, Abaco, The Bahamas | Completion of the Transmission and Distribution Network from Marsh Harbour to Coopers Town, Abaco, The Bahamas | 1342000 | Works | Direct Contracting | Ex-ante | Evaluation of Bids/Proposals | 0 | 2022-02-13 | 2023-11-10 00:00:00 | [5 empty] | 0
BH-L1048-P00036 | Interconnection Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | Interconnection Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | 30000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Evaluation of Bids/Proposals | 0 | 2023-06-28 | 2023-09-29 00:00:00 | [5 empty] | 0
BH-L1048-P00037 | Rental of Equipment for the Installation of OPS Transformers | Rental of Equipment for the Installation of OPS Transformers | 90000 | Non-Consulting Services | Shopping/Request for minimum 3 Quotations | Ex-ante | Cancelled | 0 | 2025-06-16 | 2025-06-30 00:00:00 | [5 empty] | 0
BH-L1048-P00038 | Supply of Fiber OPGW SM | Supply of Fiber OPGW SM | 272976 | Goods | Direct Contracting | Ex-ante | Contract under execution | 0 | 2023-12-01 | 2023-10-10 00:00:00 | [5 empty] | 0
BH-L1048-P00039 | Supply of Ductile Poles and other materials | Supply of Ductile Poles and other materials | 2122214 | Goods | Direct Contracting | Ex-ante | Evaluation of Bids/Proposals | 0 | 2022-12-07 | 2023-10-10 00:00:00 | [5 empty] | 0
BH-L1048-P00040 | Supply of equipment for training for installation and maintenance of solar PV generation systems | Supply of equipment for training for installation and maintenance of solar PV generation systems | 71000 | Goods | Shopping/Request for minimum 3 Quotations | Ex-ante | Procurement complete | 0 | 2023-10-13 | 2023-10-24 00:00:00 | [5 empty] | 0
BH-L1048-P00041 | Second Survey Studies in Crookled Island (Land Rail Point) | Second Survey Studies in Crookled Island (Land Rail Point) | 80000 | Non-Consulting Services | Direct Contracting | Ex-ante | Procurement complete | 0 | 2022-12-05 | 2023-01-30 00:00:00 | [5 empty] | 0
BH-L1048-P00042 | Mid-Term Evaluation | Mid-Term Evaluation | 25000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2024-01-30 | 2024-03-01 00:00:00 | [5 empty] | 0
BH-L1048-P00043 | Communication and Dissemination PR Firm | Communication and Dissemination PR Firm | 150000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Contract under execution | 0 | 2023-07-20 | 2023-09-29 00:00:00 | [5 empty] | 0
BH-L1048-P00044 | Geotechnical Studies MOE/Customs | Geotechnical Studies MOE/Customs | 71000 | Consulting Firms | Single-Source Selection of Firms (SSS) | Ex-ante | Procurement complete | 0 | 2023-12-13 | 2023-09-29 00:00:00 | [5 empty] | 0
BH-L1048-P00045 | Senior procurement advisor | Senior procurement advisor | 70000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2023-09-15 | 2023-09-18 00:00:00 | [5 empty] | 0
BH-L1048-P00046 | New renewable energy power capacity installed with resilient mini-grids in EGB: Lot 1(Freetown and High Rock) and Lot 2 (McCLeans, Sweetings Cay and Water Cay) | Lot 1 (Freetown and High Rock): US$ 2,828,000 Lot 2 (McCLeans, Sweetings Cay and Water Cay): US$ 1,609,000 | 4437000 | Works | International Competitive Bidding | Ex-ante | Cancelled | 0 | 2025-06-06 04:00 | 2025-10-18 04:00:00 | [5 empty] | 0
BH-L1048-P00047 | Procurement Specialist (Part-time) | Procurement Specialist (Part-time) | 30000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2024-12-10 | 2025-02-01 00:00:00 | * | Bahamas | Signed | 2025-01-31 | 2026-02-28 | 45000
BH-L1048-P00048 | Associate Project Manager | Associate Project Manager | 50000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Cancelled | 0 | 2024-12-10 | 2025-02-01 00:00:00 | [5 empty] | 0
BH-L1048-P00049 | Electrical Engineer Specialist | Electrical Engineer Specialist | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Unsuccessful Process | 0 | 2024-12-10 | 2025-02-01 00:00:00 | [5 empty] | 0
BH-L1048-P00050 | Financial Specialist - 2021 | Financial Specialist - 2021 | 94258.5 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00051 | Energy Electrical Engineer Consultant - 2021 | Energy Electrical Engineer Consultant - 2021 | 108000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-04-14 | 2021-06-07 00:00:00 | [5 empty] | 0
BH-L1048-P00052 | Electrical Engineer - 2021 | Electrical Engineer - 2021 | 91961 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00053 | Monitoring Assistant - 2021 | Monitoring Assistant - 2021 | 78823 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00054 | Livelihood training in services supply chain and solutions within the solar industry for women | Livelihood training in services supply chain and solutions within the solar industry for women | 25000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Expected | 0 | 2027-01-01 05:00 | 2027-03-01 05:00:00 | [5 empty] | 0
BH-L1048-P00055 | Prevention of sexual harassment and GBV trainings for all the contracting companies and PEU | Prevention of sexual harassment and GBV trainings for all the contracting companies and PEU | 25000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Process ongoing | 0 | 2027-01-01 05:00 | 2027-03-31 04:00:00 | [5 empty] | 0
BH-L1048-P00056 | Procurement Specialist - 2021 | Procurement Specialist - 2021 | 91961 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-15 | 2021-02-15 00:00:00 | [5 empty] | 0
BH-L1048-P00057 | Transmission and Distribution Electrical Engineer Consultant - 2021 | 6 months contract - part-time individual consultant | 55900 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-04-14 | 2021-07-19 00:00:00 | [5 empty] | 0
BH-L1048-P00058 | Environmental and Social Coordinator Consultant | Environmental and Social Coordinator Consultant | 70000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2022-06-30 | 2022-06-30 00:00:00 | [5 empty] | 0
BH-L1048-P00059 | Energy Sector Advisor (MOW) | Energy Sector Advisor (MOW) | 150000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Expected | 0 | 2027-01-15 05:00 | 2027-03-31 04:00:00 | [5 empty] | 0
BH-L1048-P00060 | Energy Project Management Consultant - 2021 | Energy Project Management Consultant - 2021 | 30000 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Ex-ante | Procurement complete | 0 | 2021-03-25 | 2021-04-19 00:00:00 | [5 empty] | 0
BH-L1048-P00061 | Study on potential improvements on the regulatory framework for implementation of renewable energy systems (offshore wind and wave power, etc.). | Study on potential improvements on the regulatory framework for implementation of renewable energy systems (offshore wind and wave power, etc.). | 100000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Expected | 0 | 2027-02-01 05:00 | 2027-06-30 04:00:00 | [5 empty] | 0
BH-L1048-P00062 | Communications & Training Consultant - 2022 | Communications & Training Consultant - 2022 | 55000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2022-09-12 | 2022-09-15 00:00:00 | [5 empty] | 0
BH-L1048-P00063 | Legal Consultant - 2022 | Legal Consultant - 2022 | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2022-09-22 | 2022-10-03 00:00:00 | [5 empty] | 0
BH-L1048-P00064 | Development of Solar PV Systems in North Andros (Lots 1 & 2) | Development of Solar PV Systems in North Andros (Lots 1 & 2) | 100000 | Works | Shopping/Request for minimum 3 Quotations | Ex-ante | Cancelled | 0 | 2024-03-01 | 2024-03-29 00:00:00 | [5 empty] | 0
BH-L1048-P00065 | Electrical Engineer - 2021 | Electrical Engineer - 2021 | 91961 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00066 | Monitoring Assistant - 2021 | Monitoring Assistant - 2021 | 78823 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-04 | 2021-01-18 00:00:00 | [5 empty] | 0
BH-L1048-P00067 | Procurement Specialist - 2021 | Procurement Specialist - 2021 | 91961 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-15 | 2021-02-15 00:00:00 | [5 empty] | 0
BH-L1048-P00068 | Transmission and Distribution Electrical Engineer Consultant - 2021 | 6 months contract - part-time individual consultant | 55900 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-04-14 | 2021-07-19 00:00:00 | [5 empty] | 0
BH-L1048-P00069 | Energy Project Management Consultant - 2021 | Energy Project Management Consultant - 2021 | 30000 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Ex-ante | Procurement complete | 0 | 2021-03-25 | 2021-04-19 00:00:00 | [5 empty] | 0
BH-L1048-P00070 | Administrative Assistant - 2021 | Administrative Assistant - 2021 | 38000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-01-15 | 2021-04-05 00:00:00 | [5 empty] | 0
BH-L1048-P00071 | Development of Solar PV Systems in Long Cay | Development of Solar PV Systems in Long Cay | 500000 | Works | National Competitive Bidding | Ex-ante | Cancelled | 0 | 2025-03-26 | 2025-07-01 00:00:00 | [5 empty] | 0
BH-L1048-P00072 | Environment & Social Impac/Geotechnical Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | Environment & Social Impac/Geotechnical Studies in East Grand Bahama (EGB) Freetown, High Rock, McCleans Town, Sweeting''s Cay, Water''s Cay | 162881 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Contract under execution | 0 | 2023-04-05 | 2023-09-25 00:00:00 | [5 empty] | 0
BH-L1048-P00073 | Communications & Training Consultant - 2021 | Communications & Training Consultant - 2021 | 55000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Procurement complete | 0 | 2021-07-20 | 2021-08-16 00:00:00 | [5 empty] | 0
BH-L1048-P00074 | Enviromental/Geotechnical Studies - Acklins (Salina Point and Spring Point) | Enviromental/Geotechnical Studies - Acklins (Salina Point and Spring Point) | 200000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Evaluation of Bids/Proposals | 0 | 2022-12-31 | 2023-09-25 00:00:00 | [5 empty] | 0
BH-L1048-P00075 | Environment & Social/Geotechnical Impact Studies in INAGUA and MAYAGUANA | Environment & Social/Geotechnical Impact Studies in INAGUA and MAYAGUANA | 200000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Evaluation of Bids/Proposals | 0 | 2023-02-05 | 2023-09-25 00:00:00 | [5 empty] | 0
BH-L1048-P00076 | Environment & Social Impact/Geotechnical Studies in CROOKED ISLAND & LONG CAY | Environment & Social Impact/Geotechnical Studies in CROOKED ISLAND & LONG CAY | 200000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Evaluation of Bids/Proposals | 0 | 2023-01-22 | 2023-09-25 00:00:00 | [5 empty] | 0
BH-L1048-P00077 | Energy storage regulation and E-mobility | Energy storage regulation and E-mobility | 100000 | Consulting Firms | Selection Based on the Consultants Qualification (CQS) | Ex-ante | Expected | 0 | 2026-10-30 04:00 | 2027-03-31 04:00:00 | [5 empty] | 0
BH-L1048-P00078 | Electricity tariff review and recommendations | Electricity tariff review and recommendations | 350000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Contract under execution | 0 | 2023-09-18 | 2023-12-18 00:00:00 | Mercados Aries International | Spain | In Execution | 2025-05-13 | 2025-12-28 | 256650
BH-L1048-P00078 | Electricity tariff review and recommendations | Electricity tariff review and recommendations | 350000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Contract under execution | 0 | 2023-09-18 | 2023-12-18 00:00:00 | Mercados Aries International | Spain | In Execution with Amendments | 2025-05-13 | 2026-01-13 | 256650
BH-L1048-P00079 | Works - Development of Solar PV Systems in Acklins (Spring Point & Salina Point) | Works - Development of Solar PV Systems in Acklins (Spring Point & Salina Point) | 5600000 | Works | International Competitive Bidding | Ex-ante | Cancelled | 0 | 2025-04-15 | 2025-08-01 00:00:00 | [5 empty] | 0
BH-L1048-P00080 | Development of Solar PV Systems in Inagua | Development of Solar PV Systems in Inagua | 12800000 | Works | International Competitive Bidding | Ex-ante | Cancelled | 0 | 2025-05-01 | 2025-08-16 00:00:00 | [5 empty] | 0
BH-L1048-P00081 | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Transformer purchase | Transformer purchase | 1000000 | Goods | International Competitive Bidding | Ex-ante | Unsuccessful Process | 0 | 2025-05-16 04:00 | 2025-08-22 04:00:00 | [5 empty] | 0
BH-L1048-P00082 | Support to the Government of The Bahamas In the Development of an Integrated Resource and Resilience Plan | IRRP | 350000 | Consulting Firms | Quality-and-Cost Based Selection (QCBS) | Ex-ante | Contract under execution | 0 | 2025-05-22 04:00 | 2025-07-18 04:00:00 | [5 empty] | 0
BH-L1048-P00083 | Junior Energy Electrical Engineer | To provide engineering support and conduct a comprehensive technical evaluation of the proposals received in response to the RFPs | 50000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2025-06-10 04:00 | 2025-06-12 04:00:00 | * | Bahamas | Signed | 2025-05-01 | 2026-04-30 | 50000
BH-L1048-P00084 | Monitoring & Evaluation Specialist | Project monitoring and supervision | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2025-05-23 04:00 | 2025-05-25 04:00:00 | * | Bahamas | In Execution | 2025-05-01 | 2026-04-30 | 60000
BH-L1048-P00085 | Energy Electrical Engineer Consultant | The primary objective of the Energy Electrical Engineer consultancy is to conduct a comprehensive technical evaluation of the received proposals in response to the RFP for the microgrid projects, ensuring technical compliance, feasibility, and alignment with project requirements. | 60000 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Ex-ante | Contract under execution | 0 | 2025-06-13 04:00 | 2025-06-24 04:00:00 | * | United States | In Execution with Amendments | 2025-08-01 | 2026-07-31 | 60000
BH-L1048-P00086 | Environmental, Social, Governance (ESG) Consultant | The primary objective of the Energy Electrical Engineer consultancy is to conduct a comprehensive technical evaluation of the received proposals in response to the RFP for the microgrid projects, ensuring technical compliance, feasibility, and alignment with project requirements. | 50000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Contract under execution | 0 | 2025-06-06 04:00 | 2025-06-16 04:00:00 | * | Bahamas | In Execution with Amendments | 2025-08-04 | 2026-08-03 | 30000
BH-L1048-P00087 | Financial Specialist | The primary objective of the Energy Electrical Engineer consultancy is to conduct a comprehensive technical evaluation of the received proposals in response to the RFP for the microgrid projects, ensuring technical compliance, feasibility, and alignment with project requirements. | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Process ongoing | 0 | 2025-07-01 04:00 | 2025-07-18 04:00:00 | [5 empty] | 0
BH-L1048-P00089 | Financial Specialist - Part-time | Financial Specialist - Part-time Consultant | 25000 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Ex-ante | Contract under execution | 0 | 2025-08-15 04:00 | 2025-08-20 04:00:00 | * | Bahamas | Finished | 2025-08-20 | 2026-02-19 | 25000
BH-L1048-P00090 | Communications Specialist | Consultant to complete public communications for the project | 40000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Cancelled | 0 | 2025-11-17 05:00 | 2025-12-31 05:00:00 | [5 empty] | 0
BH-L1048-P00091 | Works - Operation and Maintenance of Solar Panels at V Bethel, TG Glover, and Doris Johnson | Operation and Maintenance Services for Solar Panels at V Bethel, TG Glover, and Doris Johnson | 25000 | Works | Direct Contracting | Ex-ante | Contract under execution | 0 | 2025-10-31 04:00 | 2025-12-15 05:00:00 | [5 empty] | 0
BH-L1048-P00092 | Entry Level Engineer Consultant | The Entry-Level Electrical Engineer will assist in the planning, design, and implementation of microgrid projects. | 50000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Process ongoing | 0 | 2025-11-28 05:00 | 2026-01-16 05:00:00 | [5 empty] | 0
BH-L1048-P00093 | Supply of Caterpillar Diesel Generators and ancillary parts for the support of Solar Photovoltaic (PV) Microgrid Systems in Mayaguana, Inagua, Crooked Island, and Acklins Island, (MICAL), The Bahamas. | Procure solar (PV) microgrids 10 diesel Prime Power generators along with their associated components needed to support the installation of Solar Photovoltaic (PV) microgrids at MICAL, the Bahamas, from Machinery & Energy Ltd. (M&E). | 2000000 | Goods | Direct Contracting | Ex-ante | Expected | 0 | 2026-09-30 04:00 | 2026-12-31 05:00:00 | [5 empty] | 0
BH-L1048-P00095 | Procurement of PEU Laptops | Procurement of PEU Laptops via shopping | 5000 | Goods | Shopping/Request for minimum 3 Quotations | Ex-ante | Contract under execution | 0 | 2025-12-19 05:00 | 2025-12-30 05:00:00 | CUSTOM COMPUTERS LTD. | Bahamas | Finished | 2026-01-14 | 2026-02-13 | 4838.9
BH-L1048-P00096 | Development of Solar PV Systems in MICAL (Mayaguana, Inagua, Crooked Island, Inagua, Long Cay) | Mayaguana, Inagua, Crooked Island, Inagua, Long Cay | 14000000 | Works | International Competitive Bidding - With Prequalification | Ex-ante | Process ongoing | 0 | 2025-12-22 05:00 | 2026-06-30 04:00:00 | [5 empty] | 0
BH-L1048-P00097 | Design, Supply and Installation Services of Plant for East Grand Bahama (EGB) Resilient Microgrids (Free Town, McLean’s Town, Sweeting’s Cay, and Water Cay) | Design, Supply and Installation Services of Plant for East Grand Bahama (EGB) Resilient Microgrids (Free Town, McLean’s Town, Sweeting’s Cay, and Water Cay) | 2500000 | Works | National Competitive Bidding | Ex-ante | Evaluation of Bids/Proposals | 0 | 2026-02-20 05:00 | 2026-06-05 04:00:00 | [5 empty] | 0
BH-L1048-P00098 | Procurement of PEU Laptops and Accessories | Procurement of PEU Laptops and Accessories via shopping | 2000 | Goods | Shopping/Request for minimum 3 Quotations | Ex-ante | Contract under execution | 0 | 2026-02-20 05:00 | 2026-02-27 05:00:00 | [5 empty] | 0
BH-L1048-P00099 | T&D resilient systems reconstructed or rehabilitated in Abaco (infrastructure) - Transformer purchase | Transformer purchase | 1000000 | Goods | International Competitive Bidding | Ex-ante | Process ongoing | 0 | 2027-01-01 05:00 | 2027-05-31 04:00:00 | [5 empty] | 0
BH-L1048-P00100 | Part-time Financial Specialist | I write to request the Bank’s no objection to engage a part-time Financial Specialist for a period of six (6) months at a total cost of $30,000 to support the completion of the 2026 audit and other financial obligations under Project BH-L1048 and Grant BH-G0003. | 30000 | Individual Consultants | Single-Source Selection of Individual Consultant (SSS) | Ex-ante | Contract under execution | 0 | 2026-06-25 04:00 | 2026-08-31 04:00:00 | [5 empty] | 0
BH-L1048-P00101 | Engineering, Procurement, Construction, and Initial Operations and Maintenance of Solar PV System at Elizabeth Estates Post office, Public Library, and Clinic | Solar PV System at Elizabeth Estates Post Office, Public Library, and Clinic | 78235.96 | Works | Direct Contracting | Ex-ante | Contract under execution | 0 | 2026-07-31 04:00 | 2026-08-31 04:00:00 | [5 empty] | 0
BH-L1048-P00102 | Full-time Procurement Specialist | Full-time Procurement Specialist | 60000 | Individual Consultants | Individual Consultant Selection (3CV) | Ex-ante | Expected | 0 | 2026-07-31 04:00 | 2026-09-18 04:00:00 | [5 empty] | 0
BH-L1048-P00103 | Compass Solar Operation & Maintenance Solar Panel Replacement TG Glover Primary School – Solar Panel Repair | Compass Solar Operation & Maintenance Solar Panel Replacement TG Glover Primary School – Solar Panel Repair | 500 | Works | Direct Contracting | Ex-ante | Expected | 0 | 2026-10-20 04:00 | 2026-11-16 05:00:00 | [5 empty] | 0